## Risk template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | Peaking Ingula Pumped Storage Scheme - Strip, assess, repair and test of the 18kV SFC Line side reactor panels | [8 empty] | Department: | Electrical Maintenance | [9 empty] | Next Review Date (every 2 years): |  | Template identifier: | 240-70044602
Date: | 2022-02-10 | [8 empty] | Prepared by: | Siyanda Mbatha |  | Authorised by: |  | Name: Samkelisiwe Nkosi | [7 empty] | Document identifier
[15 empty] | Designation: EMD Manager | [7 empty] | Revision number: | 3
[15 empty] | Signed: | [7 empty] | Revision date: | 2024-05-31
Date: 2022-02-10
Refer to Occupational Health and Safety Risk assessment procedure 32-520
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | OHS opportunities | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | OH&S opportunities that can enhance OH&S performance and lead to hazard elimination and risk reduction. | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) NB: The risk shall be evaluated, assessed and rated again once additional controls have been implemented. | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Pending, In Progress, Complete | Where applicable, add IRM system reference number for tracking of treatment actions.
Strip, assess, repair and test of the 18kV SFC Line side reactor panels | R | 1 | Wet surfaces | 1 | Propert damage (collision) | Safety | Ground water ingress | Engineering to improve drainage of surface water from wet areas | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Loss Time Injury or Property Damage | Safety induction, physical medical examination, vehicle inspection, vehicle service/maintenance records | 4 | B | III | Mostly ineffective | Task specific risk assessment when executing work | Management Incident Review, Behavioural safety observations and planned job observation | Supervisor/Manager |  |  | Pending
|  | 2 | Equipmen identification | 1 | Contact with live panels | Safety | Incorrect identification of the plant (panels are the same in the SG room) | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Loss Time Injury | Configuration management, physical medical examination, on job training, skilled personel, | 4 | C | II | Mostly effective | Perform task specific risk assessment when executing work | Behavioural safety observations, planned job observation, training records | Supervisor/Manager |  |  | Complete
|  | 3 | Use of hand tools | 1 | Injury | Safety | Hand impinchment | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Injury | PPE records, safety induction, trainings, OEM Manual, physical medical examination | 4 | C | II | Mostly effective | Perform task specific risk assessment when executing work, STAR principle | Vehicle Inspection records and Incidement Management Review | Supervisor/Manager |  |  | Complete
|  | 4 | Noise | 1 | Noise Induced hearing loss | Safety | High noise level from running units | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Lost Time Injury | Safety induction, awareness, wearing hearing protection, signage | 4 | C | II | Mostly effective | Task specific risk assessment, two person rule | Behavioural safety observations, planned job observation | Supervisor/Manager |  |  | Complete
|  | 5 | Arc flash | 1 | Exposure | Safety | Plant is alive/switching during Ops activity | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Lost Time Injury | ORHVS, Training records, OEM Manuals, physical medical examination, Life saving rules | 4 | C | II | Mostly effective | Task specific risk assessment, two person rule | Behavioural safety observations, planned job observation | Supervisor/Manager |  |  | Complete
|  | 6 | Live conductors / Electric shock | 1 | Contact (electricution) | Safety | Plant is alive | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Lost Time Injury | ORHVS, Training records, OEM Manuals, physical medical examination, Life saving rules, Test before touch | 4 | C | II | Mostly effective | Task specific risk assessment, two person rule &STAR principle | Behavioural safety observations, planned job observation | Supervisor/Manager |  |  | Complete
|  | 7 | Operation plant modes | 1 | U3 at standstill | Safety | Unavailability of SFC Board | None | Ops | Supervisor/Manager | Daily, 8.75 hours | Production loss | ORHVS, Training records, OEM Manuals, physical medical examination, Life saving rules, Operating procedure | 4 | C | II | Mostly effective | Task specific risk assessment, two person rule & STAR principle | GPSS, Behavioural safety observations, planned job observation | Supervisor/Manager |  |  | Complete
|  | 8 | Carbon dust | 1 | inhalation | Health | Cleaning of the breaker, cable and breaker compartments | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Medical incident | Training, physical medical examination, PPE issue records, safety induction | 3 | B | III | Mostly ineffective | Task specific risk assessment when executing work | Behavioural safety observations, planned job observation | Supervisor/Manager |  |  | Complete
|  | 9 | Operating proceudre not available | 1 | Injury | Safety | Incorrect operating sequence | Compile the Operating instruction | Ops | Supervisor/Manager | Daily, 8.75 hours | Lost Time Injury or First Aid | OEM Manual, On job training, physical medical examination, safety induction, ORHVS training records, PPE records | 3 | B | II | Mostly ineffective | Task specific risk assessment when executing work | LTI and First Aid statistics | Supervisor/Manager |  |  | Pending
|  | 10 | Maintenance work package not available | 1 | Injury | Safety | Iadvent contact with live conductors | Compile maintenance work package | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Lost Time Injury or First Aid | OEM Manual, On job training, physical medical examination, safety induction, ORHVS training records, PPE records | 4 | B | III | Mostly ineffective | Task specific risk assessment when executing work | LTI and First Aid statistics | Supervisor/Manager |  |  | Pending
|  | 11 | Poor communication between stakeholders | 1 | Injury | Safety | Unclear instructions, noise from other plant operations | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Loss Time Injury | maintain 3-way communication | 4 | C | II | Mostly effective | Task specific risk assessment when executing work | Behavioural safety observations, planned job observation | Supervisor/Manager |  |  | Complete
|  | 12 | Fatigue | 1 | Injury | Safety | Person continous on duty, insufficient breaks | Recruitment of staff | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Medical Incident | Adhere to the rest periods as per Conditions of Service and Managing hours of work procedure, employee rotation, physical assessment | 4 | B | III | Mostly ineffective | Employee rotation | Timesheets | Supervisor/Manager |  |  | Pending
|  | 13 | Poor lighting | 1 | Trip and fall | Safety | Poor visibility | None | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | First Aid or Medical Incident | Risk assessment, use portable lighting, make use of PPE, visual screening | 4 | C | II | Mostly effective | Task specific risk assessment when executing work | LTI and First Aid statistics | Supervisor/Manager |  |  | Complete
|  | 14 | Ergonomics | 1 | Musculoskeletal discorder (MSD), technology | Health | Body posture when lifting or working | Ergonomics awareness that focus on Work Related MSD, Survey done by AIA | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | First Aid or Medical Incident | Risk assessment, make use of PPE, Ergonomics awareness, physical examination, make use of the cherry picker | 4 | B | III | Mostly ineffective | Task specific risk assessment when executing work | LTI and First Aid statistics | Supervisor/Manager |  |  | Pending
|  | 15 | Work Load assignment | 1 | stress, burnout, demotivation and moods disorder, lack of concentration, staff morale | Health | poor planning & execution, staff turnover, COVID-19 pandemic, rework, production pressure, lack of skills, fault diagnostic and root cause analysis, plant ineffeciency and nn-reliability, poor support from stakeholders | Recruitment of staff | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Medical Incident, Loss Time Injury and First Aid, Sick Leave, Fatique, depression | Scope freeze and prioritization, COVID-19 and leave roster, skills and development | 4 | B | III | Mostly ineffective | Exposure to other work areas, staff rotation for different workload, | MPI, AFR, Overtime Statistics | Supervisor/Manager |  |  | Pending
|  | 16 | Victimization | 1 | anxiety and anger, stress, burnout, demotivation and moods disorder, lack of concentration, staff morale, resource overload and scheduling, withdrawal, change of behaviour | Health | sabotaging, frustrations, fear, micro-management and low self esteem, staff turnover, mental disturbance | Engagement with EAP & IR, Recruitment of staff | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Medical Incident | Awareness, EAP services, IR services, | 4 | B | III | Mostly ineffective | Task specific risk assessment when executing work | MPI, AFR, Overtime Statistics | Supervisor/Manager |  |  | Pending
|  | 17 | Workplace Bulling | 1 | Isolation, depression, aggressive, unexplained injuries | Health | abuse of authority, stress and trauma | Engagement with EAP & IR | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Medical Incident | Awareness, EAP services, IR services, Ethics training | 4 | B | III | Mostly ineffective | Task specific risk assessment when executing work | MPI, AFR, Overtime Statistics | Supervisor/Manager |  |  | Pending
|  | 18 | Sexual Harrassment | 1 | Isolation, depression, aggressive, unexplained injuries, weight loss, sleep disorder | Safety | work culture, sleep disorder, improper sexual comments, | Engagement with EAP & IR | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Medical Incident | Awareness, EAP, Ethics training | 4 | B | III | Mostly ineffective | Task specific risk assessment when executing work | MPI, AFR, Overtime Statistics | Supervisor/Manager |  |  | Pending
|  | 19 | COVID-19 | 1 | Transmission of the virus | Health | Contact with infected person or surface | Develop individual BRA for vulnerable employees | EMD, Ops & PTM | Supervisor/Manager | Daily, 8.75 hours | Fatality or Loss Time Injury | Social distance, COVID-19 awareness, wear face mask, sanitize and vaccination, staff rotation | 5 | B | III | Mostly ineffective | Task specific risk assessment when executing work | COVID-19 statistics | Supervisor/Manager |  |  | Pending

## Contractor Baseline template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | [9 empty] | Next Review Date (every 2 years): | Template identifier:
Date: |  |  |  |  | Authorised by: |  | Name: |  |  | Document identifier | [8 empty] | R | Safety | 1 | A | Fully effective | I
[7 empty] | Designation: |  |  | Revision number: | 1 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[7 empty] | Signed: |  |  | Revision date: | 2024-05-31 | [9 empty] | 3 | C | Mostly ineffective | III
[7 empty] | Date: | [13 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [20 empty] | 5 | E
List activity | Hazard Identification | Associated risk | Risk type | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Control Owner | Legal and Other Requirements | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Consequences | 6 | III | II | I | I | I
Strip, assess, repair and test of the 18kV SFC Line side reactor panels | Wet surfaces | Propert damage (collision) | Safety | Loss Time Injury or Property Damage | Safety induction, physical medical examination, vehicle inspection, vehicle service/maintenance records | 4 | B | III | Mostly ineffective | Supervisor/Manager | 0 |  | 5 | III | II | II | I | I
[13 empty] | 4 | IV | III | II | I | I
[13 empty] | 3 | IV | III | II | II | I
[13 empty] | 2 | IV | IV | III | II | II
[13 empty] | 1 | IV | IV | III | III | III
[14 empty] | A | B | C | D | E
Likelihood
s

## Consequence rating
Consequence criteria
Consequence rating | Description | [7 empty] | R | Safety | 1 | A | Fully effective | I
| Health and Safety | [7 empty] | N | Health | 2 | B | Mostly effective | II
1 | No injuries or health effects(near misses) | [9 empty] | 3 | C | Mostly ineffective | III
2 | First-aid treatment case, and temporary discomfort case | [9 empty] | 4 | D | None | IV
3 | Medical treatment case; occupational disease with reversible/non-permanent effect | [9 empty] | 5 | E
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence | [9 empty] | 6
5 | Fatality or life threatening health effects | Consequences | 6 | III | II | I | I | I
6 | Multiple fatalities |  | 5 | III | II | II | I | I
|  |  | 4 | IV | III | II | I | I
|  |  | 3 | IV | III | II | II | I
|  |  | 2 | IV | IV | III | II | II
|  |  | 1 | IV | IV | III | III | III
|  |  |  | A | B | C | D | E
Likelihood

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required, and these risks to be captured on IRM system.
| II | High | Strong mandatory action required, and these risks to be captured on IRM system.
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.