## Risks
Grootvlei Risk Assessment Template Rev3 | [5 empty] | Contract Name: |  |  | The mechanical maintenance of the Common Plant |  |  |  |  | Dashboard Indicators
Compiled by : Bruce Kruger
[6 empty] | Contract Supervisor: |  |  | Bruce Kruger |  |  |  |  | Highest Probality Rating: (manual input, scale 1-10)
Highest Impact Rating: (manual input, scale 1-10)
[6 empty] | Employer's Representative: |  |  | Nomsa Vilakazi |  |  |  |  | Highest Exposure Rating: (manual input, 1-100)
Overall Exposure Score: (scale of 1 - 100, low to high)
[6 empty] | Date: |  |  | 2022-01-19 |  |  |  |  | Risk/contingency as (%) of the contract value: (manual input) |  |  | 10%
[14 empty] | Risk/contingency % as monetary value (R): (manual input) |  |  | 0
Legend
Impact | [12 empty] | Probability/Likelihood |  |  | Treatment
1 - 2 Ignore_event is negligible | [12 empty] | 1 - Ignore_event is negligible |  |  | Unlikely - Contingency
3 Minor_financial loss or injuries | [12 empty] | 2 - Remote_has happened somewhere
4 - 5 Significant_lost business,significant financial loss, fatalities | [12 empty] | 3 - Highly unlikely event will occur
7 - 9 Severe_lost business opportunties, financial loss,many fatalities | [12 empty] | 4 - Conceivable but unlikely |  |  | Likely - Strategy
10 Catastrophic_impact on Eskom or our business | [12 empty] | 5 - Unusual but possible
6 - Possible
Exposure Score - Actions Required (Treatment) | [12 empty] | 7 - Event can occur
>0 < 30 : Unlikely, contingency required | [12 empty] | 8 - Might well be expected |  |  | Certain - Action Plan
>30 < 70: Likely, mitigating strategy and contingency to be completed | [12 empty] | 9 - Will probably occur
>70: Certain, mitigating startegy, contingency and triggers to be conpleted | [12 empty] | 10 - Will definitely occur
| Risk Statement | [6 empty] | (1 - 10) |  | (1 - 10) |  |  | Mitigation
# | Condition/ Checklist | (Y/N) | Explain (Y/N) | Does the item pose a risk (Y/N) ? | Explain (Y/N) | Consequence | Probability - Select | Probability | Impact - (Select Closest Applicable statement) | Impact | Exposure | Contingency |  |  | Triggers | Assignee
1 | Were interfacing contracts identified? | N/A | [7 empty] | 0 | 0
2 | Have KPI's been defined in the contract? | Y | The scope of service may not be provided as per contract | Y | Poor performance |  |  | 10 |  | 3 | 30 |  | The KPIs have been included in the contract document |  |  | Contract Manager
3 | Was IBI training specified in the contract? | Y | Re-occurrence of errors while performing the service |  |  |  | Ignore_event is negligible | 10 | Minor Financial loss together with minor injuries | 3 | 30 |  | The Contractor to receive Integrated Business Improvement(IBI) training from the Employer. |  |  | Contract Manager
4 | Have the contract considered spares holding? | N | Spares may not be available when needed | N | Spares are made stock items and stored at stores |  |  |  |  | 0 | 0
5 | Was supplier infrastructure establishment considered? | Y | The Employer must ensure that the Contractor is able to provide the Service. | Y | Inability of the contractor to perform the Service. |  |  | 9 |  | 0 | 0 |  | Previous related experience will form part of tender adjudication. |  |  | Contract Manager
6 | Does the contract cater for SHE/plans? | Y | The Contractor may get injured when working or moving material | Y | Injury to Contractor's employees while working. Non- compliance to the OHS Act. |  |  | 10 |  | 3 | 30 |  | The Contractor must submit his/her SHE policy |  |  | Contract Manager
7 | Does the contract cater for risk assesments? | Y | The Contractor is exposed to risks at the start of any activity. | Y | Risks of certain tasks to be identified beforehand. |  |  | 10 |  | 3 | 30 |  | The Contractor to perform a risk assessment before any activity |  |  | Contract Manager
8 | Has a training program been specified? | Y | Incompetent workfirce | Y | People not competent to execute the work |  |  | 5 | Significant business loss together with financial loss or fatalities | 3 | 15 |  | Put a training program in place and make it to form part of the low service damages |  |  | Contract Manager
9 | Is there any risk in the contract strategy e.g. term, service, supplier? | N |  | N | [5 empty] | 0 | 0
10 | PSR responsibility | Y | The Contractor will need a Permit To Work to perform the service | Y | The Contractor will not be able to take out a Permit To Work |  |  |  |  | 0 | 0 |  | The Employer will provide training for Contractor's staff to be authorised in terms of Plant Safety Regulations |  |  | Contract Manager
11 | Will decision making by the supplier impose a risk to the organisation? | N |  | N | [5 empty] | 0 | 0
12 | Were medical/induction and associated costs considered? | Y | The Contractor to pay formedical costs | Y | The Contractor's employees will not be allowed on site without a medical certificate |  |  | 10 |  | 3 | 30 |  | Medical costs are for the Contractor's account |  |  | Contract Manager
13 | Who will be responsible for access permit/costs? | Y | The Employer will sign by the security gate for the Contractor to enter the premises. | Y | The Contractor will not be able to enter the site without a permision |  |  | 10 |  | 3 | 30 |  | The contractor must report by the security gate or call the contract Supervisor to sign for him/her. |  |  | Contract Manager
14 | Were the suppliers qualification and experience defined or requested? | Y | Contractor to submit related work experience and qualifications of the staff with tender returnables | Y | The Contractor's employees not suitably qualified |  |  | 10 |  | 3 | 30 |  | The Contractor must provide qualification and training records for all staff. The artisans are to be qualified and inpossesion of a valid trade test certificate (where applicable) and have the relevant experience. |  |  | Contract Manager
15 | Were quality requirements/objectives set in the contract? | Y | Poor workmanship - work not to specification or standard |  |  |  | Will definitely occur | 10 | Minor Financial loss together with minor injuries | 3 | 30 |  | The Contractor must submit his/her quality policy, implement a quality system and maintain the quality system for the duration of the contract. |  |  | Contract Manager
16 | Was CIDB compliance specified in the contract? | [8 empty] | 0 | 0
17 | Was a implemetation program requested in the contract? | Y | No project implementation plan.Lack of competencies/skills. |  |  |  | Will definitely occur | 10 | Minor Financial loss together with minor injuries | 3 | 30 |  | The Contractor must provide the project implementation plan and the skills /competency of his/her staff. The support system in case the appointed staff can not bring the expected results. |  |  | Contract Manager
18 | What are the licence fees considerations? | N/A | [7 empty] | 0 | 0
19 | Does the contract implemetation method pose a risk to the organisation? | N/A | [7 empty] | 0 | 0
20 | Any risk for contract to be up and running? | Y | No contract in place for services for January 2017 | Y | Plant reliability may be compromised in January 2017 if contract is not in place in time |  | Will definitely occur | 5 | Minor Financial loss together with minor injuries | 5 | 25 |  | Expedite contract presentation to the tender committee and make the tender validity period shorter |  |  | Contract Manager
21 | Does the contract pose a risk for loss of opportunities? | N |  | N | [5 empty] | 0 | 0
22 | Was the learning curve for staff considered? | N/A | [7 empty] | 0 | 0
23 | Is there any risk of double processing or duplication of work or in contract? | N |  | N | [5 empty] | 0 | 0
24 | Is this contract dependant on additional external consultants/ costs? | N |  | N | [5 empty] | 0 | 0
25 | What interfacing equipment was identified not forming part of this contract e.g. LAN? | N/A | [7 empty] | 0 | 0
26 | Does the contract pose a threat for downtime or service disruption? | Y | Labour unrest from the part of the contractor | Y | Plant maintenance will be affected and subsequently it will lead to plant breakdowns |  | Will definitely occur | 3 | Minor Financial loss together with minor injuries | 8 | 24 |  | NEC TSC to stipulate that the contractor must make provision for additional workforce during strikes |  |  | Contracts Manager
27 | Were the quality of deliverables specified? | Y |  | N | [5 empty] | 0 | 0
28 | Are there any threat of safety with contract deliverables? | N |  | N | [5 empty] | 0 | 0
29 | Was the acceptance criteria specified? | N/A | [7 empty] | 0 | 0
30 | Will this contract impact other contracts/projects? | N |  | N | [5 empty] | 0 | 0
31 | Was the cost of implementation considered? | Y |  | N | [5 empty] | 0 | 0
32 | Was the cost of training considered? | Y | The Contractor's staff may not be adequately trained | N | Contractor will make provision to train his/her own staff. Training requirements are specified in the contract. |  |  |  |  | 0 | 0 |  | The Employer to provide the necessary training. The conditions of training are set out in the contract. |  |  | Contract Manager
33 | Are there a risk for costs in mistakes? | N |  | N | [5 empty] | 0 | 0
34 | Does the contract pose in financial risk or exposure? | N |  | N | [5 empty] | 0 | 0
35 | Are there any risk i.t.o. skills and availability? | N |  | N | [5 empty] | 0 | 0
36 | Were the employment rquirements considered? | Y |  | N | [5 empty] | 0 | 0
37 | Does the contract require a change management component? | N |  | N | [5 empty] | 0 | 0
38 | Will the contract have an impact on working conditions? | N |  | N | [5 empty] | 0 | 0
39 | Will the contract have an effect on existing job descriptions? | N |  | N | [5 empty] | 0 | 0
40 | Could the contract affect staff morale? | N |  | N | [5 empty] | 0 | 0
41 | Does the contract specify compliance to specific standards? | Y | Compliance to Directive 32-421,Act 85 of 1993, GVLE001, GVLE010, GVLE 002, GVLE003, GVLIR0007, Unique No: 32-4,GVLOB 0010,32-136,GLVIR 0044 and BULLETIN 80 / 2007 | Y |  |  |  | 10 |  | 3 | 30 |  | The Employer to issue the following documents to the Contractor : Directive 32-421,Act 85 of 1993,GVLE001,GVLE010,GVLE 002, GVLE003,GVLIR0007,Unique No: 32-4,GVLOB 0010,32-136,GLVIR 0044 and BULLETIN 80 / 2007 |  |  | Contract Manager
42 | Could the contract lead to negative reactions? | N |  | N |  |  |  | 0 |  | 0 | 0
43 | Was the cost of maintenance considered? | Y |  | N |  |  |  | 0 |  | 0 | 0
44 | Is a Disaster Recovery Plan required? | N/A | [5 empty] | 0 |  | 0 | 0
45 | Could there be a risk i.t.o. supplier vulnerabilities? | N |  | N |  |  |  | 0 |  | 0 | 0
46 | Could the contract/ data result in lack in customer service? | N |  | N |  |  |  | 0 |  | 0 | 0
47 | Were legal requirements captured or referred to? | Y |  | N |  |  |  | 0 |  | 0 | 0
48 | Could industrial action have an effect on contract execution/steps taken? | Y | Performance of the service will be interrupted | Y | Breakdowns will increase and not be attended to |  |  | 3 |  | 8 | 24 |  | NEC TSC to stipulate that the contractor must make provision for additional workforce during strikes |  |  | Contracts Manager
49 | What role will weather conditions play in the excution of the contract? | Y | Rainy season will increase the number of breakdowns | Y | Plant availability due to wet coal will be affected |  |  | 3 |  | 8 | 24 |  | Implement and enforce Wet Coal Readiness plan |  |  | Contracts Manager
50 | Is the contract period the best option? | Y |  | N |  |  |  | 0 |  | 0 | 0
51 | What communications risk exist for the contract? | N |  | N |  |  |  | 0 |  | 0 | 0
52 | Are there any procurement risks? | N |  | N |  |  |  | 0 |  | 0 | 0
53 | Does time constraints pose a risk to the contract? | Y | Contract ends in 2022 March 31 | Y | No service can be rendered in April 2022 if there is no contract in place |  |  | 4 |  | 6 | 24 |  | Expedite the process of placing a new contract in place |  |  | Contract Manager
54 | Any risks in scope increasing? | N |  | N |  |  |  | 0 |  | 0 | 0
55 | Any risks in the costs/ analysis of the contract? | Y | Unforseen events happening |  |  |  |  | 0 |  | 0 | 0 |  | 0% to 10% in the contingency will cater for unknown costs. |  |  | Contract Manager
56 | Other | [6 empty] | 0 |  | 0 | 0
57 | Other | [6 empty] | 0 |  | 0 | 0
58 | Other | [6 empty] | 0 |  | 0 | 0
59 | Other | [6 empty] | 0 |  | 0 | 0
60 | Other | [6 empty] | 0 |  | 0 | 0
Contract Risk Assessment Questionnaire / Signatures
I have reviewed the information contained in this Contract Risk Assessment - Questionnaire and agree:
| Name |  | Title | Signature | Date
(YYYY/MM/DD)
The signatures above indicate an understanding of the purpose and content of this document by those signing it. By signing this document, they agree to this as the formal Contract Risk Assessment Questionnaire document.
[6 empty] | 1 | Ignore_event is negligible | 9 | Negligible Impact
[6 empty] | 2 | Remote_has happened somewhere | 1 | Either Minor Financial loss or Minor Injuries
[6 empty] | 3 | Highly unlikely event will occur | 1 | Minor Financial loss together with minor injuries
[6 empty] | 4 | Conceivable but unlikely | 1 | Either significant business loss, significant financial loss, or significant fatalities
[6 empty] | 5 | Unusual but possible | 1 | Significant business loss together with financial loss or fatalities
[6 empty] | 6 | Possible | 1 | Significant business loss together with fatalities
[6 empty] | 7 | Event can occur | 1 | Significant business loss together with financial loss as well as fatalities
[6 empty] | 8 | Might well be expected | 1 | Severe loss of either business opportunties, or severe financial loss, or many fatalities
[6 empty] | 9 | Will probably occur | 1 | Severe loss of business opportunties together with financial loss or many fatalities
[6 empty] | 10 | Will definitely occur | 1 | Severe financial loss together with many fatalities
Severe loss of business opportunties together with financial loss as well as many fatalities
Catastrophic impact on Eskom and or BU
Note on D29: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on I29: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on K28: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on M28: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on M29: Use this column to estimate the amount of impact or severity of the risk.
Note on N29: This column is computed as probability x impact. Once all risks have been entered, sort this column inascending order rank the risks.
Note on O29: Use this column to identify what needs to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on R29: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.
Note on S29: Use this column to identify which team member is responsible for tracking this risk and its changes in probability and impact. The assignee is not necessarily the person responsible for solving the problem, as risks often require escalation outside the team.

## Categories
Supplementary Information to Contract Strategy and Risk Assessment Rev1
Compiled by: Chris Roos
Category
Interface Definitions
Which existing contracts are most closely associated with this contract?
Was an interface meeting held with the associated contract supervisors to identify any mutual short comings?
Was any short comings identified in the associated contracts, if so list and advise how these shortcomings will be addressed?
Please indicate contractual continuity between this contract and the associated contracts?
Give reasons for no interface short comings?
Have any contractual duplications been identified, if so list and advise how these duplications will be addressed?
What are the dependency contracts for this contract not yet established?
What actions have been taken to fast track or influence initiation of dependency contract?
Production
Describe and explain method for contract implementation.
Are there any risk to the business i.e.. time to be up and running with the contractual/project execution?
What are the opportunities for the business, stemming from this contract?
What opportunities are there for the business outside of this contract?
Are there any risks involved from a "learning curve"?
Are there any risk of double processing, please list and identify mitigation strategy.
Extend of outside consultants required to assist in the execution of this contract?
What interfacing equipment will be required for this contract?
Are the business at any risk i.e. period of disruption?
What steps have been taken to ensure quality of deliverables?
What steps have been taken to ensure safety of contract deliverables and or system?
Marketing
What are the customer acceptance criteria?
What is the impact of the contract/project on any current systems?
Are there any spin-offs
Will the contract enhance the image of the company, if so, explain how?
Financial
Cost of the contract/ project?
What is the impact of the contract on company cashflow?
Is there a borrowing requirement?
What is the time to breakeven?
What recommendations can be made from the Payback period, NPV and IRR?
What is the cost of the implementation (if applicable)?
What is the cost of training (if applicable)?
List and describe any risk in cost of mistakes?
What is the level of financial risk (scale 1-10, 10 being high)/
Personnel
Are there any risk from a skills and skill availability perspective?
What are the training requirements and the associated costs?
Are there employment requirements, if so what are the associated costs?
Are the any risk for resistance to change or implementation of the contract?
Will the contract have any impact on the working conditions?
Are there any effects on job descriptions?
Are there any effect of morale?
Administration and Other
Are there any compliance requirements with national and international standards?
Are there any reasons for negative reactions from any stakeholders?
Does this contract include the cost of maintenance, if yes explain?
If not, explain thinking process?
What provision has been made for Disaster Recovery Planning, describe and list impact on cost?
Are there any known vulnerabilities in using a supplier?
Are there any risk of a lack in customer service?
What legal considerations were tabled?