NEC3 Engineering and Construction

Short Contract (ECSC3)

| A contract between | Eskom Holdings SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and |  |  |
| for | Grootvlei Theseus 1 T226 and Everest Perseus T389 Tower Refurbishment |  |
| Contents: | Compiled in accordance with CIDB Standard for Uniformity in Construction Procurement (May 2010 amendments) | Page No. |
| Part C1 | Agreements & Contract Data |  |
|  | C1.1 Form of Offer and Acceptance | [●] |
|  | C1.2 Contract Data provided by the Employer | [●] |
|  | C1.2 Contract Data provided by the Contractor | [●] |
| Part C2 | Pricing Data |  |
|  | C2.1 Pricing assumptions | [●] |
|  | C2.2 Price List | [●] |
| Part C3 | Scope of Work |  |
|  | C3.1 Works Information | [●] |
| Part C4 | Site Information | [●] |
| Documentation prepared by: | Y.Makale |  |

C1 Agreements & Contract Data

# C1.1 Form of Offer and Acceptance

## Offer

The Employer, identified in the Acceptance page signature block on the next page, has solicited offers to enter into a contract for the procurement of:

# Grootvlei Theseus 1 T226 and Everest Perseus T389 Tower Refurbishment

The tenderer, identified in the signature block below, having examined the documents listed in the Tender Data and addenda thereto as listed in the Tender Schedules, and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the Contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| The offered total of the Prices exclusive of VAT is | R |
| --- | --- |
| Value Added Tax @ 15% is | R |
| The offered total of the Prices inclusive of VAT is | R |
| (in words) |  |

This Offer may be accepted by the Employer by signing the form of Acceptance overleaf and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: | (Insert name and address of organisation) |  |  |  |
| Name & signature of witness |  |  | Date |  |
| Tenderer’s CIDB registration number: |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an Agreement between the Employer and the tenderer upon the terms and conditions contained in this Agreement and in the Contract that is the subject of this Agreement.

The terms of the Contract, are contained in:

Part 1	Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part 2	Pricing Data

Part 3	Scope of Work: Works Information

Part 4	Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule, which must be signed by the duly authorised representative(s) for both parties.

The tenderer shall within one week of receiving a completed copy of this Agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this Agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this Agreement.

Notwithstanding anything contained herein, this Agreement comes into effect on the date when the tenderer receives one fully completed and signed copy of this document, including the Schedule of Deviations (if any) together with all the terms of the contract as listed above.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer | (Insert name and address of organisation) |  |  |  |
| Name & signature of witness |  |  | Date |  |

Note: 	If a tenderer wishes to submit alternative tender offers, further copies of this document may be used for that purpose, duly endorsed, ‘Alternative Tender No. _____ ‘

## Schedule of Deviations

Note:

- To be completed by the Employer prior to award of contract.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

# C1.2 Contract Data

## Data provided by the Employer

[Instructions to the contract compiler:  (delete these two notes in the final draft of a contract)

- Please read the relevant clauses in the NEC3 Engineering and Construction Short Contract (April 2013) (ECSC3) before you enter data.  The number of the principal clause is shown for most statements however other clauses may also use the same data.

- Where the following symbol is used “[●]” - data is required to be inserted.]

Completion of the data in full is essential to create a complete contract.

| ## Clause |  |  | ## Statement |  | ## Data |
| --- | --- | --- | --- | --- | --- |
|  |  |  | ## General |  |  |
| 10.1 |  |  | The Employer is (Name): |  | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |
|  |  |  | Address |  | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |
| 10.1 & 14.4 |  |  | The Employer’s representative to whom the Employer in terms of clause 14.4 delegates his actions is (Name): |  | Yoliswa Makale |
|  |  |  | Address |  | Eskom Transmission, 120 Henry Street, Bloemfontein |
|  |  |  | Tel No. |  | (051) 404 5283 |
|  |  |  | E-mail address |  | MakaleYC@eskom.co.za |
| 11.2(11) |  |  | The works are |  | Replacement of bent tower members and reinforcing of affected subs at: - Everest Perseus 1 275kV tower 389 and - Grootvlei Theseus 1 400kV tower 226 |
| 11.2(13) |  |  | The Works Information is in |  | the document called ‘Works Information’ in Part 3 of this contract. |
| 11.2(12) |  |  | The Site Information is in |  | the document called ‘Site Information’ in Part 4 of this contract. |
| 11.2(12) |  |  | The site is |  | Everest Perseus 1 275kV Tower 389 and Grootvlei Theseus 1 400kV Tower 226 |
| 30.1 |  |  | The starting date is. |  | TBC |
| 11.2(2) |  |  | The completion date is. |  | TBC |
| 13.2 |  |  | The period for reply is |  | 1 weeks |
| 40 |  |  | The defects date is |  | 52 weeks after Completion |
| 41.3 |  |  | The defect correction period is |  | 2 weeks |
| 50.1 |  |  | The assessment day is the |  | 25 of each month. |
| 50.5 |  |  | The delay damages are |  | 0.1% per day up to a limit of 10% of the total contract amount |
| 50.6 |  |  | The retention is |  | 5% |
| 51.2 |  |  | The interest rate on late payment is |  | [●]% [Insert a rate only if a rate less than 0.5% per week of delay has been agreed] |
| 80.1 |  |  | The Contractor is not liable to the Employer for loss of or damage to the Employer’s property in excess of |  | R0.0 |
|  |  |  | Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) apply? |  | No |
| 93.1 |  |  | The Adjudicator is |  | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |
|  |  |  | Address |  | [●] |
|  |  |  | Tel No. |  | [●] |
|  |  |  | Fax No. |  | [●] |
|  |  |  | e-mail |  | [●] |
| 93.2(2) |  |  | The Adjudicator nominating body is: |  | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body |
| 93.4 |  |  | The tribunal is: |  | arbitration. |
|  |  |  | The arbitration procedure is |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |
|  |  |  | The place where arbitration is to be held is |  | Bloemfontein, South Africa |
|  |  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |
|  |  |  | The conditions of contract are the NEC3 Engineering and Construction Short Contract (April 2013) and the following additional conditions Z1 to Z11 which always apply: |  |  |
| Z1 |  | Cession delegation and assignment |  |  |  |
| Z1.1 |  | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |
| Z1.2 |  | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |
| Z2 |  |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |
| Z2.1 |  |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |
| Z2.2 |  |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer. |  |  |
| Z2.3 |  |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the starting date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |
| Z2.4 |  |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |  |
| Z3 |  | Confidentiality |  |  |  |
| Z3.1 |  | The Contractor does not disclose or make any information arising from or in connection with this contract available to others except where required by this contract. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to others where required by this contract the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |
| Z3.2 |  | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Employer. |  |  |  |
| Z3.3 |  | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |
| Z3.4 |  | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Employer. All rights in and to all such images vests exclusively in the Employer. |  |  |  |
| Z3.5 |  | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |
| Z4 |  | Waiver and estoppel: Add to clause 12.2: |  |  |  |
| Z4.1 |  | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties or their delegates or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |
| Z5 |  |  | Health, safety and the environment |  |  |
| Z5.1 |  |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and - undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |
| Z5.2 |  |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |
| Z6 |  | Provision of a Tax Invoice and interest. Add to clause 50 |  |  |  |
| Z6.1 |  | The Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the correctly assessed amount due for payment. |  |  |  |
| Z6.2 |  | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |
| Z6.3 |  | The Contractor is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |
| Z7 |  | Notifying compensation events |  |  |  |
| Z7.1 |  | Delete from the last sentence in clause 61.1, “unless the event arises from an instruction of the Employer.” |  |  |  |
| Z8 |  | Employer’s limitation of liability; Add to clause 80.1 |  |  |  |
| Z8.1 |  | The Employer liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand). |  |  |  |
| Z9 |  | Termination: Add to clause 90.2, after the words "or its equivalent": |  |  |  |
| Z9.1 |  | or had a business rescue order granted against it. |  |  |  |
| Z10 |  | Addition to Clause 50.5 |  |  |  |
| Z10.1 |  | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data (if any), the Employer may terminate the Contractor’s obligation to Provide the Works. |  |  |  |
|  |  | If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |  |  |
| Z11 | Ethics |  |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |  |
| Affected Party |  |  |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subconsultants or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |  |
| Coercive Action |  |  |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |  |
| Collusive Action |  |  |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |  |
| Committing Party |  |  |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees, |  |
| Corrupt Action |  |  |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |  |
| Fraudulent Action |  |  |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |  |
| Obstructive Action |  |  |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |  |
| Prohibited Action |  |  |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |  |
| Z11.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |  |  |  |
| Z11.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |  |  |  |
| Z11.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |  |  |  |
| Z11.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |  |  |  |

Z12		Insurance

Z _12.1	Replace core clause 82 with the following:

| Insurance cover | 82 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 82.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |  |  |
|  | 82.2 | The Contractor provides the insurances stated in the Insurance Table A, from the starting date until the earlier of Completion and the date of the termination certificate. |  |  |
|  |  |  | INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity; Cover provided until. Loss of or damage to the works; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance; The Employer’s certificate of Completion has been issued. Loss of or damage to Equipment, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance; The Defects Certificate has been issued. The Contractor’s liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Works; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by the applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law.. |  |
|  | 82.3 |  | The Employer provides the insurances as stated in the Insurance Table B - INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document.. |  |

| Z13 | Nuclear Liability |  |
| --- | --- | --- |
| Z13.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z13.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z13.3 | Subject to clause Z13.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z13.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z13.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z14 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z14.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z14.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z14.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z14.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z14.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z14.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z14.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

## Data provided by the Contractor (the Contractor’s Offer)

The tendering contractor is advised to read both the NEC3 Engineering and Construction Short Contract (April 2013) and the relevant parts of its Guidance Notes (ECSC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on page 31 of the ECSC3 April 2013 Guidance Notes.

Completion of the data in full is essential to create a complete contract.

| 10.1 | The Contractor is (Name): | [●] |
| --- | --- | --- |
|  | Address | [●] |
|  | Tel No. | [●] |
|  | Fax No. | [●] |
|  | E-mail address | [●] |
| 63.2 | The percentage for overheads and profit added to the Defined Cost for people is | [●]% |
| 63.2 | The percentage for overheads and profit added to other Defined Cost is | [●]% |
| 11.2(9) | The Price List is in | the document called ‘Price List’ in Part 2 of this contract. |
| 11.2(10) | The offered total of the Prices is [Enter the total of the Prices from the Price List]: | R[●] excluding VAT [in words] [●] excluding VAT |

C2 Pricing Data

# C2.1 Pricing assumptions

Entries in the first four columns in the Price List are made either by the Employer or the tendering contractor

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

All Prices are to be shown excluding VAT unless instructed otherwise by the Employer in Tender Data or in an instruction the Employer has given before the tenderer enters his Prices.

If there is insufficient space in the Price List which follows, state in which document the Price List is contained.

# C2.2 Price List

As per attached BOQs

C3:  Scope of Work

# C3.1 Works Information

1. Description of the works

Everest Perseus 1 275kV - Tower 389 Refurbishment

Replacement of the damaged tower members and the reinforcement the affected stubs.

A crane would be required to support the tower during the replacement procedure.

A conclusive bill of material needs to be drawn up on site to identify all affected tower members and associated weights.

The contractor is to submit a detailed method statement for approval by Eskom LES before conducting any work.

The contractor will conduct a detailed risk analysis, management and mitigation for the associated activities.

All replacement members can be cut and drilled on site in the absence of drawings.

- The maximum weight as seen on the table above is 13.82 tons.

- To account for the construction and wind loads a factor of about 2.5 is applied.

- A minimum of 35 ton crane is required to temporarily support the structure during refurbishment.

- Excavate around the tower leg to expose the foundation cap and to ensure enough space to carry out work.

- Cutting and drilling may be on site in the absence of manufacturing drawings.

- Where there are no lengths of the members given, the contractor is required to measure the required length on site. The stub must be reinforced first followed by the main leg member, crossing diagonals and ultimately the redundant bracings.

- All nuts must be punched and painted with a calcium based paint to prevent corrosion.

- The tower members must be galvanised to a minimum of 85μm (SANS121:2000)

- All tower members to be fabricated using S355JR grade of steel

- Bolts for the lattice structure shall be metric to SABS 136-1991 grade 6.8 with length as per SABS135-1991. All steel members within 5m from the ground level in lattice structure shall be fitted with anti-theft fasteners in at least one hole per side of the member. The anti-theft fasteners will be of minimum 8.8 grade strength bolts and shall involve metal deformation during installation.

- After the members have been replaced, the concrete cap will be casted with the top surface chamfered at an angle to prevent water collection.

- Ensure suitable back filling material after completion of the foundation construction. The material shall be mechanically compacted to a minimum of 90% of the dry density of the undisturbed material.

Grootvlei Theseus 1 400kV – Tower 226 Refurbishment

Replacement of the damaged tower members and the reinforcement the affected stubs.

A crane would be required to support the tower during the replacement procedure.

The contractor is to supply a detailed method statement on all activities for the refurbishment of the bent members and reinforcing of the stub.

A conclusive bill of material needs to be drawn up on site to identify all affected tower members and associated weights.

The contractor is to submit a detailed method statement for approval by Eskom LES before conducting any work.

The contractor will conduct a detailed risk analysis, management and mitigation for the associated activities

- The maximum weight as seen on the table above is 15 tons.

- To account for the construction and wind loads a factor of about 2.5 is applied.

- A minimum of 38 ton crane is required to temporarily support the structure during refurbishment

- Excavate around the tower leg to expose the foundation cap and to ensure enough space to carry out work.

- Remove the bent members on the leg and cut off the bent portion of the stub.

- Take measurements, mark off and drill members on site. The hole pattern on the main leg is be maintained on all the new joints.

- Where there are no lengths of the members given, the contractor is required to measure the required length on site. The stub must be reinforced first followed by the main leg member, crossing diagonals and ultimately the redundant bracings.

- All nuts must be punched and painted with a calcium based paint to prevent corrosion.

- The tower members must be galvanised to a minimum of 85μm (SANS121:2000)

- All tower members to be fabricated using S355JR grade of steel

- Bolts for the lattice structure shall be metric to SABS 136-1991 grade 6.8 with length as per SABS135-1991. All steel members within 5m from the ground level in lattice structure shall be fitted with anti-theft fasteners in at least one hole per side of the member. The anti-theft fasteners will be of minimum 8.8 grade strength bolts and shall involve metal deformation during installation.

- After the members have been replaced, the concrete cap will be casted with the top surface chamfered at an angle to prevent water collection.

- Ensure suitable back filling material after completion of the foundation construction. The material shall be mechanically compacted to a minimum of 90% of the dry density of the undisturbed material.

Risk and mitigations

The following high level risks were identified with recommended mitigations. It is important to note that the contractor still needs to identify and analyse the risks specific to each activity.

2.  Drawings

The drawings of the towers are old and hard to read. The contractor will have to cut and drill members on site

3. Specifications

Health and safety risk management

The Contractor shall control his/her activities and processes in accordance with the Occupational Health & Safety Act No. 85 of 1993, Eskom’s Safety, Health, Environmental and Quality Policy 32-727 and Eskom’s Contractor Health and Safety Requirements 32-136, Safety, Health and Environment Specification, Baseline Risk Assessment and all other related Eskom and Construction Regulations.

Environmental constraints and management

The Contractor shall control his activities and processes in accordance with Eskom’s Safety, Health, Environmental and Quality Policy 32-727. The Eskom EMP provides for the Aspects and Impacts that will

require management and must be followed strictly during construction of micro-piles foundation of anchors and other additional and related works of the project in the Southern Grid. For tendering purposes, contractor shall prepare a separate mitigation plan for all environmental concerns raised through the EMP and in any other relevant forum such clarification meetings

Any changes to the approved environmental mitigation plan (method statement / EMP) shall be reported and approved by the Grid Environmental Manager and Project Manager prior to the commencement of work and during construction.

In addition, the Contractor is required to ensure that all goods, services or works supplied in terms of this tender also conform to all applicable environment legislation(s), Eskom’s Contractor Health and Safety Requirements 32-136, SHE Specification and all other related Eskom and Construction Regulations.

The contractor is to send a flash report for any environmental incidences that has occurred on site as soon as possible or within 24 hours to the Grid Environmental Manager and PM clearly stating any impact to the environment.

No environmental records shall be destroyed or discarded by the supplier. Eskom and the supplier shall agree that the supplier retains certain environmental records.

Waste generated during construction of the works must be disposed of at a registered site and contractor shall retain records of disposal.

Deviations from these requirements will be regarded as a non-conformance. Should there be concerns regarding environmental performance and non-conformance to environmental requirements, management engagements and interventions will be introduced to determine a means to addressing the shortfalls.

Once these interventions have been explored and exhausted, then the Eskom supplier disciplinary process must be followed.

Defective steel members to be delivered to Beta or Everest substation for scrapping.

Quality assurance requirements

The Contractor shall adhere to the Quality Management System Standard such as ISO 9001:2015 Quality Management System requirements.

4. Constraints on how the Contractor Provides the Works

4.1  Meetings

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Inaugural meeting | After contract award | Contractor’s Site Office or MS Teams | PM, QS, Site Supervisor, EA, Grid safety and environmental representatives and the Contractor. |
| Toolbox talk and risk assessment | Daily before work begins. | Contractor’s Site Office | Contractor with employees and Site Supervisor. |
| Risk register and compensation events | As necessary. | Contractor’s Site Office | PM, Contractor and Site Supervisor. |
| Overall contract progress and feedback meeting | Monthly on site. | Contractor’s Site Office | PM, Contractor, Site Supervisor, and Grid representatives. |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works. Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting. Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

4.2  Use of standard forms

Contractual communication

- All correspondence is to be addressed to the Project Manager with a sequential numbering system.

- All contract communication to be done using the standard forms as per this contract and will be attachments to email.

Site communication

- Site instruction issued by the Site Supervisor with instruction from PM.

- Any communication to be addressed to the PM.

- Contractor daily site diary which must be signed daily and be kept up to date at all times.

## 4.3 Invoicing and payment

The Z clauses make reference to invoicing procedures stated here in this Works Information. Also include a list of information which is to be shown on an invoice.   The following text is provided as a guide; revise to suit actual requirements.

In terms of core clause 50 the Contractor assesses the amount due and applies to the Employer for payment.  The Contractor applies for payment with a tax invoice addressed to the Employer as follows:

______________________________________________________________________

The Contractor includes the following information on each tax invoice:

- Name and address of the Contractor

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- The total Price for Work Done to Date which the Contractor has completed;

- Other amounts to be paid to the Contractor;

- Less amounts to be paid by or retained from the Contractor;

- The change in the amount due since the previous payment being the invoiced amount - excluding VAT, the VAT and including VAT;

- (add other as required)

The Contractor attaches the detail assessment of the amount due to each tax invoice showing the Price for Work Done to Date for each item in the Price List for work which he has completed.

4.4 Records of Defined Cost

The Contractor is to keep proof / invoices of all costs incurred for a compensation event and submit them to the Project Manager if requested.

### 4.5  Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

If the ASGI-SA requirements are to be included in this contract specify constraints which Contractor must comply with after contract award in regard to any ASGI-SA requirements.  The ASGI-SA Compliance Schedule completed in the returnable tender schedules is reproduced here.  If ASGI-SA does not apply, delete this paragraph.

The Contractor complies with and fulfils the Contractor’s obligations in respect of the Accelerated and Shared Growth Initiative - South Africa in accordance with and as provided for in the Contractor’s ASGI-SA Compliance Schedule stated below

.

[Insert the agreed ASGI-SA Compliance Schedule here]

The Contractor shall keep accurate records and provide the Employer with reports on the Contractor’s actual delivery against the above stated ASGI-SA criteria.   [Elaborate on access to and format of records and frequency of submission etc.]

The	 Contractor’s failure to comply with his ASGI-SA obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract.

### 4.6  BBBEE and preferencing scheme

Specify constraints which Contractor must comply with after contract award in regard to any Broad Based Black Economic Empowerment (B-BBEE) or preferencing scheme measures.

4.7  Facilities to be provided by the Contractor

The Contractor shall provide ablution facilities, first aid and firefighting facilities as required by the Occupational Health and Safety Act.

The Contractor supplies all plant and materials required for Providing the Works.

There are no Office or Telephone facilities available on site. The Contractor is to provide his own facilities on site and ensure that these facilities are kept in a clean condition to Eskom’s satisfaction.

There are no Toilet facilities available on site. The Contractor is to provide his own toilet facilities on site and ensure that these facilities are kept in a clean condition to Eskom’s satisfaction. No work on site will be allowed to commence before the toilet facilities are available on site.

4.8  Title to material from excavation and demolition

The Contractor shall control his activities and processes in accordance with Eskom’s Construction Safety, Health and Environmental Management 32-136, SHE Specification

The Contractor shall establish a refuse control system. All waste is to be collected and disposed of as required by Eskom and the Local Authority.

4.9  Design by the Contractor

The Contractor must design the works as per the Eskom’s Standard for the Construction of overhead power lines, 240-47172520 TRMSCAAC1, Rev 5.2.

4.10  Cataloguing requirements by the Contractor

N/A

5.  Requirements for the programme

A comprehensive and fully detailed programme is to be submitted within the seven (7) days after the inaugural meeting and should be in MS Project format, indicating all milestones and critical dates. This programme must first be approved by the Project Manager and must be updated weekly or as requested by the Project Manager.

The following dates shall be clearly reflected on the programme:

Starting and completion dates for all activities as well as relevant key dates for hold or witness points. All relevant significant activities shall be shown in order to monitor the progress on site or in the workshop. The programme shall also reflect a 1-week period for inspection and correcting of Defects before the completion date.

Updated programme must be displayed on site office and must be available at all project site meetings reflecting progress to date.

6. Services and other things provided by the Employer

Not Applicable

No free issue material will be provided by the Employer

C4:  Site Information

# C4.1: Information about the site at time of tender which may affect the work in this contract

## 1. Access limitations

Entry to the site is governed by the Grid’s Lines Engineering Assistant and the property owners and the Contractor shall adhere to all regulations given. All employees are to sign the Workers declaration on entering and leaving the working area. The property owners must be informed before any work commences.

The Contractor must have an Eskom certified and authorized ORHVS person available on site at all times in accordance with Eskom’s Construction Safety, Health and Environmental Management 32-136. The authorized ORHVS person is to have a valid first aid certificate. The authorization procedure for a permit to work shall be done before the Contractor commences work on site.

It is the Contractor’s responsibility to ensure that the authorization procedure for a permit to work is obtained before access to the work can be given. The contact person is Mr Francois Du Toit at +27 57 388 2121 and at email address DuToitGF@eskom.co.za to arrange for the authorization.

The Contractor will be required to have an Eskom certified and authorized ORHVS person available in each area where work is being performed.

Access on site is restricted to the area in which the Contractor is working and which has been barricaded. Strictly no movement outside the barricaded working area unless escorted by authorized L&S personnel.

The majority of the work is to be performed in the servitude of Everest-Perseus 1 275kV line Tower 398 and Grootvlei Theseus 1 400kV Tower 226. The Contractor will take all necessary precautions and work in conjunction with Eskom personnel.

The Contractor is to supply Eskom with Police clearance for all the employees on site before Work commences. The Basic conditions of employment will be adhered to. Any work done outside this duration must be arranged through the Site Supervisor.

## 2.  Ground conditions in areas affected by work in this contract

Before any excavation commences, it will be the responsibility of the Contractor to ascertain from the “Senior Official” the position of any existing services on site. Once these are indicated to the Contractor they shall be deemed “known”. Any costs incurred for repairs to any “known” services shall be for the Contractor’s account.

## 3.  Hidden and other services within the site

Provide details of underground or other hidden services which the Contractor may encounter whilst doing the work. Instructions about how to deal with them if encountered should be included in the Works Information.

## 4.  Details of existing buildings / facilities which Contractor is required to work on

The Work is to be carried out on the servitude of Everest-Perseus 1 275kV line Tower 398 and Grootvlei Theseus 1 400kV Tower 226. The Contractor is to take note of the surrounding Farmers’ property and Eskom property like towers, conductors, and equipment, etc.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za

Except those actions which can only be done by the Employer as a Party to the contract.

If June 2005 Edition applies, delete April 2013 and insert June 2005

State whether attached as a ‘PDF’ file in terms of Eskom’s licence, or to be obtained from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za.