## Cover sht
Dimbaza 66/11kV Substation Refurbishment
Site Activities
A | Fixed Charged Items |  |  | R
B | Time Related items (Will be paid as % of work done to date) |  |  | R
C1 | Civil Works |  |  | R
C2 | Erection of Steelwork |  |  | R
C3 | Erection of Equipment |  |  | R
C4 | Conductor, Clamps and Earthing |  |  | R
C5 | MV Cabling |  |  | R
C6 | Control Plant |  |  | R
C7 | Control Building |  |  | R
C8 | Decommissioning |  |  | R
Labe Schedule
…………………………………… ………………. |  |  | 14% Vat | R
Signature Date |  |  | Total | R
CODE | STANDARD ACTIVITY | UNIT | QTY | RATE | TENDER PRICE
A | FIXED CHARGE ITEMS
A.1 | Contractual requirements i.e., insurance’s, statutory contributions, etc. | sum | 1 |  | R
A.2 | Site Establishment - including, offices, telephone and fax, lighting, fencing, toilet facilities, water, etc.
A.2.1 | Office complete as per works information | sum | 1 |  | R
A.2.2 | Staff Accommodation | sum | 1 |  | R
A.2.3 | Stores | sum | 1 |  | R
A.2.4 | Water, Sanitation and Electricity | sum | 1 |  | R
A.2.5 | Communication | sum | 1 |  | R
A.3 | Removal of site establishment on completed of the contract (Inclusive of rehabilitation in accordance with EMP & EA) | sum | 1 |  | R
Sub Total 'A' |  |  |  |  | R
B | TIME RELATED ITEMS
B.1 | Outages
Contractors must allow for outages being done of weekends.
B.1.1 | Provide detailed breakdown of outage scope complete with time allocations to be handed to the Project Co-ordinator at the outage planning meeting prior to the outage - [minimum of 48 hours] | ea | 2 |  | R
B.2 | Programme and Planning
B.2.1 | Contractors must allow for the preparation of a detailed programme reflecting the outage dates. | ea | 2 |  | R
B.3 | On-going site Costs
B.3.1 | Office complete as per works information | wks | 28 |  | R
B.3.2 | Staff Accommodation | wks | 28 |  | R
B.3.3 | Stores | wks | 28 |  | R
B.3.4 | Water, Sanitation and Electricity | wks | 28 |  | R
B.3.5 | Communication | wks | 28 |  | R
B.4 | Supervision | wks | 28 |  | R
B.5 | Site Security as per works information | wks | 28 |  | R
B.6 | Plant and Equipment | wks | 28 |  | R
B.7 | Cost for Health and Safety measures | wks | 28 |  | R
B.8 | Other time related charges (specify hereunder): | wks | 28 |  | R
Sub Total 'B' |  |  |  |  | R
TOTAL CARRIED FORWARD TO SUMMARY PAGE 'B'

## Civil Works 1
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C1 |  | Civil Works
1.1 | D-EC-862 Set 11 | Extra over all excavations:
1.1.1 | Sht 11 Rev 5 | Intermediate material (Provisional amount). | m³ | 10 | n/a
1.2 |  | Paving (Existing paved area):
1.2.1 |  | Lift & stack paving bricks neatly for re-use (See scope for more detail). | m² | 120 | n/a
1.3 |  | Cable trench cover (750mm):
1.3.1 |  | Remove and stack neatly existing trench covers. (See scope for more detail). | m | 40 | n/a
1.4 |  | Road crossing cable trench (6 Pipe):
1.4.1 |  | Supply, prepare and install 6 pipe cable trench, entrance & covers (6m Pipe Lenght). | no | 1
1.5 |  | Cable trench kerbing:
1.5.1 |  | Remove existing cable trench kerbing on cable trench ramp areas. | m | 40 | n/a
1.6 |  | Paving:
1.6.1 |  | Prepare area and re- install existing paving bricks (See scope for more detail). | m² | 20 | n/a
1.7 |  | Cable trench cover (750mm):
1.7.1 |  | Install existing trench covers. | m | 20 | n/a
1.8 |  | Cable trench cover (750mm):
1.8.1 |  | Supply and install. | m | 260
1.9 |  | Cable trench cover (1500mm):
1.9.1 |  | Supply and install. | m | 15
1.10 |  | Trench kerbing:
1.10.1 |  | Supply, prepare area and install. | m | 80
1.11 |  | Cable Trench ramp (10m):
1.11.1 |  | Supply and install to suppliers specifications (R1-R4). | no | 4
1.12 |  | Yard Stone (Stock Pile):
1.12.1 |  | Remove and stockpile yard stone for re-use. | m³ | 10 | n/a
1.13 |  | Yard Stone (Stock Pile):
1.13.1 |  | Re-install clean stock pile yard stone (Not to be mixed with ground see Project Specification) | m³ | 10 | n/a
1.14 |  | Yard Stone:
1.14.1 |  | Supply, prepare and install. | m³ | 50
1.15 |  | Weed killer:
1.15.1 |  | Supply and spray. | m² | 1800
1.16 |  | Waste bins:
1.16.1 |  | Supply bins for waste materials. | no | 4
1.17 | D-EC-862 Set 11 | Trenching (Earth Grid):
1.17.1 | Sht 04 Rev 5 | Excavate and compact for main earth grid. (Provisional Amount) | m | 130 | n/a |  | n/a
Balance C/F

## Civil Works 2
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C1 |  | Civil Works
1.18 | D-EC-862 Set 11 | Waste bins disposal of general waste:
1.18.1 | Sht 11 Rev 5 | Removable of waste material from site to nearest registered landfill site (Project specification). | trips | 24 | n/a
n/a
Total C1

## Steel Erection 1
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C2 |  | Steelwork Erection
2.1 | D-EC-862 Set 11 | Brackets, bolts/washers and (Palisade fence & gates labels):
2.1.1 | Sht11 Rev 5 | Supply and install label brackets and labels. | item | sum
2.2 | D-EC-862 Set 11 | Breaker supports (66kV):
2.2.1 | Sht 6 Rev 5 | Take delivery, assemble, erect and bolt in position (CB1). | no | 1 | n/a
2.3 |  | Tubular busbar support (11kV):
2.3.1 |  | Supply, assemble, erect and bolt in position (TB101 - TB104). | no | 4
2.4 |  | Isolator support (11kV):
2.4.1 |  | Supply, assemble, erect and bolt in position (IS101 - IS106). | no | 6
2.5 |  | Medium equipment support (2,5m):
2.5.1 |  | Supply, assemble, erect and bolt in position (CT6). | no | 1
2.6 |  | Medium equipment cap detail (M1):
2.6.1 |  | Supply, assemble, erect and bolt in position (Ct6). | no | 1
2.7 |  | Cable support bracket (medium equipment support 2,5m) :
2.7.1 |  | Supply and bolt in positions (CT1 - CT6 & VT101). | no | 7
2.8 |  | Single Core Cable Sealing End:
2.8.1 |  | Supply, assemble, erect and bolt in position (CSE101-CSE102). | no | 2
2.9 |  | Lighting mast (14m):
2.9.1 |  | Take delivery,assemble, erect and bolt in position (LM2 & LM3). | no | 2 | n/a
2.10 |  | Bracket (Busbar label):
2.10.1 |  | Supply and bolt in position (LB1-LB4,LB9 & LB10). | no | 6
2.11 |  | Bracket (Transformer Label):
2.11.1 |  | Supply and bolt in position (LB5 - LB8). | no | 4
2.12 |  | Bracket (Phasing discs label):
2.12.1 |  | Supply and bolt in position (D4 -D9, D31-D36, D55 - D72). | no | 27
2.13 |  | Cable support bracket (medium equipment support 2.5m) :
2.13.1 |  | Supply and bolt in positions (VT101). | no | 1
2.14 |  | Trench cover brackets.
2.14.1 |  | Supply and install cable trench cover support brackets: | no | 10
2.15 |  | "U" bolts:
2.15.1 |  | Supply and install. | no | 27
2.16 |  | M16 x 40mm Gal steel set screw bolts, nuts & washers for phasing disc brackets:
2.16.1 |  | Supply and install (D4 -D9, D31-D36, D55 - D72) | no | 27
2.17 |  | M10 x 30mm Stainless steel set screw bolt, nut & 2 x washers for phasing disc (2/disc):
2.17.1 |  | Supply and install (D4 -D9, D31-D36, D55 - D72) | no | 54
Balance C/F

## Steel Erection 2
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C2 |  | Steel Erection (Continued) Balance B/F
2.18 |  | M12 x 35mm Stainless steel set screw bolt, nuts and 2 x washers for equipments labels:
2.18.1 |  | Supply and install. | no | 64
2.19 |  | M12 x 45mm Gal. Steel set screw bolts, nuts, 2 x washers and 1 x tapper washers for SA's:
2.19.1 |  | Supply and install (SA10 - SA15) | no | 24
2.20 |  | M12 x 65mm Stainless steel set screw bolts, nuts & 2 x washers for Breaker palm clamps:
2.19.1 |  | Supply and install (CB1 & CB2). | no | 48
2.20 |  | M12 x 65mm Stainless steel set screw bolts, nuts & 2 x washers for Isolator palm clamps:
2.20.1 |  | Supply and install (IS5, IS6, IS9 & IS10). | no | 240
2.21 |  | M16 x 40mm Gal. Steel set screw bolts, nut washer & tapper washer for CT`s and VT`s:
2.21.1 |  | Supply and install (CT1 - CT6 & VT101 x 3). | no | 36
2.22 |  | M16 x 40mm Gal. Steel set screw bolts, nut and washer for busbar labels bracket :
2.22.1 |  | Supply and install (LB1-LB4,LB9 & LB10). | no | 8
2.23 |  | M12 x 40mm Gal. Steel set screw bolts, nut and washer for busbar labels :
2.23.1 |  | Supply and install (LB1-LB4,LB9 & LB10). | no | 16
2.24 |  | M16 x 35mm Stainless steel set screw bolt, nut and 2 x washers for floodlights:
2.24.1 |  | Supply and install. | no | 12
Total C2

## Equipment Erection 1
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C3 |  | Equipment Erection
3.1 | D-EC-862 Set 11 | Isolators control arms(66kV):
3.1.1 | Sht 7 Rev5 | Take delivery, erect and bolt in position (IS5, IS6, IS10 & IS11). | no | 4 | n/a
3.2 |  | Current transformers (66kV):
3.2.1 |  | Take delivery, erect and bolt in position (CT1-CT6). | no | 6 | n/a
3.3 |  | Post insulators (132kV): TRFR 2 & TRFR 3 Bays
3.3.1 |  | Take delivery, erect and bolt in position (PI16 - PI21) | no | 6 | n/a
3.4 |  | Post insulators (66kV): Tubular busbar
3.4.1 |  | Take delivery, erect and bolt in position (TB101- TB104)x3 | no | 12 | n/a
3.5 |  | Post insulators (66kV):CSE
3.5.1 |  | Take delivery, erect and bolt in position (CSE101 & CSE102)x6 | no | 12 | n/a
3.6 |  | Surge arrestors (66kV):
3.6.1 |  | Take delivery, erect and bolt in position (SA10-SA15). | no | 6 | n/a
3.7 |  | Surge arrestors (11kV):
3.7.1 |  | Take delivery, erect and bolt in position (SA101 - SA106)x3. | no | 18 | n/a
3.8 |  | Voltage transformers (11kV):
3.8.1 |  | Take delivery, erect and bolt in position (VT101) x 3 | no | 3 | n/a
3.9 |  | Isolators (11kV):
3.9.1 |  | Take delivery, erect and bolt in position (IS101 - IS106). | no | 6 | n/a
3.10 | D-EC-862 Set 11 | Flood lights:
3.10.1 | Sht 7 Rev5 | Supply, install & wire (LM4-LM6). | no | 12
3.11 | Project Specification | Flood lights:Reuse
3.11.1 |  | Take delivery, install & wire (LM1 & LM2). | no | 6 | n/a
3.12 |  | Labels (Equipment):
3.12.1 |  | Supply and install as per label schedule. | no | 32
3.13 |  | Key tags (Equipment):
3.13.1 |  | Supply and install as per label schedule. | no | 10
3.14 |  | Locks non standard (Equipment):
3.14.1 |  | Supply and install as per label schedule. | no | 10
3.15 |  | Substation earths:
3.15.1 |  | Supply. | no | 3
3.16 |  | Substation link stick:
3.16.1 |  | Supply. | no | 2
3.17 |  | Substation mimic board:
3.17.1 |  | Supply and install. | no | 1
Balance C/F

## Equipment Erection 2
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C3 |  | Equipment Erection (Continued) Balance B/F
3.18 |  | Fire extinguishers:
3.18.1 |  | Supply and install fire extinguishers with class fiber box: | no | 2
3.19 |  | Transport:
3.19.1 |  | Transport secondary / primary plant equipment with LDV 1 ton vehicle: | km | 200
3.20 |  | Transport:
3.20.1 |  | Transport secondary / primary plant equipment with LDV 8 ton vehicle: | km | 200
3.21 |  | Miscellaneous equipment / material:
3.21.1 |  | Supply or install equipment / material as requested. | item | sum | n/a | n/a | 30000 |  | 80000
Total C3

## Conductor, Clamps & Earthing 1
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C4 |  | Conductor, Clamps and Earthing
4.1 | D-EC-862 Set 11 | Long Rod 66kV Strain Assembly (Bull conductor)
4.1.1 | Sht 8 Rev5 | Take delivery, prepare and install. | no | 12 | n/a
4.2 |  | Long Rod 66kV Suspension Assembly
4.2.1 |  | Take delivery, prepare and install. | no | 6 | n/a
4.3 |  | Insulated Bull conductor (0 - 8m):
4.3.1 |  | Take delivery, prepare and install. | no | 24 | n/a
4.4 |  | Centipede conductor (0 - 9m):
4.4.1 |  | Take delivery, prepare and install in tubular busbars. | no | 9 | n/a
4.5 |  | Centipede conductor (0 - 5m):(11kV side)
4.5.1 |  | Take delivery, prepare and install jumpers. | no | 27 | n/a
4.6 |  | Centipede conductor (0 - 5m):(66kV side)
4.6.1 |  | Take delivery, prepare and install jumpers. | no | 39 | n/a
4.7 |  | Aluminium tubes (120mm OD x 10,5m 11kV Busbar):
4.7.1 |  | Take delivery, cut to size and install. | no | 9 | n/a
4.8 |  | Aluminium tubes (120mm OD x 1,5m Cabling sealing end):
4.8.1 |  | Take delivery, cut to size and install. | no | 6 | n/a
4.9 |  | Clamp (K/EX):
4.9.1 |  | Take delivery, prepare and install. | no | 39 | n/a
4.10 |  | Clamp (KC/EXC):
4.10.1 |  | Take delivery, prepare, crimp and install. | no | 12 | n/a
4.11 |  | Clamp (SPC/EPC):
4.11.1 |  | Take delivery, prepare, crimp and install. | no | 96 | n/a
4.12 |  | Clamp (KCP/EXCP):
4.12.1 |  | Take delivery, prepare and install. | no | 12 | n/a
4.13 |  | Clamp (TC/ETC):
4.13.1 |  | Take delivery, prepare and install. | no | 30 | n/a
4.14 |  | Clamps Tubular:
4.14.1 |  | Take delivery, prepare and install. | no | 60 | n/a
4.15 |  | Clamp (Tubular plain end cap):
4.15.1 |  | Take delivery, prepare and install. | no | 24 | n/a
4.16 |  | Clamp (Tubular busbar end conductor cap):
4.16.1 |  | Take delivery, prepare and install. | no | 18 | n/a
4.17 |  | Acrylic covers:
4.17.1 |  | Take delivery, prepare and install. | no | 18 | n/a
Balance C/F

## Conductors, Clamps & Earthing 2
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C4 |  | Conductor,Clamps and Earthing (Continued) Balance B/F
4.18 | D-EC-862 Set 11 | Putty and tape:
4.18.1 | Sht 8 Rev5 | Supply and install putty and tape for clamps. | no | 18
4.19 | D-EC-862 Set 11 | Earthing (Main Earthmat, round 10mm).
4.19.1 | Sht 4 Rev5 | Take delivery, prepare and install.(Provisional) | m | 200 | n/a
4.20 |  | Flexible earth leads for security gate:
4.20.1 |  | Supply,prepare and install | no | 4
4.21 |  | Earthing (Palisade fence, flat 50 x 3mm Drawing for quantity ):
4.21.1 |  | Take delivery, prepare and install. | item | sum | n/a
4.22 |  | Voltage transformers 11kV earthing.
4.22.1 |  | Take delivery of 50 x 3mm flat copper, prepare and install: | no | 3 | n/a
4.23 |  | NECRT 11kV earthing.
4.23.1 |  | Take delivery of 50 x 3mm flat copper, prepare and install: | no | 2 | n/a
4.24 |  | Earth Transformer & neutral (TRFR 2 &TRFR 3) complete:
4.24.1 |  | Take delivery of 50 x 3mm flat copper, prepare and install: | item | sum | n/a
4.25 |  | Flexible earth leads (66kV Current transformers):
4.25.1 |  | Supply, prepare and install. | no | 6
4.26 |  | Earthing balls:
4.26.1 |  | Take delivery, prepare and install. | no | 48 | n/a
Total C4

## MV Cabling
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C5 |  | Conductor,Clamps and Earthing (Continued) Balance B/F
5.1 | D-DT-0854 Rev 8 | 22kV MV cable.
5.1.1 | SET 8 SHT 1 & 3 | Excavate and compact for MV Cable. | m | 200
5.2 |  | 22kV MV cable:
5.2.1 |  | Supply and compact suitable backfill for MV Cable. | m | 200
5.3 |  | Cable route marker:
5.3.1 |  | Supply and install cable route marker. | no | 45
5.4 |  | 22kV MV cable:
5.4.1 |  | Take delivery and lay MV XLPE 630mm² 1 core cable complete. | m | 240 | n/a
5.5 | Proj. Spec | Outdoor heat shrink joint, earth leads & lugs etc.(Cable term. end) for XLPE 630mm² 1 core cable:
5.5.1 |  | Supply and Install on all three phases (6 ends). | no | 6
5.6 | D-DT-0854 Rev 8 | Concrete MV cable cover:
5.6.1 | SET 8 SHT 1 & 3 | Supply and Install cover complete. | m | 200
5.7 |  | Remove excess cable trench soil:
5.7.1 |  | Remove unsuitable soil from trench. | m³ | 40 | n/a
5.8 |  | Warning tape for MV cabling:
5.8.1 |  | Supply and install after cable installation. | m | 200
5.9 |  | Cleats for cable sealing end complete:
5.9.1 |  | Supply and bolt in position on cable sealing end (CSE101 - CSE102) | no | 16
Total C5

## Control Plant 1
DIMBAZA 66/11KV SUBSTATION REFURBISHMENT
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total Price Rands
C6 |  | Control Plant
6.1 |  | Take delivery and lay LV protection cables including cable labels:
6.1.1 |  | Install LV protection cable. Provisional (see item 1.6.4 in Project specifications) | m | 4012 | N/A
6.2 |  | Take delivery and lay telecomms cables including cable labels:
6.2.1 |  | Install telecomms cable. Provisional (see item 1.6.4 in Project specifications) | m | 430 | N/A
6.3 |  | Take delivery and lay remote engineering access cables including cable labels:
6.3.1 |  | Install access cable. Provisional (see item 1.6.4 in Project specifications) | m | 358 | N/A
6.4 |  | Excavate for all control plant cables in natural ground:
6.4.1 |  | Excavate 0-500mm (Provisional) | m | 49.48 | N/A
6.5 |  | Supply of glands and shrouds and make off protection cables complete:
6.5.1 |  | Gland protection cables with Pratley No. 1 Armoured glands and shrouds (Provisional) | no | 120
6.6 |  | Supply of glands and shrouds and make off protection cables complete:
6.6.1 |  | Gland protection cables with Pratley No. 2 Armoured glands and shrouds (Provisional) | no | 84
6.7 |  | Supply of glands and shrouds and make off protection cables complete:
6.7.1 |  | Gland protection cables with Pratley No. 3 Armoured glands and shrouds (Provisional) | no | 36
6.8 |  | Supply of glands and shrouds and make off protection cables complete:
6.8.1 |  | Gland protection cables with Pratley No. 4 Armoured glands and shrouds (Provisional) | no | 0
6.9 |  | Drill holes for glands where required:
6.9.1 |  | Drill holes complete (Provisional) | no | 2.4 | N/A
6.1 |  | Take delivery and install swing frame cabinets complete:
6.10.1 |  | Bolt cabinets in place (see item 1.6.4 in Project specifications) | no | 0 | N/A
6.11 |  | Loom, number & terminate LV protection cores complete:
6.11.1 |  | Make off cable cores (Provisional amount) | no | 1266 | N/A
6.12 |  | Loom, number & terminate Telecomms & Telecontrol cores complete:
6.12.1 |  | Make off cable cores (Provisional amount) | no | 650 | N/A
6.13 |  | Loom, number & terminate Remote Eng. Access & Recorders cores complete:
6.13.1 |  | Make off cable cores (Provisional amount) | no | 304 | N/A
6.14 |  | Take delivery and install junction boxes complete:
6.14.1 |  | Install junction boxes (VT/CT/ISOLATOR). | no | 2 | N/A
6.15 |  | Take delivery and install Bus Section scheme complete:
6.15.1 |  | Bolt in place. | no | 0 | N/A
6.16 |  | Take delivery and install Bus Coupler scheme complete:
6.16.1 |  | Bolt in place. | no | 0 | N/A
6.17 |  | Take delivery and install Bus Zone scheme complete:
6.17.1 |  | Bolt in place. | no | 0 | N/A
6.18 |  | Take delivery and install Distance Feeder scheme complete:
6.18.1 |  | Bolt in place. | no | 0 | N/A
6.18a |  | Take delivery and install iBox, Mounting Hardware and PSU complete:
6.18a.1 |  | Assemble and bolt in place. | no | 0 | N/A
Balance C/F

## Control Plant 2
DIMBAZA 66/11KV SUBSTATION REFURBISHMENT
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total Price Rands
C6 |  | Control Plant
6.19 |  | Take delivery and install Rural Feeder scheme complete:
6.19.1 |  | Bolt in place. | no | 0 | N/A
6.2 |  | Take delivery and install Cable Feeder scheme complete:
6.20.1 |  | Bolt in place. | no | 0 | N/A
6.21 |  | Take delivery and install Diff/Distance Feeder scheme complete:
6.21.1 |  | Bolt in place. | no | 0 | N/A
6.22 |  | Take delivery and install Current Diff Feeder scheme complete:
6.22.1 |  | Bolt in place. | no | 0 | N/A
6.23 |  | Take delivery and install OLTC scheme complete:
6.23.1 |  | Bolt in place. | no | 0 | N/A
6.24 |  | Take delivery and install Transformer scheme complete:
6.24.1 |  | Bolt in place. | no | 0 | N/A
6.25 |  | Take delivery and install Capacitor Bank scheme complete:
6.25.1 |  | Bolt in place. | no | 0 | N/A
6.26 |  | Take delivery and install UFLS scheme complete:
6.26.1 |  | Bolt in place. | no | 0 | N/A
6.27 |  | Take delivery and install AC/DC Panels complete:
6.27.1 |  | Bolt in place. | no | 0 | N/A
6.28 |  | Take delivery and install AC/DC Modules complete:
6.28.1 |  | Bolt in place. | no | 0 | N/A
6.29 |  | Take delivery and install Oil Sump Pump complete:
6.29.1 |  | Bolt in place. | no | 0 | N/A
6.3 |  | Take delivery and install Generator Supply Interface complete:
6.30.1 |  | Assemble and bolt in place. | no | 0 | N/A
6.31 |  | Take delivery and install Remote Access SS PC complete:
6.31.1 |  | Bolt in place. | no | 1 | N/A
6.32 |  | Take delivery and install Remote Access RASM complete:
6.32.1 |  | Bolt in place. | no | 0 | N/A
6.33 |  | Take delivery and install Remote Access Module (Mario Box) complete:
6.33.1 |  | Bolt in place. | no | 1 | N/A
6.34 |  | Take delivery and install Meinberg GPS complete:
6.34.1 |  | Bolt in place. | no | 1 | N/A
6.35 |  | Take delivery and install Recorder (Sherlog/PvZ) complete:
6.35.1 |  | Bolt in place. | no | 0 | N/A
6.36 |  | Take delivery and install Metering Module complete:
6.36.1 |  | Bolt in place. | no | 0 | N/A
Balance C/F

## Control Plant 3
DIMBAZA 66/11KV SUBSTATION REFURBISHMENT
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total Price Rands
C6 |  | Control Plant
6.37 |  | Take delivery and install Vectograph complete:
6.37.1 |  | Bolt in place. | no | 1 | N/A
6.38 |  | Modify chequer plate covers for new panels complete:
6.38.1 |  | Cut to size, touch up paintwork where needed and fit into new positions. | m²
6.39 |  | Supply, Install & paint angle iron to back/front of panel complete:
6.39.1 |  | Install angle iron on panel for trench cover support. | no | 0
6.4 |  | Decommission LV protection cables:
6.40.1 |  | Remove cables from trenches and pack in demarcated area (Provisional). | m |  | N/A
6.41 |  | Take delivery and lay remote engineering access ETHERNET cables incl cable labels:
6.41.1 |  | Install access cable. Provisional (see item 1.6.4 in Project specifications) | m | 0 | N/A
6.42 |  | Take delivery and lay remote engineering access piping/trunking:
6.42.1 |  | Install piping for access cable. Provisional (see item 1.6.4 in Project specifications) | m | 148 | N/A
6.43 |  | Take delivery and install GPS antenna incl cable and labels:
6.43.1 |  | Install GPS antenna. Provisional (see item 1.6.4 in Project specifications) | no | 1
6.44 |  | Take delivery and install Battery Charger cabinets complete:
6.44.1 |  | Bolt cabinets in place (see item 1.6.4 in Project specifications) | no | 0
6.45 |  | Take delivery and install Yard AC Chop-over/Outdoor Plug JB complete:
6.45.1 |  | Bolt cabinets in place (see item 1.6.4 in Project specifications) | no | 1
TOTAL C6

## Secondary Plant 1 (hidden)
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C6 |  | Secondary Plant
6.1 |  | Trenching (Depth 0 - 600mm):
6.1.1 |  | Excavate for all secondary protection cables in natural ground. | m | 60 | n/a
6.2 |  | Protection cables:
6.2.1 |  | Take delivery and lay. | m | 1624 | n/a
6.3 |  | Telecoms cables:
6.3.1 |  | Take delivery and lay | m | 96 | n/a
6.4 |  | Remote engineering access cables:
6.4.1 |  | Take delivery and lay. | m | 44 | n/a
6.5 |  | Remote engineering access cables (Ethernet):
6.5.1 |  | Take delivery and lay. | m | 44 | n/a
6.6 |  | Cable numbers (Remote access, protection & telecoms):
6.6.1 |  | Supply, prepare and install. | no | 808 | n/a
6.7 |  | Core numbers & lugs (Remote access, protection & telecoms):
6.7.1 |  | Supply. | no | 670 | n/a
6.8 |  | Glands & shrouds (No.1):
6.8.1 |  | Supply, prepare and install. | no | 25 | n/a
6.9 |  | Glands & shrouds (No.2):
6.9.1 |  | Supply, prepare and install. | no | 10 | n/a
6.10 |  | Glands & shrouds (No.3):
6.10.1 |  | Supply, prepare and install. | no | 12 | n/a
6.11 |  | Glands & shrouds (No.4):
6.11.1 |  | Supply, prepare and install: | no | 0 | n/a
6.12 |  | Holes for glands:
6.12.1 |  | Drill holes. | no | 47 | n/a
6.13 |  | Swing frame cabinets:
6.13.1 |  | Take delivery and install. | no | 7 | n/a
6.14 |  | Loom, number & terminate (LV protection):
6.14.1 |  | Make off cable cores. | no | 220 | n/a
6.15 |  | Loom, number & terminate (Telecoms & Telecontrol):
6.15.1 |  | Make off cable cores. | no | 50 | n/a
6.16 |  | Take delivery and install Cable Feeder scheme complete:
6.16.1 |  | Bolt in place. | no |  | n/a
6.17 |  | Take delivery and install Rural Feeder scheme complete:
6.17.1 |  | Bolt in place. | no |  | n/a
Balance C/F

## Secondary Plant 2 (hidden)
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C6 |  | Secondary Plant (Continued) Balance B/F
6.18 |  | Junction boxes (CT / VT / Iso):
6.18.1 |  | Take delivery and install. | no | 2 | n/a
6.19 |  | Bus Zone scheme:
6.19.1 |  | Take delivery and install. | no | 2 | n/a
6.20 |  | Distance Feeder scheme:
6.20.1 |  | Take delivery and install. | no | 0 | n/a
6.21 |  | Rural Feeder scheme:
6.21.1 |  | Take delivery and install. | no | 0 | n/a
6.22 |  | Cable Feeder scheme:
6.22.1 |  | Take delivery and install. | no |  | n/a
6.23 |  | Diff / Distance Feeder scheme:
6.23.1 |  | Take delivery and install. | no | 0 | n/a
6.24 |  | Current Diff scheme
6.24.1 |  | Take delivery and install. | no | 0 | n/a
6.25 |  | OLTC scheme:
6.25.1 |  | Take delivery and install. | no | 0 | n/a
6.26 |  | Transformer scheme:
6.26.1 |  | Take delivery and install. | no | 0 | n/a
6.27 |  | UFLS scheme:
6.27.1 |  | Take delivery and install. | no | 0 | n/a
6.28 |  | AC/DC Moduless:
6.28.1 |  | Take delivery and install. | no | 0 | n/a
6.29 |  | Remote Access SS PC:
6.29.1 |  | Take delivery and install. | no | 0 | n/a
6.30 |  | Generator Supply Interface:
6.30.1 |  | Take delivery and install. | no | 0 | n/a
6.31 |  | Remote Access Module:
6.31.1 |  | Take delivery and install. | no | 1 | n/a
6.32 |  | Meinberg GPS:
6.32.1 |  | Take delivery and install. | no | 1 | n/a
6.33 |  | Recorder (Sherlog / PvZ):
6.33.1 |  | Take delivery and install. | no | 0
6.34 |  | Metering Module:
6.34.1 |  | Take delivery and install. | no | 2
Balance C/F

## Secondary Plant 3 (hidden)
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C6 |  | Secondary Plant (Continued) Balance B/F
6.35 |  | Vectograph:
6.35.1 |  | Take delivery and install. | no | 1 | n/a
6.36 |  | Remote Access RASM:
6.36.1 |  | Take delivery and install. | no | 0 | n/a
6.37 |  | AC/DC panels:
6.37.1 |  | Take delivery and install. | no | 0 | n/a
6.38 |  | Battery charger:
6.38.1 |  | Take delivery and install. | no | 0 | n/a
Total C6

## Control Building
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C7 |  | Control Building
7.1 |  | Battery room ceiling:
7.1.1 |  | Supply, repair and install ceiling complete. | no | 1
7.2 |  | Battery room door:
7.2.1 |  | Take down the existing damaed door complete. | no | 1 | n/a
7.3 |  | Battery room door:
7.3.1 |  | Supply and install door complete. | no | 1
7.4 |  | Battery room labels:
7.4.1 |  | Supply and install Battery room labels. | no | 3
7.5 |  | Relay room floor:
7.5.1 |  | Prepare and paint control room floor. | m³ | 60
7.6 |  | Toilet:
7.6.1 |  | Supply and install all toilet accessories (Provisional). | item | sum
7.7 |  | Toilet doors:
7.7.1 |  | Supply and install all toilet doors complete. | no | 2
7.8 |  | COC for electrical works:
7.8.1 |  | Provide COC for all electrical works. | no | 1 | n/a
Total C7

## Decommission 1
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C8 |  | Decommissioning
8.1 |  | 66kV Circuit breaker complete:
8.1.1 |  | Remove Circuit breaker for reuse (existing TRFR 1). | no | 1 | n/a
8.2 |  | 66kV Circuit breaker Steel support for reuse:
8.2.1 |  | Remove Circuit breaker steel support(existing TRFR 1). | no | 1 | n/a
8.3 |  | Security fence :
8.3.1 |  | Remove Razor Mesh fence c/w 5m gate. | m | 340 | n/a
8.4 |  | Razorwire Concete post
8.4.1 |  | Decommissioning Razorwire Concete post | no | 135 | n/a
8.5 |  | 11kV Jumpers c/w clamps:
8.5.1 |  | Remove jumpers for scrap | no | 18 | n/a
8.6 |  | 11kV Glass Insulator strings:
8.6.1 |  | Remove clamps for scrap. | no | 18 | n/a
8.7 |  | 10MVA 66/11kV Transformer 1
8.7.1 |  | Disconnect, and transport Transformer to KWT Stores | no | 1 | n/a
8.8 |  | NEC Transformer 1
8.8.1 |  | Disconnect, and transport NEC to KWT Stores | no | 1 | n/a
8.9 |  | 66kV Surge arrestor: (steel supoorts shall not be removed)
8.9.1 |  | Remove surge arrestor for scrap.(TRFR 1) | no | 3 | n/a
8.1 |  | 11kV Voltage transformers:
8.10.1 |  | Remove Voltage transformers for scrap.(TFR 1) | no | 3 | n/a
8.11 |  | 11kV Voltage Transformer Steel support
8.11.1 |  | Remove VT steel support for reuse.(TFR 1). | no | 1 | n/a
8.12 |  | 11kV Voltage Transformer
8.12.1 |  | Remove VT foundations, refill & compact .(TFR 1). | no | 1 | n/a
8.13 |  | 11kV Current transformers:
8.13.1 |  | Remove Current transformers for scrap.(TFR 1) | no | 3 | n/a
8.14 |  | 11kV Current Transformer Steel support
8.14.1 |  | Remove CT steel support for reuse.(TRFR 1). | no | 1 | n/a
8.15 |  | 11kV CurrentTransformer
8.15.1 |  | Remove CT foundations, refill & compact .(TRFR 1). | no | 1 | n/a
8.16 |  | Medium Equipment support foundations
8.16.1 |  | Remove foundations, refill & compact. | no | 3 | n/a
8.17 |  | 11kV Circuit breaker:
8.17.1 |  | Remove Circuit breaker for scrap.(TRFR 1) | no | 1 | n/a
Balance C/F

## Decommission 2
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. DRG. No. Proj. Specification | Description of the item | Unit | Quantity | Material Rate | Labour Rate | Total | Total | Total Price
[7 empty] | Material Cost | Labour Cost | Rands
C7 |  | Decommissioning
7.18 |  | 11kV Circuit breaker Steel support
7.18.1 |  | Remove Circuit breaker steel support for reuse.(TRFR 1). | no | 1 | n/a
7.19 |  | 11kV Circuit Breaker foundations
7.19.1 |  | Remove Circuit breaker foundations, refill & compact .(TRFR 1). | no | 1 | n/a
7.20 |  | 11kV Line Isolator:
7.20.1 |  | Remove Line Isolator for scrap.(TRFR 1) | no | 1 | n/a
7.21 |  | 11kV Line Isolator Steel support
7.21.1 |  | Remove Circuit breaker steel support for reuse.(TRFR 1). | no | 1 | n/a
7.22 |  | 11kV Line Isolator foundation
7.22.1 |  | Remove Line Isolator foundations, refill & compact .(TRFR 1). | no | 1 | n/a
7.23 |  | 11kV Cable Sealing End
7.23.1 |  | Remove Cable Sealing End for scrap.(TRFR 1) | no | 1 | n/a
7.24 |  | 11kVCable Sealing End Steel support
7.24.1 |  | Remove Cable Sealing End steel support for reuse.(TRFR 1). | no | 1 | n/a
7.25 |  | Transformer 11kV PI :
7.25.1 |  | Remove 11kV PI from 11kV beams. | no | 3 | n/a
7.26 |  | 11kV Cable Sealing foundations
7.26.1 |  | Remove Cable Sealing foundations, refill & compact .(TRFR 1). | no | 1 | n/a
7.27 |  | MV cable Decommissioning
7.27.1 |  | Excavate existing 630mm XLPE cable (TRFR 1) | m | 60 | n/a
7.28 |  | MV cable Decommissioning
7.28.1 |  | Remove 630mm2 XLPE cable complete with termintions . | m | 120 | n/a
7.29 |  | MV cable Decommissioning
7.29.1 |  | Backfill cable trench and compact | m | 60 | n/a
7.30 |  | 14m Lighting mast:
7.30.1 |  | Remove Light Mast for reuse | no | 1 | n/a
7.31 |  | 14m Light mast foundations
7.31.1 |  | Remove Light mast foundations, refill & compact. | no | 2 | n/a
7.32 |  | Stone kerbing
7.32.1 |  | Remove nonstandard stone kerbing to scrap | m | 150 | n/a
Total C7

## Labels 1
Dimbaza 66/11kV Substation Refurbishment
Item No. | Ref. No. | Rev | Label Designation | Label Description | Key Tag |  | Lock |  | Label Size | Qty | Unit Cost | Labour Rate | Total | Total | Total Price
[5 empty] | Yes | No | Yes | No |  |  |  |  | Material Cost | Labour Rate | Rands
C5 | Supply and install equipment labels complete
5.1 | D-EC-862
5.1.1 | Set 11 Sht 1A &B | 0 | (Main gate label) | DIMBAZA SUBSTATION |  | x |  | x |  | 2
5.2
5.2.1 |  |  | TRFR 2 | 11kV BUSBAR 1 ISOLATOR | x |  | x |  | 600 x 250 | 1
5.3
5.3.1 |  |  | TRFR 3 | 11kV BUSBAR 1 ISOLATOR | x |  | x |  | 600 x 250 | 1
5.4
5.4.1 |  |  | 66kV BUS CPLR | 66kV BKR |  | x |  | x | 600 x 250 | 1
5.5
5.5.1 |  |  | TRFR 2 | 66kV BKR |  | x |  | x | 600 x 250 | 1
5.6
5.6.1 |  |  | TRFR 3 | 11kV BKR |  | x |  | x | 600 x 250 | 1
5.7
5.7.1 |  |  | TRFR 2 | 66kV BKR |  | x |  | x | 600 x 250 | 1
5.8
5.8.1 |  |  | TRFR 3 | 11kV BKR |  | x |  | x | 600 x 250 | 1
5.9
5.9.1 |  |  | TRFR 2 | 66/11 kV |  | x |  | x | 600 x 250 | 2
5.10
5.10.1 |  |  | TRFR 3 | 66/11 kV |  | x |  | x | 600 x 250 | 2
5.11
5.11.1 |  |  | 66kV BUSBAR 1 |  |  | √ |  | √ | 600 x 250 | 2
5.12
5.12.1 |  |  | 66kV BUSBAR 2 |  |  | x |  | x | 1000 x 250 | 2
5.13
5.13.1 |  |  | 11kV BUSBAR 1 |  |  | x |  | x | 1000 x 250 | 2

## App B (1)
Dimbaza 66/11kV Substation Refurbishment
List all drawings applicable to the works or the asset and temporary works, indicating whether they are approved for use (ABU) or not.
Drawing No. | Rev | Title | AFU Attached
Substation Layouts
D-EC-862-11-1A | D0 | Station electric diagram | Yes
D-EC-862-11-1B | D0 | Station electric diagram | Yes
D-EC-862-11-2 | 5 | Site plan | Yes
D-EC-862-11-4 | 5 | Earthmat layout | Yes
D-EC-862-11-5 | 5 | Foundation layout | Yes
D-EC-862-11-6 | 5 | Steelwork marking plan | Yes
D-EC-862-11-7 | 5 | General Arrangement layout | Yes
D-EC-862-11-8 | 5 | Sections and clamps | Yes
D-EC-862-11-11 | 5 | Trench and fence layout | Yes
Control building
D-DT-5280-2A | 1 | Control room Type 'A' Trench Cover Plan Layout and Section Details | Yes
D-DT-5280-3A | 1 | Control room Type 'A' Electrical Cabling, Trunking and Earthing Layout and Details | Yes
D-DT-5281-1A | 1 | Control room Type 'A' Section and details | Yes
D-DT-5281-3C | 1 | Control room doors, Windblok Schedule and Details | Yes
D-DT-5281-5E | 0 | Control room Toilet, Battery room and Septic Tank details | Yes
Trenching 750/1500mm
D-DT-5254-5A | 0 | Trench 750mm Wide- Straight installation and sections | Yes
D-DT-5254-5B | 0 | Trench 1500mm Wide- Straight installation and sections | Yes
D-DT-5254-5C | 0 | Trench 750mm to 1500mm Wide- Straight installation and sections | Yes
D-DT-5254-5D | 0 | Trench 750mm Wide- 90 Degree Type A bend installation and sections | Yes
D-DT-5254-5E | 0 | Trench 750mm Wide- 90 Degree Type B bend installation and sections | Yes
D-DT-5254-5G | 0 | Trench 750mm 'T' type A to 750mm Wide- Straight installation and sections | Yes
D-DT-5254-5I | 0 | Trench 750mm T to 1500mm Wide Straight installation and sections | Yes
D-DT-5254-1A | 0 | Trench Covers 750mm | Yes
D-DT-5254-1B | 0 | Trench Covers 1500mm | Yes
D-DT-5254-1C | 0 | Cable covers MV | Yes
D-DT-5254-2B | 0 | Substation Road Kerbing 1000mm | Yes
D-DT-5254-2C | 0 | Substation Stone Kerbing 1000mm | Yes
D-DT-5254-2A | 0 | Substation Trench Kerbing 1000mm | Yes
D-DT-5254-3C | 0 | Substation LV Cable road duct 6 pipe | Yes
D-DT-5254-6A | 0 | Substation Trench 750mm Trench cover support manufacturing details | Yes
D-DT-5254-6B | 0 | Substation Trench 1500mm Trench cover support manufacturing details | Yes
Erection of Steelwork
D-DT-5226-2B | 0 | Tubular busbar-22kV single tubular support steelwork manufacturing details & assembly - 1,5m phase CRS | Yes
D-DT-5205-2A | 9 | Isolator STD-22kV Manual lattice support steelwork manuf det & assembly | Yes
D-DT-5213-2A | 10 | MV Cable sealing end Lattice Support steelwork manuf det & assembly | Yes
Steelwork brackets
D-EC-1763-1 | 2 | Transformer label T-bracket | Yes
D-EC-1783-02 | 0 | Cable support bracket mounted on medium equipment support | Yes
D-EC-1945 | 1 | Busbar label bracket | Yes
D-EC-1949 | 1 | Palisade Fence Label Brackets | Yes
D-EC-1938-1 | 1 | Phasing disc labels mounting bracket details | Yes
0.54/1794 | 2 | Electrical Equipment Labels "L" mounitng bracket detail | Yes
Electrical
D-DT-5217-5 | 1 | Standard lighting/lightning mast for substations (8m, 14m & 21m) cable block details | Yes
D-DT-5240-25-1 | 5 | Earthing standard general notes | Yes
D-DT-5240-25-2 | 3 | Substation - Copper connections | Yes
D-DT-0854-8-2 | 8 | MV Power Cable Trench Details | Yes
D-DT-0854-8-4 | 8 | MV Power Cable Trench Details | Yes

## App B(2)
Dimbaza 66/11kV Substation Refurbishment
List all drawings applicable to the works or the asset and temporary works, indicating whether they are approved for use (ABU) or not.
Drawing No. | Rev | Title | AFU Attached
Labels
D-DT-5015 | 1 | Sign A,B & C | Yes
D-DT-5016 | 2 | Sign DE - Procedure in case of fire | Yes
D-DT-5017 | 1 | Sign F | Yes
D-DT-5018 | 0 | Sign G | Yes
D-DT-5022-1 | 0 | Sign-DCSS1 Battery room | Yes
D-DT-5022-2 | 0 | Sign-DCSS2 Battery room | Yes
D-DT-5022-3 | 0 | Sign-DCSS3 Battery room | Yes
D-EC-2198-1 | 0 | Electrical Equipment phasing disc details | Yes
D-EC-2199-1 | 0 | Electrical Equipment Label 600 x 245 | Yes
D-EC-2199-2 | 0 | Electrical Equipment Label 1000 x 245 | Yes
Specifications
D-DT-5240-1 | 4 | Earthing standard general notes | Yes
D-DT-5240-2 | 1 | Earthing standard copper joints | Yes
D-DT-6072 | 4 | Specification: Sign ABC - unauthorized entry | Yes
D-DT-6073 | 5 | Specification: Sign DE first aid | Yes
D-DT-6074 | 5 | Specification: Sign F Prohibitive | Yes
D-DT-6075 | 3 | Specification: Sign G - hard hat area | Yes
D-DT-6081-01 | 8 | Specification: Ball joint for portable earth | Yes
D-DT-6112 | 1 | Label specifications -battery room | Yes
D-DT-6113 | 1 | Label specifications -Informative and emergency signs | Yes
D-DT-4783-2 | 3 | Strain String Assembly 66kV 1 x Bull conductor | Yes
D-DT-4783-5 | 3 | Suspension String Assembly 66kV 1 x Bull conductor | Yes

## Free issue (1) (hidden)
Dimbaza 66/11kV Substation Refurbishment
Free issue material
QTY | kV | Equipment | Description | mm/kV | Stem dia mm | Sap No.
2 | 66/22 | TRFR | 10MVA | 31 | 26 | 0185767
2 | 22 | NEC/NER/AUX Trfr & supp. | 360A 100kVa | 31 | 26 | 0182732
3 | 66 | Isolator | 1600A 25kA | 31 | 38 | 0012945
8 | 22 | Isolator | 2500A 25kA | 31 | 38 | 0012904
3 | 22 | Voltage transformers | 100VA class 0.2m+100VA | 31 | 26 | 0008746
6 | 66 | Current transformers | 2P class X 2M class 0.2 | 31 | 38 | 0180035
9 | 66 | Surge Arrestor | 10kA | 31 | 26 | 0004562
15 | 22 | Surge Arrestor | 10kA | 31 | M12 lug | 0004627
12 | 132 | Post insulators | Height 1220 PCD127 | 31 | - | 0017528
27 | 66 | Post insulators | Height 770 PCD127 | 31 | - | 0017527
2 | 66 | Breakers | 1600A 20kA | 31 | 8 hole pad | 0170220
5 | 22 | Breakers & Supports | 1250A 20kA | 31 | 38 | -
24 | - | Equipment labels |  |  |  | -
QTY | Type | Description |  | Size in mm | Total kg | Sap No.
3 | UT3 | Tee clamps (Bolted-Bolted) for Stranded Conductors |  | 12-19 to 22-29 |  | 0005638
6 | K-1 | Clamps (Bolted-Bolted) for Stranded Conductors |  | 16,3 to 26 |  | 0005684
18 | K-2 | Clamps (Bolted-Bolted) for Stranded Conductors |  | 26,5 to 26 |  | 0005626
12 | K-3 | Clamps (Bolted-Bolted) for Stranded Conductors |  | 16,3 to 38 |  | 0005685
12 | K-4 | Clamps (Bolted-Bolted) for Stranded Conductors |  | 26,5 to 38 |  | 0005634
6 | K-5 | Clamps (Bolted-Bolted) for Stranded Conductors |  | 38,3 to 38 |  | 0005151
72 | KC-2 | Stud Clamps (Bolted-Compression) for Stranded Conductors |  | 38 to 26,5 |  | 0005658
24 | KC-3 | Stud Clamps (Bolted-Compression) for Stranded Conductors |  | 38 to 38,3 |  | 0005660
12 | SPC-1 drilled | Palm Clamps (Bolted-Compression) for Stranded Conductors |  | 26,5 to(50x50) |  | 0005159
2 | STP-26 | Stud palm clamp, (Bolted-Palm) |  | -
6 | EPC-38 | Clamp peg |  | - |  | 0005176
12 | ACC-3 | Clamp Acrylic cover |  | -
6 | TBST-120/38 | Bus Stud Terminal Clamps |  | 120 to 38
18 | TBST-120/26 | Bus Stud Terminal Clamps |  | 120 to 26 |  | 0213941
12 | TBSI-120/38 | Bus Stud Terminal Clamps (In Line) |  | 120 to 38 |  | 0206323
15 | TBFS-120/127 | Fixed Bus Support Clamp |  |  |  | 0213925
6 | TBSC-120/127 | Slider Type Fixed Bus Support Clamp |  |  |  | 0206341
3 | TBCT-120/26/C | Bus Tap-off Clamp for Single & Twin Cond.(Specified Angle) |  | 120 to 18-38 |  | 0206325
12 | TBFX-120/ss | Full In-line Expansion Clamp |  | 120 to 120 |  | 0216201
15 | TBEC-120 | Tubular Bus End Cap (Plain) |  | 120 O.D. & 112 I.D. |  | 0206319
15 | TBEC-120 | Tubular Bus End Cap (Conductor) |  | 120 O.D. & 112 I.D. |  | 0206320
12 |  | Clamp Pistol 3B 5mm – 16mm D7022 |  |  |  | 0185253
12 |  | D-shackle |  |  |  | 0163400
30 |  | Meters Bull Conductor 61/4 26mm AL |  |  |  | 0014452
410 |  | Meters Centipede Conductor 37/3 78mm AL |  |  |  | 0014447
21 |  | Meters Hornet PVC insulated Conductor 19/3.25mmAL |  |  |  | 0014759
40 |  | Meters Hare Conductor 6/4.72mmAL 1/4.72mm ST |  |  |  | 0014441
90 |  | Meters Bull PVC insulated Conductor 61/4. 26mmAL |  |  |  | 0014761
3 |  | Aluminum Alloy Tubes, 12,25mx120mmØx4mm thick |  |  |  | -
6 |  | Aluminum Alloy Tubes, 12mx120mmØx4mm thick |  |  |  | -
6 |  | Aluminum Alloy Tubes, 10,25mx120mmØx4mm thick |  |  |  | -
3 |  | Aluminum Alloy Tubes, 9mx120mmØx4mm thick |  |  |  | -
6 |  | Aluminum Alloy Tubes, 7,4mx120mmØx4mm thick |  |  |  | -
3 |  | Aluminum Alloy Tubes, 250mmx120mmØx4mm thick |  |  |  | -

## Free issue (2) (hidden)
Dimbaza 66/11kV Substation Refurbishment
Free issue material
QTY | Description |  |  | Size in mm | Total kg | Sap No.
12 | Clamp pistol 3B 19mm – 30mm D6042 |  |  |  |  | 0011074
12 | Longrod 66kV insulator 12kN B/S 31mm/kV D7029 |  |  |  |  | 0167609
12 | Clev-Ball 16mm IEC 120kN D6059 |  |  |  |  | 0167508
12 | Socket-Tong 16mm 120kN D6061 |  |  |  |  | 0010270
893 | kg Round Copper Bar |  |  |  |  | 0017202
624 | kg Flat Copper Bar |  |  |  |  | 0017204
60 | Ball joint, single earth assembly |  |  |  |  | 0206118
1 | Notice pin board 1200x900 |  |  |  |  | 0172500
1 | Chair |  |  |  |  | 0171863
1 | Desk |  |  |  |  | 0171904
1 | Rack for earth leads |  |  |  |  | -
1 | Rack for link stick |  |  |  |  | -
1 | Lockable key box |  |  |  |  | -
QTY | kV | Equipment | Description | mm/kV | Stem dia mm | Sap No.
1369 | LV | Cable | BVX19DCV | - | - | -
2300 | LV | Cable | BVX12DCV | - | - | -
150 | LV | Cable | BVX4HCV | - | - | -
58 | LV | Cable | BVX2HCV | - | - | -
5739 | LV | Cable | BVX4ECV | - | - | -
276 | LV | Cable | BVX2ECV | - | - | -
432 | - | Cable | Telephone Comms | - | - | -
225 | - | Cable | Remote Comms | - | - | -
302 | - | Gland | No. 1 Cable Gland | - | - | -
120 | - | Gland | No. 2 Cable Gland | - | - | -
44 | - | Gland | No. 3 Cable Gland | - | - | -
104 | - | Cable Kocos Recorder | UVG20ACX | - | - | -
87 | - | Cable Kocos Recorder | UVG4ACX | - | - | -
46 | - | Cable Kocos Recorder | UVG8ACX | - | - | -

## Data (hidden)
*Note all fields highlighted in yellow contain a formalae and is not to be changed.
All white fields is where the the qauntities are entered.
All green is specific to a substation
Dgn no. | Description | Qauntity |  | Area | Excavations | Concrete | Cemetile prod. | Formwork | H.D. Bolts | H.D. Bolts | reinforcing kg | round cu | Bricks
[5 empty] | m3 | m3 | kg | m2 | kg | no. | kg | m
Isolators
D-DT-5205 S1 R3 | 22kV Isolator | 0 |  | 0 | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A
D-DT-5203 Sht 1 Rev 2 | 66kV isolator | 0 |  | 0 | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A
Circuit breakers
0.54/4246 rev. 0 | 88kV A.E.G Circuit breaker foundation | 0 |  |  | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A | N/A
0.54/534 rev. 5 | 66kV Reyrolle type OSM O.C.B | 0 |  |  | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A
0.54/4276 rev. 0 | 22kV GEC CB (dog box) | 0 |  |  | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A
D-DT-5200 s1 r1 | 132kV circuit bkr (soil type 1&2) | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
D-DT-5201 r1 | 66kV circuit bkr (soil type 1&2) | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Other foundations
D-EC-1929 | 3m Container foundation | 0 |  | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | N/A
D-EC-1930 | Transformer supp fdn details | 0 |  | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A
D-EC-1814 S1 | Auto recloser supporrt foundation | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
D-DT-5206 S1 R1 | Medium equipment supp. foundation | 1 |  | 0.81 | 0.6885 | 0.81 |  | 0.54 | 8.68 | 4
0.54/329 | Column foundation | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
D-DT-5051-1 | Standard lighting/lightning spike foundattion 8m type 'B' | 2 |  | 2 | 1 | 1.3 | N/A | 1.2 | 25.248 | 8 | 6.6 | N/A
D-DT-5207 | NECRT Support | 1 |  | 1.8 | 0.9 | 0.9 |  | 1.62 | 8.72 | 4
|  | area for new found. = |  | 54.51
| Transformer plinth |  |  | floor Area m2
D-EC-xxxx-9 | Bund wall floor | 1 |  | 34.6 | N/A | 3.46 | N/A | N/A | N/A | N/A | N/A | N/A
D-EC-1678-2 | Auxiliary transformer | 0 |  | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | N/A
D-EC-1678-2 | Mechanism box | 0 |  | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A
| bund wall | 34 | length in m | 15.3 | 6.885 | 3.825 | [6 empty] | 1360
|  | 0.4 | Height in m
| drainage 75mm dia pipe | 15 | length in m |  | 0.5
Yard work
KB 1157 | Bullnose edging- 1m outer fence | 195 |  |  | 7.3125 | 2.925 | 4875 | N/A | N/A | N/A | N/A | N/A
KB 1002 | cable trench curbing | 0 | 1 |  | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A
KB 1020 | Figure 8 (rollover)-road curb | 79 |  |  | 3.95 | 1.975 | 8690 | N/A | N/A | N/A | N/A | N/A
| Cable trench covers 740x300mm | 0 | 0 | N/A | N/A | N/A | N/A
| Cable corner covers 740x740mm | 0 | 0
| Main earthing | 0 |  |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A
Stoning
| 9mm Road stone | 3.1 |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 19mm yard stone | 200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Diamond mesh | 0 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Barb wire | 0 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Total qauntity | 0 |  |  | 21.236 | 15.195 | 13565 | 3.36 | 42.648 | 16 | 6.6 | 0

## Decommisioning (hidden)
Dgn no. | Description | Qauntity: compl conc. Remov. | Qauntity: below gnd | Backfill m3 | complete conc. rem m3 | exc. comp. conc. rem m3 | Concrete 100mm below gnd m3 | exc. Conc. below gnd m3 | hd bolts to be cut off | Total concrete removal
Tescor 7713/6 | 66kV Isolator foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tescor 7713/6 | 66kV bkr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tescor 7713/6 | 66kV Trfr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0
Tescor 7713/6 | 66kV Neutral CT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tescor 7713/6 | SA base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Small equipment supp. (tyalara) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| foundations Tyalara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 132kV breaker base Tyalara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.54/494 rev. 5 | 6,6-11-22kV Isolator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Smithfield VT foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Smithfield trfr foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0
0.54/4276 rev. 0 | 22kV GEC CB (dog box) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.54/308 | Medium equipment supp. foundation | 0 | 4 | 0.324 | 0 | 0 | 2.754 | 0.324 | 16 | 2.754
Cable trench |  | 0 | N/A | 0 | 0 |  | N/A |  | N/A | 0
Diamond mesh |  | 0 | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Barb wire |  | 0 | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Totals |  |  |  | 0.324 | 0 |  | 2.754 |  | 16 | 2.754