## Slide 1: Transmission Incubation Program
24 May 2022

## Slide 2: External Resource Capacity Analyses
Key Transmission services and commodities were analyzed to determine potential industry shortages which could affect the execution of the 2022-2030 TDP. TDP projections were compared to industry capacity, year on year, to establish if/when the shortage would occur.
Commodity | Forecasted Shortage/Peak | Projected Shortage | Comments
Lines Construction |  | Average 700 km p.a | Target to increase 100 km p.a minimum. Intervention underway.
Transformers (Class 3b) |  | FY2022 (14 units shortage) | 1 local supplier. Security of supply risk. Recent historical data suggests supply constraints.
Steel Manufacturing |  | FY2030 (96 653 tones) | 1 local supplier. Security of supply risk. Capacity shortfall.
Composite Insulator |  | FY2024 (322 852 units) | 1 local supplier. Security of supply risk. Capacity shortfall.
Conductor |  | FY2029 (20 018 km) | Current supplier capacities indicate a shortfall. Suppliers should be able to increase capacity.
Insulators (Glass) |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Isolators |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Current Transformers |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Surge Arresters |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Circuit Breakers |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
- No capacity shortfall for the TDP
- Capacity shortfall in the 2nd half of the TDP
- Capacity shortfall in the 1st half of the TDP

## Slide 3: Line Construction Industry Capacity Growth Focus Areas
Mechanisms of HV Line Construction Industry Capacity Growth
Incubation
Contracts
Addressing Industry Barriers
Target existing accredited Local HV Line Construction Contractors and International HV Line Construction Contractors (400 kv and 765 kv)
Procurement process and Procurement Hierarchy (TOC)
Open to accredited Incubation Contractors
Realistic Work projections
Streamline payment Process
Industry Forums
Networking Session
Support Services
Partnership & Joint Ventures
Target Local Supply Market
Formal Accreditation Process
Ring Fencing of Work Opportunities (275 kv)
Appointment of Incubation Partner
Partnering with Stakeholders (CIDB, IDC, NEF, SETA)
Training Partner
Training analysis
Review EAL HV training capabilities and support
Appointment of external training service provider to support HV line capacity development

## Slide 4: HV Line Construction Incubation Model
Technical Support & Accreditation Process
Practical Work Experience
HV Line Construction Incubation Model
Financial Support
SHEQ Support & Accreditation Process
Business Management Support
Training Support

## Slide 5: Tx Incubation Strategy
Incubatee 1
Transmission
GAP Analysis
Training
Practical Experience
Work Supervision
Facilitate Funding Allocation
Incubatee 2
Incubatee 3
Incubatee 4
Monitoring Supplier Progress
Transmission
Incubation Partner

## Slide 6: Incubated Contractor Selection Criteria
The criteria for selection will be based on the following:
  Commercial (Procurement & SDL&I)
  Technical
  SHEQ
  Financial Analyst

## Slide 7: Funding Mechanism
Funding Agency
Funding Agency
Funding Agency
Incubating Contractors
Transmission
Transmission
Transmission

## Slide 8: Program Monitoring
Contractor Performance Monitoring & Feedback
Transmission:
  Technical
  SDL&I
Incubation Partners

## Slide 9: Addressing Industry Barriers
Streamline Payment Process (Analysis of Payment Process duration)
Industry Forums (Fair Market Representation)
Networking Session (Encouraging Partnership & Joint Ventures)
Support Services (Appropriate Funding requirements to encourage investment in the Line Construction)

## Slide 10: Training Partner
Dual Support Strategy for Incubatee Training & Accreditation
EAL
Practical Training
Line Construction Course and Module alignment.
Capacity Determination
External Training Service Providers
SETA
CIDB
DTIC
Duration
Cost
Capacity
Industry Experts

## Slide 11: Supplier Engagement Session
Supplier Engagement Session 2021
Feedback
Hosted 5 Supplier Engagement Session
Topics Covered:
  Contractor Renegotiations
  Transmission World
  Procurement Process
  Local Content, B-BBEE & CIDB
  Tender Readiness Workshop
Feedback:
  Attendance representative of target audience
  Session was informative and well received by target audience
Supplier Engagement Plan 2022
Host 6 Supplier Engagement Session
No | Topic Focus | Date
1 | Line Construction (Yearly Plan) | 27 May 2022
2 | Local Content & CIDB | 30 June 2022
3 | Civil Construction & Suppliers Workshop | 28 July
4 | Line Construction | 31 August 2022
5 | Procurement | 18 October 2022
6 | Line Construction Workshop | 19 January 2023
Supplier Engagements Sessions will be hosted online
Supplier Target via CSD, Eskom Vendor Database, Eskom Tender Bulletin, CIDB Database, DTIC Database
Plan could change based on business needs

## Slide 12
THANK YOU

## Slide 13: POLASA Feedback Contactor Capacity & Incubation and Subcontracting Stream
Purpose/Goal:
Propose measures to develop adequate and sustainable industry CONTRACTOR capacity
Promote sub-contracting and Incubation – new player development and skills transfer in line with Eskom’s Supplier Development, Localisation and Industrialization framework
Transmission Task Team Objectives:
Utilise POLASA for Industry experience and consultancy role.
Understanding challengers to Line Construction Contractors
sustainability.
Analysis of previous Incubation Model failures
Transmission Incubation Model guidance
Stream Progress:
One meeting conclude with both streams
POLASA presented challengers to Line Construction Contractors sustainability
POLASA presented reason for previous Incubation Model failure.
Transmission presented outline of proposed Incubation Model and scheduled activities
Meeting Plan:
May 2022
July 2022
August 2022
October 2022
January 2023
March 2023

## Slide 14: Transmission Line Supplier Base Movements South Africa
Still Operating | Exited on/or before 2017 | Exited After 2017
Mkhulu Electro Distribution Projects | Transdeco | Babcock Ntuthuko Powerlines
Larsen and Toubro T&D SA | Edison Jehamo Power | Jyoti Structures Africa
Sygen Power | Optic 1 | Eurico Ferreira
Optipower Projects | Linear Projects | Bouygues Energies and Services
Edison Power Group | Africa Power Lines | Eurico Ferreira/EPG JV
Siyavuya | KEC | 
Power Line Africa | Abengoa/Inabensa | 
Melees | Stefanutti Stocks | 
 | RGF | 
 | LPJSA | 
 | Kalpataru | 
 | Conco | 
Dwindling Local Supplier Base over the years with a few left in implementation of the current PDP Plans
Ramagale Holdings
To be noted: the above list is not exhaustive but gives an indication of supplier movements within the industry. Details discussed in the next slides.
Source: POLASA: 2020 /21and Team Analysis

## Slide 15: Contracts
The revised TDP (expedited projects), the funding challenges and the duration of incubation creates a volatile environment when trying to accurately predict the amount of supply capacity that will be needed in the short-term to adequately meet the Transmission demand. Hence, the type of Contracting Model that selected must have the ability to accommodate this volatile environment while ensuring that Transmission has sufficient capacity that will meet its short-term needs while allowing for growth of its local market.
There are multiple theories that are in the business with regards to the most appropriate methods of contracting i.e., Turnkey, Piece Meal Contracting and Panel Contracts. Each of these Contracting Models have their advantages and disadvantages, however based on the objective of Transmission Incubation Model and the volatile environment that surrounding the supply capacity issues, the most optimal method of contracting would be the Panel Contract Model.
The Panel Contract Model (if correctly implemented) ensures that supply capacity both locally and internationally are available as and when required with no commitments on Transmission. This method allows for the distribution of work based on performance and can keep suppliers sustainable over a period of time.
The Panel Contract Model can be designed to allow contractors that graduate from the incubation process to immediately migrate to the panel thereby supplementing local contracting capacity.

## Slide 16: Technical Selection Criteria
Item | Description |  |  | Point Scoring | Skil Type | Weighting | 
1 | Provide SURVEYOR to be used |  |  | Registered with no power line experience( 1) |  | 5% | Not Mandatory
 |  |  |  | Registered with one power line project experience (2) |  |  | 
 |  |  |  | Registered with two or more power line project experience (3) |  |  | 
2 | Provide a SOIL PROFILER to be used. |  |  | Registered with no power line experience( 1) |  | 5% | Not Mandatory
 |  |  |  |  | Civil/Artizan |  | 
 |  |  |  | Registered with one or more power line projects experience (2) |  |  | 
3 | Provide a FOUNDATION Designer |  |  | Registered with no power line experience( 1) | Civil Prng | 12% | Not Mandatory
 |  |  |  | Registered with one power line project experience (2) |  |  | 
 |  |  |  | Registered with two or more power line project experience (3) |  |  | 
4 | Provide a Foundation Supervisor |  |  | No Experience (1) | N/A | 5% | Not Mandatory
 |  |  |  | Power Line Project Expereince (2) |  |  | 
5 | Provide a TOWER ASSEMBLY & ERECTION SITE SUPERVISOR |  |  | No Experience (1) | N/A | 12% | Mandatory
 |  |  |  | Power Line Project Expereince (2) |  |  | 
6 | Provide the Temporary Works Engineer |  |  | No Experience (1) |  | 14% | Mandatory
 |  |  |  | Power Line Project Expereince (2) |  |  | 
7 | Provide earthing safety supervisor |  |  | No Certification (0) | OHVRS Registered | 5% | Not Mandatory
 |  |  |  | Certified with no experience (1) |  |  | 
 |  |  |  | Certified with Powerline experience (2) |  |  | 
8 | Provide a DRESSING, STRINGING & REGULATION SITE SUPERVISOR. |  |  | No Experience (1) | N/A | 12% | Mandatory
 |  |  |  | Power Line Project Expereince (2) |  |  | 
9 | Provide a temporary works designer |  |  | Registration with no experience (1) | Civil Prng/GCC | 12% | Mandatory
 |  |  |  | Registration with power line experience (2) |  |  | 
10 | Please indicate experience in transmission lines construction |  |  | No (0) |  | 5% | Not Mandatory
 |  |  |  | Years as a subcontractor (1) | N/A |  | 
 |  |  |  | Years as a main contractor (2) |  |  | 
11 | Provide a project manager |  |  | Registered with no experience (1) |  | 5% | Not Mandatory
 |  |  |  |  | CPM/PrCPM |  | 
 |  |  |  | Registered with powerline experience (2) |  |  | 
12 | Provide a construction site manager |  |  | Registered with no experience (1) | N/A | 8% | Not Mandatory
 |  |  |  | Registered with powerline experience (2) |  |  | 
 |  |  |  |  |  | 100% | 

## Slide 17: Incubation Model Schedule
No | Deliverable Progress | Due Date | Status
1 | Incubation model development | 20 May 2022 | 
2 | External stakeholder support for incubation model (DTIC, CIDB & IDC) | 10 June 2022 | 
3 | Panel contracting process | 30 June 2022 | 
4 | Addressing industry barriers (strategy) | 30 June 2022 | 
5 | Internal governance approval processes | 30 June 2022 | 
6 | Identification of training provider | 30 June 2022 | 
7 | Incubation model commencement | 04 July 2022 | 
< 25% complete
25-75% complete
75-99% complete
100% complete

## Slide 18: Phasing and Number of Incubated Contractors
Assumptions:
Accelerated TDP will be rolled out according to plan
Minimum Current Contractor Capacity = 460 km (8 contractors)
Current Contractors Capacity can be increased to = 710 km (8 contractors)
New Incubation Capacity = 50 km per contractor
Appointment of Incubated Contractors on a yearly basis.
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | TOTAL
TDP IRP 19 (accel) (km’s of line constructed) | 165 | 140 | 549 | 530 | 573 | 1 504 | 2 060 | 2 313 | 976 | 898 | 9 708
Current Line Construction Capacity | 460 | 460 | 460 | 460 | 710 | 710 | 710 | 710 | 710 | 710 | 6100
Gap | -295 | -320 | 89 | 70 | -137 | 794 | 1 350 | 1 603 | 266 | 188 | 3 608
No of Incubation Contractors | 5 | 5 | 5 | 10 | 20 | 24 | 12 | 0 | 0 | 0 | 80
Implement Success Rate @ 40% (Accumulative) |  | 2 | 4 | 6 | 10 | 18 | 27 | 32 | 32 | 32 | 32
Total Available Capacity through Incubation (Km’) |  | 100 | 200 | 300 | 500 | 900 | 1350 | 1600 | 1600 | 1600 | 8150
Total Line Construction Capacity | 460 | 560 | 660 | 760 | 1210 | 1610 | 2060 | 2310 | 2310 | 2310 | 14250
Capacity shortfall
Sufficient capacity

## Slide 19: Technical Course Modules (1/2)
Identify line hardware and related material
Inspection of EHV lines
Perform fault finding
Maintenance of EHV Lines (Non-electrical components)
Survey (Line Construction)
Foundations (Line Construction)
Tower Assembly (Line Construction)
Tower Erection Construction Risks Module (Line Construction)

## Slide 20: Technical Course Modules (2/2)
Stringing and Regulation Construction Risks Module (Line Construction)
SANS 10280 Training
Electrical Safety during line construction (Line Construction)
Line Construction Documentation
Site Access, rehabilitation and civil solutions
Construction Incidents - Case studies

## Slide 21: B) Contracts
Panel Contracting Strategy
  Design to accommodate multiple contractors while reducing the procurement process.
  Supplement Capacity Shortage
  Application of Procurement process and Procurement Hierarchy (TOC)
  Open to accredited Incubation Contractors

## Slide 22: C) Addressing Industry Barriers
Contracting Strategy (All encompassing Strategy investigations)
Realistic TDP (Work execution probability study)
Streamline Payment Process (Analysis of Payment Process duration)
Industry Forums (Fair Market Representation)
Networking Session (Encouraging Partnership & Joint Ventures)
Support Services (Appropriate Funding requirements to encourage investment in the Line Construction)

## Slide 23: Incubation to build capacity is aligned to the elements of scope of works
Line construction overview
Scope of Work
Element
Description
Survey and Pegging
Accurately determining the terrestrial position of towers and the distances and angles between them.
Civil Works (Foundations)
Excavating and pouring concrete foundation to support the steel towers.
Tower Erection
And Assembly
Building transmission line towers by assembling the fabricated steel structures and erecting them.
Stringing and Regulating
Installing the overhead aluminium conductor.
Fabricated Steel tower
Creating steel structures by cutting, bending, punching and steel members
Notes: 23

## Slide 24: Critical Success Factors
The following facts will be deemed critical in this process:
  Selection of Development Contractor
  Commitment to Incubation Process by Transmission and Contractor
  Capability and Capacity building
  Funding
  Monitoring and Reporting

## Slide 25: Ring Fence of Work Opportunities
6 to 12 month
Project Identification
12 to 24 month
24 to 36 month
Transmission Governance Approval
National Treasury Approval

## Slide 26: Analysis of Contractor Challengers
Actual Work Opportunities vs Transmission Plan (TDP)
Time lag between task award to task execution
Contractor Resource Constraint
Contractor Technical vs Financial Capabilities
Adherence to payment periods (in excess of 30 to 40 days)
Tender Cancellation ( no or limited feedback provided)
Inability to comply with SHEQ Requirements

## Slide 27: A) Objective – TX HV Line Construction Incubation
Develop and document processes that would assist:
      new local line construction contractors to participate in the Transmission Line Construction program (have not done work in Tx prior)
      develop and grow local line construction contractors that are currently participating in the Transmission Line Construction program
      established local line construction contractors to self-sustain within Transmission Line Construction Environment
The Line construction panel incubation approach focuses mainly on building capacity and development of suppliers constructing lower kV lines to constructing higher kV lines (132kV to 275kV; 275kV to 400kV; 400kV to 765kV). The smaller supplier is developed progressively from one element to another of the scope until the skill to independently construct the line is attained.

## Slide 28
- No capacity shortfall for the TDP
- Capacity shortfall in the 2nd half of the TDP
- Capacity shortfall in the 1st half of the TDP
Summary _External Resource Capacity Analyses
Key Transmission services and commodities were analyzed to determine potential industry shortages which could affect the execution of the 2022-2030 TDP. TDP projections were compared to industry capacity, year on year, to establish if/when the shortage would occur.
Commodity | Forecasted Shortage/Peak | Projected Shortage | Comments
Lines Construction |  | Average 700 km p.a | Target to increase 100 km p.a minimum. Intervention underway.
Transformers (Class 3b) |  | FY2022 (14 units shortage) | 1 local supplier. Security of supply risk. Recent historical data suggests supply constraints.
Steel Manufacturing |  | FY2030 (96 653 tones) | 1 local supplier. Security of supply risk. Capacity shortfall.
Composite Insulator |  | FY2024 (322 852 units) | 1 local supplier. Security of supply risk. Capacity shortfall.
Conductor |  | FY2029 (20 018 km) | Current supplier capacities indicate a shortfall. Suppliers should be able to increase capacity.
Insulators (Glass) |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Isolators |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Current Transformers |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Surge Arresters |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation
Circuit Breakers |  | - | International supply base. Supplier capacity is adequate. Opportunity for local capacitation

## Slide 29: Incubation Duration & Target Market
Type of contractors | Incubation Support | Duration
New Contractors | 100% | 36 month
Existing Contractor (2yrs experience) | 50-75% | 12 to 24
Existing Contractor (5yrs experience) | 25-50% | Up to 12 months
Existing Contractor (>5yrs experience) | 0-25% | Less than 3 months