## Slide 1: Transmission Lines In Development Line Construction Forum 27 May 2022 Leonard van der Walt & Alwyn Marais

## Slide 2: General & Disclaimer
This presentation gives an overview of the current Transmission line projects (275/400kV & 765kV) in development.
No customer or self-build projects are shown in this presentation.
Slides 3 & 4 are as per what was presented at the TDP Public forum 26 October 2021. The Transmission Development Plan (TDP) is a 10 year plan of all Transmission projects
The remainder of the slides are giving the updated information on the major Transmission line projects in development.
The projects where short lengths of lines are needed (< 10km long, example loop-in and loop-out to new substations) are not covered in slides 5 - 7.
The Execution Release Approval (ERA) dates shown are the current planned dates, these are subject to change depending mainly on:
  Environmental authorisation;
  Servitude Acquisition;
  Capex availability.
Eskom aims to place contracts within a year of the ERA date. Depending on the line length and the contracting strategy at the time the lines may be broken up into sections and more than one tender issued per line.

## Slide 3: Typical Transmission project timelines (assuming no hurdles)
6 - 12 months
4 - 7 yrs
24 - 48 months
CRA
DRA
ERA
Scope defined
EA
Land/ Servitude rights
Line/ sub design
Procurement & construction
Time
Activities
Outputs
Identification / siting and securing suitable land or rights is a lengthy process particularly for linear developments and influences the timing and success of a project
Construction
EIA, Land Acquisition, Surveying, Design
Network Planning & Project development

## Slide 4: Summary of Transmission infrastructure requirements over the TDP period 2022 – 2031
1504
2598
5808
124%
73%
94%
140%
Compared to the previous 5 years: 73% increase in line construction
94% increase in transformer units
The following 5 years (FY27 – FY31): 124% increase in line construction 140% increase in transformer units
~ 8406 km of line:
~ 119 transformers ~ 58 GVA:

## Slide 5
HERMES
WATERSHED
GROOTVLEI
LEANDER
MERCURY
THESEUS
ZEUS
EVEREST
HARVARD
MERAPI
ALPHA
BETA
DEDISA
DELPHI
EROS
GRASSRIDGE
IZIKO
NEPTUNE
POSEIDON
SERUMULA
VUYANI
PEMBROKE
GAMMA
KAPPA
AGGENEIS
ARIES
DROERIVIER
HELIOS
HYDRA
JUNO
KRONOS
Upington
MOOKODI
NIEUWEHOOP
PERSEUS
BOUNDARY
FERRUM
GARONA
OLIEN
GROMIS
HARIB
NAMA
ORANJEMOND
PAULPUTS
ROODEKUIL
RUIGTEVALLEI
VAN DER KLOOF
Komsberg
GARONA
KOKERBOOM
STERREKUS
ACACIA
AURORA
BACCHUS
GOURIKWA
KOEBERG
PALMIET
PROTEUS
Mahikeng
Thyspunt
Korana
Groeipunt
NAMA
GROMIS
Agulhas
Narina
Pinotage
Blouwater
`
ARIADNE
ATHENE
CAMDEN
DRAKENSBERG
HECTOR
INCANDU
INGULA
INVUBU
MAJUBA
MERSEY
NORMANDIE
PEGASUS
TUTUKA
UMFOLOZI
VENUS
KLAARWATER
Duma
Isundu
Mbewu
Inyaninga
Iphiva
MADLANZINI
NZALO
Shongweni
APOLLO
ARNOT
EDWALENI
GUMENI
KUSILE
LESEDING
MAPUTO
MATLA
MERENSKY
MINERVA
SENAKANGWEDI
ACORNHOEK
FOSKOR
KOMATI
KOMATIPOORT
SIMPLON
MARATHON
Manogeng
BORUTHO
MATIMBA
MEDUPI
NGWEDI
PHOKOJE
SPITSKOP
WITKOP
SPENCER
TABOR
Emkhiweni
Nzhelele
Sekhukhune
Silimela
MASA
DINALEDI
Diphororo
Wildebees
Nzhelele
Integration
Lowveld Strengthening
Kusile Integration
Empangeni Strengthening
Bloemfontein Strengthening
Peninsula / Mitchells Plain
West Coast
Strengthening
Upington Phase 2 Substation
Northern Cape Strengthening
NW / Kimberley Strengthening
Jhb East Strengthening
Medupi Phase 2
Integration
Highveld South
Integration
Pinetown Strengthening
East London
Strengthening
Port Elizabeth Strengthening
KZN South Strengthening
Jhb South
Strengthening
Hotazel
Projects in execution
LEGEND
Projects in development
Projects in concept
Major projects planned in the TDP period

## Slide 6
Transmission Lines in Development - Required to evacuate the IRP 2019 Renewable Energy Generation
21
5
9
18
17
4
15 & 16
6
22
Tx Lines 400kV, unless stated otherwise
1 - Aries-Upington (145 km) ERA 2022
2 - Ferrum-Upington (261 km) ERA 2022
3 - Aggeneis-Paulputs (93 km) ERA 2023
4 - Zeus-Perseus 765 kV (430 km) ERA 2024
5 - Boundary-Beta (110 km) ERA 2024
6 - Poseidon-Pembroke (150 km) ERA 2024
7 - Hydra-Kronos (187 km) ERA 2024
8 - Aries-Kronos (165 km) ERA 2025
9 - Gamma-Kappa 765 kV (400 km) ERA 2025
10 - Droerivier-Narina-Gourikwa (250 km) ERA 2025
11 - Gromis-Nama (76 km) ERA 2025
12 - Nama-Aggeneis (104 km) 2025
13 - Ferrum-Mookodi (290 km) ERA 2025
14 - Mookodi-Hermes (200 km) ERA 2025
15 - 1st Gamma-Grassridge 765 kV (355 km) ERA 2025
16 - 2nd Gamma-Grassridge 765 kV (355 km) ERA 2026
17 - Gamma-Perseus 765 kV (420 km) ERA 2026
18 - Kappa-Sterrekus 765 kV (150 km) ERA 2026
19 - Aries-Aggeneis (200 km) ERA 2026
20 - Aggeneis Groeipunt (63 km) ERA 2026
21 - Aurora-Juno (160 km) ERA 2026
22 - Ferrum-Boundary (240 km) ERA 2026
23 – Paulputs LILO from Aries-Kokerboom (2x35 km) ERA 2026
24 - Grassridge-Hlaziya (2 x 125 km) ERA 2026
- Dedisa-Hlaziya (131 km) ERA 2026
Total 400kV - 3145 km
Total 765kV – 2110 km
24
10
1
2
3
7
8
11
12
19
20
13
14
23

## Slide 7
Additional 765kV Lines in development - Required to evacuate the IRP 2019 Renewable Energy Generation
Northern Ring:
1st Mercury-Umtu 765 kV (400 km) ERA 2027
1st Umto-Aries 765kV (450 km) ERA 2027
1st Aries -Juno 765kV (350 km) ERA 2027
1st Juno-Sterrekus (250 km) ERA 2027
2nd Mercury-Umtu 765 kV (400 km) ERA 2029
2nd Umto-Aries 765kV (450 km) ERA 2029
2nd Aries -Juno 765kV (350 km) ERA 2029
2nd Juno-Sterrekus (250 km) ERA 2029
Eastern Cape - KZN:
Zanokhanyo-Delphi 765 kV (2 X 300 km) ERA TBC
Delphi-Eros 765 kV (2 X 400 km) ERA TBC
Eros-Isundu 765 kV (2 X 160 km) ERA TBC
Total 765kV – 4620km

## Slide 8: Strengthening (Non IRP 2019) Lines in Development

## Slide 9: Questions