## Bill No.1-P&G's
ESKOM
KUSILE-MINERVA 400Kv LINE- TOWER 28 REFURBISHMENT
BILL No. 1- PRELIMINARY AND GENERAL
The Contractor is referred to the full intent and meaning of each clause or item herein. He shall allow opposite each clause or item, whatever payments he may consider necessary, to carry out and observance of same.
The Contractor shall price Bill No. 1 - Preliminary and General in respect of all payment required for any work, risk, contingency or obligation whatsoever, that is not described in the Bill of Quantities and which is his responsibility under the Contract
ITEM | DESCRIPTION | UNIT | QTY | FIXED RATE | VALUE RELATED RATE | TIME RELATED RATE | AMOUNT
|  |  |  | (1) | (2) | (3) | (1+2+3)
1. | THE ENGINEERING AND CONSTRUCTION CONTRACT
WORKS INFORMATION
1.1 | Contractual Requirements | sum | 1 |  |  |  | 0
1.2 | Quality management (incl. Contractor's Quality Plans) as outlined in the enquiry document. | sum | 1 |  |  |  | 0
1.3 | Safety management (incl. Contractor's adherence to COVID-19 SHE requoirements) as outlined in the enquiry document. | sum | 1 |  |  |  | 0
1.4 | Environmental management (incl. Contractor's Environmental Management Plan) as outlined in the enquiry document. | sum | 1 |  |  |  | 0
2. | SITE COSTS AND OVERHEADS
2.1 | Off-site overhead costs | month | 1 |  |  |  | 0
2.2 | Off-site staff | month | 1 |  |  |  | 0
2.3 | Site staff | month | 1 |  |  |  | 0
2.4 | Establish contractor's yard, site offices, workshops, stores etc. including all necessary water and electricity supplies, drainage and waste disposal systems, telecoms/telephone facilities etc. and remove on completion. | month | 1 |  |  |  | 0
2.5 | Establish staff accommodation and camp, including sanitation and remove on completion. | month | 1 |  |  |  | 0
2.6 | Establish concrete batching plant and remove on completion. | sum | 0 |  |  |  | 0
2.7 | Establish concrete laboratory and remove on completion, or use independent concrete laboratory. | sum | 0 |  |  |  | 0
2.8 | Provide survey equipment and remove on completion. | month | 2 |  |  |  | 0
2.9 | Establish temporary works and remove on completion. | sum | 0 |  |  |  | 0
2.1 | Establish constructional equipment and remove on completion. | sum | 1 |  |  |  | 0
2.11 | Take delivery of, off-load, check for completeness, register and store until use, in a suitable secure area, all stringing and other material supplied by the Employer. | month | 1 |  |  |  | 0
2.12 | On site security required to protect the Contractor's and the Employer's assets before completion. | month | 0 |  |  |  | 0
2.13 | Contractor's transport inclusive of taxi association requirements. | month | 1 |  |  |  | 0
|  |  |  | 0 | 0
| Rates to be entered for all items |  |  |  |  | Carried forward to Bill No. 5 - SUMMARY OF PRICES | 0
Note on A20: Aunese Mahlaku: additional SHE officer AND sacpmp

## Bill No.2-Tower 28 Refurb
ESKOM
KUSILE-MINERVA 400Kv LINE- TOWER 28 REFURBISHMENT
BILL No. 2- TOWER 28 REFURBISHMENT
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
|  |  | (1) | (2) | (1)*(2)
1 | Dewatering (If necessary)
1.1 | Pumping out of water and exposing the soil around the tower footprint. | days | 16 |  | 0
1.2 | Maintaine low water level for a minimum of two weeks to allow the area around the tower foundations to dry. | sum | 1 |  | 0
2 | Preparing ground surface
2.1 | Create a solid platform to work on with 10MPa blinding layer. The blinding layer will placed around every tower leg. | m3 | 10 |  | 0
3 | Breaking of the existing tower foundation cap
3.1 | Break concrete cap using hand tools or a hand held jack hammer. Care should be taken to make sure that the steel members are not damaged during the process. | No | 4 |  | 0
3.2 | In a case where the concrete cap will not be totally removed it will have to be scabbled to a depth of 25mm to prepare for the bonding with the new concrete cap. | sum | 1 |  | 0
4 | Excavations
4.1 | Excavate in soft material, exceeding 500mm deep but not exceeding 1000mm deep. An excavation of about 1000mm x1000mm and 500mm around each tower leg will be required to expose the existing concrete cap. | m2 | 4 |  | 0
5 | Cleaning of the tower leg members and stub
5.1 | Prepare tower members for application of a protective coat. A steel brush will be used to clean the rust on the members and cleaned with potable water and left to dry prior to application of paint. A simple adhesive tape test can be conducted to ensure that the surfaces are dry and there is no flakes or rust particles adhering to the tape in order to apply the paint coatings | No | 4 |  | 0
6 | Painting of the tower leg members and stub
6.1 | Apply two coats of bitumen protective coating (Ravenol or similar approved) on the tower members. The stubs are to be painted from exposed surfaces up to 500mm above final concrete level. The concrete cap is to be painted at least 150mm all around the stub-to-concrete interface. | No | 4 |  | 0
7 | Formwork
7.1 | Place formwork before casting of concrete for all four legs of the tower. All concrete placed against shuttering shall be free from irregularities, fins, rock pockets or other imperfections. Ensure that for caps there is a watershed. | m2 | 8 |  | 0
8 | Casting of the concrete block
8.1 | A concrete mix design must be submitted to Lines Engineering Services before casting. | sum | 1 |  | 0
8.2 | Before casting the new concrete block, apply the cement slurry. A minimum 25MPa concrete block (triangular prism shape) will be cast. The size of the block will be 1000mm by 1000mm with a height of 1000mm.The bonding between the existing concrete and the new concrete is of vital importance to prevent water (moisture) to penetrate and reach the steel. A cement slurry should be poured on the scabbled area and immediately cast the new concrete. The new concrete must be cast to a watershed and properly cured as per TRMSCAAC 5.2 requirements. | m3 | 4 |  | 0
9 | Concrete cube test
9.1 | Four concrete cubes should be prepared per concrete truck/batch to confirm the concrete strength. One concrete cube will be tested at 7 days and three cubes at 28 days. | No | 4 |  | 0
10 | Concrete curing & wood floating
Concrete will be cured using an approved curing compound
10.1 | The top surface of the new concrete encasement shall have a wood float finish, and shall be contoured to allow water to shed. There should be a difference of 50mm from the highest to the lowest point of the cap surface to ensure adequate watershed. | m2 | 100 |  | 0
11 | Backfill
11.1 | Backfill and compact each excavation with suitable engineering material such as G7 or better with backfill and compaction as per TRMSCAAC 5.2 requirements in layers as per next point and to a minimum compactive effort of 93% Mod Aashto. | m3 | 6 |  | 0
11.2 | The material to be utilised for compacted backfill shall be moistened to OMC (optimum moisture content +10%), and deposited in horizontal layers, having a thickness of not more than 300 mm before being compacted | m3 | 6 |  | 0
12 | ACCESS ROADS
12.1 | As per TRMSCAAC- latest revision and Environmental Management Plan, to maintain all existing private farm roads and tracks used to gain access to the servitude for construction purposes and reinstate to at least the original condition upon completion. Photographic evidence of the original condition must be provided by the Contractor before use. | sum | 1 |  | 0
12.1 | As per TRMSCAAC- latest revision and Environmental Management Plan, to establish all temporary access roads necessary to gain access to the servitude and tower positions for construction purposes and close on completion, if instructed by the Project Manager. | sum | 1 |  | 0
13 | ENVIRONMENTAL AND REHABILITATION REQUIREMENTS
13.1 | Rehabilitation of damage caused during construction to tower sites, access and servitude roads, camp sites, batching plant site, etc. in accordance with the requirements of the EA, EMP, TRMSCAAC1 and ESKASABG3. | sum | 1 |  | 0
Rates to be entered for all items |  |  |  | Carried forward to Bill No.5 | 0
All quantities are estimated and will be re-measured on completion

## Bill No.3-Summary
ESKOM
KUSILE-MINERVA 400Kv LINE- TOWER 28 REFURBISHMENT
BILL No. 3- SUMMARY
BILL No. | DESCRIPTION |  | TOTAL
1 | PRELIMINARY AND GENERAL |  | 0
2 | TOWER 28 REFURBISHMENT |  | 0
|  | BILL No.3 SUMMARY OF PRICES | 0