## EMP
ESKOM TRANSMISSION | [8 empty] | Template Identifier |  | 240-43921898 | REV |  | 7
BASELINE ENVIRONMENTAL MANAGEMENT PROGRAMME FOR SUPPLIERS / CONTRACTORS | [8 empty] | Document Identifier |  | 240-109832932 | REV |  | 2
or http:www.imbewuregisters.co.za / http:www.sabinet.co.za / https://my.libryo.com | [8 empty] | Effective Date |  | December 2017
[9 empty] | Review Date |  | December 2021
* This EMP should be used as a guideline to assist Project Managers / Contractors / Vendors in compiling their project specific EMP* *The contents of this EMP is not limited and the responsibility remains with the relevant supplier / contractor to ensure all project specific activities and legislation (including local by-laws) have been identified and managed* *The purpose of this EMP is to provide a guideline to manage project activities that are not subjected to the EIA process i.t.o. National Environmental Management Act, 1998 (Act No.107 OF 1998) Environmental Impact Assessment Regulations (2014)*
NR | ACTIVITY | ASPECT | IMPACT | SIGNIFICANCE | OBJECTIVE | TARGET | MEANS / METHOD STATEMENT | DUE DATE | RESPONSIBLE PERSON | COMPLETION DATE | COMPLIANCE OBLIGATIONS | ACTION EFFECTIVENESS
[12 empty] | Fully effective | Partially effective | Ineffective
1 | PROCUREMENT | Evaluation and adjudication of tender submissions | Failure to include environmenta l requiremets during tender prossess could results into environmental degredation | MEDIUM | Ensure Eskom SHEQ requirements are specified / included during tender process | With the submission of each tender | Ensure Environmental requirements are taken into account during tender process . | Tender submission | Buyer |  | 32-726 - SHE Requirements for the Eskom Commercial Process
|  | Placement of order/contract with suppliers | Specifying environmental criteria for supplies & advice on the use of products or services to minimise the environmental impacts. | MEDIUM | Ensure Environmental requirements are taken into account when placing an order | Placement of order | Specifying environmental criteria for suppliers/service providers . | Tender stage | Buyer |  | 32-726 - SHE Requirements for the Eskom Commercial Process
|  | Assessing contractors | Failure to make contractors aware of the impact of their deviations from set procedures could lead to negative environmental impacts | MEDIUM | Ensure that contractors are aware of the impact of their deviations from / non-comliance to set procedures. | Prior commencement of activities | SHEQ File evaluation and approval for tender requirements | Prior commencements of activities | Transmission Environmental Management / Project Manager |  | 32-726 - SHE Requirements for the Eskom Commercial Process
2 | PROJECT MANAGEMENT | The management of the project according to EMP and relevant environmental legal requirements . | Failure to ensure compliance with the EMP and relevant compliance obligations requirements may lead to legal contraventions, customer complaints, claims against the business and damage to the environment and private / state properties. | HIGH | To ensure that the project is effectively managed according to all compliance obligation requirements. | 0 Legal Contraventions / 0 Safety Incidents | Through discussing all environmental non-compliances and requirements under an agenda items at the project inaugural meeting and progress meetings, allocating responsible persons and action dates for mitigations. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
3.1 | PROJECT MANAGEMENT | Assesment & Planning | Failure to conduct line risk assessments and proper planning during the excecution of the project activities may lead to environmental and safety incidents and damage to private / state property that my result in disputes with landowners. | HIGH | To ensure that risk assessments and proper planning are conducted to minimise or avoid environmental aspects that might lead to negative environmental impacts | 0 Legal Contraventions / 0 Safety Incidents | 1. Environmental requirements can be discussed daily during the toolbox talks. 2. Environmental Risks assessments of the area can be done together with safety observations / assessments. 3. Emergency contact numbers must be available on site. 4. Land owners must be notified of dates contractors will be working in the servitude, crossing private properties. 5. Contractors working for Eskom must have identity cards, clearly marked clothing and vehicles. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
3.2 | PROJECT MANAGEMENT | Environmental Training & Awareness of contractors. | Lacking environmental awareness / knowledge of Eskom Transmission and other relevant compliance obligations requirements may lead to legal contravention, damage to the environment and private property that may result into disputes and claims with landowners. | HIGH | To ensure contractors are aware of environmental requirements i.t.o. the EMP and other compliance obligations requirements | 0 Legal Contraventions / 0 Safety Incidents | 1. SHE & Security Induction Training must be provided to all contractors before any project activity may start. 2. Attendance Registers of SHE Induction must be kept by the project manager / BU SHE Depts and copies included in the contractor's SHE file 3. Environmental Requirements can be highlighted daily during the toolbox talks to refresh workers minds on what is required. 4. Relevant training requirements must be identified up front before tender award and will be checked during tender approval and SHE file evaluations and approvals. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
3.3 | PROJECT MANAGEMENT | During / Final Construction Audits | Failure to conduct audits during the course of the project can result in non compliances that are overlooked and failure to mitigate and prevent environmental incidents that have occurred. | HIGH | To ensure that non compliances or NCRs are picked up during construction activities and rectified / mitigated a.s.a.p. after it occurred. To conduct a final construction audit to ensure that the project is completed without any non compliances and NCRs open. | 0 Legal Contraventions / 0 Safety Incidents | 1. During construction audits must be conducted on a weekly basis by conducting site visits to where activities of the project are taking place. 2. A Final construction audit must be conducted on project completion. Objective evidence of close out of previous NCRs if any. 3. During / Final constructions audits can also be conducted by the relevant Environmental profesional at any given time. 4. NCRs will be raised for non-conformances. | Duration of project On project completion Duration of project Duration of project | Project Site Supervisor / SHE Rep Project Site Supervisor / SHE Rep BU Environmetnal Professional Project Manager / BU Environmental Professional. |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
4.1 | VEGETATION MANAGEMENT & BUSHCLEARING | The cutting / removing of protected plant / tree species (Cut, disturb, damage or destroy any protected tree or possess, collect, remove, transport, export, purchase, sell, donate or in any other manner acquire or dispose of any protected tree or any forest product derived from a protected tree) | Resulting into a legal contravention. Financial and legal prosecution implication from the authorities and or private property owners. | HIGH | To ensure that no protected tree /species are cut , disturbed, destroyed or damaged / transported without a permit. | 0 Legal Contraventions | Any Eskom staff / contractors must undergo SHE & Security Induction prior to the start of any project. Relevant Eskom staff / contractors must have done tree identification training prior to them starting with any vegetation mgt/ bushclearing program. Permits must be obtained from the Dept. of Agriculture & Forestry before any protected tree is cut. Tx Landowner Approval Certificate / Consent form must be completed prior to the start of the project and landowners must sign off on status of property after completion of any bush clearing activities. | Before project start On contract award / before project start Before project start Before entering servitdue / private property | Project Manager / Contractor / Site supervisor Contractor BU Env Department Contractor / Site Supervisor |  | National Environmental Management Act, Act 107 of 1998 Section 28 Duty of care and remendiation of environmental damage. -National Environmental Management: Biodiversity Act 10 of 2004 - Threatened or Protected Species Regulations, 2007 - Apply for permits for restricted activities involving specimens of listed threatened or protected species in accordance with these Regulations. - National Forests Act, 1998 - Notice of the List of Protected Tree Species Under the National Forests Act, 1998 (Act no. 84 of 1998), 2014, Section 15(1) no person may cut, disturb, damage or destroy any protected tre or possess, collect, remove, transport, export, purchase, sell, donate or in any other manner acquire or dispose of any protected tree or any forest product derived from a protected tree, except under a licence or exemption granted by the Minister to an applicant and subject to such period and conditons as may be stipulated.
4.2 | VEGETATION MANAGEMENT & BUSHCLEARING | Proliferation of Alien Invasive species | It is legally non-compliant to allow alien species to proliferate. Sites should be montiored continously to control spread of alien species. | HIGH | To ensure that Alien Invasive species are removed according to legal and other requirements (compliance obligation). | 0 Legal Contraventions | 1. To ensure alien invasive species are included in scope of work during bush clearing programmes 2. To ensure contractors / staff are trained on tree identification 3. Method statement on removal and disposal of alien invasive species in SHE files 4. Quality checks on scope of work completed | Before project start On contract award Before project start Duration of project | Project Manager / Contractor Contractor BU Env Dept BU Lines & Servitude Supervisor |  | National Environmental Management Act, Act 107 of 1998 Section 28 Duty of care and remendiation of environmental damage. - Environment Conservation Act 73 of 1989 s31a - Conservation Of Agricultural Resources Act, 43 of 1983 , 5. Prohibition of the spreading of weeds - Conservation Of Agricultural Resources Act, 43 of 1983 - Regulations (GNR 1048)- Part II: Weeds And Invader Plants - National Environmental Management: Biodiversity Act, 10 of 2004, 65. Restricted activities involving alien species, 66,67,68 - National Environmental Management: Biodiversity Act 10 of 2004 - Alien and Invasive Species Regulations, 2014: Part 2-6 - National Environmental Management: Biodiversity Act 10 Of 2004: Alien And Invasive Species Lists, 2016 -
4.3 | VEGETATION MANAGEMENT & BUSHCLEARING | Herbicide Application | Incorrect application of herbicide can lead to environmmental degradation. Leaching of herbicide can affect groundwater and neighbouring farms. Financial and legal prosecution may also arrised out of such a contravention. | HIGH | Ensure herbicides are applied in accordance with legal requirements | 0 Legal Contraventions | 1. Only contractors in possesion of a PCO licence and accredited can apply herbicide within the terms and conditions of the contract and legal requirements. 2. Contractor PCO Licence holders must be on site during herbicide application 3. Herbicide application must be done as soon as vegetation has been removed to avoid regrowth 4. A Herbicide Application register must be kept on site and copies must be submitted to the BU Lines & Servitude supervisor. | By contract award / project start Duration of project Duration of project Duration of project | Project Manager / Contractor Contractor Contractor Contractor / Lines and servitude supervisor |  | Fertilizers, Farm Feeds, Agricultural Remedies and Stock Remedies Act, 36 of 1947 , Se 3. Registration of fertilizers, farm feeds, agricultural remedies, stock remedies, sterilizing plants and pest control operators - Fertilizers, Farm Feeds, Agricultural Remedies and Stock Remedies Act, 36 of 1947 - GN R98 - Pest Control Operator Regulations , 12. Responsibilities of pest control operators, 14. Offences and penalties and 13. Records to be kept- - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage. duty of care on every person to prevent and Sec 30. Control of emergency incidents - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - National Environmental Management: Waste Act, 59 of 2008, Sec 26. Prohibition of unauthorised disposal
4.4 | VEGETATION MANAGEMENT & BUSHCLEARING | Bush clearing in sensitive / protected areas such as: National parks Privately owned game reserves / farms Rivers / riverbanks 500m from Wetlands / water bodies Proclaimed protected areas Graves sites | If bush clearing is done indiscriminately there is the possibilty of affecting protective / sensitive ecosystems systems negatively and enhance erosion in the servitude. | HIGH | To ensure that good vegetation management practices according to legal and other requiremets | 0 Legal Contraventions | 1. Working according to established bushclearing program for bushclearing in servitudes 2. Tx Landowner Approval certificate / consent form must be completed and signed off by contractor / site supervisor / landowner before and on completion of project 3. Identify and obtain all relevant permits required i.t.o. legislaiton prior to the start of any project activity. 4. To include sensitive / protected areas in scope of work for relevant bush clearing programmes | Duration of project Before entering servitude / private property Beofre leaving servitude / private property after work completion Before project starts / kick-off On task order award for project activity to start | Project Manager / Contractor Contractor / Site Supervisor BU Env Dept BU Lines & Servitude supervisor |  | Environment Conservation Act 73 of 1989 s31a - National Environmental Management Protected Areas Act 57 Of 2003, Sec 9. Kinds of protected areas, 17. Purpose of protected areas, Part 1 - Special nature reserves, Part 3 - Nature reserves, Chapter 4 - Management Of Protected Areas and chapter 6- Acquisition of right in or to land - National Environmental Management: Protected Areas Act, 57 Of 2003 - Regulations For The Proper Administration Of Special Nature Reserves, National Parks And World Heritage Sites , Part 3 - Access to special nature reserves, national parks and world heritage sites and Part 5 - Activities that may be carried out in terms of section 50 - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents -National Heritage Resources Act, 25 of 1999, S
5.1 | ACCESS | Use of access roads | The incorrect use of access roads in areas, which are prone to erosion, especially during wet conditions can lead to serious erosion. This can eventually make the entire area inaccessible and can affect the landowner's farm's carrying capacity. Damage to access roads and property can lead to claims and legal disputes and rehabilitation cost incured. | MEDIUM | To use access roads which belongs to land owners on private property responsibly according to legal and other requirements, EMP, method statements | 0 Legal Contraventions | 1. To capture the condition of any access road prior to the start of the project for record purposes. 2. All defects / damages occuring during the project should be reported, rectified immediately on occurrence . 3. The onus is on the contractor to be responsible for any rehabilitation on site/s should it damage / pollution incidents resulted from this project. 4. Landowner's consent must be obtained prior to the start of the project and landowners must sign off on status of property after completion of any project activities. | Before project starts Duration of project Duration of project Beofre entering servitude / private property | Project Manager / Contractor Contractor Contractor Contractor / Site Supervisor |  | Eskom Access to to Farms Standard (32-1173) -Conservation of Agricultural Resources Act, 43 of 1983
5.2 | ACCESS | Access of Eskom staff and or Contractors to sites along the servitude. | Employees entering the servitude on private property must understand specific requirements . People / Contractos from outside the network can have a negative impact on environment and and pose security risks to landowners as well as affecting relationships negatively. This may lead to deputes and claims against Eskom. | MEDIUM | To ensure that external people / contractors working on behalf of Eskom Tx do not contravene any legal or other requirment / brigde any agreement. | 0 Legal Contraventions | 1. All Eskom staff and contractors must be in possession of a form of identification indicating who they are, employer and project and have marked clothing and vehicles. 2. All landowners who's property will be accessed during the duration of the project must be contacted prior to accessing the servitude / line crossing private / state property. 3. All contractors staff must have SA Police clearance submitted with their copies of identification during SHE evaluations and approvals | Duration of project Duration of project Before project start | Project Manager / Contractor |  | Fencing Act , 31 of 1963, Sec 22 leaving gates open - Eskom Access to to Farms Standard (32-1173)
5.3 | ACCESS | Bad Access | River crossings, servitude access route in poor condition, access gates removed / locked, etc. | MEDIUM | To ensure that areas where accessibility are difficult / poor condition are identified and managed | 0 Legal Contraventions / claims from landowners | 1. To identified such areas in advance to access required and plan project activities accordingly. 2. To report such occurrences so it can be rectified and managed. 3. Not to damaged fences, gates or cut locks without concent / prior agreement of landowner / project manager. 4. To conduct risk asessment of poor access roads to avoid vehicle accidents and safety incidents. | Duration of project | Project Manager / Contractor |  | Eskom Access to to Farms Standard (32-1173) -Conservation of Agricultural Resources Act, 43 of 1983
6.1 | SOCIAL INTERACTION | Unlawful occupation of land. | Unlawful occupation of land my lead to pollution of the environment, damage / theft of tower members as well as damage to private property. | HIGH | Illegal occupants to be handeled in accordance with legal requirements | 0 Public complaints arising from illegal land occupation | No Eskom Employee / contractor may make use of private property for camping during the duration of any project without written concent from / formal agreement with the property owner / Eskom Management. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
6.2 | SOCIAL INTERACTION | Public / Landowner Complaints | Inappropriate activities, activities in non-compliance to the EMP, legal and other requirements may lead to customer complaints. | MEDIUM | To ensure that public complaints are address and succesfully resolved. | Resolution / Management of public and landonwer complaints | 1. All public complaints must be kept in a register with proof of resolution on the site SHE file. 2. All public complaints must be reported to the relevant BU Env Dept. under which the project is executed. 3. BUs to record and monitor public / landowner complaint until resolved 4. Public complaints must be closedo ut on project completion / handover to the BU | Duration of project Duration of project Duration of project Project completion | Project Manager / Contractor Contractor BU Env Dept Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
6.3 | SOCIAL INTERACTION | Serivtudes through cropfields | Cropfields might cause restriction of access to towers. Damage to cropfields can lead to claims against Eskom. | MEDIUM | Ensure that these areas of crop fields are identified so alternative routes can be used or access negotiated with landowner. | 0 Legal Contraventions / law suits / claims | 1. By conducting risk assessments prior to the start of projects i.t.o. access. 2. To obtain written consent from property owner, stipulating any specific requirements from the property owner. 3. Avoid interaction with land owners activities. 4. No fires to be made anywhere. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage. duty of care on every person to prevent L64
6.4 | SOCIAL INTERACTION | Social-Civil liability due to inappropriate activities while working in servitudes / private property and or activities arising from substations | Employees entering a private property can have an impact if they leave gates open and animals are lost, damage cultivated areas and incorrect use of access to roads. Various public complaints may arise from this project activities and if not resolved my lead to social, civil and financial liabilities for Eskom. Substation activities may lead to pollution incidents that may result intosocial, civil and financial liabilities for Eskom | HIGH | To ensure that public complaints are successfully resolved | 0 Legal Contraventions / law suits / claims | 1. To attend to customer complaints and have minutes of meetings / any other documentation kept for record purposes. 2. Keep a public complaint register in the Environmental & Safety File on site. 3. To refer complaints involving legal action taken agains Eskom to the Eskom Legal and Claims Department for resolution | Duration of project | Project Manager / Contractor Contractor Project Manager / BU Env Dept |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
7.1 | WILDLIFE INTERACTION | Bird Nests | The removal of bird nest from towers without a without authorisation will lead to a legal contravention. Injuring and killing of red data / protected bird species. | HIGH | To remove bird nests posing a risk to the tower i.t.o. quality of supply etc. according to legal and other requirements. | 0 Legal Contraventions / 0 public complaints | 1. Identify affected towers where nest removal are required and report for mitigation. 2. All Bird nests requires a permit for removal from the Provincial DEA / relevant national parks authority. Obtain relevant bird nest removal permit 3. Any nest including Red Data / Protected bird nests identified should NOT be removed until the chicks have fledged and left the nest (only in an emergency situation). 4. For assessments contact relevant env practitioner and Endangered Wildlife Trust (EWT). | Before / Duration of project Before project start Duration of project Duration of project | Project Manager / Contractor BU Env Dept Contractor Project Manager / Contractor |  | Provincial Nature Conservation Ordinances - National Environmental Management: Biodiversity Act, 10 of 2004 - Publication of Lists of Critically Endangered, Endangered, Vulnerable and Protected Species (GN 389 - Publication of Lists of Species that are Threatened or Protected, Activities that are Prohibited and Exemption from Restriction) - National Environmental Management: Biodiversity Act 10 of 2004 - Threatened or Protected Species Regulations, 2007
7.2 | WILDLIFE INTERACTION | Bird / wildlife / animal electrocutions and collisions with powerline infrastructure. | Bird / Wildlife fatalities can be due to electrocutions and collisions plant infrastructure. This may cause failure of equipent and interruption of supply. Killing of protected & endangered species. | HIGH | To ensure bird electrocution / collisions are reported. | 0 Legal Contraventions / 0 plant failures or interruption of supply | To report occurences of bird incidents to the BU Environmental Dept and EWT | Duration of project | Project Manager / Contractor |  | Provincial Nature Conservation Ordinances - National Environmental Management: Biodiversity Act, 10 of 2004 - Publication of Lists of Critically Endangered, Endangered, Vulnerable and Protected Species (GN 389 - Publication of Lists of Species that are Threatened or Protected, Activities that are Prohibited and Exemption from Restriction) - National Environmental Management: Biodiversity Act 10 of 2004 - Threatened or Protected Species Regulations, 2007
7.3 | WILDLIFE INTERACTION | Poaching of game / wild / domestic animals. | The poaching of game / wild / domestic animals on private property is illegal. | MEDIUM | To ensure NO poaching of game / wild / domestic animals occurs on private property. | 0 Legal Contraventions / 0 law suits / claims | 1. To communicate EMP and legal requirements to all contractors working on project during SHE & Security Induction 2. To include EMP and legal requirements in daily toolbox talks / risk assessments 3. To ensure SA police clearence for all contractor employess is done and submitted with ID documents duirng SHE file assessment and approval | Before project start Duration of project Beofre project start | Project Manager / Contractor |  | - National Environmental Management Protected Areas Act 57 Of 2003, Sec 9. Kinds of protected areas, 17. Purpose of protected areas, Part 1 - Special nature reserves, Part 3 - Nature reserves, Chapter 4 - Management Of Protected Areas and chapter 6- Acquisition of right in or to land - National Environmental Management: Protected Areas Act, 57 Of 2003 - Regulations For The Proper Administration Of Special Nature Reserves, National Parks And World Heritage Sites , Part 3 - Access to special nature reserves, national parks and world heritage sites and Part 5 - Activities that may be carried out in terms of section 50 - National Environmental Management: Biodiversity Act, 10 of 2004 - Publication of Lists of Critically Endangered, Endangered, Vulnerable and Protected Species (GN 389 - Publication of Lists of Species that are Threatened or Protected, Activities that are Prohibited and Exemption from Restriction) - National Environmental Management: Biodiversity Act 10 of 2004 - Threatened or Protected Species Regulations, 2007
7.4 | WILDLIFE INTERACTION | Interaction between people and animals. | The injuring or killing of animals accidently with vehicles can lead to claims against Eskom. Interaction with dangerous animals can lead to employee fatalities / injuries | MEDIUM | To ensure that vehicles are driven responsibily with causion and legal / safe speeds. That all wildlife incidents are reported for investigation and mitigaiton. | 0 Legal contraventions / claims / safety incidents | 1. To conduct detailed risk assessments of areas where work needs to be done 2. To identify servitudes with game camps keeping dangerous animals eg) lion, buffalo, etc before entering property / servitude 3. To establish landowner requirements upfront on entering areas where dangerous animals are kept 4. To keep and maintain a Environmental Incident register on site which includes Wildlife Incidents. 5. To report such incident at to the Project Manager immediately after occurrence. | Before / Duration of project Before project start Before / Duration of project Duration of project Duration of project | Project Manager / Contractor Project Manager / Site supervisor Project Manager / Contractor Contractor Contractor |  | - National Environmental Management Protected Areas Act 57 Of 2003, Sec 9. Kinds of protected areas, 17. Purpose of protected areas, Part 1 - Special nature reserves, Part 3 - Nature reserves, Chapter 4 - Management Of Protected Areas and chapter 6- Acquisition of right in or to land - National Environmental Management: Protected Areas Act, 57 Of 2003 - Regulations For The Proper Administration Of Special Nature Reserves, National Parks And World Heritage Sites , Part 3 - Access to special nature reserves, national parks and world heritage sites and Part 5 - Activities that may be carried out in terms of section 50 - National Environmental Management: Biodiversity Act, 10 of 2004 - Publication of Lists of Critically Endangered, Endangered, Vulnerable and Protected Species (GN 389 - Publication of Lists of Species that are Threatened or Protected, Activities that are Prohibited and Exemption from Restriction) - National Environmental Management: Biodiversity Act 10 of 2004 - Threatened or Protected Species Regulations, 2007
8 | DRIVING OF VEHICLES | The incorrect use of access roads, speeding or driving irresponsibly, maintenance of vehicles, causing damage to property or injuring of animals / people. | This can eventually make the entire area inaccessible and can affect the landowner's relations negatively resulting in claims and or civil / criminal liability. | HIGH | To ensure no environmental damage is cause by vehicles during this project. | 0 Claims / Safety incidents | 1. Use existing roads 2. No vehicle maintenance on site or in the servitude or on private property. 3. Be aware of environmental sensitive areas / soil(sand) and steep area 4. Leave gates in the position it was found/ or as agreed by land owner. 5. Damaged locks to be replaced. 6. Record all damage to infrastructure/ towers /anticlimbing devices 7. Vehicles which are not road worthy (i.e. leaking oil) shall not be used or allowed on site. | Duration of project | Project Manager / Contractor |  | National Road Traffic Act, 93 of 1996 - 42. Certification of roadworthiness required in respect of motor vehicle - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
9.1 | WASTE MANAGEMENT | Domestic / General Waste and litter generated during this project in the servitude. This include uncontaminated building rubble | These types of activities cause pollution and degradation to the environment. Leaving waste under the line and on private property can lead to landowner complaints and claims against Eskom | HIGH | Waste is handled and dispose of as required by legislation and best practices. | 0 Legal contraventions / landowner complaints | No waste to be left on site/ servitude after shift ends. | Duration of project | Project Manager / Contractor |  | Eskom Waste Standard (32-245) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec 24. Collection of waste, Se 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering - National Environmental Management: Waste Act, 59 of 2008 - Waste Classification and Management Regulations, 2013 (GN R634) , Sec 4. Waste Classification and Sec 6. General - National Environmental Management: Waste Act, 59 of 2008 - National Waste Information Regulations, 2012 - Annexure 3 - General Waste Types For Reporting To The Sawis
[7 empty] | Domestic / general waste to be disposed of at the closest registered / licensed municipal waste site. | Duration of project | Project Manager / Contractor
[7 empty] | 1. Waste disposal register to be completed for waste disposal and kept on site in environmental and safety file. 2. Retain all waste disposal documentation / records 3. Report waste disposal figures to BU Env Dept. | Duration of project Duration of project Duration project / project completion | Project Manager / Contractor
9.2 | WASTE MANAGEMENT / HANDLING OF CONSTRUCTION RUBBEL / WASTE | Incorrect storage and diposal of wate | Oil contamination to natural environment. | MEDIUM | To prevent or minimise polution incidents resulting from the stroage and disposal of construction rubbel/waste | During construction | Rubbel to be stored in demarcated area. Ensure no water resources are contaminated ensure no lad degradation due to incorrect storage Disposal to take place at legal site | During and after construction | Project manager/Contractor |  | National Environmental Management Act 107 of 1998, Duty of Care Section 28 and Sec 30. Control of emergency incidents - Eskom Waste Standard (32-245) - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering
9.3 | WASTE MANAGEMENT | Hazardous waste including but not limited to asbestos containing material, silica gel, PCBs, oil and oil contaminated soils and materials, chemicals, old herbicides and herbicide containers, pesticides, building rubble contamindated with hazardous waste types, etc. | Hazardous waste are dangerous to humans and animals, causing land, water and ground water pollution. Incorrect handling and disposal may lead to claims against the business and legal contraventions. | HIGH | Hazardous waste is identified and stored, transported and dispose according to legal and other requirements. | 0 Legal contraventions | 1. Hazourdous waste must be identified and disposed off at a regisitered hazarous waste site by an hazardous waste contractor. 2. Disposal certificates, waste manifest and weigh bridge receipts must be obtained and available. 3. Copies of any disposal certificate must be submitted to BU Environmental Dept. and records kept in Environmental and safety file. 4. All waste disposal figures must be report to the BU Env Dept 5. A waste disposal control register must be kept on site at all times with disposal figures recorded | Duration of project | Project Manager / Contractor |  | National Environmental Management Act 107 of 1998, Duty of Care Section 28 and Sec 30. Control of emergency incidents - Eskom Waste Standard (32-245) - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering - National Environmental Management: Waste Act, 59 of 2008 - Waste Classification and Management Regulations, 2013 (GN R634) , Sec 4. Waste Classification and Sec 6. General - National Environmental Management: Waste Act, 59 of 2008 - National Waste Information Regulations, 2012 , Annexure 4 - Hazardous Waste Types For Reporting To The Sawis - National Environmental Management: Waste Act, 59 of 2008 - Waste Classification and Management Regulations, 2013 (GN R634) , Sec 5. Safety Data Sheets - National Environmental Management: Waste Act 59 of 2008 - National Norms and Standards for the Storage of Waste (GN 926) , Sec 10. General Requirements of Waste Storage Containers - National Environmental Management : Waste Act 59 of 2008 - National Norms and Standards for Disposal of Waste to Landfill (GN R636) , Sec 5. Waste Disposal Restrictions
10.1 | OIL MANAGEMENT | Planning for oil management activities on site. | Incorrect / poor oil management practices can lead to serious ground, ground water / surface water pollution. Oil spill causes serious environmental damage and can lead to health and saftey risks for humans and animals. Oil spill that caused damage to the environment and or private property can lead to legal contravention, claims and rehabilitation costs for the business. | HIGH | To ensure that correct planning of oil management activities forms part of the scope of work of any project to minimise and avoid pollution incidents. To ensure all legal requirements are identified well in advance to ensure authorisation, permits are obtained prior to the start of such a project where required . To avoid costly delays in projects while waiting to obtain permits and authorisations. | 0 Legal Contraventions | 1. Identifiy activities involved in oil management in scope of work before project commence. 2. Complete a risk assessment prior to the start of project on the management of all oil spillages, storage, disposal activities. The risk assessment must be verified and signed off by the BU Environmental professional. 3. Establish quantities of oil to be used, stored on or disposed from site. 4. Ensure that an EPP for oil management on site is in place. 5. Ensure that an oil management plans is in place and forms part of the project EMP. | Before project starts Duration of project Duration of project Before project starts Before project starts | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 16. General duty in respect of waste management, Sec 21. General requirements for storage of waste and Sec 25. Duties of persons transporting waste - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Hazardous Substances Act, 15 of 1973 - Declaration of Group I Hazardous Substances (GNR 452) - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - National Road Traffic Act, 93 of 1996 - National Road Traffic Regulations, 2000 - Chapter 8 - Transportation of Dangerous Goods and Substances by Road, Sect 277. Duties of Operator, Driver, Consignor and Consignee, Sec 278. Dangerous Goods to be Compatible, Sec 280. Driver to Undergo Training and Sec 281. Documents to be Held by Driver - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities -Hazardous Substances Act (15/73) Section 1 and 2 - classifies hazardous substances into Group I, Group II, Group III and Group IV hazardous substances. - Hazardous Substances Act (15/73) Regulation 453 – Disposal of hazardous chemical substance containers SANS Code of Practice 10228 - National Roads Act (54/71) Section 16 – Dumping of material on or near a national road -
10.2 | Oil Management | The maintenance, leaks or explosion of Power transformers: CVTs, CTs ,VTs and breakers;CVTs, CTs ,VTs and breakers. Oil leaks from transportation vehicles, vehicles with hydrolic cranes, etc. | Incorrect / poor oil management practices can lead to serious ground, ground water / surface water pollution. Oil spill causes serious environmental damage and can lead to health and saftey risks for humans and animals. Oil spill that caused damage to the environment and or private property can lead to legal contravention, claims and rehabilitation costs for the business. | HIGH | To ensure that all oil spills are reported and that reasonable measure are in place from the incident continuing, recurring. To ensure that the contaminated site is rehabilitated and cleaned up according to all legal requirements, policies and procedures. | 0 Legal Contraventions | 1. All oil spills must be reported within 24 hours of occurrence to the project manager and relevant BU Environmental Department. 2. Small oil spills must effectively be cleaned up by using an oil spill clean-up kit on site. 3. For large oil spill and registered oil spill clean-up consultant must be appointed. 4. The site must be cleaned and rehabilitated where necesarry. 5. An incident register must be kept on site where all environmental incidents must be captured (including oil spills). | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
10.3 | OIL MANAGEMENT | Oil disposal | Oil spill that caused damage to the environment and or private property can lead to legal contravention, claims and rehabilitation costs for the business. | HIGH | To ensure that all oil is treated as hazardous waste and disposed according to legal and other requirements. | 0 Legal Contraventions | 1. Oil used on site or any oil contaminated material, soil, water, etc. are regarded as hazardous waste and need to be disposed of by an registered hazardous waste consultant to a registered hazardous waste site. 2. On collection of oil / oil contaminated material the appointed contractor must issue a waste manifest for which all detail, such as quantity, dates, site names, etc. must be recorded correctly. 3. After waste disposal a waste disposal certificate, weigh bridge receipt, etc must be obtained from the appointed consultant and details must once again be checked and verified for correctness. 4. Copies of these records must be given to the relevant BU Environmental Department. | Duration of project | Project Manager / Contractor |  | - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - National Road Traffic Act, 93 of 1996 - National Road Traffic Regulations, 2000 - Chapter 8 - Transportation of Dangerous Goods and Substances by Road, Sect 277. Duties of Operator, Driver, Consignor and Consignee, Sec 278. Dangerous Goods to be Compatible, Sec 280. Driver to Undergo Training and Sec 281. Documents to be Held by Driver - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities - Hazardous Substances Act (15/73) Regulation 453 – Disposal of hazardous chemical substance containers - SANS Code of Practice 10228 - National Environmental Management: Waste Act, 59 of 2008, Sec 24. Collection of waste, Se 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering
10.4 | OIL MANAGEMENT | Oil Bunds | Incorrect / poor oil management practices can lead to serious ground, ground water / surface water pollution. Oil spill causes serious environmental damage and can lead to health and saftey risks for humans and animals. Oil spill that caused damage to the environment and or private property can lead to legal contravention, claims and rehabilitation costs for the business. | HIGH | Oil bunds can be used as an reasonable mitigation measure to contain an oil spill and prevent it from spreading to a larger areas. | 0 Legal Contraventions | 1. The use / construction of temporary / permanent oil bund will be based on the outcome of the risk assessment for the project oil management activities on site. 2. This will be approved in the form of method statements during the SHE evaluation and assessment | Duration of project Before project start | Project Manager / Contractor BU Env Dept |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
10.5 | OIL MANAGEMENT | Oil dams | Incorrect / poor oil management practices can lead to serious ground, ground water / surface water pollution. Oil spill causes serious environmental damage and can lead to health and saftey risks for humans and animals. Oil spill that caused damage to the environment and or private property can lead to legal contravention, claims and rehabilitation costs for the business. | HIGH | To ensure that where oil dams that are build, maintaned, cleaned and or refurbished complies with all relevant legal requirements, policies and procedures and current Eskom specification. | 0 Legal Contraventions | 1. New oil dams to be build on a substation site, or refurbished must be done according to the scope of work and Eskom specifications. 2. The use / construction of an oil dam / trap on a substation site as containment for an possible oil spill as part of reasonable preventative measures will be based on the outcome of the risk assessment for the project oil management activities on site. 3. Oil dams to be cleaned and checked for structural damage periodically | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
10.6 | OIL MANAGEMENT | Oil storage | Incorrect / poor oil management practices can lead to serious ground, ground water / surface water pollution. Oil spill causes serious environmental damage and can lead to health and saftey risks for humans and animals. Oil spill that caused damage to the environment and or private property can lead to legal contravention, claims and rehabilitation costs for the business. | HIGH | To ensure that oil storage on site is done according to legal requirements, policy and procedures. | 0 Legal Contraventions | Oil storage practices during projects will be based on the following requirements: 1. Legal Requirements 2. Outcome of risk assessment completed and verified prior to the start of the project. 3. Volumes stored and duration of storage | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 16. General duty in respect of waste management, Sec 21. General requirements for storage of waste - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
11 | Supply Top-Up Oil for the Transformer | Oil handling and storage | Oil contamination to natural environment. Potential of hydrocarbon contamination of ground due to spillage or leaks If oil is not stored on a non-bunded area or impermeable surface will cause hydrocarbon contaminatation on both ground and water surface | HIGH | To prevent environmental pollution | 0 Legal Contraventions | 1. No oil leaks, 2. Oil leaks to be cleaned with spillage kit. 3. All oil contaminated material to be disposed as hazardous waste by hazardous waste contractor | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 16. General duty in respect of waste management, Sec 21. General requirements for storage of waste - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
12 | Drain Into Bags (PCB), ISO Tanks | Use of vacuum pipe. Workers with hand tools | Oil contamination to natural environment and ground and water bodies | HIGH | To minimise oil pollution on the natural environment | 0 Legal Contraventions | 1. No oil leaks. 2. Ensure that PCB contaminated oil is disposed on the registered hazardous waste landfill site. 3. Safe disposal certificates to be obtained from accredited service provider. 4. PPE to be used It is highly recommended that ISO tanks that are certifies must be used to drain and transport old oil | Duration of project | project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 16. General duty in respect of waste management, Sec 21. General requirements for storage of waste - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
13 | Remove Oil From Existing Transformer | Handling of transformer oil | Oil spillage to the natural environment and possible injury to workers | HIGH | Minimize oil spillage to the natural environment and possible injury of pernnell during pumping of transfomer oil. | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. 3. All personnel to wear proper PPE 4. When pumping existing oil from the transfomer. 5. Test transformer oil for PCB Levels. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 16. General duty in respect of waste management, Sec 21. General requirements for storage of waste - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids - Occupational Health and Safety Act, 85 of 1993 - Regulations for Hazardous Chemical Substances, 1995 Sec 3, 9-15 - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 , Sec 25. Use and temporary storage of flammable liquids on construction sites and Sec29. Fire precautions on construction sites - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities
14.1 | PCB MANAGEMENT | Loading of PCB contaminated soil . PCB contaminated soil run-off due to rain. | Handling, exposure and disposal of PCB containing substances. Land, Water, Pollution. Negative impact on wildlife . Health risks | HIGH | To ensure that PCB containing substances are managed according to legal and other requirements To avoid environmental pollution and health risks associated with PCB exposure. | 0 Legal Contraventions | Ensure that contractors and vendors are trained and accredited in the handling, transport, storage & disposal of PCB containing substances. Ensure that contractors / vendor staff working with PCB equipment / plant have the relevant HAZMAT training. If working with capacitor banks check for damanged / leaking capacitor cans. Store leaking capacitor cans in recovery bags (300 micron) with Peatsorb and seal bag to prevent PCB from leaking. | Duration of project | Project Manager / Contractor |  | The Stockholm Convention on Persistent Organic, under Article 6.2Pollutants. - SANS 0290, 2008: Mineral oils - Management and Handling of PCB - National Environmental Management Act 107 of 1998 section 28 Duty of care - National Environmental Management Act,107 of 1998 - Regulations to Phase-out the Use of Polychlorinated Biphenyls (PCBs) Materials and Polychlorinated Biphenyl (PCBs) Contaminated Materials Sec 3. General prohibitions, 4. Phase-out time frames, 5. Registration, 7. Testing and labelling and 9. Reporting. - National Environmental Management : Waste Act 59 of 2008 - National Norms and Standards for Disposal of Waste to Landfill (GN R636)- 5. Waste Disposal Restrictions - The Basel Convention on the Control of Transboundary Movement of Hazardous Wastes and their Disposal (Annexture A , page 22 Elimination of the use of PCB in equipments) - The Rotterdam Convention on the Prior Informed Consent Procedure for Certain Hazardous Chemicals and Pesticides in International Trade, Ann 3 , -
14.2 | PCB MANAGEMENT | Loading of PCB Capacitors | Handling, exposure and disposal of PCB containing substances. Land, Water, Pollution. Negative impact on wildlife . Health risks | HIGH | To ensure that PCB containing substances are managed according to legal and other requirements To avoid environmental pollution and health risks associated with PCB exposure. | 0 Legal Contraventions | 1. Ensure that contractors and vendors are trained and accredited in the handling, transport, storage & disposal of PCB containing substances. 2. Ensure that contractors / vendor staff working with PCB equipment / plant have the relevant HAZMAT training. 3. If working with capacitor banks check for damanged / leaking capacitor cans. 4. Store leaking capacitor cans in recovery bags (300 micron) with Peatsorb and seal bag to prevent PCB from leaking. | Duration of project | Project Manager / Contractor |  | Eskom PCB Phase out standard (EPC 32-1135) - SANS 0290, 2008: Mineral oils - Management and Handling of PCB - National Environmental Management Act 107 of 1998 section 28 Duty of care - National Environmental Management Act,107 of 1998 - Regulations to Phase-out the Use of Polychlorinated Biphenyls (PCBs) Materials and Polychlorinated Biphenyl (PCBs) Contaminated Materials Sec 3. General prohibitions, 4. Phase-out time frames, 5. Registration, 7. Testing and labelling and 9. Reporting. - National Environmental Management : Waste Act 59 of 2008 - National Norms and Standards for Disposal of Waste to Landfill (GN R636)- 5. Waste Disposal Restrictions - The Basel Convention on the Control of Transboundary Movement of Hazardous Wastes and their Disposal (Annexture A , page 22 Elimination of the use of PCB in equipments) - The Rotterdam Convention on the Prior Informed Consent Procedure for Certain Hazardous Chemicals and Pesticides in International Trade, Ann 3 -
15 | SF6 MANAGEMENT | Sulphor Hexa Fluoride (SF6) Gas Insulated Breakers | SF6 gas is a greenhouse gas contributing negatively to climate changes and in large volumes may have health and safety risks when inhaled | HIGH | To ensure compliance to legal and other requirements and prevent environmental, health and safety impacts. | 0 Legal Contraventions / 0 Safety incidents | 1. Equipment must be checked for SF6 gas leaks and it must be reported on an Environmental Incident Notification form. 2. SF6 gas cylinders should be weighed before and after FS6 gas usage and differences recorded. 3. SF6 purchases and disposal should also be recorded. 4. Disposal of SF6 gas cylinders must be done by a Hazardous waste consultant and the disposal certificate obtained and submitted to BU Env Dept. | Duration of project | Project Manager / Contractor |  | Occupational Health & Safety Act 85 of 1993 Sec 8 duties of employer - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage - NEM: Air Quality Management Act (39 of 2004, Notice 172 (Gazette 37421) - Kyoto Protocol to the United Nations Framework convention on climate change, Article 2 and Annexture A
16 | CHEMICAL SUBSTANCE MANAGEMENT | Incorrect storage of Solvents, chemical substances & Paints | Health hazard to humans and environmental pollution | MEDIUM | To ensure that solvent and paints are stored in accordance with legal and other requirements. | 0 Legal Contraventions | 1. To store all solvents, chemical substances and paints in appropriate storage areas / facilities where chemical / solvent registers are available and updated. 2. The temporary storage of Nitrogen gas cylinders in workshop must be chained to wall (empy / full one). 3. To ensure comformance with Environmental EPP Procedure to address spillages. 4. To ensure MSDS are available at areas where such products are stored and meets the 16 point requirements as set by the OSH Act (1993). 5. To store hazardous chemicals substances which may cause a spillage in bunded areas. 6.. To label demarcated hazardous chemical store. | Duration of project | Project Manager / Contractor |  | - Basil Convention , Annexture 2,3 and article 4 and 12 , Rotterdam Convention Article 1,2 and 9 - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage. duty of care on every person to prevent significant pollution or degradation of the environment or where it cannot reasonably be avoided, stopped or is authorised by law, to minimise and rectify such pollution or degradation. - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 16. General duty in respect of waste management - National Environmental Management: Waste Act, 59 of 2008, Sec 21. General requirements for storage of waste- National Environmental Management: Waste Act, 59 of 2008, Se 25. Duties of persons transporting waste - National Water Act, 36 of 1998, Sec 19. Prevention and remedying effects of pollution - National Water Act, 36 of 1998, Sec 20. Control of emergency incidents - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 4. Use and storage of flammable liquids
17 | ARCHEOLOGICAL SITES | Disturbance and damage to archeological sites when doing line inspection/maintenance / project activities . | Could lead to sosial impact on communities involved and litigation. | HIGH | Ensure archeological site are not desturbed or damaged. | 0 Legal Contraventions | 1. Identify and communicate areas where archeological sites are present on the servitude / site. 2. Take necessary measures to avoid such sites. 3. Ensure records area kept on location of sites. | Duration of project | Project Manager / Contractor |  | National Heritage Resources Act, 25 of 1999, Sec 35. Archaeology, palaeontology and meteorites
18 | MOVEMENT IN SENSITIVE AREAS | Incorrect movement of vehicles / unlawful tresspassing during this project in sensitive areas could lead to sosial issues with land owners and damage and or pollution to the natural environment. Protected areas / sensitive ecosystems: National parks Privately owned game reserves / farms Rivers / riverbanks 500m from Wetlands / water bodies Proclaimed protected areas Graves sites | Land owners could refuse/restrict access to their properties. Pollution, erosion, damage to the environment. | HIGH | Ensure that no damage in sensitive area to the natural environment takes place. Legal requirements are adhered to | 0 Legal Contraventions | 1. Tx Landowner Approval certificate / consent form must be completed and signed off by contractor / site supervisor / landowner before and on completion of project 2. Identify and obtain all relevant permits required i.t.o. legislaiton prior to the start of any project activity. 3. To include sensitive / protected areas in scope of work for relevant bush clearing programmes | 1. Before entering servitude / private property 2. Beofre leaving servitude / private property after work completion Before project starts / kick-off 3. On task order award for project activity to start | Project Manager / Contractor BU Env Dept Project Manager |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
19 | EQUIPMENT MANAGEMENT | Cleaning of Machinery | Chemical pollution is caused by vehicle oils, grease or solvents. Chemical pollution to the environment can lead to a legal contravention and | MEDIUM | To ensure that no machinery is maintained / Cleaned in the servitude / on substation that can result to pollution | 0 Legal contraventions and landowner complaints | 1. By inspecting machinery prior to maintenance / project activity starting. 2. Not to make use of the incorrect tools for the job and not to make use of malfunctioning machinery. 3. To ensure all staff and contractors are sufficiently trained in using the machinery correctly. 4. Have records where relevant available in SHE file | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
20 | Civil Works: Establishment of Construction Camps and Store. Off - Loading Construction Material and Equipment | Site Establishment | Potential negative on the indigenous vegetation when clearing the land for site establishment. Possible damage to construction equipment that might cause contamination of the natural environment, air t, ground and surface water | HIGH | To minimise water wastage and pollution of land and water | 0 Legal contraventions and landowner complaints | 1. No camp sites on servitudes / private property or Eskom sites without written consent from landowners / Eskom Management. 2. Camp sites must not be located next 100 year flood line of the stream or the river. And 300 meters of the geo-hydrological gradient of the surface water. 3. Ensure proper effluent / sewerage management and implemented. 4. Ensure that all equipments are inspected for possible leaks. 5. Ensure sites have good housekeeping and kept clean | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage. duty of care on every person to prevent
21 | DELIVERY MATERIALS | Heavy vehicles | Oil contamination to natural environment. Potential of hydrocarbon contamination of ground due to spillage or leaks | HIGH | To prevent or minimise pollution incidents resulting from delivery of materials from heavy vehicles | 0 Legal Contraventions | No oil leaks, oil leaks to be cleaned with spillage kit. All oil contaminated supersorb to be disposed as hazardous waste. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
22 | EARTHMAT | The use of Heavy vehicles. Workers with hand tools | Oil contamination to natural environment. Poor topsoil can result in disturbed areas prone to erosion and invasion of alien plants or bush encroshment possible injury | HIGH | To minimise oil pollution on the natural environment | 0 Legal Contraventions | No oil leaks.PPE to be used Should and oil spill occur oil spill kit must be used and contaminated super zorb to be disposed at a registered facility. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
23 | Protection, Delivery of ERTU Cabling and Panels | Heavy vehicles: Oil and lubricants, Exhaust fumes Packaging materials | Oil contaminamination natural environment and illegal disposal of the packaging material on the natural environment | HIGH | Minimize contamination to the environment, minize air pollution | 0 Legal Contraventions | Ensure only licenced drivers are driving delivery vehicles, all waste to be stored on the proper waste facilities. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
24 | Off-Loading of ERTU Equipment | Oil and lubricants, Exhaust fumes Packaging materials damage to equipment or infrastructure. Incorrect storage of equipment | Oil contaminamination natural environment and illegal disposal of the packaging material on the natural environment | HIGH | Minimize contamination to the environment, minize air pollution | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
25 | Excavate new foundations | Heavy vehicles | Oil contaminamination natural environment | HIGH | Minimize contamination to the environment, minize air pollution | 0 Legal Contraventions | 1. Top soil escavated may not be removed from site/s without a permit. 2. No archeological found must be destroyed during the excavation process 3. Top soil from escavations must be stored on site and used for backfilling where required 4. Care should be taken to store topsoil and ensure it does not become contaminated with hazardous material eg) oils | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
26 | Backfilling of foundation and trenchs and storm water drainage | Compacting machinery workers with hand tools | Possible hydrocarbon contamination with from heavy machinery into the natural environment | HIGH | minimize hydrocarbon contamination to the natural environment, minize air pollution | 0 Legal Contraventions | 1. Backfilling must be done according to method statements 2. Backfilling and soil compacting must be done to prevent erosion from occurring after escavations 3. Only use uncontaminated backfilling material 4. Backfilling material brought into site/s must meet legal and other requirements | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
27 | Place steel work into the foundation | Steel off-cuts and steel cutting and gridding | Illegal dumping of steel off-cut waste on the natural environment | HIGH | Ensure that steel off-cuts are stored and disposed in an environmentally friendly manner | No steel off-cuts are disposed on the natural environment | 1. Ensure that the site has adequate waste receptors to store waste prior transportation. 2. All recyclable waste to be recycled with licensed recyclers. | Duration of project | Project Manager / Contractor |  | Eskom Waste Standard (32-245) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste - National Environmental Management: Waste Act, 59 of 2008, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec 24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering
28 | Connect earthing to steel work | Weildind and brazing | Possible fire veld due to uncontrolled sparks | HIGH | Ensure that weilding is controlled | No veld fires are started due to weilding activity / 0 Legal contraventions | All welding areas to have serviced fire extiguishers and all workers to be trained, to use fire extinguisher in the event of fire. | Duration of project | Project Manager / Contractor |  | National Veld And Forest Fire Act, 101 of 1998 , Sec 17. Readiness for fire fighting and Sec 18. Actions to fight fires
29 | Reistate yard stone | Heavy machinery and workers with rakes | Oil spillage to the natural environment and possible injury to workers | MEDIUM | Minimize oil spillage to the natural environment | 0 Legal Contraventions | 1. All personell to wear appriate PPE when working on site 2. Stockpiling yard stone to prevent contamination | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
30 | Stringing & Cabling, Measure & Cut to size to fit clamps | Hand tools and cable off -cuts | Proper disposal & storage of cable off-cuts | HIGH | All waste to be managed in an environmentally sound manner | 0 Legal Contraventions | Adequate waste facilities to be available on site to store waste material. | Duration of project | Project Manager / Contractor |  | Eskom Waste Standard (32-245) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste - National Environmental Management: Waste Act, 59 of 2008, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec 24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering
31 | Cast blinding layer | Use of concrete | Possible concrete spillage during construction. | HIGH | All concrete spills to managed | 0 Legal Contraventions | All concrete spills to cleaned before completion of shift | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
32 | Dismantling of existing transformer | Crane trucks & Engine & Hydraulic oil | Possible hydrocarbon contamination with from heavy machinery into the natural environment | HIGH | Minimize hydrocarbon contamination to the natural environment, minize air pollution | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
33 | Moving existing transfomer to spare spilt | Transformer and hydraulic oil | Possible hydrocarbon contamination with from heavy machinery into the natural environment | HIGH | minimize hydrocarbon contamination to the natural environment, minize air pollution | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. 3. All personnel to wear proper PPE When pumping existing oil from the transfomer. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
34 | Remove fittings and fixtures from the transformer | Electrical cables | Improper disposal of old electrical cables | HIGH | All old electrical cables to be disposed in an environmentally sound manner | 0 Legal Contraventions | 1. Ensure that Eskom Scrapping procedure to be followed and all personnel working on the transfomer to be suitably qualified. 2. All waste to be diposed on the registered landfill sites. | Duration of project | Project Manager / Contractor |  | Eskom Waste Standard (32-245) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste - National Environmental Management: Waste Act, 59 of 2008, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec 24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering
35 | Extract and ventilate the remaining oil and gases from existing transfomer | Flammable oil and gases | Possible contamination to the environment and fire hazard. | HIGH | No Contamination to the natural environment | No pollution to the natural environment | 1. All personell to wear appriate PPE when working on site, 2. The site to have serviced fire exstinguishers | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
36 | Draw vaccum on the transfomer | Transfomer oil | Possible contamination to the environment. | HIGH | No Contamination to the natural environment | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. 3. All personnel to wear proper PPE When pumping existing oil from the transfomer. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
37 | Build bundwall infront of the transformer | Oil spill prevention methods | Possible oil contamintion of the natural environment | HIGH | No Contamination to the natural environment | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. 3. All personnel to wear proper PPE When pumping existing oil from the transfomer. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
38 | Refill transfomer with new oil | Transfomer oil | Possible contamination of natural environment with transformer oil | HIGH | No Contamination to the natural environment | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. All personnel to wear proper PPE 3. When pumping existing oil from the transfomer. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
39 | Circulate transfomer oil withn required specifications | Transfomer oil Filtering | Possible contamination of natural environment with transformer oil | HIGH | No Contamination to the natural environment | 0 Legal Contraventions | 1. Ensure that the site has spillage kit and the personel are trained how to deal with small to MEDIUM spillages. 2. Only licensed drivers must operate construction vehicles. 3. All personnel to wear proper PPE When pumping existing oil from the transfomer. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
40 | Redundant equipments (Circuits breakers, VT's , CT's, earth switches ,isolators and Surge Arrestors) | Disposal of redundant equipments | Inappropriate management of underrated equipments could result to legal contravention (illegal dumping) | MEDIUM | Comply with legal & other requirements on the disposal of waste | 100% Compliance according to legal and othe rEskom requirements | 1. Project Department to liaise with Investment Recovery regarding the management (scrapping) of redundant equipments 2. To follow Tx Asset Management / Disposal process 3. Ensure that the contractor is evaluated by Tx environmental Department before tender award | Duration of project | Project Manager / Contractor |  | Eskom Waste Standard (32-245) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste - National Environmental Management: Waste Act, 59 of 2008, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec 24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering
41.1 | Batttery & Charger | Delivery and assembling of lead acide (hydrauchrolic) battery and charger | Acid spills due to incorrect offloading could lead to corrosion damage | MEDIUM | Correct handling acid batteries during offloading | No battery spills / 0 Legal Contraventions | 1. Driver must be licenced and accredited to operate the crane 2. Treat Battery acid spillage with Bicarbonate of Soda to neutralise 3. Report acid spillage to BU Env Dept 4. Dispose any contaminated material from battery acid spillage according to legal and other requirements 5. All personell involved in the assembling of batteries to be suitably accredited to perform the duties | Duration of project | Contractor / Eskom |  | Constitution of the Republic of SA 1992 s24 :the Right to a healthy Environment. - National Environmental Management: Waste Act 59 of 2008, Section 16, General duty in respect of waste management. - Hazardous Substances Act 15 of 1973 s1-4, R452, R453, R690, R1302, R1382 - OHSA Regulations General Safety Regulations 1986, R1031 4(9)a, 4(9)c,
41.2 | Batttery & Charger | Replacement of lead acid (hydrauchrolic) battery and charger | Illegal dumping of lead acid (hydrauchrolic) battery could results to water pollution and possible health risk |  | All battery cells returned to the supplier for recovery or recycling | No battery spills / 0 Legal Contraventions | 1. Return all redundant battery cells to the supplier 2. Ensure that all the used acid polygans are returned to the supplier 3. Report acid spillage to BU Env Dept 4. Dispose any contaminated material from battery acid spillage according to legal and other requirements | Duration of project | Contractor |  | Eskom Waste Standard (32-245) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 30. Control of emergency incidents - National Environmental Management: Waste Act, 59 of 2008, Sec 17. Reduction, re-use, recycling and recovery of waste - National Environmental Management: Waste Act, 59 of 2008, Sec 21. General requirements for storage of waste, Sec 22. Storage of general waste, Sec 24. Collection of waste, Sec 25. Duties of persons transporting waste, Sec 26. Prohibition of unauthorised disposal and Sec27. Littering National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Road Traffic Act, 93 of 1996 - National Road Traffic Regulations, 2000 - Chapter 8 - Transportation of Dangerous Goods and Substances by Road, Sect 277. Duties of Operator, Driver, Consignor and Consignee, Sec 278. Dangerous Goods to be Compatible, Sec 280. Driver to Undergo Training and Sec 281. Documents to be Held by Driver - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 , Sec 3. First aid, emergency equipment and procedures and Sec 2. Personal safety equipment and facilities - Hazardous Substances Act (15/73) Regulation 453 – Disposal of hazardous chemical substance containers SANS Code of Practice 10228
42 | REHABITATION | Land rehabilitation | Failure to rahibilitate the area may results negatively on the environment e.g soil erosion | MEDIUM | Rehabilitate disturbed areas at the completion of the contract | All disturbed areas successful rehabilitated after completion of contract | Identify indigenous plant for replanting and avoid invader plants | Duration of project | Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
43 | FIRE MANAGEMENT | Starting of fires due to negligence | Damage to property, fatalites of people and animals / livestock, legal contraventions, claims | HIGH | To avoid fires from Eskom activities / negligence | 0 Legal contraventions / claims / safety incidents | 1. No fires allowed to be made on any Eskom site / private property in servitudes 2. Risk assessments to be done for all project activities and precautions / preventative measures to be taken for activities which may pose a fire risk 3. Ensure EPP address fire risks 4. Have emergency contact details in place. | Duration of project | Contractor |  | National Veld And Forest Fire Act, 101 of 1998 , Sec 17. Readiness for fire fighting and Sec 18. Actions to fight fires
44 | ADMINISTRATION | Environmental & Safety File | Non compliance to legal requirements and non conformance to other requirements and ocnditions set out in the EMP can lead to servere impacts rusulting form the list of aspects identified. Failure to keep relevant and required documents for record purposes can lead to legal contraventions, civil and financial liability Failure to comply with the EMP and other Eskom requirements will result in the issuing of an NCR against the contractor. | HIGH | Ensure documentation system is maintained | 0 Legal contraventions / claims / safety incidents | 1. Update documents as activities takes place. 2. Keep all records and documentation with regards to project. 3. Submit reports as required after inspections/investigations/and completion of work. 4. All Environmental incidents to be reported. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
45 | REPORTING | Recording and reporting of Environmental related incidents | Failure to report could have a major impact on the environment, human health and well being and could lead to mitigation measures not taken | HIGH | Ensure all incidents are recorded and reported | 0 Legal contraventions / claims / safety incidents | 1. To keep and SHE incident register on site 2. To record and report all SHE incidents within 24 hours to Project Manager / BU Env Dept | Duration of project | Project Manager / Contractor |  | 240-133087117 - Eskom Environmental Incident Management Procedure - EnvironmentalInspections Report for Substation (TRM-FM-0071) - National Environmental Management Act 107 of 1998 section 28 Duty of Care and section 30 (Control of emergency incidents) - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents - 240-80662342 : Environmental Monitoring and Measurement work instruction
46 | TRAINING | Environmental Training & Awareness of contractors. | Lacking environmental awareness / knowledge of Eskom Transmission and other relevant environmental legal requirements may lead to legal contravention, damage to the environment and private property that may result into disputes and claims with landowners. | HIGH | To ensure contracts are aware of environmental requirement i.t.o. the EMP and environmental legal and other requirements | Daily | 1. Environmental Induction Training must be provided to all contractors who will be conducting work for this project. 2. Attendance Registers of this induction training must be kept by the project manager and copies included in the contractor's Environmental & Safety file 3. Environmental Requirements can be highlighted daily during the toolbox talks to refresh workers minds on what is required. 4. Relevant training requirements must be identified and be applicable to the scope of work of each project prior to the start of the project. | Duration of project | Project Manager / Contractor |  | National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
47 | ACTIVITIES WITHIN 500 METER RADUIS OF A WEDLAND OR 30 METERS OF ANY WATERCOURSE | Licences, authorisations or directives to be in place before work starts | Activities within 500 meters of an Wedland and 30 meters of any watercourse (river, spring, natural channel, lake or a dam) may lead to legal contraventions and claims against the business. | HIGH | Compliance with legal requirements | 0 Legal Contraventions | Comply to directive issued by Water Affairs. | Duration of project | L&S Technical Adviser / BU Environmental Professional. |  | National Water Act, 36 of 1998 - Regulations Requiring That A Water Use Be Registered Regulations Requiring That A Water Use Be Registered - Sec 21 - National Water Act, 36 of 1998- General Authorisation in terms of section 39 of the NWA for water uses as defined in section 21(c) or section 21(i) - National Environmental Management Act 107 of 1998 section 28 Duty of Care and section 30 (Control of emergency incidents) - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents
48 | SOIL EROSION | The incorrect activities in areas, which are prone to erosion, can lead to serious erosion. This can eventually make the entire area inaccessible. | Erosion on comunal propertiescan affect the landowner's carrying capacity, and affect Eskom infrastructure that could lead to Quality of supply been affected to customers as well as replacement and rehabilitation cost. | HIGH | To ensure that activiies which may lead to erosion are identified and managed to avoid or minimise further erosion from resulting and adhere to relevant legal requirements. | On Ocurance | 1. By identifying activities that may cause erosion. 2. By assessing site/s for existing erosion and to avoid these areas if and where possible. 3. By removing vegetation selectively and compacting soil after excavation activities. 4. To rehabilitate areas of erosion caused by project activities. | Duration of project | Project Manager / Contractor and ECO |  | Conservation of Agricultural Resources Act, 43 of 1983 - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage.
49 | ASBESTOS MANAGEMENT | Handling of asbestos and asbestos containing material. Asbestos has a negative impact on the environment and human health and well-being & pollution could be caused and legislation contravened if not managed according to legal requirements. | Pollution to soil, and water resources could be caused and affect human health and well-being and possible legal contravention. | HIGH | Broken asbestos is handled according to legal & other requirements. | 0 Legal contraventions | Employees / Contractors are trained on all requirements of handling asbestos. | Duration of project | Project Manager / Contractor |  | Environment Conservation Act, 73 of 1989 - Regulation for the Prohibition of the Use, Manufacturing, Import and Export of Asbestos and Asbestos Containing Materials (GNR. 341) - Section 2. Prohibitions, 4. Registration and Reporting, 5. Asbestos Phase-Out Plan, 6. Disposal of Asbestos or Asbestos Containing Material and7. Packaging and Transport of Asbestos - SANS 10228: The identification and classification of dangerous goods for transport by road and rail modes - SANS 10229: Transport of dangerous goods - Packaging and large packaging for road and rail transport Part 1: Packaging - Compensation for Occupational Injuries and Diseases Act, 130 of 1993 (COIDA)- Sec 65-67 - Occupational Health and Safety Act, 85 of 1993 (OHSA) - Sec 13-15 - Occupational Health and Safety Act, 85 of 1993 - GN R1031 - General Safety Regulations, 1986 Secc 2. Personal safety equipment and facilities - Occupational Health and Safety Act, 85 of 1993 - Asbestos Regulations, 2001 - Sec 2-22 - Occupational Health and Safety Act, 1993 - Notice of Inclusion in terms of Section 43 (1) (b) (xii) of The Occupational Health and Safety Act, 1993 (AIA SANAS Accreditation) - National Environmental Management Act, 107 of 1998 (NEMA), Sec 28. Duty of care and remediation of environmental damage and Sec 30. Control of emergency incidents - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incident
50 | SANITATION | Regular monitoring of sanitation (portable toilets) to prevent pollution to soil and ground water resources | Hazardous waste are dangerous to humans and animals, causing land, water and ground water pollution. Incorrect handling and disposal may lead to customer complains and claims against the business and legal contraventions. | MEDIUM | To ensure that non compliances or NCRs are picked up during construction activities and rectified / mitigated a.s.a.p. after it occurred. Chemical waste is transported and dispose according to legal and other requirements. | 0 Legal Contraventions | Portable toilets should be made available for use on site if required, to accommodate the number of employees working on site. Permission to be obtained from Eskom to make use of facilities on site. | Duration of project | Project Site Supervisor |  | Eskom Waste Standard (32-245) - Occupational Health and Safety Act, 85 of 1993 - Facilities Regulations, 2004- Sec 2 sanitation - Occupational Health and Safety Act, 85 of 1993 - GN R84 - Construction Regulations, 2014 - Sec 30. Construction employees? facilities - National Building Regulations and Building Standards Act, 103 of 1977 - Regulations Under Section 17 (1), Part 3 - Control of objectionable discharge and P4 industrial effluent - National Environmental Management - Integrated Coastal Management Act, 24 of 2008 - Chapter 8 - Marine And Coastal Pollution Control - National Environmental Management: Waste Act 59 of 2008 - List of Waste Management Activities That Have, or are Likely to Have, a Detrimental Effect on the Environment (GN 921 of 2013) -National Health Act, 61 of 2003 - National Environmental Health Norms and Standards For Premises and Acceptable Monitoring Standards For Environmental Health Practitioners - Sec 1. Norms and standards applicable to premises, Sec 26 Environmental pollution control measures applicable to premises and Se 22. Permissible water use -Occupational Health and Safety Act, 85 of 1993 - Facilities Regulations, 2004 - Sec 2 Sanitation -Water Services Act, 108 of 1997 - Sec 3. Right of access to basic water supply and basic sanitation, - 240-133087117 - Eskom Environmental Incident Management Procedure - EnvironmentalInspections Report for Substation (TRM-FM-0071) - National Environmental Management Act 107 of 1998 section 28 Duty of Care and section 30 (Control of emergency incidents) - National Water Act, 36 of 1998, Se 19. Prevention and remedying effects of pollution and Sec 20. Control of emergency incidents
Project Site Supervisor / BU Environmental Professional.
Transmission Project Manager | [8 empty] | Transmission Environmental Representative
Name & Surname | [8 empty] | Name & Surname
Signature | [8 empty] | Signature
Date | [8 empty] | Date
CONTRACTORS DETAILS I...............................................................................................................................(Name of Contractor), accept the above Environmental Management Plan and acknowledge having read and understood my responsibilities.
SIGNATURE | [8 empty] | DATE
CONTACT DETAILS
PROJECT MANAGER/ SITE REPRESENTATIVE (NAME)
SIGNATURE | [8 empty] | DATE