## Risks Assessment
Grootvlei Risk Assessment Template Rev2
Compiled by : Marbel Mbazima
Dashboard Indicators
Note:
Highest Consequence Rating: (manual input) | [6 empty] | Once printed, insert in contract file.
Highest Likelihood Rating: (manual input)
Risk/contingency as (%) of the contract value: (manual input)
Risk/contingency % as monetary value (R): (manual input - correspond with Contract Strategy & Cost Analysis)
# | Risk Statement | Y/N | Consequence Description | Consequence Rating | Likelihood | Potential Exposure | Risk Control | Priority for Attention | Contingency | Treatment/Control Strategy | Triggers | Assignee
| Link to Reference Document |  |  | Table 4 | Table 5 | Table 3 | Table 7 | Table 8
1 | Were interfacing contracts identified? | N
2 | Have KPI's been identified in the contract? | Y | Poor performance and come backs on scope execution. | 2 | E - 99% Probability | BU Impact | Fully Effective | I - S/Term (1mth) | N/A | Low service damages wil concluded with suppliers on contract negotiation stage | Repeat incidents | Service manager
3 | Was IBI training specified in the contract? | Y | Poor performance and safety incidents | 1 | E - 99% Probability | Departmental Impact | Fully Effective | I - S/Term (1mth) | N/A | The contractor and its employees will attend IBI training | Repeat incidents | Service manager
4 | Have the contract considered spares holding? | Y | Delays in spares delivery and shortage of spares will contribute to load shading due to shortage of palnts | 1 | E - 99% Probability | BU Impact | Partially Effective | IV - Ongoing | Yes | The contractor to supply a list of spares required for the gearbox and keep them readily available. | Repeat incidents | Contractor/Service Manager/Contract Supervisor
5 | Was supplier infrastructure established considered? | N
6 | Does the contract cater for SHE/plans? | Y | Safety risk to employees and plant | 2 | E - 99% Probability | BU Impact | Fully Effective | IV - Ongoing | Submission of a SHE plan is a specified requirement in the contract | The contractor shall submit safety plan which comply to safe work procedure for employer and it must be accept by Project Manager | Physical injury or property damages | Service Manager
7 | Does the contract cater for risk assessments? | Y | Safety risk to employees and plant | 2 | D - >50% Probability | Departmental Impact | Fully Effective | IV - Ongoing | Risk assessment is specified and is included in safety requirements. | The contractor shall submit risk assessment forms to the project Maneger. | Physical injury or property damages | Service Manager
8 | Has a training program been specified? | N
9 | Is there any risk in the contract strategy e.g. term, service, supplier? | N
10 | PSR responsibility | Y | Safety risk to employees and plant | 1 | E - 99% Probability | BU Impact | Fully Effective | IV - Ongoing | N/A | All contractors employees shall be authorised in plant safety regulation. | Physical injury and plant damage | Service Manager/Contract Supervisor
11 | Will decision making by the supplier impose a risk to the organisation? | Y | Lack of maintenance by the team will see plants not performing and creating load lossses | 2 | D - >50% Probability | BU Impact | Partially Effective | IV - Ongoing | duty to inform is included in the contract. | maintenance procedures to be followed | Financial Impact | Service Manager/Contract Supervisor and Procument
12 | Were medical/induction and associated costs considered? | Y | All employees to be compliant | 1 | B - >5 Probability | Departmental Impact | Fully Effective | III - 1Yr | N/A | Included in the contract | Medical induction due date compliance | Supervisor
13 | Who will be responsible for access permit/costs? | Y | Eskom, delay in execusion of work | 1 | E - 99% Probability | BU Impact | Partially Effective | IV - Ongoing | N/A | Included in the contract | Employee rused to access site | Service Manager
15 | Were quality requirements/objectives set in the contract? | Y | Poor workmanship | 2 | E - 99% Probability | BU Impact | Partially Effective | IV - Ongoing | its within the contract | The contractor must adhered to quality check plan,use IBI tool (job observation, pre-job debriefs etc) | Poor perfomance | Service Manager
16 | Was CIDB compliance specified in the contract? | Y | Contractor will be disqulified if not compliant to CIDB. | 3 | E - 99% Probability | Beyond Eskom Impact | Fully Effective | IV - Ongoing | Yes - CIDB | Service providers to be registered and compliant to Regulation 25-1B for Grade 6 Contractors | No attached provided with returnables | Supervisor
17 | Was a implementation program requested in the contract? | Y | The contractor must supply the programme. Non compliant contractor will loose points | 1 | B - >5 Probability | Departmental Impact | Fully Effective | IV - Ongoing | Included in the contract | The contractor should supply a programme | Poor perfomance | Contractor
18 | What are the license fees considerations? | N
19 | Does the contract implementation method pose a risk to the organisation? | Y | If contract not placed on time, maitenance will stall | 1 | B - >5 Probability | BU Impact | Partially Effective | IV - Ongoing | No Risk | All maintenance philosophy to be adhered to | Poor perfomance | Contractor
20 | Any risk for contract to be up and running? | N
21 | Does the contract pose a risk for loss of opportunities? | N
22 | Was the learning curve for staff been considered? | Y | New contractor will absorb the old team | 2 | A - <5% Probability | Departmental Impact | Fully Effective | III - 1Yr | N/A | Old staff will work with old staff as they impart knowledge | Delay in maintenance | Supervisor/ Service Manager
23 | Is there any risk of double processing or duplication of work or in contract? | N
24 | Is this contract dependant on additional external consultants/ costs? | N
25 | What interfacing equipment was identified not forming part of this contract e.g. LAN? | N
26 | Does the contract pose a threat for downtime or service disruption? | N
27 | Were the quality of deliverables specified? | Y | Adherence to ISO related maintenance standards | 1 | B - >5 Probability | BU Impact | Partially Effective | IV - Ongoing | specified within the contract | Compliance to ISO | Poor perfomance | Contractor
28 | Are there any threat of safety with contract deliverables? | N
29 | Was the acceptance criteria specified? | Y | Refer to technical evaluation QCP. If work does not meet quality will be rejected and posing spares shortage and intern plant load loss leading to load shedding. | 1 | C - >20% Probability | BU Impact | Fully Effective | IV - Ongoing | Contract deliverables are specified in the contract | All contractors to be evaluated will be subject to compliance to the evaluation criteria | Compliance to KPI | Contract Supervisor
30 | Will this contract impact other contracts/projects? | N
31 | Was the cost of implementation considered? | Y | If this funding not released we will see ourselves witout gearboxes leadind to load loses and then load shedding due to shortage of MW | 1 | C - >20% Probability | BU Impact | Fully Effective | IV - Ongoing | detailed scope issued | Contract value will ber monitored on a monthly basis. | Task order compliance | Contract Supervisor
32 | Was the cost of training considered? | N
34 | Does the contract pose in financial risk or exposure? | N
35 | Are there any risk i.t.o. skills and availability? | Y | poor workmanship. | 1 | E - 99% Probability | BU Impact | Partially Effective | I - S/Term (1mth) | Compency forms part of returnables in the contract | The contractor's employees will be trained if skills are a challenge to quality of deliverables, Contractot will be responsible for his employees skills | Breakdown rate will increase | Service Manager
36 | Were the employment requirements considered? | Y | Employment of all new staff | 2 | A - <5% Probability | BU Impact | Partially Effective | I - S/Term (1mth) | N/A | Absorb half of the old staff to train new staff | Increase in breakdowns | Supervioser/Service Manager
37 | Does the contract require a change management component? | N
38 | Will the contract have an impact on working conditions? | N | [6 empty] | N/A
39 | Will the contract have an effect on existing job descriptions? | Y | Scope change | 1 | A - <5% Probability | Departmental Impact | Partially Effective | II - M/Term (<3mths) | N/A | Contract seperated | challenges in stating of the new contract | Service Manager
40 | Could the contract effect staff morale? | N
41 | Does the contract specify compliance to specific standards? | Y | Adherence to all legislated standards | 1 | B - >5 Probability | Departmental Impact | Partially Effective | I - S/Term (1mth) | N/A | NEC will specify all related standards to Service Provider | Non compliance | Contractor/Supervisor/ Service mamanger
42 | Could the contract lead to negative reactions? | N
43 | Was the cost of maintenance considered? | Y | Lack of funds leading to no maintenance | 2 | A - <5% Probability | BU Impact | Partially Effective | I - S/Term (1mth) | N/A | Project finance is critical | Non payment of staff | Service Manager
44 | Is a Disaster Recovery Plan required? | N
45 | Could there be a risk i.t.o. supplier vulnerabilities? | N
46 | Could the contract/ data result in lack in customer service? | Y | If not enough information is shared to contractors and compliance thereof | 1 | A - <5% Probability | Departmental Impact | Fully Effective | IV - Ongoing | Full scope will be agreed with supplier prior to repairs | Sign off scope to be executed | To always be in contact with the repairer during maintenance | Supervisor
47 | Were legal requirements captured or referred to? | Y | Compliance to all legal requirements | 1 | A - <5% Probability | Departmental Impact | Fully Effective | I - S/Term (1mth) | All legal requirements are in the contract | Contractor to familiarise themselves | Non compliance | Supervisor/service manager
48 | Could industrial action have an effect on contract execution/steps taken? | Y | Blackage at the main gate | 1 | B - >5 Probability | BU Impact | Partially Effective | IV - Ongoing | Escort by the police | To use alternativeaccess to site | run will scalaton staff if need be and work after hours | Supervisor
49 | What role will weather conditions play in the execution of the contract? | N
50 | Is the contract period the best option? | Y | 60 months, after the contract ends we will establish a new one to open market. | 1 | A - <5% Probability | BU Impact | Fully Effective | IV - Ongoing | Yes | Starting a new contarct for the same service when it lapses | Contract duration | Service Manager
51 | What communications risk exist for the contract? | N
52 | Are there any procurement risks? | Y | Yes, delays on procurement will lead to contract placement delays. Procurement to assist for easy placement. | 2 | C - >20% Probability | Departmental Impact | Fully Effective | IV - Ongoing | Follow proper procurement processes to go to external market on time | Proper procument process should be followed . | Delays on delivery | Service manager and Contract Supervisor
53 | Does time constraints pose a risk to the contract? | Y | Yes. Breakdown take longer than anticipated, leading to load losses, then to shortage of MW. | 1 | E - 99% Probability | BU Impact | Fully Effective | IV - Ongoing | Scope will be commnunicated promptly | The contractor must perfom skills matrix and train their staff to close the gap identified. | Unavailability of the plant | Service manager
54 | Any risks in scope increasing/ | N
55 | Any risks in the costs/ analysis of the contract? | N
Note on B14: Chris Roos: Click on the hyperlink document to obtain detailed information on the risk topic.
Note on E12: Chris Roos: A consequence rating should be chosen (drop down box in cell) on the basis of the the most likely impact on Eskom and its stakeholders choosing the worst case of the consequence type given, refer to Table 4 of the "New Eskom Risk Management Model.
Note on F12: Chris Roos: A likelihood category should be chosen (drop down box in cell) on the basis of the chance that Eskom or its stakeholders could be affected at the chosen level of consequence.
Note on G12: Chris Roos: Select Impact from drop down box in cell.
Note on H12: Chris Roos: Define Level of Control from drop down box in cell.
Note on I12: Chris Roos: Insert treatment timing.
Note on J12: Chris Roos: Define Contingency Strategy.
Note on K12: Chris Roos: Define the Control Strategy.
Note on L12: Chris Roos: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.
Note on M12: Chris Roos: Use this column to identify which team member is responsible for tracking this risk and its changes in probability and impact. The assignee is not necessarily the person responsible for solving the problem, as risks often require escalation outside the team.

## Consequence Criteria
Table 4: Consequence criteria

## Likelihood Criteria
Table 5: Likelihood criteria
Category | Criteria
E | · 99% probability, or
· impact is occurring now, or
· could occur within “days to weeks”
D | · >70% probability, or
· balance of probability will occur, or
· could occur within “weeks to months”
C | · >20% probability, or
· may occur shortly but a distinct probability it won’t, or
· could occur within “months to years”
B | · >5% probability, or
· may occur but not anticipated, or
· could occur in “years to decades”
A | · <5% probability
· occurrence requires exceptional circumstances
· exceptionally unlikely, even in the long term future
· only occur as a “100 year event”

## Risk Control Guide
Table 7: Risk Control Effectiveness
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventative and address the root causes and Management believes that they are effective and reliable at all times. Reactive controls only support preventative controls.
Partially effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or Management has doubts about operational effectiveness and reliability.
Ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently very effective. There may be an over-reliance on reactive controls.
or
Some of the controls do not seem correctly designed in that they do not treat root causes, those that are correctly designed are operating effectively.
Totally ineffective | Significant control gaps. Either controls do not treat root causes or they do not operate at all effectively. Controls, if they exist are just reactive.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved due to poor control design and/or very limited operational effectiveness.

## Potential Exposure
Table 3: Potential Exposure Criteria
Level of Potential Exposure | Equivalent Financial Impact on Eskom (Rand Net Profit)
Beyond Eskom impact | > R1b
Across Eskom Divisions impact | ≥ R200m
Divisional impact | ≥ R 35m
Business Unit impact | ≥ R10m
Departmental impact | ≥ R1m

## Priority Timing
Table 8: Priority for attention
Priority | Suggested timing of treatment | Authority for continued toleration of residual risk
I | Short term. Normally within 1 month. | Managing Directors, Chief Executive and Board
II | Medium term. Normally within 3 months. | Managing Directors, Senior General Managers and General Managers
III | Normally within 1 year | Senior General Managers, General Managers and Managers
IV | Ongoing control as part of a management system. | All staff