## Risk template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | Power Delivery Projects: BRA for Transmission Line Construction Rev 4 | [7 empty] | Department: | SHEQ | [9 empty] | Next Review Date (every 2 years): | 2021-09-01 | Template identifier: | 240-70044602
Date: | 2020-01-15 | [7 empty] | Prepared by: | R. Masiza J. Sibanyoni L. Shezi R. Leduma D. Kotlolo S. Nxumalo A. Sintu P. Mojela R. Moabelo L. Shabalala K. Mudau |  | Authorised by: |  | Name: Geoffrey Small | [7 empty] | Document identifier | PDPMAN-FM-99 | [7 empty] | R | Safety | 1 | A | Fully effective | I
[14 empty] | Designation: PDP SHEQ Manager | [7 empty] | Revision number: | 1 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[14 empty] | Signed: | [7 empty] | Revision date: | 2024-05-31 | [9 empty] | 3 | C | Mostly ineffective | III
[14 empty] | Date: Septembrt 2019 | [18 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [32 empty] | 5 | E
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Pending, In Progress, Complete | Where applicable, add IRM system reference number for tracking of treatment actions. | Consequences | 6 | III | II | I | I | I
Identification and demarcation of protected and/or listed vegetation at the identified construction location. | Yes | 1 | 1.1 Uneven surfaces (rocks, tree stumps, etc) Thorns | 1 | Trips and falls; Prick injuries | Safety | Lack of concentration; Distractions Failure to properly remove vegetation during bush clearing activities. | Surveyors; Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | LTI; MED | Eskom and contractor site specific induction training; Employees and all visitors should be aware of their surroundings, i.e tree stumps, and other obstacles. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Construction Regulations 7; Eskom's Personal Protective Equipment Specification 240-44175132 | Contractor to determine the date | Contractor to state progress | N/A |  | 5 | III | II | II | I | I
| Yes |  | 1.2 Biological Hazards (snake bites, bee stings) |  | Snake bites and bee stings | Health | Invasion of their habitat; Lack of knowledge & training | Surveyors; Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | F; LTI | Appoint snake handlers and persons with knowledge of bees and similar insects; Awareness training | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A |  | 4 | IV | III | II | I | I
| Yes |  | 1.3 Wild animals |  | Attacks by wild animals | Safety | Lack of knowledge & training; Failure to inform how to react when faced with wild animals. | Surveyors; Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | F; LTI | Awareness training on how to react when faced with wild animals; Do not feed animals; Fence off animals and prevent contact with workers; | 5 | 1 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A |  | 3 | IV | III | II | II | I
| Yes |  | 1.4 Extreme weather conditions (heat , cold) |  | Dehydration / Frost bite / hypo and hyperthermia (cold stress / heat stress) | Health | Inadequate water intake; Inadequate or failure to provide suitable PPE | Surveyors; Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | MED | Ensure adequate water supply on site; Work rotation, Regular work breaks; Overalls with long sleevs, safety boots; Warm thermal jackets for winter; | 3 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Environmental Regulations for Workplaces; Eskom's Personal Protective Equipment Specification 240-44175132 ; Occupational Hygiene Survey Reports | Contractor to determine the date | Contractor to state progress | N/A |  | 2 | IV | IV | III | II | II
Bush & shrub clearing and tree felling | No | 2 | Biological hazards; Wild animals | 2 | Snake bites and bee stings; Attacks by wild animals | Safety or health | Invasion of natural habitat, Lack of knowledge & training | Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | F LTI | Site specific SHE induction; Appoint snake handlers and persons with knowledge of bees and similar insects; Awareness training on how to react when faced with wild animals; Fence off animals and prevent contact with workers; Do not feed animals | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132 | Contractor to determine the date | Contractor to state progress | N/A |  | 1 | IV | IV | III | III | III
| No |  | Uneven surfaces (rocks, tree stumps, etc) |  | Slips, trips and falls | Safety | Obstacles on the surface; Lack of concentartion; | Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | LTI MED | Remove obstacles on the surface; Awareness training. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A |  |  | A | B | C | D | E
| Yes |  | Use of Hand/Power tools e.g. chain saw, hand saws and other cutting tools |  | Injuries; Exposure to Noise; Exposure to Dust; Exposure to fumes | Safety | Lack of training; Lack of concentration; Poor maintenance; Lack of inspection; Poor supervision; Failure to follow procedures | Bush clearing team | PM | 8 hours per day | LTI; MED | Operators shall be trained; Awareness training; Develop a maintenance schedule for all machinery; Provide general supervision; Develop safe work procedures, and communicate to all employees. Hearing, and respiratory PPE | 4 | 2 | III | p | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A |  |  | Likelihood
| Yes |  | Cutting of trees |  | Injuries | Safety | Lack of training; Lack of concentration; Poor maintenance; Poor supervision; Failure to follow procedures | Bush clearing team | PM | 8 hours per day | LTI; MED | Operators shall be trained; Awareness training; Develop a maintenance schedule for all machinery; Provide general supervision; Develop safe work procedures, and communicate to all employees. | 5 | 2 | II | p | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Moving machinery (eg TLB); |  | Struck by | Safety | Lack of training; Lack of concentration; Failure to demarcate walk areas | Environmental and Health and Safety personnel; Workers; Visitors | PM | 8 hours per day | F LTI | Operators shall be trained; Awareness training; Develop a site specific traffic plan; Provide trained flagmen and give them high visibility vests. . | 5 | 3 | II | p | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; SHE Specification. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  |  |  | Noise exposure | Health | Failure to provide, train and use hearing protection; Failure to monitor / supervise use of ear protection | Bush clearing team | PM | 8 hours per day | LTI; MED | Conduct health risk assessment and communicate to employees; Provide and train employees on use of PPE (ear protection); Provide supervision. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | NHLR; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Extreme weather conditions (heat , cold) |  | Frost bite / hypo and hyperthermia | Health | Faillure to conduct health risk assessment; Failure to provide PPE( thermal gloves and jackets, wide brim hats etc) | Bush clearing team | PM | 8 hours per day | MED | Conduct health risk assessment and communicate results to employees; Provide PPE (thermal gloves and jackets, wide brim hats etc) as per risk assessment; Provide supervision. | 3 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | Environmental Regulations for Workplaces 2; Eskom's Personal Protective Equipment Specification 240-44175132 | Contractor to determine the date | Contractor to state progress | N/A
Surveying & Pegging | No | 3 | Hand tools eg. Hammer | 3 | Finger injuries; Hand blisters | Safety | Incorrect work position; Impact between tools and ground surface; Defective equipment | Surveying team | PM | 8 hours per day | LTI; MED | Awareness training of employees in the use of hand tools like hammers, spanners, chisels etc; Provide protective cap for chisels Inspect before use; Provide non defective equipment; Quarantine defective equipment | 4 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Extreme weather conditions; |  | Dehydration / Frost bite / hypo and hyperthermia | Health | Inadequate water supply, inadequate or failure to provide suitable PPE (thermal gloves and jackets, wide brim hats etc) | Surveying team | PM | 8 hours per day | MED | Work rotation, Regular work breaks; Overalls with long sleevs, safety boots; Warm thermal jackets for winter. | 3 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | Environmental Regulations for Workplaces 2; Eskom's Personal Protective Equipment Specification 240-44175132 | Contractor to determine the date | Contractor to state progress | N/A
| No |  | Biological hazards (snakes, bees, scorpions); Wild animals (rhinos, elephants etc) |  | Snake bites and bee stings Attacks by wild animals | Health | Invasion of natural habitat; Lack of knowledge & training, | Surveying team | PM | 8 hours per day | F LTI | Awareness training; Induction training; Appointment of trained snake handlers; Awareness training on how to react when faced with wild animals; Fence off animals and prevent contact with workers | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
Excavation / trenching | Yes | 4 | Collapse of sides of excavation; | 4 | Entrapment of persons / material inside excavation; | Safety | Weak and soft type of soil structure; Failure to adequately stabilise the sides and ends; | Excavation team; Members of the Public; Animals; Visitors | PM | 8 hours per day | F LTI MED | Contractor to ensure excavation is adequately stabilised as per Method Statement; Construction Regulations 13; | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act Construction Regulation 13; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 (Excavations); Construction Regulations 13 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Open excavation |  | Falling into | Safety | Inadequate barricading Inadequate warning; | Excavation team; Members of the Public; Animals; Visitors | PM | 8 hours per day | F LTI | Adequate barricading Adequate warning; | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 (Excavations); Construction Regulations 14 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Underground services (services pipes, eletrical & telecoms cables etc); |  | Damage to underground services; | Safety | Failure to identify underground services; Failure to communicate results of tests for underground services to operator; Unavailability of plans for underground services; Failure to follow procedure by the operator; . | Excavation team; | PM | 8 hours per day | F LTI | Use underground services detector (eg cable detector) to identify / trace underground services; Obtain and use underground service plan; Communicate the results of the tests to all employees. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Material / people/ animals falling into excavation |  | Injuries to employees / animals; | Safety | Failure to barricade the excavation area. | Excavation team; Members of the Public; Animals | PM | 8 hours per day | MED | Provide barricades to prevent people and animals from falling onto excavation. | 4 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; CR 13 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Moving machinery (eg TLB); |  | Damage to excavation, injury to employees | Safety | Moving machinery is too close to the excavation. | Excavation team; Members of the Public; | PM | 8 hours per day | F LTI | Supervision (ensure the moving machinery is at a distance of at least 1.5m from the excavation); Erect barricading aroung excavation. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; CR 13 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Restricted view of operator; |  | Struck against | Safety | Boom of the excavator / TLB restricts view of operator; Operator not being directed by a trained flagman; Lack of supervision. . | Excavation team; Members of the Public; Animals | PM | 8 hours per day | F LTI | Operators must be competent to operate the machinery; Ensure there are trained flagmen during these operations; Provide adequate supervision; Provide high visibility PPE. | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; CR 23; Eskom Procedure 39-98 Section 2.6 & 2.18 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Noise, Dust |  | Noise induced hearing loss, Dust inhalation | Health | Failure to provide, train and use hearing and respiratory protection; Failure to supervise use of hearing and respiratory protection. | Excavation team; Members of the Public; Animals | PM | 8 hours per day | LTI | Conduct health risk assessment and communicate hazards to employees; Provide hearing and respiratory protection, and supervise their use. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; NHLR; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Biological hazards |  | Snake bites and bee stings Attacks by wild animals | Health | Invasion of natural habitat; Lack of knowledge & training. | Excavation team; Members of the Public; Animals | PM | 8 hours per day | F LTI | Awareness training; Induction training; Appointment of trained snake handlers; Awareness training on how to react when faced with wild animals; Fence off animals and prevent contact with workers | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act Section 8 | Contractor to determine the date | Contractor to state progress | N/A
Batching | Yes | 5 | Batch plant (Conveyor belt/rollers); | 5 | Pinching of fingers; ; | Safety | Lack of machine guarding and lack of visibility; Lack of training. | Batch Plant Team | PM | 8 hours per day | LTI MED | Install machine guarding; Training of batch plant operator; Supervision by a competent person. | 4 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; DMR 12 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Dust/ Wet Cement; |  | Mesothelioma, Cement burns and Dermatitis | Health | Lack of training; Failure to provide suitable PPE; | Batch Plant Team | PM | 8 hours per day | LTI | Persons mixing concrete to use proper PPE including gumboots safety gogggles, long PVC gloves, respiratory protection etc; Provide awareness training for cement work | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act Section 8; HCSR; Eskom's Personal Protective Equipment Specification 240-44175132; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Noise |  | Noise Induced | Health | Failure to conduct health risk assessment and communicate results and recommendations to employees; Failure to provide, train and use hearing protection; Failure to supervise use of ear protection; NHLR | Batch Plant Team | PM | 8 hours per day | LTI | Conduct health risk assessment and communicate to employees; Provide supervision. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; NHLR; Eskom's Personal Protective Equipment Specification 240-44175132; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Ergonomics |  | Body aches | Health | Incorrect lifting techniques; Ergonomics (incorrect/awkward posture). | Batch Plant Team | PM | 8 hours per day | MED | Awareness training on correct lifting techniques; Job rotation and work rest periods | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
Foundations | No | 6 | Concrete mixing; ; | 6 | Concrete burns | Safety or health | Failure to risk assess and develop SWP; Lack of supervision; Lack of knowledge; Lack of/Inadequate PPE. | Foundation and other relevant teams | PM | 8 hours per day | MED | Persons mixing concrete to use proper PPE including gumboots safety gogggles, long PVC gloves, respiratory protection etc; Training of supervisors, and awareness training of relevant employees on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.6 Concrete Foundations; Supervisor to be present during delivery to ensure that raw material deliverd to site is up to specifications | 4 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Concrete not according to specification |  | Weak structure support; Foundation failure during erection causing injuries to employees; | Safety | Lack of supervision; Lack of knowledge; Raw material not according to requirements. | Foundation and other relevant teams | PM | 8 hours per day | F LTI | Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Section 6.3.3 which deals with foundations for concrete or steel poles. | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Section 6.3.3 which deals with foundations for concrete or steel poles. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Incorrect setting of foundation; |  | Misalignment of the tower legs leading to tower collapse and injuries to employees; | Safety | Lack of supervision; Lack of knowledge. | Foundation and other relevant teams | PM | 8 hours per day | F LTI | Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Section 6.3.3 which deals with foundations for concrete or steel poles. | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Section 6.3.3 which deals with foundations for concrete or steel poles. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | 6.4 Underestimate the impact area (Overkill during blasting) |  | Injuries from dislodged particles, | Safety | Failure to use the services of a competent service provider for blasting, and appoint competent and certificated person; Failure by Contrator / blasting service provider to determine the danger area, as well as authorised entry / exit points; Failure to ensure that the safe distances are applied for the relevant explosive category; | Foundation and other relevant teams; Members of the public. | PM | 8 hours per day | F LTI | Contractor / blasting service provider shall determine the danger area, as well as authorised entry / exit points; Contractor shall only use the services of a competent service provider for blasting; Contractor to ensure that the safe distances are applied for the relevant explosive category; Explosives Regulations 6, 11 and 12 | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Explosives Regulations 6, 11 and 12 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Awkward posture Bending (Ergonomics) |  | Musculoskeletal injuries | Safety | Inadequate training on ergonomics; Lack of supervision | Foundation and other relevant teams; Members of the public. | PM | 8 hours per day | MED | Employees to receive basic ergonomics awareness training, including: -recognizing ergonomic risk factors • recognizing signs and symptoms of musculoskeletal disorders (MSD’s) that may be related to the work environment • General principles for controlling ergonomic risk factors. • An awareness of other ergonomics factor/s which may affect their postures | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; PDPMAN-GL-50 | Contractor to determine the date | Contractor to state progress | N/A
Tower Assembly | Yes | 7 | Assembly not done according to specifications and standard requirements (SANS Codes, TRMSCAAC 5.2); | 7 | Collapse of the assembled structure, leading to injuries / property damage; | Safety | Assembly not done according to specifications and standard requirements (SANS Codes, Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Clause 7.4 (Tower erection); Inadequate supervision / training, complacency; Failure to complete Pre task planning | Assembly team | PM | 8 hours per day | F LTI | Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Clause 7.4 (Tower erection); Supervision / training. Pre task planning | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Clause 7.4 (Tower erection) | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Biological Hazards (snake bites, bee stings etc) |  | Snake bites, bee stings; tick bites | Health | Invasion of natural habitat; Lack of knowledge & training, | Assembly team | PM | 8 hours per day | F LTI | Awareness training; Induction training; Appointment of trained snake handlers; | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; NEMA; EMP | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Wild animals |  | Animal bites; | Health | Invasion of natural habitat; Lack of knowledge & training. | Assembly team | PM | 8 hours per day | F LTI | Awareness training on how to react when faced with wild animals; Fence off animals and prevent contact with workers; Induction training; | 5 | 2 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; NEMA / EMP; | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Extreme weather conditions (heat , cold, frost); |  | Heat stress / stroke / exhaustion, Hypo and hyperthermia, frost bite | Health | Inadequate water supply; Inadequate or failure to provide suitable PPE (thermal gloves and jackets, wide brim hats etc). | Assembly team | PM | 8 hours per day | MED | Ensure adequate water supply for employees; Conduct health risk assessment and communicate results to employees; Provide PPE as per risk assessment; Provide supervision. Induction training | 4 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Environmental Regulations for Workplaces; PDPMAN-GL-50 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Ergonomics (awkward posture, bending, lifting objects) |  | Musculoskeletal disorder | Health | Inadequate training on ergonomics; Inadequate supervision; Incorrect lifting techniques; Ergonomics (incorrect/awkward posture). | Assembly team | PM | 8 hours per day | MED | Awareness training on correct lifting techniques; Job rotation and work rest periods. | 4 | 2 | III | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; PDPMAN-GL-50 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Heavy equipment & material (Loading / off loading) |  | Lifting equipment failure while loading / off loading; Injuries to workers. | Safety | Failure to chose the correctly rated lifting equipment; Poor maintenance and failure to subject lifting equipment to statutory tests; Workers standing underneath load being lifted; Failure to follow correct procedure. | Assembly team | PM | 8 hours per day | F LTI | Supervisor to ensure that the correctly rated litfing equipment is used; Lifting equipment to be subjected to statutory tests at prescribed intervals, and a maintenance schedule be developed; Inspection of Lifting equipment; Supervisor to ensure that workers do not stand underneath suspended load. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; DMR 18 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Manual handling |  | Heavy load falls onto employee, trapping hands, fingers, feet etc under; Back strains / musculoskeletal injuries | Safety | Failure to provide lifting equipment for heavy loads; Failure to give training / awareness on correct manual lifting techniques. | Assembly team | PM | 8 hours per day | LTI MED | Provide suitable liting equipment for heavy loads; Give training / awareness on correct manual lifting tecnniques. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; PDPMAN-GL-50 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Psychological Hazards eg, Repetitive work, Stress related / work pressures / personal problems |  | May lead to incidents / injuries | Safety | Failure to concentrate / inattentiveness / complacency; Failure to give councelling to employees eg EAP); Lack of job rotation; Extended periods away from home. | Assembly team | PM | 8 hours per day | LTI MED | Ensure that employees receive councelling when needed; Provide job rotation; Ensure employees are able to go to their homes on pay weekends | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; BCEA | Contractor to determine the date | Contractor to state progress | N/A
Tower Erection | Yes | 8 | Suspended load; | 8 | Fall onto persons, causing injuries | Safety | Use of incorrect / damaged lifting equipment; Incorrect and unapproved rigging and lifting methods; Failure to maintain, and inspect by approved service providers (LME/I); Inadequate training and supervision | Erection Team | PM | 8 hours per day | F LTI | Routine and pre use inspections by appointed competent person; Safe work procedures; Training and supervision. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; DMR 18 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Defective Lifting equipment (Crane, slings, shackles) |  | Lifting Equipment failure leading to injuries | Safety | Use of defective lifting equipment; Incorrect and unapproved rigging and lifting methods; Failure to maintain, and inspect by approved service providers; Failure to inspect by the user (rigger); deviating from the standards. | Erection Team | PM | 8 hours per day | F LTI | Routine and pre use inspections by appointed competent person; Statutory load tests by LME | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; DMR 18 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | 8.3 Elevated position |  | Fall from height (Objects and persons) leading to injuries / fatilities | Safety | Failure to identify correct anchor points; Not following procedure (e.g Abseiling); Underlying medical condition; Failure to secure proprely / hook up at heights( persons and objects); Inadequate WAH training / supervision. | Erection Team | PM | 8 hours per day | F LTI | Training on work at height from an accreditated organisation; Identification of anchor point by supervisor; No work is allowed during inclement weather conditions; Client approved contractor fall protection plan; Direct supervision; Erect safety nets to catch falling material; Demarcate drop zone area, | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; CR 10; Eskom Work at Height Procedure 32-418 Section 3 | Contractor to determine the date | Contractor to state progress | N/A
| No |  | Uneven surfaces (rocks, tree stumps, etc) |  | Slipping / falling leading to injuries | Safety | Steep incline area with loose rock material; Failure to provide awarenss training to employees on work on uneven surfaces / mountainous area; Failure to provide employees with relevant equipment for mountain work (e.g ankle boots). | Erection Team; Visitors | PM | 8 hours per day | MED | Awareness training of affected employees on rock / mountain climbing techniques; Provide employees with the relevant equipment for working in uneven terrain. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 32-520 "Occupational Health & Safety Risk Assessment Procedure' | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Driving on uneven terrains |  | Motor Vehicle Accidents | Safety | Corrugations on the road; Intoxication; Failure to buckle up; Failure to maintain the stipulated speed as determnined during risk assessment exercise. Lack of 4X4 training for gravel roads | Erection Team; Visitors | PM | 8 hours per day | F; LTI; MED | Maintain the speed limit as determined during the risk assessment; Training of drivers in defensive driving (4x4 training). Prohibition of driving under the influence; All drivers to buckle up | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Road Traffic Management Act; Eskom life saving rules; Eskom Procedure "Vehicle and Driver Safety Management Procedure 240-62946386 | Contractor to determine the date | Contractor to state progress | N/A
Hand erection | No |  | Lifting equipment(Jibs,winches,steel wire anchors) |  | Falling equipments(Jibs) and steel members; Failure of lifting equipment | Safety | Mountainous area(uneven terrain); Failure to maintain lifting equipment; Ineffective communication. | Erection Team | PM | 8 hours per day | MED | Contractor to determine safe anchor points for lifting equipment on mountanious / uneven terrain; Supervision by a competent and experienced supervisor; Contractor to use certified jibs and winches that are inspected on a daily basis to be used. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; DMR 18 | Contractor to determine the date | Contractor to state progress | N/A
| No |  | Ergonomics (awkward posture, bending, lifting and pulling of steel members) |  | Musculoskeletal disorder | Health | Incorrect lifting and pulling techniques; Ergonomics (Incorrect/awkward posture). | Erection Team | PM | 8 hours per day | LTI | Awareness training on correct lifting techniques; Job rotation and work rest periods. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
Stringing | Yes | 9 | Running blocks; | 9 | Derailed conductor (fall onto employees) | Safety | Incorrect number and size of running blocks on strain towers; Improper selection of lifting equipment; Failure to maintain, and inspect by approved service providers; Deviating from the standards; Interfacing between different tower types; Using incorrect sized pulling equipment, and lack of maintenance; Lack of training / experience, inclement weather conditions; equipment failure. | Stringing Team | PM | 8 hours per day | F LTI | Eskom and Contrator supervisors to be trained on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 (Stringing Operations); Direct supervision; Regular inspection of Lifting Equipment as per manufacture's manual; Riggers to be trained and appointment; Client approved contractor fall protection plan; Training to be provided by Eskom approved service providers; No work at height is allowed during inclement weather; Direct supervision; Identified and tested anchor point (SANS 50795); Eskom's Work at Height Procedure 32-418 section 3.13 (Falling objects); Erect safety nets to catch falling material; Demarcate safe drop zone area; No person to work or stand beneath persons working at height | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 (Stringing Operations; SANS 50795; Eskom's Work at Height Procedure 32-418 section 3.13 (Falling objects); | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Square lifting |  | Equipment failure and fall onto employees |  | Improper selection of lifting equipment, Failure to maintain, and inspect by approved service providers; Deviating from the standards | Stringing Team | PM | 8 hours per day | F LTI | Eskom and Contrator supervisors to be trained on Eskom Procedure The design and construction of overhead power lines (240-47172520)- Section on Stringing Operations, Direct supervision, Regular inspection of Lifting Equipment as per manufacture's manual. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure The design and construction of overhead power lines (240-47172520)- Section on Stringing Operations, | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Tower configuration and hardware integration; |  | Earth wire and OPG come in contact with conductor leading to failure and/or damage |  | Interfacing between different tower types; Incorrect sequence of activity; Inadequate management of change; Inadequate planning; Material unavailability. | Stringing Team | PM | 8 hours per day | F LTI | Eskom and Contrator supervisors to be trained on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 (Stringing Operations); Direct supervision; Regular inspection of Lifting Equipment as per manufacture's manual. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure The design and construction of overhead power lines (240-47172520)- Section on Stringing Operations, | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Pulling equipment e.g. tensioner / puller |  | Failure of pulling equipment, causing the conductor to swing wildly; |  | Using incorrect / lower rated pulling equipment. | Stringing Team | PM | 8 hours per day | F LTI | Eskom and Contrator supervisors to be trained on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 (Stringing Operations); Direct supervision; Regular inspection of Lifting Equipment as per manufacture's manual. | 5 | 3 | II | p | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure The design and construction of overhead power lines (240-47172520)- Section on Stringing Operations, | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Step bolt (with carbon content > 0.2%) |  | Failure of the step bolt | Safety | High carbon content of the bolt | Climbers | PM | 8 hours per day | LTI | Monitor and ensure the material properties (carbon content) of the step bolts are below 0.2% During manufacturing there are hold points to measure the carbon content | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure The design and construction of overhead power lines (240-47172520)- Section on Stringing Operations, | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Fall arrest anchoring device (150 mm < 35°) |  | Failure of the anchoring device | Safety | Anchoring device place at the wrong orientation, namely less than 35° | Stringing Team | PM | 8 hours per day | F LTI | Training of supervisors and climbers to insert the anchoring device at the correct orientation. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure The design and construction of overhead power lines (240-47172520)- Section on Stringing Operations, | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Work at elevated position; |  | Fall from height |  | Failure to secure proprely( persons and objects); Lack of training. | Stringing Team | PM | 8 hours per day | F LTI | Training on work at height from an accreditated organisation; Identification of anchor point by supervisor; Work at Height Procedure 32-418 section 3; No person is allowed to work/stand beneath persons working at height No work is allowed during incliment weather conditions; Client approved contractor fall protection plan; No work at height is allowed during inclement weather; Direct supervision; Erect safety nets to catch falling material; Demarcate drop zone area. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Work at Height Procedure 32-418 section 3; Eskom Procedure 39-3 "Minimum SHE Training" | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Abseiling |  | Fall from height |  | Taking short cuts to ground level; Inadequate supervision | Stringing Team | PM | 8 hours per day | F LTI | Training on work at height from an accreditated organisation; Direct supervision | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Work at Height Procedure 32-418 section 3; Eskom Procedure 39-3 "Minimum SHE Training" | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Falling of equipment from heights to ground. |  | Equipment falling on employees working below | Safety | Failure to secure equipment proprely; Lack of training. | Stringing Team | PM | 8 hours per day | F LTI | Training on work at height from an accreditated organisation; Identification of anchor point by supervisor; Work at Height Procedure 32-418 section 3 No person is allowed to work/stand beneath persons working at height; No work is allowed during incliment weather conditions; Client approved contractor fall protection plan; Direct supervision; Erect safety nets to catch falling material; Demarcate drop zone zone area. | 5 | 3 | II | p | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Work at Height Procedure 32-418 section 3; Eskom Procedure 39-3 "Minimum SHE Training" | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Live overhead lines in close proximity to work area / induced electricity |  | Electrocution, Serious burns | Safety | Failure to observe clearamces; Inadequate supervision. | Stringing Team | PM | 8 hours per day | F LTI | Supervisor shall ensure that the safety clearances are observed as per Electrical Machinery Regulations 19 & 21; Eskom Procedure "Operating Regulations for High Voltage Systems (ORHVS)-32-846" Section 5.03.6.3 (Work in close proximity to live conductors / apparatus); Supervisors shall be trained in the Eskom ORHVS (see above). | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Electrical Machinery Regulations 19 & 21; Eskom Procedure "Operating Regulations for High Voltage Systems (ORHVS)-32-846" Section 5.03.6.3 (Work in close proximity to live conductors / apparatus | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Crossing roads during stringing operations |  | Damage to cars that belong to the public | Safety | Failure to erect rugby poles; Failure to warn the public / motorist of road crossing; Inadequate supervision. | Stringing Team | PM | 8 hours per day | PD | The contactor must ensure that rugby poles are erected at all road crossings; Contractor to ensure that the public is warned, and flagmen placed at strategic positions to warn traffic / motorists. |  |  |  |  | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
Tower Dressing | Yes | 10 | Hardware; | 10 | Structural damage, damage to hardware causing injuries to employees; . | Safety | Lack of direct supervision; Lack of concentration; Inadequate MS / SWP; Failure to conduct pre task planning | Dressing team | PM | 8 hours per day | F LTI | Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing). Conduct Pre task planning | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Work at elevated poistion; |  | Fall from height; | Safety | Lack of training / experience; Inclement weather conditions; Improper use of fall arrest equipment, equipment failure; Failure to identify safe anchor points. | Dressing team | PM | 8 hours per day | F LTI | Eskom Working at Height (32-418) - Section 3.7 PPE and Section 3.8 Anchor Points, read with SANS 50795;. PPE to include Climber helmet with 3 point chin straps, full body safety harness; Ensure Eskom and contrator supervisors are trained in the Eskom Procedure The design and construction of overhead power lines (24047172520) Section 7.5 (Tower Dressing). | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing; Eskom Working at Height (32-418) - Section 3.7 PPE and Section 3.8 Anchor Points; SANS 50795 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Hardware lifted to elevated position / lifting operations |  | Hardware fall to ground, causing injuries. | Safety | Lack of training / experience; Inclement weather conditions; Lifting equipment failure; Inadequate supervision / training; Incorrect lifting methods | Dressing team | PM | 8 hours per day | F LTI | Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing); Testing and inspection / maitenance of lifting equipment; No lifting during periods of inclement weather, e.g. strong winds | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing); Eskom Procedure 39-98 Section 2-10 | Contractor to determine the date | Contractor to state progress | N/A
Tower Regulation | Yes | 11 | Clamping in (applicable to strain towers and suspension towers); | 11 | Conductor can fall to the ground causing fatalities / injuries | Safety | Conductor not inserted onto the lifting shoes. | Regulation team | PM | 8 hours per day | F LTI | 11.1 Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation; Direct supervision during this activity by appointed competent person / ensure the conductor is held by the lifting shoes | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation; | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Lifting equipment failure (Slippage of conductor whilst being tensioned, overtensioning of conductor leading to its failure); |  | Conductor can fall to the ground causing fatalities / injuries | Safety | Conductor not inserted onto the lifting shoes. | Regulation team | PM | 8 hours per day | F LTI | Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation. Direct supervision during this activity by appointed competent person; Ensure Inspection of lifting equipment. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation; | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Conductor |  | Snapping of conductor causing injuries |  | Overtensioning of conductor; Lack of calibration of tensioner; Inadequate supervision; Inadequate communication | Regulation team | PM | 8 | F LTI | Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation. Direct supervision during this activity by appointed competent person; Ensure Inspection and maintenance of lifting equipment. Ensure Adequate communication | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation; | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Work at elevated position on strain towers and suspension towers; |  | Workers can fall from height, | Safety | Lack of training / experience; Inclement weather conditions, Improper use of fall arrest equipment, equipment failure; Failure to identify safe anchor points. | Regulation team | PM | 8 hours per day | F LTI | Client approved contractor fall protection plan; Training to be provided by Eskom approved service providers; No work at height is allowed during inclement weather; Direct supervision; Identified and tested anchor points (SANS 50795); Eskom's Work at Height Procedure 32-418 section 3 | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; SANS 50797; Eskom's Work at Height Procedure 32-418 section 3. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Fall of equipment from height (during installation of spacers, bird diverters, warning spheres, vibrations dampers etc. |  | Hardware can fall to ground onto persons | Safety | Failure to properly secure equipment at height. | Regulation team | PM | 8 hours per day | F LTI | Direct supervision; Eskom's Work at Height Procedure 32-418 section 3.13 (Falling objects) Erect safety nets to catch falling material, Demarcate drop zone area, no person to work or stand beneath persons working at heights. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Work at Height Procedure 32-418 section 3.13 (Falling objects) | Contractor to determine the date | Contractor to state progress | N/A
Rehabilitation | Yes | 12 | Earth Moving Machinery (graders, tractors) | 12 | Struck by /Contact with machinery | Safety | Lack of concentration, fatigue; Failure to demarcate walk areas and appoint signalmen. Inadequate observation by the driver; Inadequate inspection and maintenance; Incompetent operator; Inadequate lock out system; Failure to put in chock blocks | Rehabilitation team | PM | 8 hours per day | F LTI | Site traffic plan to demarcate safe walk areas for employees; Awarness training on work hazards; Appoint signal / flag man Ensure adequate observation by the driver; Ensure adequate inspection and maintenance; Only Competent operator to operate machinery; Ensure there is an adequate lock out system; Ensure that chock blocks are inserted when vehicles are stationery | 5 | 2 | II |  | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Dust and noise |  | Lung infection; hearing loss | Health | Moving machinery; Failure to use or provide ear protection and respiratory protection. | Rehabilitation team | PM | 8 hours per day | LTI | Provide adeguate PPE(dust masks, hearing protection e.g ear muffs, ear plugs; Demarcate noise zones and noise equipments with pictograms; Subject employees to audiometric and lung testing and medical surveillance | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; NHLR; | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Hazardous Chemical Substances – cement |  | Mesothelioma / Silicosis | Health | Lack of training; Failure to provide and train in the use of respiratory protection | Rehabilitation team | PM | 8 hours per day | MED | Provide adeguate PPE (dust masks / respirators; Subject employees to lung testing and medical surveillance. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Hand tools (eg pliers) |  | Caught between Struck by(Punctured skin) | Safety | Lack of concentration,fatigue; | Rehabilitation team | PM | 8 hours per day | LTI | Work rest periods for employees; Awarness training on work hazards for certain tasks, eg use of hand tools. | 4 | 3 | II |  | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act | Contractor to determine the date | Contractor to state progress | N/A
Helicopter Operations | Yes | 13 | Helicopter blades; | 13 | Struck by /Contact with; | Safety | Failure to demarcate safe zone for helicopter parking. | Pilots and Eskom Employees | PM | 8 hours per day | F LTI | Dermacate safe zone for Helicoper ; Awareness training; Supervision | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Inspection by service provider. | Contractor appointed responsible person | OHS Act Section 8; Civil Aviation Act | Contractor to determine the date | Contractor to state progress | N/A
| No |  | Flying helicopter; |  | Helicopter crash; | Safety | Failure to maintain and inspect; Pilot error; Inclement weather conditions. | Pilots, Employees, members of public | PM | 8 hours per day | F LTI | Provide and develop maintanance schedule; Use of trained and experienced pilots Ensure no flights during inclement weather conditions. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Civil Aviation Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Noise and dust |  | Noise induced hearing loss and dust inhalation; | Safety | Exposure to excessive noise and dust. | Pilots, Employees, members of public | PM | 8 hours per day | LTI | Provide adequate hearing and respiratory PPE. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132; NHLR | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Lifting operations (eg. Steel structures) |  | Dislodgement of the structures/equipment or material being lifted. | Safety | Incorrect lifting techniques; Deviation from approved lifting techniques. | Pilots, Employees, members of public | PM | 8 hours per day | F LTI | Eskom Procedure 39-98 Section 2-10; Routine and pre use inspections by appointed competent person; Safe work procedures for lifting operations | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; DMR 18; Eskom Procedure 39-98 Section 2.28 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Strapping loads to be lifted / attaching sling to cargo hook; |  | Injuries | Safety | Incompetent person setting strapping, Incorrect strapping procedures followed, Incorrect weight straps used, Straps not fastened correctly; | Pilots, Employees, members of public | PM | 8 hours per day | LTI | Strapping of setting to be done by competent person; Safe Work Procedure to be followed. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 39-98 Section 2.39 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Flying chopper to the location and Landing / Air lifting cargo; |  | Mechanical failure of the chopper, cargo becomes loose and drops to ground; | Safety | Failure to maintain chopper; Chopper not inspected prior to departure; Load not properly attached | Pilots, Employees, members of public | PM | 8 hours per day | F LTI | Chopper to be inspected and records to be kept on the file for inspection; Ensure there is a maintenance programme in place for the chopper; Obtain Civil Aviation Authority approval for chopper operations; Load to be properly attached by trained person. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure 39-98 Section 2-10; Civil Aviation Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Weather (strong winds, rain, poor visibility) |  | Strong wind can cause the cargo to to swing, compromising chopper balance, poor visibility can cause chopper to crash; | Safety | Failure to consult the weather sevices to check on weather conditions; Failure to to take precautionary measures as per weather conditions. | Pilots, Employees, members of public | PM | 8 hours per day | F LTI | Pilot should not fly during inclement weather conditions (too windy and rainy) | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Civil Aviation Act | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Dropping of cargo on site |  | Damage to property | Safety | Drop off zone not conducive to landing. | Pilots, Employees, members of public | PM | 8 hours per day | LTI | The area to be cleared before drop ; Only competent person to guide the cargo for dropping; Cargo to be dropped in a safe and accessible area according to the building layout. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Civil Aviation Act | Contractor to determine the date | Contractor to state progress | N/A
Hazardous Biological Agents | Yes | 14 | HBA exposure in clinic environment e.g. HIV / AIDS, TB, Hepatitis A&B, | 14 | Contact with infectious fluids, blood,faeces, airborne pathogens, | Health | Failure to conduct awareness training on prevention and control of infectious diseases; Failure to conduct medical surveillance. | Eskom / contractor employees eg first aiders | PM | 8 hours per day | LTI | Awareness training, medical surveillance programme, vaccination of first aiders and health care workers for Hepatitis A & B and flu vaccine. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Reportable diseases, i.e. Malaria, Diphtheria, Rabies, Tetanus, Viral hepatitis, Yellow fever, Rheumatic / Congo fever |  | Contact with infectious fluids, blood,faeces, airborne pathogens, | Health | Failure to conduct awareness training on prevention and control of infectious diseases; Failure to conduct medical surveillance. | Eskom / contractor employees eg first aiders | PM | 8 hours per day | MED | Awareness training, medical surveillance programme. | 3 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Infectious disease exposure i.e. Bacterial diarrhoea, Typhoid fever, Hepatitis A, Tinea. |  | Contact with infectious fluids, blood,faeces, airborne pathogens, | Health | Failure to conduct awareness training on prevention and control of infectious diseases; Failure to conduct medical surveillance. | Eskom / contractor employees | PM | 8 hours per day | MED | Awareness training, medical surveillance programme. | 3 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | HBA exposure in general work environment e.g Viruses - Tuberculosis, Bacteria - Anthrax in soil and Parasites – Tape/hook worms.; |  | Contact with infectious fluids, blood,faeces, airborne pathogens, | Health | Failure to conduct awareness training on prevention and control of infectious diseases; Failure to conduct medical surveillance. | Eskom / contractor employees | PM | 8 hours per day | MED | Awareness training, medical surveillance programme. | 3 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Vulnerable persons i.e. Lactating women and pregnant employees; |  | Contact with infectious body fluids, eg saliva, blood,faeces,airborne pathogens, | Health | Failure to conduct awareness training on prevention and control of infectious diseases specifically for pregnant / lactating and vulnareble employees | Pregnant women, immune compromised employees | PM | 8 hours per day | MED | Awareness training, medical surveillance programme. | 3 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Emergency personnel exposed to HBA |  | Contact with infectious body fluids, eg saliva, blood,faeces,airborne pathogens, | Health | Failure to adhere to processes and procedures for handling emergency situations. | Emergency personnel and first aiders | PM | As and when required | LTI | Awareness training; Medical surveillance programme; Vaccination of first aiders and health care workers for Hepatitis A & B and flu vaccine; Refresher training fo rthe emergency personnel. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329. | Contractor to determine the date | Contractor to state progress | N/A
Commuting / travelling between sites | Yes | 15 | Bad gravel road conditions | 15 | Motor Vehicle Accidents | Safety | Fatigue; Corrugations on the road; Road slippery after rains; Failure to maintain the stipulated speed as determnined during risk assessment exercise; Inadequate driver training; Members of the public and animals on the road. | Drivers, Passengers, Members of the public, Animals on the road | PM | 8 hours per day | F LTI PD | Take regular breaks; Adhere to the stipulated speed; Be on the lookout for other road users and animals on the road. Drive carefully on slippery roads after rains; Ensure adequate driver training; | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure "Vehicle and Driver Safety Management Procedure 240-62946386 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Inconsiderate road users |  | Motor Vehicle Accidents | Safety | Other road users driving unsafe. | Drivers, Passengers, Members of the public, Animals on the road | PM | 8 hours per day | F LTI MED | Be on the lookout for other road users; Advanced / defensive driving. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure "Vehicle and Driver Safety Management Procedure 240-62946386 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Poor road conditions / potholes etc |  | Motor Vehicle Accidents / damage to vehicle rims and tryes | Safety | Failure to maintain public roads | Drivers, Passengers, Members of the public, Animals on the road | PM | 8 hours per day | LTI; MED | Be on the lookout for potholes and other obstacles on the road; Advanced / defensive driving. | 4 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | OHS Act; Eskom Procedure "Vehicle and Driver Safety Management Procedure 240-62946386 | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Use of hired vehicles (roadworthiness) |  | Accidents / traffic fines / hijacking | Safety | Failure to inspect vehicle on receipt from hire company; Failure to familiarise yourself with hired vehicle | Drivers, Passengers, | Driver | 8 hours per day | LTI; MED Traffic fines; Theft of vehicle during hijack | Inspect vehicle on receipt from hire company; Familiarise yourself with hired vehicle Awareness training on how to minimise being hijacked; Avoid stopping at unsafe areas | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | Eskom Procedure "Vehicle and Driver Safety Management Procedure 240-62946386 | Contractor to determine the date | Contractor to state progress | N/A
Security work | Yes | 16 | Criminals | 16 | Assault | Safety | Criminal activity in the vicinity of the project | Security team Construction team | PM | 12 hours per day | F LTI MED | Liaison with local communities; Adequate training and resources; Eskom Policies and Procedures. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | Private Security Industry Regulation Act, Act 56 of 2001; | Contractor to determine the date | Contractor to state progress | N/A
| Yes |  | Criminals |  | Theft of material | Safety | Criminal activity in the vicinity of the project | Security team Construction team | PM | 12 hours per day | Financial Loss Project delays | Liaison with local communities; Adequate training and resources; Eskom Policies and Procedures. | 5 | 3 | II | P | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor | Contractor appointed responsible person | Private Security Industry Regulation Act, Act 56 of 2001; | Contractor to determine the date | Contractor to state progress | N/A
Interaction between persons | R | 17 | COVID 19 (Novel Corona Virus) | 17.1 | Cross infection | Health | Failure to keep a social distance of 1m to 2m and then coming into contact with droplets from mouth or nose of an infected person; Touching face after coming into contact with droplets from infected person; Coming into contact with contaminated surface and then touching face; | All employees, visitors | Responsible Managers & all employees | Daily | Epidiomological treatment case | Eskom's Tactical Command Centre (TCC) as well as Emergency Protocols have been activated; Work from home; Keep a social distance of 1m to 2m and restrict unnecessary visits / contacts; Home / hospital quarantine for the suspected infected; Awareness campaigns; Practice good hygiene, avoid touching face; Wear appropriate risk based PPE (respiratory masks, gloves); Regular disinfection and sanitizing of all areas, focusing on frequently touched surfaces like desks, photo copiers, telephones and similar equipment, bathrooms, offices, common areas, etc. | 4 | C | II | Mostly effective | External medical services (Public and private); Hand and surface sanitisers | Statistics from Health and Wellness; NCID- National Centre for Infectious Diseases | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002 | Mostly effective | Mostly effective
|  |  |  | 17.2 |  | Health | Poor hygiene practices (1. Failure to cough onto elbow / sneeze into a tissue etc 2. Failure to follow good hand hygiene measures, i.e., washing hands often with soap and water at least 20 seconds, or a hand sanitiser with at least 70% alcohol content); Failure to provide adequate PPE / failure to wear providd PPE Lack of awareness on the disease; Inefficient ventilation. | All employees, visitors | Responsible Managers & all employees | Daily | Epidiomological treatment case | Practice good hygiene, i.e.,washing hands often with soap and water at least 20 seconds, or a hand sanitiser with at least 70% alcohol content);; Wear appropriate risk based PPE (respiratory masks, gloves); Ensure efficient ventilation in the workplace; Home / hospital quarantine for the suspected infected; Awareness campaigns; Regular disinfection and sanitizing of all areas, focusing on frequently touched surfaces like desks, photo copiers, telephones and similar equipment, bathrooms, offices, common areas, etc. | 4 | C | ii | Mostly effective | External medical services (Public and private); Hand and surface sanitisers | Statistics from Health and Wellness; NCID- National Centre for Infectious Diseases | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002 | Mostly effective | Mostly effective

## Contractor Baseline template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | [9 empty] | Next Review Date (every 2 years): | Template identifier:
Date: |  |  |  |  | Authorised by: |  | Name: |  |  | Document identifier | [8 empty] | R | Safety | 1 | A | Fully effective | I
[7 empty] | Designation: |  |  | Revision number: | 1 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[7 empty] | Signed: |  |  | Revision date: | 2024-05-31 | [9 empty] | 3 | C | Mostly ineffective | III
[7 empty] | Date: | [13 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [20 empty] | 5 | E
List activity | Hazard Identification | Associated risk | Risk type | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Control Owner | Legal and Other Requirements | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Consequences | 6 | III | II | I | I | I
Identification and demarcation of protected and/or listed vegetation at the identified construction location. | 1.1 Uneven surfaces (rocks, tree stumps, etc) Thorns | Trips and falls; Prick injuries | Safety | LTI; MED | Eskom and contractor site specific induction training; Employees and all visitors should be aware of their surroundings, i.e tree stumps, and other obstacles. | 4 | 3 | II | P | Contractor appointed responsible person | OHS Act; Construction Regulations 7; Eskom's Personal Protective Equipment Specification 240-44175132 |  | 5 | III | II | II | I | I
Bush & shrub clearing and tree felling | Biological hazards; Wild animals | Snake bites and bee stings; Attacks by wild animals | Safety or health | F LTI | Site specific SHE induction; Appoint snake handlers and persons with knowledge of bees and similar insects; Awareness training on how to react when faced with wild animals; Fence off animals and prevent contact with workers; Do not feed animals | 5 | 2 | II | P | Contractor appointed responsible person | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132 |  | 1 | IV | IV | III | III | III
[14 empty] | A | B | C | D | E
Likelihood
Surveying & Pegging | Hand tools eg. Hammer | Finger injuries; Hand blisters | Safety | LTI; MED | Awareness training of employees in the use of hand tools like hammers, spanners, chisels etc; Provide protective cap for chisels Inspect before use; Provide non defective equipment; Quarantine defective equipment | 4 | 2 | III | P | Contractor appointed responsible person | OHS Act
Excavation / trenching | Collapse of sides of excavation; | Entrapment of persons / material inside excavation; | Safety | F LTI MED | Contractor to ensure excavation is adequately stabilised as per Method Statement; Construction Regulations 13; | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act Construction Regulation 13; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.5.1 (Excavations); Construction Regulations 13
Batching | Batch plant (Conveyor belt/rollers); | Pinching of fingers; ; | Safety | LTI MED | Install machine guarding; Training of batch plant operator; Supervision by a competent person. | 4 | 2 | III | P | Contractor appointed responsible person | OHS Act; DMR 12
Foundations | Concrete mixing; ; | Concrete burns | Safety or health | MED | Persons mixing concrete to use proper PPE including gumboots safety gogggles, long PVC gloves, respiratory protection etc; Training of supervisors, and awareness training of relevant employees on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 6.6 Concrete Foundations; Supervisor to be present during delivery to ensure that raw material deliverd to site is up to specifications | 4 | 2 | III | P | Contractor appointed responsible person | OHS Act; Eskom's Personal Protective Equipment Specification 240-44175132; Eskom's Medical Surveillance Procedure 240-84733329.
Tower Assembly | Assembly not done according to specifications and standard requirements (SANS Codes, TRMSCAAC 5.2); | Collapse of the assembled structure, leading to injuries / property damage; | Safety | F LTI | Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Clause 7.4 (Tower erection); Supervision / training. Pre task planning | 5 | 2 | II | P | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section Clause 7.4 (Tower erection)
Tower Erection | Suspended load; | Fall onto persons, causing injuries | Safety | F LTI | Routine and pre use inspections by appointed competent person; Safe work procedures; Training and supervision. | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act; DMR 18
Hand erection | Lifting equipment(Jibs,winches,steel wire anchors) | Falling equipments(Jibs) and steel members; Failure of lifting equipment | Safety | MED | Contractor to determine safe anchor points for lifting equipment on mountanious / uneven terrain; Supervision by a competent and experienced supervisor; Contractor to use certified jibs and winches that are inspected on a daily basis to be used. | 4 | 3 | II | P | Contractor appointed responsible person | OHS Act; DMR 18
Stringing | Running blocks; | Derailed conductor (fall onto employees) | Safety | F LTI | Eskom and Contrator supervisors to be trained on Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 (Stringing Operations); Direct supervision; Regular inspection of Lifting Equipment as per manufacture's manual; Riggers to be trained and appointment; Client approved contractor fall protection plan; Training to be provided by Eskom approved service providers; No work at height is allowed during inclement weather; Direct supervision; Identified and tested anchor point (SANS 50795); Eskom's Work at Height Procedure 32-418 section 3.13 (Falling objects); Erect safety nets to catch falling material; Demarcate safe drop zone area; No person to work or stand beneath persons working at height | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 (Stringing Operations; SANS 50795; Eskom's Work at Height Procedure 32-418 section 3.13 (Falling objects);
Tower Dressing | Hardware; | Structural damage, damage to hardware causing injuries to employees; . | Safety | F LTI | Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing). Conduct Pre task planning | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 7.5 (Tower Dressing
Tower Regulation | Clamping in (applicable to strain towers and suspension towers); | Conductor can fall to the ground causing fatalities / injuries | Safety | F LTI | 11.1 Ensure Eskom and contrator supervisors are trained in the Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation; Direct supervision during this activity by appointed competent person / ensure the conductor is held by the lifting shoes | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act; Eskom Procedure 240-47172520 "The design and construction of overhead power lines', Section 8 dealing with Stringing / Regulation;
Rehabilitation | Earth Moving Machinery (graders, tractors) | Struck by /Contact with machinery | Safety | F LTI | Site traffic plan to demarcate safe walk areas for employees; Awarness training on work hazards; Appoint signal / flag man Ensure adequate observation by the driver; Ensure adequate inspection and maintenance; Only Competent operator to operate machinery; Ensure there is an adequate lock out system; Ensure that chock blocks are inserted when vehicles are stationery | 5 | 2 | II | 0 | Contractor appointed responsible person | OHS Act
s
Helicopter Operations | Helicopter blades; | Struck by /Contact with; | Safety | F LTI | Dermacate safe zone for Helicoper ; Awareness training; Supervision | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act Section 8; Civil Aviation Act
Hazardous Biological Agents | HBA exposure in clinic environment e.g. HIV / AIDS, TB, Hepatitis A&B, | Contact with infectious fluids, blood,faeces, airborne pathogens, | Health | LTI | Awareness training, medical surveillance programme, vaccination of first aiders and health care workers for Hepatitis A & B and flu vaccine. | 4 | 3 | II | P | Contractor appointed responsible person | OHS Act; Eskom's Medical Surveillance Procedure 240-84733329.
Commuting / travelling between sites | Bad gravel road conditions | Motor Vehicle Accidents | Safety | F LTI PD | Take regular breaks; Adhere to the stipulated speed; Be on the lookout for other road users and animals on the road. Drive carefully on slippery roads after rains; Ensure adequate driver training; | 5 | 3 | II | P | Contractor appointed responsible person | OHS Act; Eskom Procedure "Vehicle and Driver Safety Management Procedure 240-62946386
Security work | Criminals | Assault | Safety | F LTI MED | Liaison with local communities; Adequate training and resources; Eskom Policies and Procedures. | 5 | 3 | II | P | Contractor appointed responsible person | Private Security Industry Regulation Act, Act 56 of 2001;
Interaction between persons | COVID 19 (Novel Corona Virus) | Cross infection | Health | Epidiomological treatment case | Eskom's Tactical Command Centre (TCC) as well as Emergency Protocols have been activated; Work from home; Keep a social distance of 1m to 2m and restrict unnecessary visits / contacts; Home / hospital quarantine for the suspected infected; Awareness campaigns; Practice good hygiene, avoid touching face; Wear appropriate risk based PPE (respiratory masks, gloves); Regular disinfection and sanitizing of all areas, focusing on frequently touched surfaces like desks, photo copiers, telephones and similar equipment, bathrooms, offices, common areas, etc. | 4 | C | II | Mostly effective | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002

## Consequence rating
Consequence criteria
Consequence rating | Description
Health and Safety
1 | No injuries or health effects(near misses)
2 | First-aid treatment case, and temporary discomfort case
3 | Medical treatment case; occupational disease with reversible/non-permanent effect
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL) | gv g
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required, and these risks to be captured on IRM system.
| II | High | Strong mandatory action required, and these risks to be captured on IRM system.
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.