## Risk template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | Sere Wind Farm | [7 empty] | Department: | [10 empty] | Next Review Date (every 2 years): |  | Template identifier: | 240-70044602
Date: 28/05/2025 | [8 empty] | Prepared by: | Bongani Langa |  | Authorised by: |  | Name: Deon Van Der Merwe | [7 empty] | Document identifier | 192/3905
[14 empty] | Designation: O&M Manager | [7 empty] | Revision number: | 5
[14 empty] | Date: 28/05/2025 | [7 empty] | Revision date: | 2027-05-28
Refer to Occupational Health and Safety Risk assessment procedure 32-520
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) NB: The risk shall be evaluated, assessed and rated again once additional controls have been implemented and those controls listed as existing controls. | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls (if applicable) | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed (if applicable) | Pending, In Progress, Complete (if applicable) | Where applicable, add IRM system reference number for tracking of treatment actions. (applicable to risks that have an impact on business objectives or require intervention from Senior or Executive management such as impementing major engineering projects as a control)
Security Access | Routine | 1.1 | Access control (Person searching) | 1.1 | Possible Improvise Explosive Device, illegal items(firearms, explosives, sharp objects) | Safety | Attempted illegal item being brought to site | Workers, Visitors, Public | Security Manager | Daily | LTI/Medical | Access Control Procedure | 4 | C | III | Fully effective | Access control procedure/training | Safety Observation, Audit, Inspection | Security Manager | Fire arms control act 60 of 2000, National Road Traffic Act 93 of 1996 , Occupational health ans safety Act 85 of 1993, Ohsa: Environmental regulation for workplace 1987, Ergonomics Regulation 2019, General Safety Regulation 1987 | 30/05/2025 | In Progress | N/A
|  | 1.2 | Access control (Vehicle searching) | 1.2 | Hazards when searching vehicles (contact with objects, fingers/hands caught between, head injury) | Safety | Accidental contact with vehicle elements (Doors, bonnet, boot, moving engine parts) | Workers, Visitors, Public | Security Manager | Daily | LTI/Medical, First aid incidents | Access control procedure, vehicle searching techniques | 4 | C | III | Fully effective | Access control procedure/training | Safety Observation, Audit, Inspection | Security Manager | Fire arms control act 60 of 2000, National Road Traffic Act 93 of 1996 , Occupational health ans safety Act 85 of 1993, Ohsa: Environmental regulation for workplace 1987, Ergonomics Regulation 2019, General Safety Regulation 1988 | 30/05/2025 | In Progress | N/A
|  | 1.3 | Unauthorized entry | 1.3 | Theft, vandalism, injury | Safety | Lack of fencing, no access control | Workers, Visitors, Public | Security Manager | Daily | Property damage, theft, unauthorized access, injuries | Security fencing, access control logs, on-site security personnel | 4 | B | III | Fully effective | None | Security inspections, incident reports | Security Supervisor | OHS Act Sec. 8, Construction Regulations | 30/05/2025 | In Progress | N/A
Driving to the Station | Routine | 2.1 | Unroadworthy vehicles | 2.1 | Unroadworthy vehicles | Safety | - Inadequate communication - Lack of vehicle pre-trip inspection - Lack of vehicle maintenance - Vehicles not replaced as per the request | Workers, Visitors, Public | Manager/ Supervisor | Daily | Vehicle breakdown | - Pre –trip inspections to ensure that the vehicle is in good condition before driving. - Regular maintenance as per the manufature's specification or when required. | 1 | D | III | Fully effective | Weekly/ Monthly vehicle Inspections | Inspections , Audits | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003 - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.2 | Vehicle brakedown and brake failure | 2.2 | Vehicle brakedown and brake failure | Safety | - Lack of vehicle maintenance | Workers, Visitors, Public | Manager/ Supervisor | Daily | Fatalities Lost Time Injury Medical Incident Property damage | Vehicles to be maintained in a roadworthy condition as per the manufature's instruction. | 4 | C | II | Fully effective | Weekly/ Monthly vehicle Inspections | Maintenance, Inspection, Audits | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003 - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.3 | Vehicle not meeting Eskom minimum vehicle specification. | 2.3 | Vehicle not meeting Eskom minimum vehicle specification. | Safety | - Failure to ensure compliance to Eskom vehicle specification | Workers, Visitors, Public | Manager/ Supervisor | Whenever vehicles are purchased | Fatalities Lost Time Injury Medical Incident | - All vehicle must be fitted with airbags, ABS, power steering, fitted with seatbelts, etc - Vehicles must be provided with first aid kit, 2 x warning triangle and fire extinguisher | 4 | B | III | Fully effective | Weekly/ Monthly vehicle Inspections | Inspections, Audits | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.4 | Excessive travelling | 2.4 | Excessive travelling | Safety | - Not taking rest period when required - Prolonged driving (long distance driving); - Traffic congestion - psychological stress due to fatigue | Workers, Visitors, Public | Manager/ Supervisor | Daily | Fatalities Lost Time Injury Property damage Fatigue | - Employees to do road / trip planning and risk assessment prior to embarking on a trip. - Employees are should take a resting period based at their own discretion while travelling / driving to site. - Employees should buy some refreshment while driving to sites when feeling fatigue. - Employees’ vehicles must be maintained in good working operations. The maintenance of the vehicles includes that of the seats and suspensions. Adequate and regular maintenance of the vehicles will reduce exposure to whole body vibration to a larger extent. | 4 | B | III | Fully effective | Weekly/ Monthly vehicle Inspections | Monitoring Inspection | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | 30/05/2025 | In Progress | NA
|  | 2.5 | Collision with an object while reversing | 2.5 | Collision with an object while reversing | Safety | - Poor observation and judgement - Lack of concentration | Workers, Visitors, Public | Manager/ Supervisor | Daily | Property damage | Caution should be taken when reversing and if backround view is obstructed a passenger should be utilised to give guidance. | 1 | B | IV | Fully effective | Weekly/ Monthly vehicle Inspections | Observation | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | 30/05/2025 | In Progress | NA
|  | 2.6 | Driver error due to substance abuse | 2.6 | Driver error due to substance abuse | Health | - Failure to adhere to road safety and Eskom rules | Workers, Visitors, Public | Manager/ Supervisor | Daily | Lost Time Injury Medical Incident Property damage | Drivers not to drive vehicle when under the influence of any intoxicating substances. | 4 | C | II | Fully effective | Weekly/ Monthly vehicle Inspections | Alcohol Testing Observation | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.7 | Non-adherence to road safety rules | 2.7 | Non-adherence to road safety rules | Safety | - Negligence and reckless - Overtaking unsafely - Talking on cellphone while driving - Impatience and road rage - Driving at excessive speed - Third party error | Workers, Visitors, Public | Manager/ Supervisor | Daily | Lost Time Injury Medical Incident Property damage | - Monitor and analyse driver behaviour on MIX Telematics System and encourage good driving - Promote vehicle driver safety during statutory safety meetings / departmental meetings | 4 | B | III | Fully effective | Weekly/ Monthly vehicle Inspections | Monitoring, Observation | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.8 | Driver inexperience | 2.8 | Driver inexperience | Safety | - Lack of driver training - Lack of driver license and driver permit - Inadequate Risk assessment | Workers, Visitors, Public | Manager/ Supervisor | Daily | Fatalities Lost Time Injury Medical Incident Property damage | - All drivers must be in possession of valid driver's licence. - Drivers must undergo advance driver training and driver evaluation before issued with Eskom driver permit or authorised to drive for Eskom business. | 4 | B | III | Fully effective | Weekly/ Monthly vehicle Inspections | Inspection, Audit | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.9 | Health Condition | 2.9 | Health Condition | Health | - Inadequate medical surveillance | Workers, Visitors, Public | Manager/ Supervisor | Daily | Lost Time Injury Medical Incident Property damage | - All drivers before allowed to drive for Eskom business must do driver risk assessment, medical surveillance and be in possession of valid driver licence. - Drivers are encouraged to inform their Managers/ Supervisors of any health conditions that render them unfit to drive. | 4 | B | III | Fully effective | Weekly/ Monthly vehicle Inspections | Inspection , Audit | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.1 | Poor visibility due to rain, mists, etc | 2.1 | Poor visibility due to rain, mists, etc | Safety | - Inadequate planning - Lack of driver experience | Workers, Visitors, Public | Manager/ Supervisor | Depending on season or weather condition | Fatalities Lost Time Injury Medical Incident Property damage | - Drivers to do risk assessment at they drive and adjust speed as per the environmental condition. - Drivers to be causious when driving in an adverse weather condition and plan the routes properly. | 4 | B | III | Fully effective | Weekly/ Monthly vehicle Inspections | Observation Monitoring | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
|  | 2.11 | Wild life interaction i.e. stray animals, etc | 2.11 | Wild life interaction i.e. stray animals, etc | Safety | - Inadequate Risk assessment - Driving very early in the morning or at night | Workers, Visitors, Public | Manager/ Supervisor | Daily | Lost Time Injury Medical Incident Property damage | Be on a look out of stray / wild animals and adjust speed where necessary as per the road warning signs. | 4 | C | II | Mostly effective | Weekly/ Monthly vehicle Inspections | Observation | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | 30/05/2025 | In Progress | NA
|  | 2.12 | Poor road condition | 2.12 | Poor road condition | Safety | - Inadequate Risk assessment - Uneven, damaged and gravel road conditions and bad terrain - Poor vehicle maintenance which might lead to whole body vibrating when driving on gravel road | Workers, Visitors, Public | Manager/ Supervisor | Daily | Lost Time Injury Medical Incident Property damage | - Caution should be taken when driving is in an uneven, damaged and gravel road conditions or an alternative route should be taken. - Reduce speed as per road condition. - Adhere to prescribed speed limit and road warning signs. - Adequate and regular maintenance of the vehicles to reduce exposure to whole body vibration to a larger extent. | 4 | C | II | Mostly effective | Weekly/ Monthly vehicle Inspections | Observation | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | NA
General Work | N | 3.1 | Ergonomics | 3.1 | Ergonomics stress, caused by repetitive strain | Health | - Non-compliance to procedures - Inadequate training / experience - Work posture due to prolonged crouching position - Awkward body postures | Contractor Employees | Manager/ Supervisor | Daily | - Work related Musculo-skeletal disorder: Overuse or overexertion injuries, osteo-arthritis, degenerative joint disease, and repetitive strain injuries - Back injuries | Task rotation, Mechanical Rotation | 2 | B | IV | Mostly effective | Medical surveillance | Surveys Inspection Audit | Security Supervisor | - Occupational Health and Safety Act, Act 85 of 1993 (OHS Act) - Compensation for Occupational Injuries and Diseases Act, Act 130 of 1993 (COID) - Environmental Regulations for Workplaces, 1987 - General Safety Regulations, 1986 - General Administrative Regulations, 2003 | 30/05/2025 | In Progress | NA
|  | 3.2 | Poor physical layout or housekeeping | 3.2 | Entrapment | Safety | - Inadequate inspection - Blocked or improperly planned means of egress - Employees become trapped due to improper egress during an emergency - Inadequate inspection - Poor planning / arrangements - Poor housekeeping - Obstructions on exits or egress | Contractor Employees | Manager/ Supervisor | Daily | Lost Time Injury Medical Incident First Aid Incident | - Rearrange traffic routes within the work area to reduce traffic. - All exit access must be within requirements - Employees must be aware of exits and trained in procedures for evacuation. - Reporting of safety hazards which must be followed by swift maintenance response - Means of egress and emergency exit, should be free of obstructions | 2 | B | IV | Mostly effective | SHE representative inspections | Inspection Audit | Security Supervisor | - Occupational Health and Safety Act, Act 85 of 1993 (OHS Act) - Compensation for Occupational Injuries and Diseases Act, Act 130 of 1993 (COID) - Environmental Regulations for Workplaces, 1987 - General Safety Regulations, 1986 - General Administrative Regulations, 2003 - Facilities Regulations, 1990 | 30/05/2025 | In Progress | NA
|  | 3.3 | Manual handling | 3.3 | Repititive strain, back injuries | Safety | - Lack of training / experience - Incorrect lifting techniques - Inadequate supervision - Lifting heavy, large, difficult to grasp or unstable load - Tasks too strenuous or involving awkward postures or movements - Working environment lacking sufficient space, having slippery, uneven or unstable surfaces - Ineffective PPE - Lack of concentration - Inadequate Risk assessment | Contractor Employees | Manager/ Supervisor | Daily | Musculoskeletal disorders: Sprains, strains, and inflamed joints | - An effective control program incorporating employee awareness and training and ergonomic design of work tasks can reduce back injuries. - Organising manual handling tasks in a safe way, with loads split into smaller ones, and proper rest periods provided. - Providing information and training to workers on tasks, and the Use of equipment and correct handling techniques. - Always check before lifting to see if mechanical aids such as wheelbarrows are available. - Get help with heavy or awkward loads. - Assess the weight of the load. - Identify the weight of the load. - Be sure that you can lift the load without over-exertion. - Be sure that the load is "free" to move. - Check that the planned location of the load is free of obstacles and debris. - Be sure that the path to the planned location of the load is clear. Grease, oil, water, litter and debris can cause slips and falls. - Particular handling and lifting techniques are needed for different kinds of loads or materials being handled. - Do not lift if you are not sure that you can handle the load safely. | 3 | C | II | Mostly effective | Awareness training, safety talks | Risk Assessment | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - Compensation for Occupational Injuries and Diseases Act, 1993 (Act 130 of 1993) - General Administrative Regulations, 2003 - General Safety Regulations, 1986 | 30/05/2025 | In Progress | NA
|  | 3.4 | Improper Lifting | 3.4 | Repititive strain, back injuries | Safety | - Lifting heavy, large, difficult to grasp or unstable load - Tasks too strenuous or involving awkward postures or movements - Working environment lacking sufficient space, having slippery, uneven or unstable surfaces - Ineffective PPE - Lack of concentration - Inadequate Risk assessment | Contractor Employees | Manager/ Supervisor | Daily | musculoskeletal disorders: Low back pain; Neck and upper limb disorders and Lower limb disorders Sprain, strain and inflammed joints | - Organising manual handling tasks in a safe way, with loads split into smaller ones, and proper rest periods provided. - Providing information and training to workers on tasks, and the Use of equipment and correct handling techniques. | 4 | C | II | Mostly effective | Awareness training, safety talks | Inspections Audits Supervision | Security Supervisor | - Occupational Health and Safety Act (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003 | 30/05/2025 | In Progress | NA
|  | 3.5 | Emergency Preparedness | 3.5 | Lack of Emergency Preparedness | Safety | No clear muster points, missing emergency signage | Contractor Employees | Manager/ Supervisor | Daily | Delayed response, escalation of incidents | Emergency muster points, emergency drills | 4 | C | II | Fully effective | None | Emergency response testing, incident drills | Plant Manager | OHS Act, Fire Safety Regulations | 30/05/2025 | In Progress | NA
|  | 3.6 | Trenching & Earthworks | 3.6 | Trench collapse | Safety | Unstable soil, lack of proper shoring | Contractor Employees | Manager/ Supervisor | Daily | Buried alive, injuries | Shoring, excavation permits, PPE compliance | 5 | C | II | Fully effective | None | Supervisory inspections, geotechnical assessments | Site Engineer | OHS Act, Construction Regulations | 30/05/2025 | In Progress | NA
|  | 3.7 | Equipment & Machinery Operation | 3.7 | Moving Heavy machinery | Safety | Poor operator training, blind spots, site congestion | Contractor Employees | Manager/ Supervisor | Daily | Crushing injuries, collisions | Certified operators, pedestrian exclusion zones, spotters | 4 | B | III | Fully effective | None | Daily equipment inspections, operator assessments | Construction manager/ Superviser | OHS Act, Machinery Safety Regulations | 30/05/2025 | In Progress | NA
Plant Walkabout | N | 4.1 | Climbing the stairways | 4.1 | Slip, trips and fall | Safety | - Failure to identify the risk - Lack of concentration - Not applying three point contact | Contractor Employees | Plant manager | Daily | Lost Time Injury Medical Incident First Aid Incident | - Ensure that continuous risk assessment is done during climbing. - Inspection of work areas on a regular basis as per the procedure and implement control measures - Employees are trained on slip, trips and fall risks and control measures. - Providing personal protective equipment (e.g.slip-resistant footwear) | 4 | B | III | Fully effective | Awareness training, safety talks | Inspections Audits Supervision | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003 | 30/05/2025 | In Progress | NA
|  | 4.2 | Uneven surfaces | 4.2 | Slip, trips and fall | Safety | - Failure to identify the risk - Lack of concentration - Uneven work surface | Contractor Employees | Plant manager | Daily | Lost Time Injury Medical Incident First Aid Incident | - Ensure that continuous risk assessment is done during climbing. - Inspection of work areas on a regular basis as per the procedure and implement control measures - Employees are trained on slip, trips and fall risks and control measures. - Providing personal protective equipment (e.g.slip-resistant footwear) | 4 | B | III | Fully effective | Awareness training, safety talks | Inspections Audits Supervision | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003 | 30/05/2025 | In Progress | NA
|  | 4.3 | Vehicle movement/ Diesel Trucks | 4.3 | Caught / crushed between moving equipment / vehicle | Safety | - Inadequate site planning - Non-compliance to procedures - Inadequate of signage - Lack of supervision - Inadequate of control - Inadequate guarding - Inadequate access control | Contractor Employees | Manager/ Supervisor | Daily | Fatality Lost Time Injury Medical Incident | - Ensure that all moving equipment / vehicles are inspected as required by a competent person before use and records of inspections are kept in the file. - All moving equiment / vehicles to be operated by trained / competent person - All drivers to adhere to road safety rules and life saving rules at all times. - Risk assessment to be conducted before any work commences and riaks, hazards and control measures to be communicated to all employees involved in a task. - Ensure that employees are medically fit to work | 4 | C | II | Mostly effective | Adhere to life saving rules | Supervision Inspection SMAT Observation | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Transport Act, 2008 (Act No. 93 of 2008) - Compensation for Occupational Injuries and Diseases Act, 1993 (Act 130 of 1993) - General Administrative Regulations, 2003 - General Safety Regulations, 1986 | 30/05/2025 | In Progress | NA
|  | 4.4 | Civil unrest/Community unrest/Industrial strike | 4.4 | Violance, injuries and damage to property | Safety | - Confrontation with criminals - Revolt or strikes by employees during salary negotiations | Contractor Employees | Plant manager | Quarterly | Lost time injuries Medical Incident | - Strict access control - Adhere to instructions by Senior Management - Provide security personnel with PPE (bulletproof vests are mandatory). - Relevant equipment is available for use, two way radios for communication. - Backup by SAPS is available. EP action plans are in place. - Emergency services are on site 24 hrs. - Psychometric testing | 3 | C | II | Mostly effective | None | Inspection Audit | Security Supervisor | - National Key Point Act 102 of 1980 - Firearms and Ammunition Act No. 60 of 2000 - PSIRA Act No 56 of 2001 | 30/05/2025 | In Progress | NA
|  | 4.5 | Extreme weather condition | 4.5 | Exposure to thermal stress (heat or cold) depending on season | Health | - Ultra-violet radiation from the sun - Inclement Weather Conditions (extremely cold / hot conditions) | Contractor Employees | Manager/ Supervisor | Daily | Heat rashes Heat stroke Heat edema Heat exhaustion Heat syncope Heat cramps Heat cramps Hypothermia | - Drinking lot of fluids to prevent dehydration. - Work-rest Regime:Employees are should take a resting period or stop an activity when there are warnings of extreme weather condition. - Reduction of duration of exposure. If exposure occurs, it would be over short durations. - Employees must be subjected to training and education (induction), which includes heat exposure, cold exposure and PPE including control measures. - Employees must be acclimatised to working in these weather condition particular hot environment. - Natural ventilation: work is performed outdoors under adequate natural ventilation conditions. The effectiveness of the ventilation condition is mainly determined by weather conditions. - Wearing of correct PPE:safety shoes; hard hats; safety overalls / long pants and warm clothing (jackets) | 3 | B | III | Fully effective | Awareness training, safety talks | IAQ Surveys Inspection Audit | Security Supervisor | - Occupational Health and Safety Act, Act 85 of 1993 (OHS Act) - Compensation for Occupational Injuries and Diseases Act, Act 130 of 1993 (COID) - Environmental Regulations for Workplaces, 1987 - General Safety Regulations, 1986 - General Administrative Regulations, 2003 | 30/05/2025 | In Progress | NA
Daily Work Activities | N | 5 | Psychosocial factors | 5 | Suicide, Stress, Depression , Bullying, Harrassment | Health | Divorce, Work Pressure, Personal Problems, Fanancial Issues, Loss of loved one | Contractor Employees | Manager/ Supervisor | Daily | Medical, Poor work perfomance | Eskom Assistant Program | 3 | B | III | Mostly effective | Training and awareness, employee engagement | Incident Analysis | Construction manager/ Superviser | ISO 45001 | 30/05/2025 | On-going | N/A
General site surroundings | N | 6 | Animal/Insect bites or stings | 6 | Risk of snake bite, bee sting, scorpion stings | Safety | Minor/Serious Injury/Death | Contractor Employees | Manager/ Supervisor | Daily | First aid, Medical | Safety awareness/Bee swarm management | 3 | B | III | Fully effective | Safety awareness, enrinomental management | Safety Observation, Audit, Inspection | Plant Manager | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Traffic Act, 1996 (Act No. 93 of 1996) | 30/05/2025 | In Progress | N/A

## Contractor Baseline template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | [9 empty] | Next Review Date (every 2 years): | Template identifier:
Date: |  |  |  |  | Authorised by: |  | Name: |  |  | Document identifier |  | R | Safety | 1 | A | Fully effective | I
[7 empty] | Designation: |  |  | Revision number: | 5 | N | Health | 2 | B | Mostly effective | II
[7 empty] | Signed: |  |  | Revision date: | 2025-04-30 |  |  | 3 | C | Mostly ineffective | III
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [13 empty] | 5 | E
List activity | Hazard Identification | Associated risk | Risk type | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Control Owner | Legal and Other Requirements |  |  | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control.
Security Access | Access control (Person searching) | Possible Improvise Explosive Device, illegal items(firearms, explosives, sharp objects) |  | LTI/Medical | Access Control Procedure |  |  |  |  | Security Manager | Fire arms control act 60 of 2000, National Road Traffic Act 93 of 1996 , Occupational health ans safety Act 85 of 1993, Ohsa: Environmental regulation for workplace 1987, Ergonomics Regulation 2019, General Safety Regulation 1987
Driving to the Station | Unroadworthy vehicles | Unroadworthy vehicles |  | Vehicle breakdown | - Pre –trip inspections to ensure that the vehicle is in good condition before driving. - Regular maintenance as per the manufature's specification or when required. |  |  |  |  | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003 - National Road Traffic Act, 1996 (Act No. 93 of 1996)
General Work | Ergonomics | Ergonomics stress, caused by repetitive strain |  | - Work related Musculo-skeletal disorder: Overuse or overexertion injuries, osteo-arthritis, degenerative joint disease, and repetitive strain injuries - Back injuries | Task rotation, Mechanical Rotation |  |  |  |  | Security Supervisor | - Occupational Health and Safety Act, Act 85 of 1993 (OHS Act) - Compensation for Occupational Injuries and Diseases Act, Act 130 of 1993 (COID) - Environmental Regulations for Workplaces, 1987 - General Safety Regulations, 1986 - General Administrative Regulations, 2003
Plant Walkabout | Climbing the stairways | Slip, trips and fall |  | Lost Time Injury Medical Incident First Aid Incident | - Ensure that continuous risk assessment is done during climbing. - Inspection of work areas on a regular basis as per the procedure and implement control measures - Employees are trained on slip, trips and fall risks and control measures. - Providing personal protective equipment (e.g.slip-resistant footwear) |  |  |  |  | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - General Safety Regulations, 1986 - General Administrative Regulations, 2003
Daily Work Activities | Suicide, Stress, Depression , Bullying, Harrassment | #REF! |  | Medical, Poor work perfomance | Eskom Assistant Program |  |  |  |  | Construction manager/ Superviser | ISO 45001
General site surroundings | Vehicle movement/ Diesel Trucks | Caught / crushed between moving equipment / vehicle |  | Fatality Lost Time Injury Medical Incident | - Ensure that all moving equipment / vehicles are inspected as required by a competent person before use and records of inspections are kept in the file. - All moving equiment / vehicles to be operated by trained / competent person - All drivers to adhere to road safety rules and life saving rules at all times. - Risk assessment to be conducted before any work commences and riaks, hazards and control measures to be communicated to all employees involved in a task. - Ensure that employees are medically fit to work |  |  |  |  | Security Supervisor | - Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) - National Road Transport Act, 2008 (Act No. 93 of 2008) - Compensation for Occupational Injuries and Diseases Act, 1993 (Act 130 of 1993) - General Administrative Regulations, 2003 - General Safety Regulations, 1986
s

## Consequence rating
Consequence criteria
Consequence rating | Description | R | Safety | 1 | A | Fully effective | I
| Health and Safety | N | Health | 2 | B | Mostly effective | II
1 | No injuries or health effects(near misses) |  |  | 3 | C | Mostly ineffective | III
2 | First-aid treatment case, and temporary discomfort case |  |  | 4 | D | None | IV
3 | Medical treatment case; occupational disease with reversible/non-permanent effect |  |  | 5 | E
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence |  |  | 6
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
,
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required.
| II | High | Strong mandatory action required
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.