## OHS RA ERIC #01
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | Group Finanace Division Eskom Real Estate: Eskom Research and Innovation Centre: Client Baseline SHE Risk Assessment | [8 empty] | Department: | Eskom Real Estate: Projects | [9 empty] | Next Review Date (every 2 years): | 2024-05-01 | Template identifier: | 240-70044602
Date: | 2022-05-01 | [8 empty] | Prepared by: |  |  | Authorised by: |  | Name: | [7 empty] | Document identifier | ERIC_RA_BS OHS_001
[15 empty] | Designation: | [7 empty] | Revision number: | 1
Revision date:
Refer to Occupational Health and Safety Risk assessment procedure 32-520
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | OHS opportunities | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | OH&S opportunities that can enhance OH&S performance and lead to hazard elimination and risk reduction. | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) NB: The risk shall be evaluated, assessed and rated again once additional controls have been implemented. | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Pending, In Progress, Complete | Where applicable, add IRM system reference number for tracking of treatment actions.
Contractor / Contract Management | R | 1 | Inadequate Resources; Incompetent Resources; and Inadequate Management Systems. | 1.1 | Incidents/Accidents; Injuries; Contravention or Prohibition Notices; Project Delays; and Poor SHEQ Performance. | Safety | Poor or no SHEQ compliance and lack of competencies in the management of principal contractor. Poor SHEQ requirements enforcement. Lack of stringent management of contractors on SHEQ compliance. Poor or lack of supervision. Insufficient supervision. Underqualified and inexperienced SHEQ Practitioners. Lack of management support to SHEQ functions and responsibilities |  | Principle contractor | Principle contractor & Eskom Project Manager | Daily ± 8 Hours | Fatality, Lost Time Injuries, Medical treatment, Damage, Financial & Production loss, Project Delays | Currently there are no existing controls. | 5 | E | I
Project Execution | R | 2 | Physical attacks ,conflicts, high exposure to stress factors, SHEQ related incident/ injuries, motor vehicle accidents. | 2.1 | Work related or induced stress, Injuries , ill-health, property damage and project delays/schedule disruption. | Safety | Work related or induced stress, Injuries , ill-health, property damage and project delays/schedule disruption. |  | Principle contractor | Principle contractor | Daily ± 8 Hours | Missed targets (Poor SHEQ Performance Statistics, Injuries, ill-health) | Currently there are no existing controls. | 5 | E | I
| R | 3 | Work Acceleration | 3.3 | Works acceleration, insufficient supervision, insufficient competent personnel performing specific activities. Insufficient general workers and failure to ensure compliance and conformance with Eskom and ERE SHEQ requirements which includes SHE Specification, Eskom Rules, applicable legislations and SANS standards by contractors on site. | Safety | Works acceleration, insufficient supervision, insufficient competent personnel performing specific activities. Insufficient general workers and failure to ensure compliance and conformance with Eskom and ERE SHEQ requirements which includes SHE Specification, Eskom Rules, applicable legislations and SANS standards by contractors on site. |  | Principle contractor | Principle contractor | Daily ± 8 Hours | Missed targets (Poor SHEQ Performance Statistics, Injuries, ill-health) | Currently there are no existing controls. | 5 | E | I
Working at heights | R | 4 | Working at heights | 4.1 | Fall from heights | Safety | High structures, Adverse weather conditions, Slips and Falls, Risk Takers, Inadequate tools and Equipment |  | Principle contractor employees | Principle contractor | Daily ± 8 Hours | Fatality,Lost Time ,Medical treatment, production loss. | Currently there are no existing controls. | 5 | E | I
| R | 4 |  | 4.2 | Fall from heights |  | Instability of roof, roof caving in. |  | Principle contractor employees | Principle contractor | Daily +8 Hours | Fatality,Lost Time ,Medical treatment, production loss. | Currently there are no existing controls. | 5 | E | I
| R | 4 |  | 4.3 | Emergency preparedness |  | No fall rescue plan |  | Principle contractor employees | Principle contractor | Daily +8 Hours | Fatality,Lost Time ,Medical treatment, production loss. | Currently there are no existing controls. | 5 | E
Insect bites | R | 5 | Insect bites such as wasps/bees | 5.1 | Allergic reaction to insect posion. |  | Allergic reaction to insect posion. |  | Principle contractor employees | Principle contractor | Daily +8 Hours | Lost Time ,Medical treatment, production loss. | Currently there are no existing controls. | 5 | E
Waste Management | R | 6 | Poor waste management | 6.1 | Mixing of waste |  | Disposal of Hazardous Chemical Substance with General Waste. |  |  | Principle Contractor | Daily +8 Hours | Environmental incidents | Currently there are no existing controls. | 5 | E
Security |  | 7 | Job-site Access Control | 7.1 | Obstructed Access , inadequate access control |  | Incompetent personnel, No or insufficient barricading or signage, Lack of supervision |  | Contractors & Employees | Principle Contractor | Daily | Unauthorised access, Financial loss, Legal liability, Production loss | Currently there are no existing controls. | 5 | E
Weather Conditions | R | 8 | Adverse Weather Conditions | 8.1 | Extreme Temperatures, Rain |  | Natural causes |  | Contractors & Employees | Principal Contractors | Infrequently | Injuries, Project delays | Currently there are no existing controls. | 5 | E
Covid-19 | R | 9 | Infected Persons | 9.1 | Cross transmission to other persons. | Health | Through bad hygiene etiquette, when coughing, blowing nose. |  | Contractors & Employees | Principal Contractors | Daily ± 8 Hours | Wide spread infection & transmission with the Covid-19 viruses to persons. Lost time due to employees being booked off. Fatalities. | Currently there are no existing controls. | 5 | E
Risk Rating Matrix
I | 0
II | 0
III | 0
IV | 0

## Consequence rating
Consequence criteria
Consequence rating | Description | [7 empty] | R | Safety | 1 | A | Fully effective | I
| Health and Safety | [7 empty] | N | Health | 2 | B | Mostly effective | II
1 | No injuries or health effects(near misses) | [9 empty] | 3 | C | Mostly ineffective | III
2 | First-aid treatment case, and temporary discomfort case | [9 empty] | 4 | D | None | IV
3 | Medical treatment case; occupational disease with reversible/non-permanent effect | [9 empty] | 5 | E
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence | [9 empty] | 6
5 | Fatality or life threatening health effects | Consequences | 6 | III | II | I | I | I
6 | Multiple fatalities |  | 5 | III | II | II | I | I
|  |  | 4 | IV | III | II | I | I
|  |  | 3 | IV | III | II | II | I
|  |  | 2 | IV | IV | III | II | II
|  |  | 1 | IV | IV | III | III | III
|  |  |  | A | B | C | D | E
Likelihood

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required, and these risks to be captured on IRM system.
| II | High | Strong mandatory action required, and these risks to be captured on IRM system.
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.