NEC3 Engineering and Construction

Short Contract (ECSC3)

| A contract between | Eskom Holdings SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and |  |  |
| for | SUPPLY AND APPLICATION OF RTV SILICONE RUBBER RE-COATING(INCLUDING SHED EXTENDERS WHEN REQUIRED) ON PORCELAIN SURFACED EQUIPMENT AT VARIUOS SUBSTATION CAMDEN,KRIEL AND MATLA SUBSTATIONS |  |
| Contents: | Compiled in accordance with CIDB Standard for Uniformity in Construction Procurement (May 2010 amendments) | Page No. |
| Part C1 | Agreements & Contract Data |  |
|  | C1.1 Form of Offer and Acceptance | 2 |
|  | C1.2 Contract Data provided by the Employer | 5 |
|  | C1.2 Contract Data provided by the Contractor | 12 |
| Part C2 | Pricing Data |  |
|  | C2.1 Pricing assumptions | 13 |
|  | C2.2 Price List | 14 |
| Part C3 | Scope of Work |  |
|  | C3.1 Works Information | 15 |
| Part C4 | Site Information | 28 |
| Documentation prepared by: | Marks Mathelele |  |

C1 Agreements & Contract Data

# C1.1 Form of Offer and Acceptance

## Offer

The Employer, identified in the Acceptance page signature block on the next page, has solicited offers to enter into a contract for the procurement of:

SUPPLY AND APPLICATION OF RTV SILICONE RUBBER RE-COATING (INCLUDING SHED EXTENDERS WHEN REQUIRED) ON PORCELAIN SURFACED EQUIPMENT AT CAMDEN, KRIEL AND MATLA SUBSTATIONS

The tenderer, identified in the signature block below, having examined the documents listed in the Tender Data and addenda thereto as listed in the Tender Schedules, and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the Contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| The offered total of the Prices exclusive of VAT is | R[●] |
| --- | --- |
| Value Added Tax @ 14% is | R[●] |
| The offered total of the Prices inclusive of VAT is | R[●] |
| (in words) [●] |  |

This Offer may be accepted by the Employer by signing the form of Acceptance overleaf and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: | (Insert name and address of organisation) |  |  |  |
| Name & signature of witness |  |  | Date |  |
| Tenderer’s CIDB registration number: |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an Agreement between the Employer and the tenderer upon the terms and conditions contained in this Agreement and in the Contract that is the subject of this Agreement.

The terms of the Contract, are contained in:

Part 1	Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part 2	Pricing Data

Part 3	Scope of Work: Works Information

Part 4	Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule, which must be signed by the duly authorised representative(s) for both parties.

The tenderer shall within one week of receiving a completed copy of this Agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this Agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this Agreement.

Notwithstanding anything contained herein, this Agreement comes into effect on the date when the tenderer receives one fully completed and signed copy of this document, including the Schedule of Deviations (if any) together with all the terms of the contract as listed above.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer | (Insert name and address of organisation) |  |  |  |
| Name & signature of witness |  |  | Date |  |

Note: 	If a tenderer wishes to submit alternative tender offers, further copies of this document may be used for that purpose, duly endorsed, ‘Alternative Tender No. _____ ‘

## Schedule of Deviations

Note:

- To be completed by the Employer prior to award of contract.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

# C1.2 Contract Data

## Data provided by the Employer

Completion of the data in full is essential to create a complete contract.

| ## Clause |  | ## Statement | ## Data |
| --- | --- | --- | --- |
|  |  | ## General |  |
| 10.1 |  | The Employer is (Name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |
| 10.1 & 14.4 |  | The Employer’s representative to whom the Employer in terms of clause 14.4 delegates his actions is (Name): | TBA |
|  |  | Address | [●] |
|  |  | Tel No. | [●] |
|  |  | Fax No. | [●] |
|  |  | E-mail address | [●] |
| 11.2(11) |  | The works are | SUPPLY AND APPLICATION OF RTV SILICONE RUBBER RE-COATING(INCLUDING SHED EXTENDERS WHEN REQUIRED) ON PORCELAIN SURFACED EQUIPMENT AT CAMDEN,KRIEL AND MATLA SUBSTATIONS |
| 11.2(13) |  | The Works Information is in | the document called ‘Works Information’ in Part 3 of this contract. |
| 11.2(12) |  | The Site Information is in | the document called ‘Site Information’ in Part 4 of this contract. |
| 11.2(12) |  | The site is | CAMDEN, KRIEL AND MATLA Substations |
| 30.1 |  | The starting date is. | 01 September 2022 |
| 11.2(2) |  | The completion date is. | 31 August 2025 ( Please note the work is outage related ) |
| 13.2 |  | The period for reply is | 5 (five) working days |
| 40 |  | The defects date is | 26 weeks after Completion |
| 41.3 |  | The defect correction period is | Defects which the Supervisor notifies may jeopardise the performance of the works in use is the shortest possible time starting immediately upon notification of the Defect. Defects which the Supervisor notifies require urgent correction is 48 (forty eight) hours |
| 50.1 |  | The assessment day is the | Between the 25th day of each successive month. |
| 50.5 |  | The delay damages are | 0.1% of contract value per day up to a limit of 10% of the contract value |
| 50.6 |  | The retention is | 5% retention bond of the contract value ( 2,5 % to be payable when the works is taken over on project completion and 2,5% to be payable on the expiry of the defects period which is 26 weeks after the works has been taken over) |
| 51.2 |  | The interest rate on late payment is | 0% [Insert a rate only if a rate less than 0.5% per week of delay has been agreed] |
| 80.1 |  | The Contractor is not liable to the Employer for loss of or damage to the Employer’s property in excess of | the amount of the deductibles relevant to the event described in the applicable “Format ECSC3” policy available on http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx |
| 82.1 |  | The Employer provides this insurance | as stated for “Format ECSC3” available on http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_ From_1_April_2014_To_31_March_2015.aspx (See Annexure A for basic guidance) |
| 82.1 |  | The minimum amount of cover for the third insurance stated in the Insurance Table is: | whatever the Contractor deems necessary in addition to that provided by the Employer. |
| 82.1 |  | The minimum amount of cover for the fourth insurance stated in the Insurance Table is: | As prescribed by the Compensation for Occupational Injuries and Diseases Act No. 130 of 1993 and the Contractor’s common law liability for people falling outside the scope of the Act with a limit of Indemnity of not less than R500 000 (Five hundred thousand Rands) |
|  |  | Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) apply? | No |
| 93.1 |  | The Adjudicator is | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. This must be agreed to by both parties (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |
|  |  | Address | [●] |
|  |  | Tel No. | [●] |
|  |  | Fax No. | [●] |
|  |  | e-mail | [●] |
| 93.2(2) |  | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body |
| 93.4 |  | The tribunal is: | arbitration. |
|  |  | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |
|  |  | The place where arbitration is to be held is | Johannesburg South Africa |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |
|  |  | The conditions of contract are the NEC3 Engineering and Construction Short Contract (April 2013) and the following additional conditions Z1 to Z11 which always apply: |  |
| Z1 | Cession delegation and assignment |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |
| Z2 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |
| Z2.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |
| Z2.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer. |  |
| Z2.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the starting date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |
| Z2.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |
| Z2 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |
| Z2.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |
| Z2.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer. |  |
| Z2.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the starting date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |
| Z2.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |
| Z3 | Confidentiality |  |  |
| Z3.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to others except where required by this contract. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to others where required by this contract the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |
| Z3.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Employer. |  |  |
| Z3.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |
| Z3.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Employer. All rights in and to all such images vests exclusively in the Employer. |  |  |
| Z3.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |
| Z4 | Waiver and estoppel: Add to clause 12.2: |  |  |
| Z4.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties or their delegates or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |
| Z5 |  | Health, safety and the environment |  |
| Z5.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and - undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |
| Z5.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |
| Z6 | Provision of a Tax Invoice and interest. Add to clause 50 |  |  |
| Z6.1 | The Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the correctly assessed amount due for payment. |  |  |
| Z6.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |
| Z6.3 | The Contractor is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |
| Z7 | Notifying compensation events |  |  |
| Z7.1 | Delete from the last sentence in clause 61.1, “unless the event arises from an instruction of the Employer.” |  |  |
| Z8 | Employer’s limitation of liability; Add to clause 80.1 |  |  |
| Z8.1 | The Employer liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand). |  |  |
| Z9 | Termination: Add to clause 90.2, after the words "or its equivalent": |  |  |
| Z9.1 | or had a business rescue order granted against it. |  |  |
| Z10 | Addition to Clause 50.5 |  |  |
| Z10.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data (if any), the Employer may terminate the Contractor’s obligation to Provide the Works. |  |  |
|  | If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |  |
| Z11 | Ethics |  |  |

For the purposes of this Z-clause, the following definitions apply:

Affected Party	means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

Coercive Action	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

Collusive Action	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

Committing Party	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees,

Corrupt Action	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

Fraudulent Action	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

Obstructive Action	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action and

Prohibited Action	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

Z 11.1 	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

Z 11.2 	The Employer may terminate the Contractor’s obligation to Provide the Works if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Works for this reason.

Z 11.3 	If the Employer terminates the Contractor’s obligation to Provide the Works for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2.

Z 11.4 	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.

Annexure A:	Insurance provided by the Employer

These notes are provided as guidance to tendering contractors and the Contractor about the insurance provided by the Employer. The Contractor must obtain its own advice. Details of the insurance itself are available from the internet web link given below.

- For the purpose of works contracts likely to be let under this contract (low value straight forward work), insurance provided by Eskom (the Employer) has been arranged on the basis of “Format ECSC3” as described on the web link given at the foot of this page.

- Tendering contractors should note that cover provided by the Employer is only per the policies available on the internet web link listed below under the Format ECSC3 and may not be the cover required by the tendering contractor or as intended by each of the listed insurances in the left hand column of the Insurance Table in clause 82.1.  In terms of clause 82.1 “The Contractor provides    the insurances stated in the Insurance Table.  The Contractor does not provide an insurance which the Employer is to provide as stated in the Contract Data”.  Hence the Contractor provides insurance which the Employer does not provide and in cases where the Employer does provide insurance the Contractor insures for the difference between what the Insurance Table requires and what the Employer provides.

- When Marine Insurance is required the Contractor needs to obtain a copy of the latest edition of Eskom’s Marine Policies Procedures found at internet website given below.

- Further information and full details of all Eskom provided policies and procedures may be obtained from:

http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_

From_1_April_2014_To_31_March_2015.aspx

## Data provided by the Contractor (the Contractor’s Offer)

The tendering contractor is advised to read both the NEC3 Engineering and Construction Short Contract (April 2013) and the relevant parts of its Guidance Notes (ECSC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on page 31 of the ECSC3 April 2013 Guidance Notes.

Completion of the data in full is essential to create a complete contract.

| 10.1 | The Contractor is (Name): | [●] |
| --- | --- | --- |
|  | Address | [●] |
|  | Tel No. | [●] |
|  | Fax No. | [●] |
|  | E-mail address | [●] |
| 63.2 | The percentage for overheads and profit added to the Defined Cost for people is | [●]% |
| 63.2 | The percentage for overheads and profit added to other Defined Cost is | [●]% |
| 11.2(9) | The Price List is in | the document called ‘Price List’ in Part 2 of this contract. |
| 11.2(10) | The offered total of the Prices is [Enter the total of the Prices from the Price List]: | R[●] excluding VAT [in words] [●] excluding VAT |

C2 Pricing Data (Refer to BOQ attached)

# C2.1 Pricing assumptions

Entries in the first four columns in the Price List are made either by the Employer or the tendering contractor

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

All Prices are to be shown excluding VAT unless instructed otherwise by the Employer in Tender Data or in an instruction the Employer has given before the tenderer enters his Prices.

If there is insufficient space in the Price List which follows, state in which document the Price List is contained.

# C2.2 Price List

The Price List is as the attached pricing schedules. Please note that the works is outage related per generator and feeder bays at Camden, Kriel, and Matla substation.

C3:  Scope of Work

# C3.1 Works Information

3.1.1. Description of the works

Background

Camden, Kriel and Matla substations are situated in the North East Transmission Grid, Matla and Kriel power stations are near Kriel town and Secunda. Camden Power station is 20Km outside Ermelo along the N2 route

The scope of works

The scope of work includes SUPPLY AND APPLICATION OF RTV SILICONE RUBBER RE-COATING (INCLUDING SHED EXTENDERS WHEN REQUIRED) ON PORCELAIN SURFACED EQUIPMENT AT CAMDEN, KRIEL AND MATLA SUBSTATION is as per the attached below standard documents:

- RTV Silicone rubber Insulator Coating and Shed Extender Application Standard 240-56063877

- RTV Silicone rubber Insulator Coating and Shed Extender Supplier Standard 240-56062705

3. Specifications

| Title | Date or revision | Tick if publicly available |
| --- | --- | --- |
| General Specifications: |  |  |
| 32-37 Substance Abuse rev3 | 3 |  |
| 32-95 Occupational Health and Safety Management Procedure Rev8 | 8 |  |
| 32-136 Contractor Health and Safety Requirements rev4 | 4 |  |
| 32-418 Working at Height Standard rev3 | 3 |  |
| 32-520 Occupational Health and Safety Risk Assessment Procedure Rev 2 | 2 |  |
| 32-1126 Smoking Policy Rev 1 | 1 |  |
| 240 43848327 Employees' right of refusal to work in unsafe situations procedure rev1 | 1 |  |
| 240 62196227 Eskom life-saving rules rev6 | 6 |  |
| 240 62946386 Vehicle and Driver Safety Management rev6 | 6 |  |
| 240 100979499 Personal Protective Equipment for Work at Heights Specification rev1 | 1 |  |
| 240-120054284 Eskom Personal Protective Equipment rev1 | 1 |  |
| 240-120054284 Eskom Personal Protective Equipment rev1 | 1 |  |
| 20181018_SHE Tender Evaluation_PDP 765kV Projects_Rev0 | 0 |  |
| Acknowledgement Form for Eskom SHE Rules and other Requirements | 2 |  |
| Occupational_Hygiene_Management_PDPMAN-GL-50 | 2 |  |
| 32-727 Safety, Health, Environment and Quality Policy | 1 |  |
| 240-70172585 Vegetation Management and Maintenance within Eskom Land ,Servitudes and rights of way | 1 |  |
| 20131219_PDPMAN-PN-53_Waste Management Plan_Rev0 | 0 |  |
| Environmental Authorisation Extension letter |  |  |
| Final Construction and Operations Site Specific EMPR |  |  |
| PDPMAN-ST-37-Environmental Requirements for Contractors and Supplies | 0 |  |
| PDPMAN-SP-28 Quality Requirements for Organisations Presentation | 1 |  |
| 20130730_FM__1Quality_Assurance_Tender_Evaluation_Report_PDPMAN-FM-119_Rev3 | 3 |  |
| Pricing schedule |  |  |
| Electrical Hazardous Risk Assessment |  |  |
| Risk Register Template |  |  |
| Technical specifications: |  |  |
| RTV Silicone rubber insulator coating and shed extender application standard – 41 -170 | 1 |  |
| RTV Silicone rubber insulator coating and shed supplier standard – TSP 41 -223 | 1 |  |

4. Constraints on how the Contractor Provides the Works

## 4.1 Temporary works, Site services & construction constraints

### 4.1.1 Employer’s Site entry and security control, permits, and Site regulations

The Contractor is to have an Eskom certified and authorized Operating Regulation for High Voltage Systems (ORHVS) person available on site at all times in accordance with Eskom Transmission Standard Occupational Health and Safety Requirements to be met by Contractors and Sub-contractors Employed by Eskom.

The Contractor shall control his activities and processes in accordance with Eskom’s Occupational Health and Safety Requirements to be met by Contractors and Sub-contractors Employed by Eskom.

The authorization procedure for a permit to work shall be done before the contractor commences work on site. It is the Contractors responsibility to ensure that a permit to work is obtained before access to the work can be given.

Contractor to provide barricading where there are open trenches and around the sumps and manholes. The Contractor shall occupy only such ground as is necessary to carry out the works. All fences and other structure that have been damaged or interfered with by the Contractor shall be restored to be a condition at least equivalent to their original condition.

The contractor must be in possession of current H.V. Regulations and is responsible to be authorized by Flourish Smart  SmartF@eskom.co.za  +27 82 056 3030, North East Grid GMR 2.1 and the Grid Safety Officers to work in the region. Also one of his workers must have a current first aid level 2 certificate. All workers to have police clearance (no criminal record)

The contractor’s trucks must have a valid and current crane test certificate with the truck driver and crane operator’s certificate. All slings, shackles and crimping tools must have valid and current test certificates, which must be produced on site establishment.

It is the contractor’s responsibility to ensure that a permit to work is obtained before access to the site can be given. Arrangements can be made with Transmission- North East Grid, High Voltage Plant Manager to arrange for an interview.

The Contractor will be required to have an Eskom certified and authorized ORHVS person available where work is being performed. In addition to NFM 74 Rev 0 requirements, contractors to have a level 2 first aid certificate appointee and supply certified ID copies ( with police clearance) and medical records certificates for all workers on site .

Before any work is commenced, it will be the responsibility of the contractor to ascertain from the “engineering assistant” the position of any existing services on site.  Once these are indicated to the contractor they shall be deemed “known”.

Any costs incurred for repairs to any “known” services shall be for the contractor’s account. The contractor shall make his own arrangements for the provision of accommodation for his employees. The contractor shall control his activities and processes in accordance with the Occupational Health & Safety Act no. 85 of 1993 and Eskom Safety Standard nws 1058 and 1494.

The Complete Works Method Statement, Environmental Method statement, SHEQ Site Implementation File must be submitted 3 weeks before works commences for approval. Only upon approval will access to site be permitted.

### 4.1.2 Restrictions to access on Site, roads, walkways and barricades

The Contractor’s attention is drawn to the fact that other contractors will be on site and access and interfacing with them will be required. The Contractor shall allow safe access for other contractors and Eskom personnel when required.

The contractor is fully responsible for all temporary works, which may be required. This includes storm water control, de-watering of excavations, excavation support, foundations and runways for construction plant etc, and is to allow for it in his rates.

Access to Substations is controlled by the Site Supervisor, and the contractor will adhere to all procedures set out by them, including acquiring security permits and attending safety induction courses if required. Id's etc will be submitted to Eskom by all workers on the Eskom site. There is a single main access control point to the stations and the security is responsible to provide personnel to main this access points during working hours. All employees and visitors to site must undergo an alcohol test which must be carried out by the said contractor personnel.

Access to the area of the works is limited and the contractor should be aware of the conditions on site and allow for this in his rates.

### 4.1.3 People restrictions on Site; hours of work, conduct and records

The Contractor must clearly indicate their proposed working hours in the tender and specifically in the programme issue with the tender. After award the Contractors will adhere to these agreed working hours and keep detailed and accurate records of such on a daily basis. The Supervisor must sign these records on a daily basis and the Project Manager and Supervisor must have access to these records at any time.

The Contractor must clearly indicate any shift work or extended working hour work that is required in order to meet with the required completion dates of the contract. The Project Manager and SHEQ manager’s permission must be obtained prior to working such hours. Permission will only be granted if the longer hours worked have been accepted in writing by the Department of Labour.

### 4.1.4 Health and safety facilities on Site

The contractor to comply with all health and safety regulations and specifications stated in section 2.3 on site.  At all times during the fabrication, erection and testing of the equipment the Contractor is responsible for the safety of all persons on the Site and on the equipment and shall have the necessary systems and procedures in place to effectively manage this. The contractor to comply with all environment regulations and specifications stated in section 2.4 on site. The contractor shall have an environmental management system in place that will ensure that the requirements of the environmental regulation and specifications are effectively implemented and managed.

### 4.1.5 Title to materials from demolition and excavation

The Contractor has no title to an object of value or historical or other interest within the site. The Contractor shall notify the Project Manager when such an object is found and the Project Manager will instruct the Contract how to deal with it.  The Contractor does not move the object without instruction.

### 4.1.6 Cooperating with and obtaining acceptance of Others

During the course of the contract, departments of Eskom and other contractors may be working in the general area surrounding the working area. The Contractor must make allowance for the necessity to interface with the activities of others, and to allow for safe access and working conditions. The success of the project depends on the effective co-operation of all contractors on site, and the Contractor, if necessary, must discuss his programme on a day to day basis with the Project Manager to ensure effective co-ordination.

### 4.1.7 Publicity and progress photographs

The Supervisor will record progress by means of a photographic record as required by the Project Manager.

The works will be photographed at the QITP hold points so that a photographic records exists of the quality compliance of the work during the various stages of construction.

The Contractor may also take photographs as a photographic record of the progress on site. The Contractor must obtain the Project Managers permission to take photos on site for any other purpose as mentioned above.

### Contractor’s Equipment

The contractor to comply with form 74 SHE specification for all issues related to contractor’s equipment.

### Equipment provided by the Employer

The Contractor is obliged to provide the necessary equipment to do the works at his own cost.

### 4.1.8 Facilities provided by the Contractor

- Facilities provided by the Contractor

- The Contractor shall provide their supply (generator) points necessary for the works.  Adequate and/or continuous supply is not guaranteed and no claims for delay or standing time as a result of insufficiencies or failures will be considered.  Any measures which the Contractor may require to maintain continuity and quality of supply shall be arranged by him at his own expense.

- A site for the Contractor’s yard will be provided adjacent to the site of the works.  The Contractor shall not occupy any site area other than that allocated to him

- Toilet facilities are not available on site; the contractor is advised to provide his own portable toilet facilities.  The Contractor is to ensure that these facilities are kept in a clean condition to Eskom’s satisfaction.

- There is no drinking water and the contractor has to bring their own water.

- Contractor to provide pumping systems to pump water from the bore hole for construction

- It is the Contractors responsibility to provide their own living accommodation outside the substation property and Eskom’s servitudes.

- Contractor to provide own temporary office, telephone and workshops on site.

- Contractor to provide own safe storage for material and plant.

- The Contractor must make his own arrangements for the disposal of sewerage and wastewater. Sewerage may not be wasted on site. Eskom facilities may not be used

- There is no telecommunication service at site, the contract to provide telecommunication facilities for his use during the execution of the works.

- The Contractor shall provide everything else necessary for Providing the Works

### 4.1.9 Existing premises, inspection of adjoining properties and checking work of Others

Before any excavation is commenced, it will be the responsibility of the Contractor to ascertain from the "Site Supervisor" the position of any existing services on site. Once these are indicated to the Contractor they shall be deemed “known”.  Any costs incurred for repairs to any “known” services shall be for the Contractor’s account.

### 4.1.10 Underground services, other existing services, cable and pipe trenches and covers

The contractor to familiarise with the site conditions before commencing construction work. It will be the responsibility of the Contractor to ascertain from the "Site Supervisor" the position of any existing services on site. Once these are indicated to the Contractor they shall be deemed “known”.  Any costs incurred for repairs to any “known” services shall be for the Contractor’s account

### 4.1.11 Control of noise, dust, water and waste

The contractor is required to comply to the SHE regulations and specification for controlling noise, dust,

water and waste

### 4.1.12 Sequences of construction or installation

Please note that the works is outage related per generator and feeder bay.

### 4.1.13 SHEQ related non-Performance

- Termination due to None Compliance

Employer reserves the right to terminate the contract in the event that the contractor is found to be consistently non-compliant to any SHEQ related issue.

- Penalty for health and safety statistics

Should the LTIR at any stage during the contact exceed the ESKOM target of 0.4 a penalty of R100 000 will be imposed by the client. This penalty will be refunded in the event that the LTIR drops below 0.4 at contract completion

- Fines for Health and Safety violations

The following fines will apply for health and safety violations and non- refundable:

- Cardinal rule violations (1st Violations): R10 000.00 per event, payable by the Contractor.

- Cardinal rule violation ( 2nd  Violation): Removal of repeat offender from site and R10 000.00 payable by the contractor.

- Risk assessment and / or method statement not in place or available at activity: R15 000 per event

- Non-compliance to legislation: R20 000 per event

- Fines for environmental violations

For fines related to Environmental violations please refer to the document titled “environmental Requirements for Contractors working on PDP projects

- Fines for quality related issues

NCR’s not closed out satisfactory within 30 days: R10 000 per event

- Fines for Sub – Contractor Management

Sub – contractor are to be managed in accordance with the requirements of form 74. Failure to comply will result in a fine of R50 000 per non-compliance.

All the above fines and penalties will be implemented by the Project Manager at his discretion.

### 4.1.14 Giving notice of work to be covered up

Contractor will submit schedule of works to be done to the project PM. The project PM will forward the schedule to the site supervisor as notice of work to be covered up

4.1  Meetings

The Project Manager shall arrange for a design meeting during the planning phases of the contract. For the remainder of the contract, the Contractor shall attend all management meetings as called by the Project Manager. The monthly site construction progress meetings, plus weekly site meetings during the site erection phase and daily meetings during the commissioning phase, will be held. The Contractor must present all relevant information including quality plans, schedules and health, environmental and safety issues at such meetings.

The Project Manager shall arrange for regular inspections during the manufacturing phase in accordance with agreed hold and witness points and shall also be used as a manufacturing progress report evaluation. The Contractor shall attend risk reduction meetings as and when called by the Project Manager. Other meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.

Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting. All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting. Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | When required | ESKOM – CLN Depot office | Employer and Contractor |
| Site construction progress and feedback | Monthly (at least once month) | Camden, Kriel and Matla substation | Employer, Contractor, Supervisor, and project team |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

## 4.3 Invoicing and payment

In terms of core clause 50 the Contractor assesses the amount due and applies to the Employer for payment.  The Contractor applies for payment with a tax invoice addressed to the Employer as follows:

The Contractor includes the following information on each tax invoice:

- Name and address of the Contractor

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- The total Price for Work Done to Date which the Contractor has completed;

- Other amounts to be paid to the Contractor;

- Less amounts to be paid by or retained from the Contractor;

- The change in the amount due since the previous payment being the invoiced amount - excluding VAT, the VAT and including VAT;

Ensure that the Eskom order number is clearly indicated on your invoice together with the line number on the order you are billing for.

•	All Electronic invoices must be sent in PDF format only.

•	Each PDF file should contain one invoice; or one debit note; or one credit note only as Eskom’s SAP system does not support more than one PDF being linked into workflow at a time.

•	Your E-mail may contain more than one PDF file (e.g. 2 invoices on 2 separate PDF files in one e-mail)

•	Send all invoices in PDF to invoiceseskomlocal@eskom.co.za.

•	For Foreign invoices, suppliers will still be required to physically deliver hard copies of original documents to the respective documentation management centers even though you have e-mailed those invoices (Eskom is still seeking clarity from the South African Reserve Bank regarding e-invoicing for Foreign Invoices or invoices in foreign currency. Current requirements are that these manual invoices should still be submitted. You can send the invoice copy to the email addresses indicated below).

•	Tax Requirement

•	A PDF file that was created directly from a system meets the definition of original document and is allowed (including saving documents from excel to PDF, word to PDF etc.)

•	An Invoice that was printed and then scanned to PDF by the Vendor is not acceptable as this is not an original tax invoice by SARS definition but a copy.

The following wording needs to appear on the invoice: “Your invoice is encrypted in order to comply with SARS requirements that invoices and statements sent electronically are tamperproof.”

•	If there is Cost Price Adjustment (CPA) on your invoice we recommend that you issue a separate invoice for CPA so that if there are any issues on the CPA the rest of the invoice can be paid while resolving the CPA issues.

•	Introduction of electronic invoicing does not guarantee payment but will ensure visibility of all invoices and ensure that no invoices get lost. If the goods receipt is not done the invoice will be parked and the system will automatically send an e-mail to the end user to do the goods receipt. This is also tracked by Eskom through the park invoice report.

•	Your company can request a park invoice report from the Finance Shared Services (FSS) contact center which can then be followed up and corrected. You are welcome to forward the details of invoices corrected to the FSS contact center.

•	Email addresses for invoice submission:

invoiceseskomlocal@eskom.co.za

The Contractor attaches the detail assessment of the amount due to each tax invoice showing the Price for Work Done to Date for each item in the Price List for work which he has completed.

### 4.4 Supplier Development and Localisation – South Africa (SD&L)

Eskom SOC Limited as an organ of State is required to implement South African Government Policy in a number of areas. SD&L is the South African Government’s accelerated shared growth initiative. The initiative has identified Government spending on infrastructure – such as power station construction - as a key area for SD&L intervention and Eskom Holdings Limited is accordingly required to set skills development and local content targets and minimums as key evaluation criteria in tenders that it awards.

Eskom SOC Limited has long had a policy in place regarding procurement from black individuals and companies owned and controlled by black individuals. This policy  is number 32-416 “Implementation of Eskom’s Black Economic Empowerment Strategy” which is in line with The Codes of Good Practice gazetted by the Minister of Trade and Industry on the 9 February 2007.  For the purposes of this tender the targets for black procurement have been set both as part of the SD&L evaluation and as part of commercial evaluation of whether the Contractor meets the Required BEE score.  The SD&L requirements only are discussed in this document.

For this tender all tenderers must demonstrate at least a sixty percent (60%) overall SD&L score for their tender to be evaluated.  SD&L compliance is given twenty three percent (23%) of the total tender points and as such this is a key evaluation criterion for the tender.  A scorecard approach to measuring the SD&L compliance of tenderers is followed and a weighting is given to each aspect of SD&L.

For the purposes of tendering, the tenderer must demonstrate the manner in which the SD&L requirements will be met in due course in an implementation program.  If the tender is awarded all SD&L undertakings (the Contractor’s SD&L Obligations) must be made by the Contractor at the time of contracting.

SD&L SCORECARD

The SD&L scorecard generally identifies five areas for SD&L evaluation.  These are procurement from LBSs, BWOs, SBEs; local content of the tender as a whole; and Skills Development commitments of the tenderer.  Targets and weighting are set for each.

| SD&L COMPLIANCE SCHEDULE FOR THIS TENDER as a total for sections A and B (The skills developments for each section are split 50:50) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Criteria | Weight | Target | Proposed | Actual | Score |
| LBS |  |  |  |  |  |
| BWO |  |  |  |  |  |
| SBE |  |  |  |  |  |
| Local Content |  |  |  |  |  |
| Skills Development Total |  |  |  |  |  |
| Total Score |  |  |  |  |  |
| Skills Development |  |  |  |  |  |
|  | 100.0% |  |  |  |  |

Definitions and Interpretation

The definitions below shall be referred to in the interpretation of this Annexure T1.2. The targets for BWO, LBS and SBE are a percentage of the local content portion of the tender only.

LBS

This refers to procurement from “Large Black Suppliers” as defined in Directive 32-416.

32-416 defines Large Black Suppliers as follows: An LME that is a minimum of a “Level Four Contributor” to BEE. Large Black Supplier has an annual turnover of more than R35 million.

BWO

This refers to procurement from “Black Woman Owned Enterprises” as defined in Directive 32-416.

32-416 defines BWO as follows: An EME or QSE that is 50% or more owned and effectively managed by Black women.

SBE

This refers to procurement from “Small Black Enterprise” as defined in Directive 32-416.

32-416 defines an SBE as follows:  An EME or QSE that is 50% or more owned and effectively managed by Black persons.

The turnover limit for Enterprises to qualify as SBE’s is R35 Million.

SD&L Progress Report

Means the Contractor’s SD&L progress report contemplated in clause 7 of this annexure

Local Content

“Local Content” refers to value added in South Africa by South African resources. Where a single contract involves a combination of local and imported goods and or services, the tender response must be separated

into its components (where applicable) and included with tender documents. Local content is total spent minus the imported component.

This is calculated by subtracting the cost of imported goods and services in respect of the works from the total contract amount.

Imported Goods and Services

“Imported goods and services” means, but is not limited to:

Goods and services directly imported into South Africa;

Goods which although stored in South Africa are produced and/or wholly manufactured outside the borders of South Africa and/or have a minimum of 50% (fifty percent) of production costs (including labour) incurred outside of South Africa and payable to foreign residents and/or foreign registered entities;

Goods that have been "substantially transformed" outside of South Africa. Substantially transformed refers to the irreversible incorporation of imported components in the goods, with the labour costs and profit content earned by foreign residents and/or foreign registered entities exceeding 50% (fifty percent) of the Contract Amount  and/or the significant assembly and manufacture of the goods occurring outside of South Africa's borders; and/or

Services with at least 50% (fifty percent) of the labour cost incurred outside of South Africa's borders and/or with at least 50% (fifty percent) of the service fee payable to foreign residents and/or foreign registered entities, regardless of whether the service involves domestic capital goods or other domestic costs

Final Review

Final Review means the review (to be conducted at the completion date of the whole of works by the Project Manager) of the Contractor’s performance in respect of the Contractor SD&L Obligations.

Skills Development

This is the requirement that tenderers commit to train certain individuals in specified trades.

The requirement is that the targeted numbers of individuals are trained and complete practical tasks to achieve the outcome of passing a trade test and qualifying as an artisan, or the equivalent for any other required skill.

Contractor’s SD&L Commitments

Means those commitments regarding local content, skills development and procurement from LBSs, BWOs and SBEs made by the Contractor in his tender submission and used by the Employer for the purposes of calculating the Contractor’s SD&L score in the tender evaluation process.

Contractor’s SD&L Obligations

Means those obligations of the Contractor regarding local content, skills development and procurement from LBSs, BWOs and SBEs derived from Contractor’s SD&L Commitments and agreed between the Contractor and the Employer.

Certificate of Fulfilment

Means the certificate issued by the Employer after the Final Review as evidence of the Contractor’s successful fulfilment of the Contractor SD&L Obligations.

SD&L PROGRESS REPORTS

The Contractor shall submit monthly SD&L progress reports to the Project Manager.  SD&L progress reports shall be submitted by the 7th (seventh) day of the month following the months to which the report relates.  Each report shall include:

An executive summary;

Charts and detailed descriptions of the progress in narrative format, including each stage of progress of the Contractor SD&L Obligations, the meeting (or delay in the meeting) of anticipated dates and targets (as set out in the program) and any documents, statistics or other form of verification of the dates and targets to be provided in respect thereof;

Percentage progress and the actual or expected dates of commencement of any of the major stages making up the Contractor SD&L Obligations;

Schedule of forecast and actual, together with a 3 (three) month look-ahead of major activities and events;

Comparisons of actual and planned progress in terms of the Implementation Program;

Details of actual and planned resources;

An Affidavit from the sub-Contractors stating the work that has been subcontracted to meet the Contractor’s SD&L obligations;

a schedule identifying all details of persons in the process of undergoing or who have successfully completed the Skills Transfer for the relevant period (including details of their personal information and certified copies of their test results and certificates received);

a risk register and assessment dealing with all areas of concern which may cause delays to the fulfilment of the SD&L obligations and details of the corrective or other measures being adopted, or to be adopted to mitigate or overcome such delay; and such other matters and information (including schedules and charts) as the Project Manager may require to be included in the SD&L progress report from time to time.

An electronic copy and two hard copies of each SD&L progress report shall be submitted to the Project Manager.

Additional Reports

The Project Manager shall be entitled to request the Contractor to provide additional reports when in his opinion they are warranted to monitor the progress of the fulfilment of the Contractor SD&L obligations.

The Final Review

The parties’ record that the purpose of the final review is for the Project Manager to determine whether the Contractor has fulfilled the Contractor’s SD&L obligations as at completion date.

The Contractor shall provide the Project Manager with the following documentation to be used by the Project Manager as a basis for the final review:

A consolidated SD&L progress report recording all steps taken to meet the Contractor’s SD&L obligations from the starting date to the completion date including all information and documentation referred to in clause 8.1 above;

All of the SD&L progress reports provided by the Contractor during the course of the contract and any other additional report, documentation or information that the Project Manager deems to be reasonably relevant to the conduct of the final review (to be provided by the Contractor at least 21 (twenty one) business days prior to the final review). The Project Manager shall notify the Contractor of such request by way of written notice at least 30 (thirty) business days prior to the final review.

The Employer shall, in its reasonable discretion, conduct the final review by comparing those Contractor’s SD&L obligations actually fulfilled by the Contractor as at the time of the final review against with the Contractor’s SD&L obligations as a whole.

The Project Manager shall notify the Contractor of its findings on the final review by way of written notice within 30 (thirty) business days of the final review. The notice shall contain the Project Manager’s reasons for its findings.

Should the final review reveal that the Contractor has not fulfilled and/or complied with any of the Contractor’s SD&L obligations as at the completion date:

The Contractor shall be in breach of a material obligation under the contract and the employer shall be entitled to have immediate recourse to and make a claim against the whole of the retention bond as the penalty for the Contractor’s breach of the Contractor SD&L obligations.

Should the final review reveal that the Contractor has fulfilled and/or complied with all of the Contractor’s SD&L obligations as at the completion date, the employer shall issue a certificate of fulfilment.

### 4.5  BBBEE and preferencing scheme

Specify constraints which Contractor must comply with after contract award in regard to any Broad Based Black Economic Empowerment (B-BBEE) or preferencing scheme measures.

5.  Requirements for the programme

5.1 General

The Contract programme, progress reports, subsequent updates, revisions and supplementary programmes  as detailed in this section are an essential part of the project control system used by the Employer for managing the works and in monitoring the progress of the work under the Contract. The information and data provided by the Contractor pursuant to this procedure must therefore be reliable, accurate and timely in presentation.

5.2 Programme submission

A copy of the Contractor’s First Programme shall be submitted with the Tender Document returnables that shall comply with the requirements as indicated in the Works Information. The Contractor’s Detailed Programme shall be submitted in both hard and soft copy forms within two weeks of award using a computer software package approved by the Project Manager. The preferred software package is Microsoft Projects or recognised computerised planning system for which the Project Manager’s acceptance in writing is obtained.

The contractor submits one programme that incorporates all his sub-contractors activities within 14 days from the contract date; at least a summary barchart shall be submitted with the tender. A programme that is properly tracked shall be available at all site meetings and progress meetings A programme that is properly tracked shall be available at all site meetings and progress meetings

5.3 Contract programme (baseline)

The Contractor’s First Programme, agreeing with the tender submission, shall become the “Contract Programme” or “baseline” against which actual time performance will be compared. Once the baseline has been established, all subsequent programmes will have baseline (target) bars shown against each activity. This programme will be used as the basis on which all variations, extensions of time and changes to methods of delivery shall be assessed. Identified deviations from the baseline shall be addressed by the Contractor by either demonstrating that the deviation does not constitute a problem to the overall Contractor’s Programme or providing a course of action to remedy the deviation.

5.4 Revisions to contract schedule

The Project Manager’s written approval of any revised contract programme shall be given prior to the revised contract programme becoming the new contract programme. Additional detail may be inserted into the Contract Programme at the request of either the Contractor or the Project Manager. In such cases, the overall start and finish dates of the detail activities shall not vary from the original summary activity(s) that were replaced. All revisions to the contract programme shall be prepared by, and at the cost of the Contractor. The revised programme should reflect the effect of the change on the programme, completion date and cost before acceptance by the project manager within 7 days.

5.5 Supplementary programmes

The Project Manager may at any time, and at the cost and expense of the Contractor, direct the Contractor to produce supplementary programmes to highlight a particular aspect of the work under the Contract. The Project Manager shall not unreasonably request supplementary programmes.

5.6 Cash flow

The Contractor shall submit to the Project Manager a detailed monthly cash flow  chart based  by the 20thof each month on the contract programme showing the anticipated cash flow as represented by expected payment claim submissions, not only payments received.

5.7 Progress reporting

To demonstrate the actual progress of the work under the Contract the Contractor shall, on a monthly basis, update and submit the contract programme and the progress to the Project Manager. The contract programme shall be in the form of a three week look ahead schedule, and shall show the following two separate bars for each activity so as to enable comparison of the actual progress to the contract programme:

- The contract programme “baseline” activity bar

- The current schedule activity bar identifying the currently forecast start and finish dates of the activity, and the status (% completion of each activity).

5.8 Progress monitoring and review

Monitoring and review of the progress of work under the Contract shall consist of an assessment of all activities currently in progress. The following shall be determined:

- Contract start date

- Possession date

- Site construction commencement date

- percentage complete;

- forecast completion date;

- Hold, inspection and Witness points

- Payments milestones (linked to completion of specific activities)

- Design review meetings

- deviations from the baseline programme; and

- actions required to remedy any deviations.

All relevant activities shall be shown in order to monitor the progress on site or in the workshop. All major interfaces of services and or other contracts logically required for completion are clearly shown. The programme shall indicate ALL dependencies on the Employer. The programme shall also reflect 2 week period for inspection and correcting of defects before the final completion dates

5.9 Monthly status report

The Contractor shall provide a written status report by the 20thof each month or such other reporting period as may be required by the Project Manager from time-to-time. The report shall summarise progress and problems encountered during that month in respect of all parts of the work under the Contract. As a minimum the report shall include:

- Statement and report on activities where slippage against programme has occurred, together with the reasons why delay has occurred and plan denoting  the location to be taken and the period of time necessary to recover such delay;

- Statement and report on those sections of the works that are currently ahead of programme ( if any);

- The impact of any programming changes arising is reflected in revised forecast rate payment schedules and resource schedule.

- progress against the current approved contract programme;

- summary of progress achieved during the period;

- list of milestones achieved during the period;

- status of design, procurement, and off-site works;

- status of on-site works;

5.10 Resource Schedule

Resource information for manpower, plant and equipment on the accepted programme/ works methodology and reflected in the resource histograms is provided. The contractor to ensure that resources are available at Camden, Kriel and Matla Substation.

5.11 Detailed Workshop Manufacturing programmes

The Project Manager request detailed workshop manufacturing schedules which fit into the logic and time span of the accepted programme, and meet the manufacturing completion dates.

5.12 Time analysis

Should the contractor require to reserve built in float to control subcontractors, shipping facilities and transport, such float is shown as an activity named “project float” thus eliminating unrealistically long activity duration’s.

The total “float” or “slack” of an activity is defined as the difference between the earliest completion and the latest completion dates of the activity.

Automatic manipulation of “lags” ”overlaps” “leads” “relations” or “dummies” (with positive, zero or negative durations) to cause the float to remain constant when updates are performed is not acceptable.

5.13 Time reporting

Reporting on remaining duration:

The method for reporting on activities in progress is by remaining duration, i.e. the time, in working days, needed to complete the activity from the report date. Once an activity has started, the remaining duration is assessed for each update.

Automatic reduction of remaining duration as the report date moves forward is not accepted.

Actual dates:

When completion of any activity is confirmed by quoting document numbers, these numbers are given in a remarks appendix, e.g. suborders, drawings, inspection, certificates, delivery notes, etc. the actual starting and completion date of all activities is reported

6. Services and other things provided by the Employer

The contractor shall provide everything else necessary for proving the works

C4:  Site Information

# C4.1: Information about the site at time of tender which may affect the work in this contract

Matla Substation

The site is Matla Substation located at this site coordinates -26.282216S 29.139325E. The site is situated about 17KM from Kriel Town and 35KM from Secunda in the Mpumalanga North East Grid region.

The contractor is to inspect the site in order to ascertain the conditions and extent of his risk.

Matla substation is situated at Matla power in the Mpumalanga North East Grid region

Camden Substation

The site is Kriel Substation located at this site coordinates - 26.6171° S,30.0936° E. The site is situated about 20KM from Ermelo Town in the Mpumalanga North East Grid region.

The contractor is to inspect the site in order to ascertain the conditions and extent of his risk.

Camden substation is situated at Camden power in the Mpumalanga North East Grid region

Kriel Substation

The site is Kriel Substation located at this site coordinates - S 25°54.30" E 029°15.20". The site is situated about 20KM from Kriel Town and 35KM from Secunda in the Mpumalanga North East Grid region.

The contractor is to inspect the site in order to ascertain the conditions and extent of his risk.

Kriel substation is situated at Kriel power in the Mpumalanga North East Grid region

## Existing buildings, structures, and plant & machinery on the Site

As per Control Room equipment layout and Foundation, Trench and earth-mat layout and Key Plan

## Ground conditions in areas affected by work in this contract

The site works are within the Eskom servitude boundary of Camden, Kriel and Matla Substation and all Eskom rules and regulations shall be adhered to when operating in these areas. No un-authorised earthworks will be permitted.

Except those actions which can only be done by the Employer as a Party to the contract.

If June 2005 Edition applies, delete April 2013 and insert June 2005

State whether attached as a ‘PDF’ file in terms of Eskom’s licence, or to be obtained from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za.