## Risk template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | Transmision Power Delivery Projects Baseline Risk Assessment: Mersey Bus Zone 275kV Replacement project | [7 empty] | Department: | PDP SHEQ | [9 empty] | Next Review Date (every 2 years): | 20240615 | Template identifier: | 240-70044602
Date: | 20220805 | [7 empty] | Prepared by: | L. Shezi |  | Authorised by: |  | Name: Geoffrey Small | [7 empty] | Document identifier | [8 empty] | R | Safety | 1 | A | Fully effective | I
[14 empty] | Designation: Middle Manager SHEQS | [7 empty] | Revision number: | 4 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[14 empty] | Date: 2022-08-05 | [7 empty] | Revision Date: | 2027-04-30 | [9 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [32 empty] | 5 | E
List activity | Activity type (Routine/Non-routine) | Hazard nr | Hazard Identification | Risk Nr | Associated risk | Risk type | Cause(s) of the risk | Exposed group/employees | Risk Owner | Exposure patterns | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Target Date | Current Status | Integrated Risk Management (IRM) reference number | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | # | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | # | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | Who is exposed to the hazard i.e. visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Pending, In Progress, Complete | Where applicable, add IRM system reference number for tracking of treatment actions. | Consequences | 6 | III | II | I | I | I
Support Steel (Structural and Tubular Steelwork) | [24 empty] | 5 | III | II | II | I | I
Assembly and Installation of steel structure(s) | R | 1 | Uneven surfaces / terrain (Applicable to all substation work) | 1.1 | Slips, trips and falls | Safety | Lack of concentration Horse play Inadequate Risk assessment Inadequate communication | All persons in the area | PM | 8 hours daily | Medical Incidents, First aid incidents | Compulsory reporting of all employees to the site office for SHE induction, Not allowing visitors to site without the presence of a site supervisor or Health and safety officer | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations |  |  |  |  | 4 | IV | III | II | I | I
|  |  | Open trenches (Applicable to all substation work) | 1.2 | Slips, trips and falls | Safety | Inadequate planning Inadequate rehydration Underlying diseases Poor Nutrition Improper PPE | General workers | PM | 8 hours daily | Medical Incident | Risk assessment to be conducted prior to the execution of the activity; Open trenches and excavation must be barricaded or closed off it’s possible | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations |  |  |  |  | 3 | IV | III | II | II | I
|  |  | Adverse weather conditions (Applicable to all substation work) | 1.3 | Exposure to extreme elements; Dehydration; Frost bite | Safety | Improper use of equipment Worn out equipment PPE not worn Inadequate / Pre-use Inspections | General workers and visitors | PM | 8 hours daily | Fatality | All employees are encouraged to dress warm and drink warmer or hot liquids during the cold season. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations |  |  |  |  | 2 | IV | IV | III | II | II
Measure Foundation Assembly | N | 2 | Sharp edges on steel measuring tape (Applicable to all substation work) | 2.1 | Cuts (Injuries) | Safety | Improper use of equipment Worn out equipment PPE not worn Inadequate / Pre-use Inspections | Foundation team | PM | 8 hours daily | Medical Incident | Perform task specific risk assessment before the execution of the activity, Supervision of the employees; Employees to be provided with the training on the use of PPE and enforcement of the use of PPE is to be monitored. | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations |  |  |  |  | 1 | IV | IV | III | III | III
Assembly and Installation of steel structure(s) | N | 3 | Protruding copper tails | 3.1 | Trips and Falls | Safety | Protruding metal objects not “capped” or demarcated Lack of concentration | Assembly and Installation of | PM | 8 hours daily | Medical Incident | Effective site supervision and Proper housekeeping, | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations | [5 empty] | A | B | C | D | E
|  |  | Improper hand tools usage (e.g. spike spanner) (Applicable to all substation work) | 3.2 | Tool slipping | Safety | Over torqueing Inadequate PPE | Assemblers | PM | 8 hours daily | LTI | Ensure employees are trained on the usage of tools. Effective site supervision and job observations. | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations | [5 empty] | Likelihood
|  |  | Unsecured steel / material | 3.3 | Falling steel / material | Safety | Improper handling Inadequate inspection | Assemblers | PM | 8 hours daily | Fatality | Risk assessment and the usage of SWP for all critical activities. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Manual handling of heavy objects / material (Applicable to all substation work | 3.4 | Ergonomics | Safety | Improper lifting techniques Under estimation of the weight/ load Underlying medical condition Lack of PPE Inadequate training / experience | Assemblers | PM | 8 hours daily | LTI | Conducting an ergonomics risk assessment, Training or coaching of the employees on the correct techniques of lifting heavy equipment. Avoid manual handling and encourage the usage of the cranes to lift heavy materials. | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Integrity of lifting equipment for lifting of equipment and employees | 3.5 | Equipment failure Hydraulic failure Falling material | Safety | Inadequate maintenance; Inadequate inspections; Inadequate Risk assessment; Incorrect equipment; Incorrect slinging; Latent defects; Inadequate training; Inadequate supervision | Operators Riggers Assemblers | PM | 8 hours daily | Fatality | Inspection of all the lifting tackles, Ensure that all the certificates remain valid and ensure that equipment operators are trained and competent. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Deviation from approved lifting methodology | 3.6 | Falling material Load shifting Failure of equipment / tackle | Safety | Incorrect slinging; Exceeding load limits; Inadequate inspection; Inadequate training; Lack of supervision | Operators Riggers Erection team Bystanders | PM | 8 hours daily | Fatality | Training employees on the usage of the approved SWPs. Effective supervision and observation of the employees during the execution of the activity. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced equipment operator(s) (Applicable to all substation work) | 3.7 | Lose control of equipment Falling material | Safety | Lack of supervision Underlying medical condition | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | Rigging activities to be done by certified riggers under the supervision of a responsible site supervisor or construction manager. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Suspended load | 3.8 | Exposure to falling objects Falling from height | Safety | Failure to inspect lifting equipment, Failure to fasten the loads securely, Failure to develop Elevated position SWP procedures. | Erection Team Bystanders | PM | 8 hours daily | Fatality | Inspection of lifting equipment, All the loads must be fastened securely, Elevated position SWP procedures must be developed. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Unstable terrace / platform | 3.9 | Crane overturn | Safety | Sinking terrace Poor compaction Fill material used not according to specification Inadequate method statement or Noncompliance to method statement | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | Cranes to be operated by competent operators, Levelling of the terraces before the commencement of the lifting activity. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Tightening and torqueing of bolts and nuts | N | 4 | Incorrect application of hand tools e.g. torque wrench(Applicable to all substation work) | 4.1 | Falling, slipping | Safety | Worn out tools Inadequate pre-use inspections Use of self-made tools Incorrect tool application Inadequate training Use of defective tools Awkward body posture | Erection team | PM | 8 hours daily | LTI | Worn out tools are not to be used. Adherence to the approved pre-use inspections tools. | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Elevated positions | 4.2 | Fall from elevated positions | Safety | Failure to secure PPE failure Inadequate training Underlying medical conditions Engineering design constraints Non-compliance to method statement Worker complacency | Climbers; Bystanders | PM | 8 hours daily | Fatality | Adherence to the working at heights SWP. Implementation of an ongoing training program for all climbers, Identification and management of employees with underlying medical conditions. Usage of the relevant Engineering designs. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Component failure | 4.3 | Collapsing of steel structure | Safety | Latent defects on bolts Incorrect size of bolts Exceeding safe work load limits Inadequate inspections of bolts Inappropriate storage of bolts (exposure to elements) | Erection team, Bystanders | PM | 8 hours daily | Fatality | Identification of latent defects on bolts and nuts. Training of employees and awareness on the dangers of exceeding safe work load limits. | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced employees/workers | 4.4 | Collapsing of steel structure Incorrect assembly | Safety | Inadequate training Inadequate supervision Non-compliance to procedure | Co-workers Bystanders | PM | 8 hours daily | Fatality | Ensure that employees are adequately trained on the erection of towers, Effective supervision of employees. Development of no-compliance to procedure | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Elevated positions | 4.5 | Fall from elevated positions (Material) | Safety | Failure to secure Inadequate training Engineering design constraints Non-compliance to method statement Complacency | Climbers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Working at Height (32-418) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Incorrect application of hand tools (purpose made / special tools) | 4.6 | Equipment failure | Safety | Inadequate training Non-compliance to procedure | Assemblers | PM | 8 hours daily | Fatality | SHE Specification Form 74 SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Assemble / erect structures (steelwork) | N | 5 | Heavy material (Applicable to all substation work) | 5.1 | Musculoskeletal disorders | Safety | Incorrect lifting techniques Inadequate training / experience Underestimation of weight Physical incapability - Inadequate selection process | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 SANS 1200 ALL PARTS Project specific drawings | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  |  | 5.2 | Caught between | Safety | Lack of concentration Non-compliance to procedures Lack of supervision Incorrect body position Lack of risk assessment | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Animals - Wildlife (Applicable to all substation work) | 5.3 | Bites and stings | Safety | Habitat invasion; Lack of concentration | All present in work area | PM | 8 hours daily | Fatality | SHE Specification Form 74 Project specific Environmental Management Plan Construction Site Establishment and Dismantling (PDPMAN-PC-49) Eskom Personal Protective Equipment (240-44175132) Occupational Hygiene Management (PDPMAN-GL-50) Occupational Health Risk Assessment (OHRA/PDP) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Circuit breakers
Breaker preparation and Gassing | N | 6 | Breaker hardware failure | 6.1 | Porcelain Failure | Safety | Inappropriate lifting technique Jerking during lifting Inexperienced crane operator | Assemblers | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Performing tasks at elevated positions | 6.2 | Fall from elevated positions | Safety | Failure to secure; PPE Failure; Inadequate training; Underlying medical conditions Engineering design constraints Non-compliance to method statement Complacency | Climbers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Working at Height (32-418) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Incorrect application of hand tools (purpose made / special tools) | 6.3 | Equipment failure | Safety | Inadequate training Non-compliance to method statement | Assemblers | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Incorrect installation of stack and T Connection(Applicable to all substation work) | 6.4 | Crushing of employee limb | Safety | Crane failure Lack of concentration / attention by the operator Inadequate training / experience Extreme weather conditions Non-compliance to method statement | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Gassing | N | 7 | Inappropriate SF6 gas cylinder handling | 7.1 | Uncontrolled release of gas | Safety | Not properly secured Improper storage practices | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Manual handling of cylinder(s) | 7.2 | Musculoskeletal injuries and diseases Pinched by / Caught between cylinders | Safety | Improper lifting technique Awkward position | Assemblers | PM | 8 hours daily | Medical Incident | Occupational Hygiene Management (PDPMAN-GL-50) Occupational Health Risk Assessment (OHRA/PDP) SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
[8 empty] | Assemblers | PM | 8 hours daily
Isolators |  | 8 | [5 empty] | Assemblers | PM
|  |  | Assembly of parts – See assessment Assembly above |  |  |  |  | Assemblers | PM
|  |  | Measure Foundation Assembly – see Measure foundation assessment above |  |  |  |  | Assemblers | PM
|  |  | Torque/ Tighten – See Tightening and torque assessment above | [5 empty] | PM
PM
Levelling of Top Cap (applicable to all substation works) | N | 9 | Performing task at elevated positions | 9.1 | Fall from elevated position (i.e. person/material) | Safety | Improperly secured | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Working at Height (32-418) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Hand tools | 9.2 | Slipping / falling | Safety | Worn out tools Inappropriate use of tools Awkward position | Assemblers | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  |  | 9.3 | Pinch points | Safety | Awkward position Non-compliance to procedures | Assemblers | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  |  | 9.4 | Caught between | Safety | Awkward position Non-compliance to procedures | Assemblers | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Eskom Personal Protective Equipment (240-44175132) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Improper handling of heavy equipment | 9.5 | Overexertion | Safety | Repetitive action | Assemblers | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (32-282) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Sling, Lift Transformer and Place on structure | N | 10 | Suspended load | 26.1 | Exposure to falling objects Falling from height | Safety | Failure of lifting equipment Improperly secured load Elevated position Not following procedures Inadequate training | Erection Team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Uneven / Unstable platform | 26.2 | Crane overturn | Safety | Sinking terrace Poor compaction Fill material used not according to specification Inadequate method statement or Noncompliance to method statement | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Deviation from approved lifting methodology | 26.3 | Falling material Load shifting Failure of equipment / tackle | Safety | Incorrect slinging Exceeding load limits Inadequate inspection Inadequate training Lack of supervision | Operators Riggers Erection team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced equipment operator(s)(Applicable to all substation work) |  | Lose control of equipment Falling material | Safety | Inadequate training / experience Lack of supervision Underlying medical condition | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Improper handling of heavy equipment(Transformers) | 28.1 | Crushing Fall | Safety | Incorrect lifting techniques Inadequate supervision | Assemblers Supervisors Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
| Ballows cover (open and remove packaging) | 11 | Hand tools | 28.2 | Contact with | Safety | Lack of concentration; Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Civil Team | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Check for equipment manual | N | 12 | Improper assembly | 29.1 | Defective equipment | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection | Civil team | PM | 8 hours daily | Fatality | SHE Specification Form 74 | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Connect Sterm | N | 13 | Hand tools | 29.2 | Contact with | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Civil Team | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Sling first part of the CVT, Lift up, Connect to middle part, Lift complete CVT, connect to base and secure | N | 14 | Deviation from approved lifting methodology | 29.3 | Falling material Load shifting Failure of equipment / tackle | Safety | Incorrect slinging Exceeding load limits Inadequate inspection Inadequate training Lack of supervision | Operators Riggers Erection team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced equipment operator(s)(Applicable to all substation work) | 29.4 | Lose control of equipment Falling material | Safety | Inadequate training / experience Lack of supervision Underlying medical condition | (Applicable to all substation work) | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (32-282) Safe use of lifting machines and lifting tackles (39-98) Project specific drawings SANS 1200 ALL PARTS Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Suspended load | 30.1 | Exposure to falling objects Falling from height | Safety | Failure of lifting equipment Improperly secured load Elevated position Not following procedures Inadequate training | Erection Team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Project specific drawings SANS 1200 ALL PARTS Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Unstable terrace / platform | 30.2 | Crane overturn | Safety | Sinking terrace Poor compaction Fill material used not according to specification Inadequate method statement or Noncompliance to method statement | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | Mandatory SHE Specification to be met by contractors and suppliers during refurbishment and construction (PDPMAN-ST-001) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Post Insulators |  |  |  | 30.3
Levelling of Top Cap | N | 15 | Hand tools | 30.4 | Contact with | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Civil Team |  | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Unpack and assembly | N | 16 | Manual handling | 30.5 | Musculoskeletal disorders | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Improper lifting techniques Inadequate experience/training Underlying medical conditions | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Packing material | 30.6 | Contact with sharp objects | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Assemblers | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Packing material | 30.7 | Slips and trips | Safety | Lack of concentrationInadequate supervisionInadequate inspectionPPE not wornInadequate experience/trainingPoor housekeeping | Assemblers All persons in work area | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Protruding nails from wood | 30.8 | Contact with | Safety | Lack of concentration Inadequate supervision Non-compliance to procedures Inadequate inspection PPE not worn Inadequate experience/training Poor housekeeping | Assemblers Persons in area | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Insects and snakes | 30.9 | Bites and stings | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Assemblers | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Fit Busbar Clamps | N | 24 | Hardware | 31.1 | Contact with | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Assemblers | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Sling, Lift and Install Post Insulators |  | 26 | Deviation from approved lifting methodology | 31.2 | Falling material Load shifting Failure of equipment / tackle | Safety | Incorrect slinging Exceeding load limits Inadequate inspection Inadequate training Lack of supervision | Operators Riggers Erection team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced equipment operator(s)(Applicable to all substation work) | 31.3 | Lose control of equipment Falling material | Safety | Inadequate training / experience Lack of supervision Underlying medical condition | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (32-282) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Suspended load | 31.4 | Exposure to falling objects Falling from height | Safety | Failure of lifting equipment Improperly secured load Elevated position Not following procedures Inadequate training | Erection Team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Busbars
Measure PI to PI | N | 28 | Elevated positions |  | Fall from elevated positions | Safety | Failure to secure PPE failure Inadequate training Underlying medical conditions Engineering design constraints Non-compliance to method statement Worker complacency | Climbers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Working at Height (32-418) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Hand tools |  | Contact with | Safety | Lack of concentration Non-compliance to procedures Inadequate supervision Inadequate inspection PPE not worn Inadequate experience/training | Civil Team | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Cut Tube to size | N | 29 | Improper material handling | 32.1 | Strains and sprains Fingers caught between | Safety | Incorrect lifting technique Not wearing PPE Lack of concentration | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Use of cutting tools | 32.2 | Exposure to noise levels above 85dB | Safety | PPE not worn Lack of noise suppression | Assemblers | PM | 8 hours daily | LTI Noise induced hearing loss | Occupational Hygiene Management (PDPMAN-GL-50) Occupational Health Risk Assessment (OHRA/PDP) SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) Hearing Conservation Procedure (32-425) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Use of cutting tools | 33.1 | Uncontrolled moving objects | Safety | Incorrect PPE Disintegration of cutting disc Guarding not in place Non-compliance to procedure | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Use of cutting tools | 33.2 | Contact with revolving cutting edge | Safety | Guarding not in place Non-compliance to procedure | Assemblers | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Fit end caps and tack weld | N | 30 | Presence of inert gases e.g. argon | 34.1 | Asphyxiation | Safety | Uncontrolled release of gas Poor ventilation Leaking pipes Lack of maintenance and/or inspection | Welder Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Improperly “earthed” welding machine | 34.2 | Electrical contact | Safety | Inspections and/or maintenance not done Worn out insulation on electrical wires Plugs not properly “earthed” | Welder | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Life saving rules (32-421) Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Molten metal | 34.3 | Burns | Safety | Insufficient PPE Insufficient protection e.g. welding curtain, blankets Insufficient barricading | Welder Bystanders | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Welding emissions | 35.1 | Fume inhalation | Safety | Poor ventilation Inadequate risk assessment Inadequate PPE Inadequate training Incorrect mixture air/gas/setting | Welder | PM | 8 hours daily | LTI | Occupational Hygiene Management (PDPMAN-GL-50) Occupational Health Risk Assessment (OHRA/PDP) SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 4 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Fire | 36.1 | Smoke inhalation Heat exposure | Safety | Poor house keeping Presence of combustible material No fire safety plan Fire blankets not used Non-compliance to procedure | Welder Bystanders | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Non - Ionised Radiation | 37.1 | Eye irritation Skin burns | Safety | Incorrect/ Inadequate PPE Inadequate training | Welder Bystanders | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 3 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Malfunctioning safety devices e.g. non return valve | 37.2 | Explosion | Safety | Non-compliance to procedure Lack of flashback arrestor Inadequate inspections/ maintenance Inadequate training | Welders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Malfunctioning safety devices e.g. non return valve | 38.1 | Fire | Safety | Non- compliance to procedure Lack of flashback arrestor Lack of inspections/ maintenanceInadequate training Unauthorized Welder | Welders Bystanders Persons in vacinity | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Loose Earth welding cables | 39.1 | Trips and falls | Safety | Lack of inspections Poor housekeeping Lack of concentration | Welders Employees in close proximity | PM | 8 hours daily | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Lift and place on PI,s Fit PI clamps and Remove lifting equipment | 31 | 31 | Suspended load | 39.2 | Exposure to falling objects Falling from height | Safety | Failure of lifting equipment Improperly secured load Elevated position Not following procedures Inadequate training | Erection Team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Deviation from approved lifting methodology | 39.3 | Falling material Load shifting Failure of equipment / tackle | Safety | Incorrect slinging Exceeding load limits Inadequate inspection Inadequate training Lack of supervision | Operators Riggers Erection team Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (32-282) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Inexperienced equipment operator(s) (Applicable to all substation work) | 40.1 | Lose control of equipment Falling material | Safety | Inadequate training / experienceLack of supervisionUnderlying medical condition | Operator Riggers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Improper handling of heavy equipment | 41.1 | CrushingFall | Safety | Incorrect lifting techniques Inadequate supervision | Assemblers Supervisors Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
41.2
41.3
Earth wire |  |  |  | 41.4
Drums placement and storage | N | 32 | Rotten Drums | 42.1 | Collapsed drums | Safety | Untreated wood Wood rot Improper storage | Installers Bystanders Crane operators | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Unsecured Drums | 42.2 | Drums may roll over | Safety | Stop blocks/ Wedge / Chocks not in place Uneven surface | Installers Bystanders | PM | 8 hours daily | Fatality | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Place drums on cable Jacks | N | 33 | Unsecured Drums | 43.1 | Drums may fall from jacks | Safety | Incorrect Lifting techniques Uneven surface | Installers | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Jack Failure | 43 | Jack and drum collapse | Safety | Exceeding safe workload Lack of Inspections / maintenance Uneven surface Incorrect Lifting techniques Defective Jacks | Installers Bystanders | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Remove cover material (Wood) | N | 34 | Fragmented Wood splinters | 43 | Contact with splinters | Safety | Lack of PPE; Lack of concentration | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Protruding nails | 43 | Stepping on nails | Safety | Incorrect PPE Lack of concentration Poor housekeeping Non- Compliance to Procedure Inadequate Risk assessment | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Insects | 43 | StingsBites | Safety | Lack of PPELack Inattention | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Pulling of Earth wire | N | 35 | Earth wire - Pulled by hand | 43 | Ergonomics | Safety | Trestle failure Earth wire- entanglement on drum | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Earth wire pulled from structure to structure | N | 36 | Elevated position | 43 | Fall from height | Safety | Failure to secure PPE failure Inadequate training Underlying medical conditions Engineering design constraints Non-compliance to method statement Worker complacency | Installer | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Eskom Personal Protective Equipment (240-44175132) | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Install Pistol Grip Clamps | N | 37 | Clamps failure | 43 | Earth wire collapse | Safety | Manufacturing defects Lack of pre-use inspection | Installer | PM | 8 hours daily | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) Eskom Personal Protective Equipment (240-44175132 | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
| N |  | Falling of equipment e.g. clamp | 43 | Employees struck by falling objects | Safety | Equipment bags not worn Non- compliance to Procedure | Installer Bystander | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) Eskom Personal Protective Equipment (240-44175132 | 4 | B | III | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Install Clamps and hook to U bolt | N | 38 | Hardware failure e.g. clamps and hooks | 43 | Clamp / hookfalure | Safety | Manufacturing defects Lack of pre-use inspection | Installer | PM | 8 hours daily | Fatality | SHE Specification Form 74 ) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) Eskom Personal Protective Equipment (240-44175132 | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Tensioning of Earth wire - Fit come along and dynamomete rtensioning | N | 39 | Tensioned Earth wire | 43 | Earth wire failure / snapping | Safety | Metal Fatigue Over tensioning Latent defects | Installer Bystander | PM | 8 hours daily | Fatality | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98)Eskom Personal Protective Equipment (240-44175132 | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Come along clamp | 43 | Come along clamp failure | Safety | Incorrect size Metal fatigue Poor maintenance Lack of Pre- use Inspections Incorrect handling Defective equipment Non- compliance to Procedure Lack of Statutory inspections | Installer Bystander | PM | 8 hours daily | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) Eskom Personal Protective Equipment (240-44175132 | 4 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Eskom Personal Protective Equipment (240-44175133 | 43 | Equipment failure | Safety | Inadequate calibration Inadequate inspection/ maintenance Lack of Pre- use Inspections Incorrect handling Defective equipment Non- compliance to Procedure | Installer | PM | 8 hours daily | Medical Incident | SHE Specification Form 74 ) Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Security work | N | 40 | Criminals | 43 | Gross bodily harm | Safety | Criminal activity in the vicinity of the sub-station | Security team | PM | 12 hours per day | Fatality | Eskom Procedure 32-1134 (Physical Access Control at Eskom Premises); Eskom Procedure 32-1133 (Wearing of Ballistic Body Armour by Security Personnel Policy); Training; 240-66963836_ Process Control Manual for Conduct Security Operations | 5 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Dismantling old busbars and insatll new busbars / isolators/ breakers | N | 41 | Cherry Picker | 43 | Equipment failure | Safety | Improper maintenance; Failure to train operator; Inadequate supervision; Inadequate safe work procedute; Inadequate risk assessment; | Installation team | PM | 8 hours daily | Fatality | Eskom Work ar Height Procedure; Proper training of operators; Aduquate supervison; Develop adequate safe work procedute; Conduct adequate risk assessment; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Working in close proximity to live equipment |  | Electrical contact | Safety | Failure to identify and observe safety clearance; Failure to barricade; Inadequate earthing; Inadequate communication between PDP Project Team and Distribution / Transmission; Inadequate PPE; Inadequate training; Deviation from permit to work process; Inadequate formal risk assessment and failure to communicate effectively prior to work commencement; Unauthorised / responsible persons permitted to apply and remove a portable working earth; Improper positioning of portable earths relevant to the work not scrutinised and if they interfere with the work area, be reported to the authorised/ responsible person, prior to commencement of work. Only the Engineering Assistant (EA) may remove / relocate the control earths. Be your brother’s keeper | Installation team | PM | 8 hours daily | Fatality | Identify and observe safety clearance; Erect effective barricing; Install adequate earthing; Ensure adequate communication between PDP Project Team and Distribution / Transmission; Provide adequate PPE; Provide adequate training on Eskom's ORHVS and provide adequate supervision; Inadequate safe work procedute; Inadequate risk assessment; Training on permit to work process; Adequate formal risk assessment and communication prior to work commencement; Authorised / responsible persons only to apply and remove a portable working earth; Proper positioning of portable earths relevant to the work area, be reported to the authorised/ responsible person, prior to commencement of work; Only the Engineering Assistant (EA) may remove / relocate the control earths. Be your brother’s keeper | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Static |  | Electrical contact | Safety | Inadequate earthing; Inadequate safe work procedute; Inadequate risk assessment; | Installation team | PM | 8 hours daily | Fatality | Install adequate earthing; Ensure adequate communication between PDP Project Team and Distribution / Transmission; Provide adequate PPE; Provide adequate training on Eskom's ORHVS and provide adequate supervision; Inadequate safe work procedute; Inadequate risk assessment; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
|  |  | Multiple overhead live line crossing |  | Electrical flashover | Safety | Failure to identify and observe safety clearance; Failure to barricade; Inadequate communication between PDP Project Team and Distribution / Transmission; | Installation team | PM | 8 hours daily | Fatality | Identify and observe safety clearance; Install adequate barricading; Ensureadequate communication between PDP Project Team and Distribution / Transmission; | 5 | B | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls. | Eskom Inspections and Audits on Contractor |  | OHS Act, Act 85 of 1993 and its Regulations
Interaction between persons | R | 42 | COVID 19 (Corona Virus) |  | Cross infection | Health | Failure to keep a social distance of 1m to 2m and then coming into contact with droplets from mouth or nose of an infected person; Touching face after coming into contact with droplets from infected person; | All employees, visitors | Responsible Managers & all employees | Daily | Medical Incident | Eskom's Tactical Command Centre (TCC) as well as Emergency Protocols have been activated; Ensure efficient ventilation in the workplace; Work from home; Keep a social distance of 1m to 2m and restrict unnecessary visits / contacts; As far as practicable, avoid touching face; Awareness campaigns; Practice good hygiene; Home / hospital quarantine for the suspected infected; | 4 | C | II | Mostly effective | External medical services (Public and private); Hand and surface sanitisers | Statistics from Health and Wellness; NCID- National Centre for Infectious Diseases | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002 | Mostly effective | Mostly effective
[7 empty] | Coming into contact with contaminated surface and then touching face; Poor hygiene practices (1. Failure to cough onto elbow / sneeze into a tissue etc 2. Failure to follow good hand hygiene measures, i.e., washing hands often with soap and water at least 20 seconds, or a hand sanitiser with at least 70% alcohol content); | All employees, visitors | Responsible Managers & all employees | Daily | Medical Incident | Home / hospital quarantine for the suspected infected; Awareness campaigns; Practice good hygiene; Wear appropriate risk based PPE (respiratory masks, gloves); Regular disinfection and sanitizing of all areas, focusing on frequently touched surfaces like desks, photo copiers, telephones and similar equipment, bathrooms, offices, common areas, etc. | 3 | C | II | Mostly effective | External medical services (Public and private); Hand and surface sanitisers | Statistics from Health and Wellness; NCID- National Centre for Infectious Diseases | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002 | Mostly effective | Mostly effective
|  | 43 | Monkeypox |  | Cross infection |  | •Direct contact with the infectious rash, scabs, or body fluids respiratory secretions during prolonged, face-to-face contact, or during intimate physical contact, such as kissing, cuddling, or sex. | All employees, visitors | Responsible Managers & all employees | Daily | Medical Incident | •Avoid contact with animals that could harbor the virus (including animals that are sick or that have been found dead in areas where monkeypox occurs). | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls.
[7 empty] | •Touching items (such as clothing or linens) that previously touched the infectious rash or body fluids. |  |  |  | Medical Incident | •Avoid contact with materials, such as bedding, that has been in contact with a sick animal. | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls.
[7 empty] | •It’s also possible for people to get monkeypox from infected animals, either by being scratched or bitten by the animal or by preparing or eating meat or using products from an infected animal. |  |  |  | Medical Incident | •Isolate infected patients from others who could be at risk for infection. | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls.
[12 empty] | •Practice good hand hygiene after contact with infected animals or humans. For example, washing your hands with soap and water or using an alcohol-based hand sanitizer. | 3 | C | II | Mostly effective | Contractor shall develop and implement additional controls and rating post implementation of these additional controls.
•Use personal protective equipment (PPE) when caring for patients.

## Contractor Baseline template
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | [9 empty] | Next Review Date (every 2 years): | Template identifier:
Date: |  |  |  |  | Authorised by: |  | Name: |  |  | Document identifier | [8 empty] | R | Safety | 1 | A | Fully effective | I
[7 empty] | Designation: |  |  | Revision number: | 1 | [7 empty] | N | Health | 2 | B | Mostly effective | II
[7 empty] | Signed: |  |  | Revision date: | 2024-05-31 | [9 empty] | 3 | C | Mostly ineffective | III
[7 empty] | Date: | [13 empty] | 4 | D | None | IV
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [20 empty] | 5 | E
List activity | Hazard Identification | Associated risk | Risk type | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating |  | Control Owner | Legal and Other Requirements | [9 empty] | 6
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Consequences | 6 | III | II | I | I | I
Support Steel (Structural and Tubular Steelwork) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 | III | II | II | I | I
Assembly and Installation of steel structure(s) | Uneven surfaces / terrain (Applicable to all substation work) | Slips, trips and falls | Safety | Medical Incidents, First aid incidents | Compulsory reporting of all employees to the site office for SHE induction, Not allowing visitors to site without the presence of a site supervisor or Health and safety officer | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations |  | 4 | IV | III | II | I | I
[13 empty] | 3 | IV | III | II | II | I
[13 empty] | 2 | IV | IV | III | II | II
Measure Foundation Assembly | Sharp edges on steel measuring tape (Applicable to all substation work) | Cuts (Injuries) | Safety | Medical Incident | Perform task specific risk assessment before the execution of the activity, Supervision of the employees; Employees to be provided with the training on the use of PPE and enforcement of the use of PPE is to be monitored. | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations |  | 1 | IV | IV | III | III | III
Assembly and Installation of steel structure(s) | Protruding copper tails | Trips and Falls | Safety | Medical Incident | Effective site supervision and Proper housekeeping, | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations |  |  | A | B | C | D | E
Likelihood
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tightening and torqueing of bolts and nuts | Incorrect application of hand tools e.g. torque wrench(Applicable to all substation work) | Falling, slipping | Safety | LTI | Worn out tools are not to be used. Adherence to the approved pre-use inspections tools. | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Assemble / erect structures (steelwork) | Heavy material (Applicable to all substation work) | Musculoskeletal disorders | Safety | LTI | SHE Specification Form 74 SANS 1200 ALL PARTS Project specific drawings | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Circuit breakers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Breaker preparation and Gassing | Breaker hardware failure | Porcelain Failure | Safety | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Gassing | Inappropriate SF6 gas cylinder handling | Uncontrolled release of gas | Safety | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Isolators | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Levelling of Top Cap (applicable to all substation works) | Performing task at elevated positions | Fall from elevated position (i.e. person/material) | Safety | LTI | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Working at Height (32-418) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sling, Lift Transformer and Place on structure | Suspended load | Exposure to falling objects Falling from height | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Check for equipment manual | Improper assembly | Defective equipment | Safety | Fatality | SHE Specification Form 74 | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Connect Sterm | Hand tools | Contact with | Safety | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Sling first part of the CVT, Lift up, Connect to middle part, Lift complete CVT, connect to base and secure | Deviation from approved lifting methodology | Falling material Load shifting Failure of equipment / tackle | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
s | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Post Insulators | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Levelling of Top Cap | Hand tools | Contact with | Safety | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) SANS 1200 ALL PARTS Project specific drawings | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Unpack and assembly | Manual handling | Musculoskeletal disorders | Safety | LTI | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Fit Busbar Clamps | Hardware | Contact with | Safety | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sling, Lift and Install Post Insulators | Deviation from approved lifting methodology | Falling material Load shifting Failure of equipment / tackle | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Busbars | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Measure PI to PI | Elevated positions | Fall from elevated positions | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Working at Height (32-418) Eskom Personal Protective Equipment (240-44175132) Life saving rules (32-421) SANS 1200 ALL PARTS Project specific drawings | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Cut Tube to size | Improper material handling | Strains and sprains Fingers caught between | Safety | LTI | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Fit end caps and tack weld | Presence of inert gases e.g. argon | Asphyxiation | Safety | Fatality | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132) | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Lift and place on PI,s Fit PI clamps and Remove lifting equipment | Suspended load | Exposure to falling objects Falling from height | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Earth wire | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drums placement and storage | Rotten Drums | Collapsed drums | Safety | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Place drums on cable Jacks | Unsecured Drums | Drums may fall from jacks | Safety | LTI | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98) | 4 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Remove cover material (Wood) | Fragmented Wood splinters | Contact with splinters | Safety | Medical Incident | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Pulling of Earth wire | Earth wire - Pulled by hand | Ergonomics | Safety | Medical Incident | SHE Specification Form 74 Eskom Personal Protective Equipment (240-44175132 | 3 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Earth wire pulled from structure to structure | Elevated position | Fall from height | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Eskom Personal Protective Equipment (240-44175132) | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Install Pistol Grip Clamps | Clamps failure | Earth wire collapse | Safety | Fatality | SHE Specification Form 74 Medical Surveillance Procedure (240-84733329) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) Eskom Personal Protective Equipment (240-44175132 | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Install Clamps and hook to U bolt | Hardware failure e.g. clamps and hooks | Clamp / hookfalure | Safety | Fatality | SHE Specification Form 74 ) Safe use of lifting machines and lifting tackles (39-98) Employee’s right of refusal to work in an unsafe situation Procedure (240-43848327) Eskom Personal Protective Equipment (240-44175132 | 5 | B | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Tensioning of Earth wire - Fit come along and dynamomete rtensioning | Tensioned Earth wire | Earth wire failure / snapping | Safety | Fatality | SHE Specification Form 74 Safe use of lifting machines and lifting tackles (39-98)Eskom Personal Protective Equipment (240-44175132 | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Security work | Criminals | Gross bodily harm | Safety | Fatality | Eskom Procedure 32-1134 (Physical Access Control at Eskom Premises); Eskom Procedure 32-1133 (Wearing of Ballistic Body Armour by Security Personnel Policy); Training; 240-66963836_ Process Control Manual for Conduct Security Operations | 5 | C | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Dismantling old busbars and insatll new busbars / isolators/ breakers | Cherry Picker | Equipment failure | Safety | Fatality | Eskom Work ar Height Procedure; Proper training of operators; Aduquate supervison; Develop adequate safe work procedute; Conduct adequate risk assessment; | 5 | B | II | Mostly effective | 0 | OHS Act, Act 85 of 1993 and its Regulations
Interaction between persons | COVID 19 (Corona Virus) | Cross infection | Health | Medical Incident | Eskom's Tactical Command Centre (TCC) as well as Emergency Protocols have been activated; Ensure efficient ventilation in the workplace; Work from home; Keep a social distance of 1m to 2m and restrict unnecessary visits / contacts; As far as practicable, avoid touching face; Awareness campaigns; Practice good hygiene; Home / hospital quarantine for the suspected infected; | 4 | C | II | Mostly effective | Responsible Managers | 240-100092892 Outbreak, Pandemic or Epidemic Disaster Response Plan; Disaster Management Act 57 of 2002

## Consequence rating
Consequence criteria
Consequence rating | Description
Health and Safety
1 | No injuries or health effects(near misses)
2 | First-aid treatment case, and temporary discomfort case
3 | Medical treatment case; occupational disease with reversible/non-permanent effect
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL) | gv g
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE | Guide
Fully effective | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventive and address the root causes. Management believes that they are effective and reliable at all times. Reactive controls only support preventive controls.
Mostly effective | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or management has doubts about operational effectiveness and reliability of the controls.
Mostly ineffective | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently operationally very effective. There may be an over-reliance on reactive controls, or some of the controls do not seem correctly designed in that they do not treat root causes.
None | Virtually no credible control. Management has no confidence that any degree of control is being achieved.

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
| Priority | Risk ranking | Action required
| I | Very high | Immediate action required, and these risks to be captured on IRM system.
| II | High | Strong mandatory action required, and these risks to be captured on IRM system.
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.