## Risk Assessment
| Project Risk Assessment |  |  |  | Unique Identifier | 240-51017565
[5 empty] | Revision | Rev.0
[5 empty] | Revision Date | 2019-08-01
Group Commercial Division
Risk # | Hazard | Risk | Consequences | Existing Control Measures | Control Owners | Consequence Rating | Likelihood Rating | Risk Rating
1 | Ineffective incident management | Incidents root causes not identified and mitigated | Reoccurence of incidents | Induction | Induction, , 32-95 Procedure | 4 | 3 | II
| No/insufficient system to manage vehicles and drivers on route to various Eskom sites | Motor Vehicle accidents,Driver fatigue | atalities,Serious Injury , property damage | Induction | Contractor | 4 | 3
|  |  |  | Induction, Contractor SHE Plan | Eskom and Contractors
4 | Failure to manage emergencies | Inability to respond promptely and effectively to emergencies; Industrial actions | Fire, burns,legal contravention;delivery failure resulting in lack of electricity supply | Induction,Eskom Emergency preparedness plan. | Eskom and Contractors | 5 | 3 | II
5 | Failure to appoint as per the OHSAct and legal requirements | Management and employees responsibilities, acountability not clearly defined and understood | Legal contravention | Induction | Eskom and Contractors | 4 | 2 | II
6 | Communicable diseases(COVI19) | Contamination / infections | Sickness,Fatalities | Adhere to national disaster regulations: - Permit to work.PPE, Provision of sanitisers at strategetic points and for the truck driver. Awareness, Mantaining distance between the wookspaces. Induction, | Eskom and Contractors | 5 | 3 | II
7 | Lack of HSE training and awareness of employees | Employees not aware of hazards related to the scope of work | Fatalities and serious injuries | Induction | Eskom and Contractors | 4 | 2 | II
8 | Office Safety( ergonomics, slip trips and falls) | Employee not complying to Eskom requirements | Fatalities, serious injuries, | SHE specification | Eskom and Contractors | 5 | 2 | II
Compiled by:
Name: | Signatures:
Mandla Mkhwanazi