## Risk template
Occupational Health and Safety Baseline risk assessment
Project/Dept: | [9 empty] | Scope of Risk Assessment: |  | GOU |  |  | ROOF REPAIRS PROJECTS | Next Review Date: |  |  |  | Unique identifier | 240-70044602
Date: |  |  |  |  | Prepared by: |  |  | Authorised by: | [11 empty] | Revision: | 0
Revision date:
Refer to Occupational Health and Safety Risk assessment procedure 32-520 | [36 empty] | Yes | Safety | 1 | 1 | F | I
1: List activity | 2: Hazard identification |  | 3: Risk identification | [7 empty] | 4: Assess & Analyse Risks | [5 empty] | 4: Evaluate Risk |  |  |  |  | 5: Reduce & Eliminate Risk | [14 empty] | No | Health | 2 | 2 | P | II
List activity | Hazard nr | Hazard Identification | Risk Nr | Exposed group/employees | Risk Owner | Exposure patterns | Associated risk | Risk type | Conditions(Normal/Abnormal) | Cause(s) of the risk | What are the Consequences? | First determine Consequence and then the Likelihood of that Consequence. |  | Risk Priority Rating | Existing Controls |  | Additional Controls or Tasks Aimed at improving Existing Controls | First determine Consequence and then the Likelihood of that Consequence. |  | Risk Priority Rating | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Initial Target Date | Revised Target Date | Current Status | Independent Verification (i.e. Confirmation that the objectives have been met) |  | Comments | [9 empty] | 3 | 3 | I | III
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | # | A hazard is anything that is likely to lead to an event that will have an adverse impact on achieving an objective. A hazard can pose more than one risk. | # | Who is exposed to the hazard i.e. Employees, visitors, members of the public, etc. | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | A physical event occurs in relation to the hazard | Safety or health | Indicate Yes or No. These short-term changes to conditions that could not be reasonably anticipated e.g. Emergencies | What causes the risk to come into effect? | What is the expected adverse impact on the objective? | Consequence | Likelihood |  | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) | Consequence | Likelihood |  | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Used if, for any reason, a Target Date is revised. Use the Comments field to explain. | Pending, In Progress, Complete | Date Done: | By whom: |  | III | II | I | I | I |  |  |  |  | 4 | 4 | Ti | IV
Driving of vehicles | 1 | Driving on public roads | 1 | Exposed group/employees | Company Owner | Daily | Involved in accident | Safety | Normal | Not adhering to the speed limit,Not paying attention, not farmialr with the road,making use of cellphone, distractions, exposed to unsafe behavours, congested roads, Pedestrians and live stock, Taxi and Truck on the road, Civil unrest. Negligent driving | Fatalities,Injuries, Property damage | 4 | 3 | II | Staff driving vehicles to have national driver's license and Eskom driver's evaluation permit, vehicles in roadworthy condition, only transport authorised staff in vehicle, pre-trip checks,and obeying of all traffic laws, Adherence to life saving rules and drive Cam.Discuss in safety meetings | P | To adhere to the existing controls | 4 | 3 | II | Vehicle Inspections | Employer | National Road Safety Act. ESKOM Procedure 32-93 (Vehicle and driver safety management) . ESKOM Procedure 36-588 (Vehicle safety and transportation management) , Life saving rules
| 2 | Overspeeding of vehicles |  | Exposed group/employees | Company Owner | Daily | Risk of personnel being injured by overspeeding vehicles. Drivers losing control of vehicles. Damaging injury to third parties | Safety | Normal | Not adhering to speed limit by drives | Fatalities,injuries to driver and pedestrians or property damage | 4 | 3 | II | Drivers to adhere to company rules and srtrictly drive at required speed limits on the premises.Driving assessment and Behaviour observations.valid drivers permit and eskom driving permit |  | Securities to monitor movement of vehicles and report overspeeding of vehicles.monitoring of speeding fines.wreckless drivers to be accompanied by Manager/supervisor | 1 | 3 | III | Report on speed violations | Employer | Eskom Procedure and National Traffic Regs
| 3 | Driving without safety belt buckled up |  | Exposed group/employees | Company Owner | Daily | Severe Injuries when involved in an Accident | Safety | Normal | Not adhering to life saving rules | Fatality or severe Injuries | 4 | 3 | II | Life Saving Rules. |  | Adherence to National Traffic Rules | 4 | 3 |  |  | Employer
| 5 | Personnel movement and vehicle within the premises |  | Exposed group/employees | Company Owner | Daily | Personnel are at risk of being bumped by a vehicle or an Accident | Safety | Normal | Faillure of observation by drivers and pedesetrians and unavailability of pedestrian crossings | minor injuries and property damage | 3 | 3 | II | Drivers and pedestrians to ensure good observation is maintained, adherence to pedestrian crossings and speed limits |  | Improve signage ,communication to staff and visibility of pedestrian crossing.adhering to speed limits | 1 | 3 | III |  | Employer | [13 empty] | 5 | III | II | II | I | I
| 6 | Driving | 2 | Exposed group/employees | Company Owner | Daily | Vehicle incidents | Safety | Normal | Not paying attention, risk assement not done, not farmialr with the road,wet roads, making use of cellphone,driver fatique distractions, exposed to unsafe behavours, Less rest periods, Taxi and Truck, Pedestrians and live stock. Negligence and wreckless driving | Injuries, Property damage | 4 | 3 | II | Staff driving vehicles to have national driver's license and Eskom driver's evaluation permit, vehicles in roadworthy condition, only transport authorised staff in vehicle, pre-trip checks,and obeying of all traffic laws, adherence to life saving rules. | P | To adhere to the existing controls | 3 | 2 | III | Incident records | Employer | National Road Safety Act. ESKOM Procedure 32-93 (Vehicle and driver safety management) . ESKOM Procedure 36-588 (Vehicle safety and transportation management) , Life saving rules | [12 empty] | 4 | IV | III | II | I | I
| 17 | Insects | 17 | Exposed group/employees | Company Owner | Daily | Insects bites | Health | Normal | Insects disturbance, Weather conditions | Experience burning, pain, itching, rediness, headache, rash, nausea, vomiting | 3 | 2 | III | OPERATIONAL CONTROL: Individuals to be aware of their status regarding allergies. Seek immediate emergency care for treatment. Treatment may include: Wash the area well with soap and water. Apply a cold or ice pack wrapped in a cloth, or a cold, wet washcloth to the site. Protect against infection. Elevate the site if the bite occured on an arm or leg (to help prevent swelling). PROGRAMME: SHE talks, medical surveillance and situational awereness. | P | Employees to be tested for allergies | 2 | 3 | III |  |  | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) 85 of 1993 Section: 14 GENERAL DUTIES of EMPLOYER Subsection: (a) - (d) read with Section: 21 GENERAL PROHIBITIONS Subsection: (c) |  |  | In Progress | [9 empty] | 3 | IV | III | II | II | I
Working in the field | 7 | Bees | 18 | Exposed group/employees | Company Owner | Daily | Bee stings | Health | Normal | Employees with Anaphylaxis for bee stings are especially at high risk | Allergic reaction ie. pain, redness. swelling, itching, sweating, anxiety, dizziness or fainting. Possible fatality. | 3 | 2 | III | Individuals to be aware of their status regarding allergies and inform rest of group. In the case of a bee sting, make use of a first aider. | P | Employees to confirm for bee allergies | 2 | 2 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) 85 of 1993 Section: 14 GENERAL DUTIES of EMPLOYER Subsection: (a) - (d) read with Section: 21 GENERAL PROHIBITIONS Subsection: (c) |  |  | In Progress | [9 empty] | 2 | IV | IV | III | II | II
| 8 | Snakes | 19 | Exposed group/employees | Company Owner | Daily | Snake bites | Health | Normal | Working in the field, vegetation & weather condition | Shock, fever, fainting, rapid pulse and breathing difficulties and worse case fatality. | 3 | 2 | III | Leave snakes alone. Always be aware of your surroundings. Stay out of tall grass unless you wear thick leather boots.Keep hands and feet out of areas you cannot see. It is very important to try and note what the snake looked like (colour, size etc).... to assist Medical Services or treating physician to establish what anti-venom to administer | P | Employees to be tested for allergies | 2 | 4 | III |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) 85 of 1993 Section: 14 GENERAL DUTIES of EMPLOYER Subsection: (a) - (d) read with Section: 21 GENERAL PROHIBITIONS Subsection: (c) |  |  | In Progress | [9 empty] | 1 | IV | IV | III | III | III
| 9 | Wet or slippery or uneven surfaces | 20 | Exposed group/employees | Company Owner | Daily | Slip, Trip & Fall on wet floors or uneven surfaces | Safety | Normal | Weather conditions,not paying attention & un even surface | Injury | 3 | 3 | II | Obey barricades & sign posting, PPE to be worn, be aware of where you are stepping, clean up spills immediately, Safety talks & Risk Assesment | P | Awareness | 2 | 2 | IV | Records | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) section 8 (1): Employer shall provide and maintain as far as is reasonably practocable a working environment that is safe and without risk to the health of his employees. |  |  | In Progress | [10 empty] | 1 | 2 | 3 | 4 | 5
| 180 | Heavy material - Transformers, Reclosers, Section Links/Fuses, Capasitor, Reculator, Poles, Conductor, A-Frame, Special Arms, Cables, Distrution, Surge Arrestors HV, etc | 187 | Exposed group/employees | Company Owner | Daily | Injury | Safety | NO | Handling of Material - No Supervision | Possible Fatality,Lost time injury and back injuries | 4 | 3 | II | Training/authorisation. correct lifting equipment. Supervision, Q52 Critical Task Procedure. Critical Task Training. Observations. pre-job brief. SHE talks. Inspection certificate. Use of Vehicle Mounted Crane | P | Maintain existing controls | 2 | 1 | IV |  |  | (EPC 32-247, EPC 32-245, EPC 32-249, DPC 34-350, DPC 34-2200, DPC 34-350) | [13 empty] | Likelihood
Storage of Material | 1 | Light material - Stay Rods, Earth Spikes, Insulators Bolts & Nuts, Vibration Dempers, Meterboxes, Distribution boxes, Fuse carriers, Fuse holders, T-Jointa, Lugs, Ferrules, Thimbles, Dead-end Grip, Stay insulators, Fuse Links, Bird Diverters, Foot Plates, Strut Brackets, Binding Straps, Meters, etc. | 188 | Exposed group/employees | Company Owner | Daily | Injury | Safety | NO | Handling of Material - No Supervision | Possible Fatality,Lost time injury and back injuries | 2 | 3 | II | Training/authorisation. correct lifting equipment. Supervision, Q52 Critical Task Procedure. Critical Task Training. Observations. pre-job brief. SHE talks. Inspection certificate. Use of Vehicle Mounted Crane | P | Maintain existing controls | 2 | 1 | IV |  | Employer | (EPC 32-247, EPC 32-245, EPC 32-249, DPC 34-350, DPC 34-2200, DPC 34-350) | [13 empty] | Likelihood
| 2 | Compressor, Jackhammer, Pruner, Chain Saw, Portable Electrical Equipment, Spade & Picks, Compactors, Vehicles, Office Equipment, etc. | 189 | Exposed group/employees | Company Owner | Daily | Injury | Safety | NO | Incorrect Handling of Tools - No Supervision, Improper use of PPE, Man Handling of tools | Possible Fatality,Lost time injury and back injuries | 4 | 3 | II | Training/authorisation. correct lifting equipment. Supervision, Q52 Critical Task Procedure. Critical Task Training. Observations. pre-job brief. SHE talks. Inspection certificate. Use of Vehicle Mounted Crane | P | Maintain existing controls | 2 | 1 | IV | Inventory, inspections, | Employer | (EPC 32-247, EPC 32-245, EPC 32-249, DPC 34-350, DPC 34-2200, DPC 34-350)
Storage of tools | 1 | Oil, Petrol, Diesel, Thinners, Paint etc. | 190 | Exposed group/employees | Company Owner | Daily | Burning/ Asphyxiation | Health | NO | Fire fightng equpment available, Regular inspection of equipment, Training of Fire Fighting, MSDS (Material Safety Data Sheet) | Lost time injury, Medical injury and environmental impact | 4 | 2 | III | Firefighting training, regular inspection of fire fighting equipment, Supervision | P | Maintain existing controls | 2 | 1 | IV | Inventory | Employer | (EPC 32-247, EPC 32-245, EPC 32-249, DPC 34-350, DPC 34-2200, DPC 34-350) | [11 empty] | Yes | Safety | 1 | 1 | F | I
Storage of flammables | 2 | Litter,general construction and maintenance waste | 191 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk | Health | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 2 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | [11 empty] | No | Health | 2 | 2 | P | II
Storage of Waste | 3 | Hazardous waste | 192 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk | Health | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 2 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | [13 empty] | 3 | 3 | I | III
| 4 | Oil contaminated soil and materials | 193 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk | Health | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 2 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | [13 empty] | 4 | 4 | Ti | IV
| 5 | Disposal of printer ink and cartidges | 194 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk | Safety | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 2 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | [13 empty] | 5 | 5 | N
| 6 | Herbicides and contaminated containers | 195 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk | Health | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 4 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993) | [13 empty] | 6
| 7 | Mercury containing lamps and tubes | 196 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk | Health | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 4 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 8 | Waste on site | 197 | Exposed group/employees | Company Owner | Daily | ground-, air-, water pollution - environmental risk. | Health | no | Not following safe working procedures, staff not properly trained, bad housekeeping | Damage to people and the enivronment | 2 | 3 | III | Waste management training, Safe working procedures, applicable PPE, medical surveilance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 9 | Poisonous Substances | 199 | Exposed group/employees | Company Owner | Daily | Poisoning of the body, irritation to skin & eyes | Health | NO | Not wearing PPE (Gloves & Face Mask) | LTI or Medical | 4 | 3 | II | Wearing PPE (Gloves & Face Mask) | F | Maintain existing controls, use appropriate decanting device | 1 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Herbicide Application | 22 | Environmental Hazard | 200 | Exposed group/employees | Company Owner | Daily | Damage to the environment | Safety | NO | Wrong Product & incorrect application | Damaging Fauna & Flora | 1 | 3 | III | Only purchace approved products, provide sufficient training. | F | Maintain existing controls. | 1 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 23 | Diesel fumes and dust | 1 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Making Use of Excavation machine | Respiratory discomfort or complications | 2 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 2 | IV | Incident register/coida reports/ annexure 1 forms | Employer | Hazardous Chemical Substance Regulations 7
EXCAVATION by machinery - digging of holes, trenches |  |  | 2 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, injuries | 4 | 2 | III | Fire fighting equipment available, Regular inspection of equipment, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Inspection register | Employer | Environmental Regulations for Workplaces 9 and SANS 10400
| 24 | Moving machinery eg. Swinging boom | 3 | Exposed group/employees | Company Owner | Daily | Staff struck by moving machinery | Safety | NO | Operation of the machine, No Supervision, Inadequate risk assessment | Possible Fatality,Lost time injury and back injuries | 4 | 3 | II | Keep safe working space around the machine, Supervision,proper risk assessment and Training of staff | P | Maintain existing controls | 2 | 1 | IV | Inspection register | Employer | Construction Regulations 21
| 25 | Noise | 4 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the machine | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
| 26 | Excavation | 5 | Exposed group/employees | Company Owner | Daily | Excavation collapse, Staff falling into excavations, Machine falling into excavation | Safety | NO | No proper supervision, NoShoring of excavation, Improper barrication | Possible fatalities - Back injuries | 5 | 4 | I | Excavate to natural angle of repose - Excavation shored/braced, Sides of excavation fenced off, Supervision. | P | Staff to be trained on excavation work, Appointment of Excavation Supervisors | 2 | 1 | IV | Supervision | Employer | Construction Regulations 11
| 27 | Loading / off- loading of the machine, | 6 | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | Safety | NO | Inadequate Supervision, Not following safe work procedure, Staff not properly trained, Inadequate risk assessment. | Possible property damage - Injury to staff | 4 | 3 | II | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Section 8
| 28 | Underground services | 7 | Exposed group/employees | Company Owner | Daily | Damage to services/ property - Electrocution | Safety | NO | Way leave not up to date | Possible fatalities - Injury to staff | 5 | 4 | I | Way leave | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Construction Regulations 11
| 29 | Repetitive work | 8 | Exposed group/employees | Company Owner | Daily | Carpal tunnel syndrome | Health | NO | No Regular breaks | Hand injuries | 3 | 2 | III | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
EXCAVATION by Hands - digging of holes, trenches | 30 | Improper use of hand tools | 9 | Exposed group/employees | Company Owner | Daily | Damaged hand tools | Safety | NO | No regular inspection of tools, Incorrect hand tools, | Hand injuries, Broken bones | 2 | 3 | III | Safaty Talks, Correct PPE for the job, use of correct tools for the job, tools to be in good condition, pre-job brief,.Use "hand free" approach Regular inspection of hand tools, PPE | P | Maintain existing controls | 2 | 1 | IV | Inspection register | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 31 | Trenches collapsing |  | Exposed group/employees | Company Owner | Daily | Injuries | Safety | NO | No boxing and shoring of excavation | Lost Time Injuries / Fatalaties | 5 | 4 | I | Excavate to natural angle of repose - Excavation shored/braced, Sides of excavation fenced off, Training on excavation work, Supervision. | p | Maintain existing controls, Medical surveillances, Appoint Excavation Supervisor | 2 | 1 | IV | Register, Observations | Employer | Construction Regulations 8 (2)
| 32 | Open trenches | 10 | Exposed group/employees | Company Owner | Daily | Excavation collapse, Staff falling into excavations, | Safety | NO | No proper supervision, NoShoring of excavation, Soil structure, | Possible fatalities - Back injuries | 5 | 2 | II | Excavate to natural angle of repose - Excavation shored/braced, Sides of excavation fenced off, Training on excavation work, Supervision. | P | Excavation Supervisor, Assistant Supervisor | 2 | 1 | IV | Inspection, Supervision | Employer | Construction Regulations 11
| 33 | Underground services | 11 | Exposed group/employees | Company Owner | Daily | Damage to services/ property - Electrocution | Safety | NO | Way leave not up to date | Possible fatalities - Injury to staff | 5 | 4 | I | Way leave | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Construction Regulations 11
| 11 | Noise | 12 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the machine | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
JACKHAMMER - digging of holes, braking up of rocks or stones, pavements | 34 | Vibration | 13 | Exposed group/employees | Company Owner | Daily | Hand body vibration | Health | NO | Operation of the machine | Injuries | 2 | 1 | IV | Rotation of jackhammer operator, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Inspections, Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 35 | Flying debris | 14 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases - Eye injury | Safety | NO | Operation of the machine, Not making use of PPE | Injuries | 2 | 3 | III | Eye protection,Q25 Dust masks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 36 | Diesel fumes and dust | 15 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Operation of the machine, Not making use of PPE | Injuries | 2 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Hazardous Chemical Substance Regulations 7
|  |  | 16 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment, Training on the use of the equipment | P | Maintain existing controls | 2 | 1 | IV | Inspection register | Employer | Environmental Regulations for Workplaces 9 and SANS 10400
| 37 | Awkward posture | 17 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Safety | NO | No Regular breaks | Injuries | 2 | 2 | IV | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 38 | Underground services | 18 | Exposed group/employees | Company Owner | Daily | Damage to services/ property - Electrocution | Safety | NO | No proper way leave, Using incorrect tools | Possible fatalities - Injury to staff | 5 | 2 | II | Way leave | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Construction Regulations 11
| 17 | Noise | 19 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the machine, Not making use of PPE | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
COMPRESSOR ( diesel) - supply jackhammer with air | 18 | Hot compressor exhaust | 20 | Exposed group/employees | Company Owner | Daily | Burns injuries, | Safety | NO | Not | Lost time injury | 4 | 2 | IV | Proper personal protective equipment | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 19 | Heavy lifting | 21 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | No Regular breaks, Not assisting one another | Lost time injury | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 20 | Diesel fumes | 22 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Making use of unserviced equipment | Lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Hazardous Chemical Substance Regulations 7
|  |  | 23 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Faulty equipment, lack of propre maintenance | Damage to equipment and structures, injuries | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment, Training on the use of the equipment | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Environmental Regulations for Workplaces 9 and SANS 10400
| 21 | Explosion / or rupture of the compressor - Pipe bursting | 24 | Exposed group/employees | Company Owner | Daily | Possible property damage - Fatalities, Amputation, Fractures | Safety | NO | Faulty equipment, lack of proper maintenance | Possible fatalities - Injury to staff | 5 | 1 | III | Regular inspections and pressure testing of air receivers, Regular inspection of pipes | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 22 | Noise | 25 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | health | NO | Operation of the machine | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
Generators (petrol)- Providing portable power for drilling and lighting at night / day time | 23 | Heavy lifting | 26 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | No Regular breaks, Not assisting one another | Injuries | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 24 | Petrol fumes | 27 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation |  | NO | Making use of unserviced equipment | Injuries | 2 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Hazardous Chemical Substance Regulations 7
|  |  |  | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment, Training on the use of the equipment | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Environmental Regulations for Workplaces 9 and SANS 10400
| 25 | Noise | 28 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise |  | NO | Operation of the machine | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
Compactors ( diesel /petrol) - For compacting sand after laying cables/ planting poles | 26 | Vibration | 29 | Exposed group/employees | Company Owner | Daily | Hand body vibration | Safety | NO | Operation of the machine | Injuries | 2 | 1 | IV | Rotation of compactor operator, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Inspections, Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 27 | Diesel/Petrol Fumes, Dust | 30 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation |  | NO | Making use of unserviced equipment | Lost time injury | 2 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Hazardous Chemical Substance Regulations 7
|  |  | 31 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment, Training on the use of the equipment | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | ERW 9 and SANS 10400
| 28 | Awkward posture | 32 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort |  | NO | Operation of the machine | Lost time injury | 4 | 2 | IV | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 29 | Flying debris | 33 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases - Eye injury | Safety | NO | Operation of the machine | Lost time injury | 4 | 3 | III | Eye protection, Dust masks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 30 | Heavy lifting | 34 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | Not assisting one another | Lost time injury | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 31 | Lifting heavy equipment | 35 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | Not assisting one another | Lost time injury | 4 | 4 | I | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Vehicle Mounted cranes (diesel) loading and off loading, equipment and planting of poles | 32 | Loading / off- loading of the equipment | 36 | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | Safety | NO | Not services cranes, Inadequate inspection of lifting equipment, Incorrect rigging | Possible property damage - Injury to staff | 4 | 4 | I | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 33 | Working from man cage (Bucket) / Working at a fall risk position | 37 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | Serious injuries, fatalities, | 5 | 4 | I | Legal certificate, Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness, | P | Maintain existing controls | 2 | 1 | IV | Supervision, Observations | Employer | Construction Regulation 8: (Fall Protection). Working at Height Procedure 32-418.
| 34 | Working from man cage (Bucket) / Falling objects | 38 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | People standing underneath the bucket, Hand tools not secured, | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Make sure safe working loads of tool and equipment (conductors, slings ext.). Visual inspections before use. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision, Observations | Employer | Construction Regulation 8: (Fall Protection). Working at Height Procedure 32-418.
| 33 | Working close to live electrical apparatus | 39 | Exposed group/employees | Company Owner | Daily | Burn wounds - Electrocution | Safety | NO | No training of operator, encroaching safety clearance | Serious injuries/fatalities | 5 | 4 | I | Proper PPE, Supervision, Proper training, authorisation for operator, relevant certificate for the aerial bucket, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 34 | Unauthorised personnel operating lifting equipment | 40 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees | Safety | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 5 | 4 | I | Training/authorisation. correct lifting equipment. Supervision, Q52 Critical Task Procedure. Critical Task Training. Observations. pre-job brief. SHE talks. Inspection certificate | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Driven Machinery Regulation 18: (Lifting Machines and Lifting Tackles
| 35 | Diesel fumes | 41 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation |  | NO | Operation of the machine | Lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Hazardous Chemical Substance Regulations 7
|  |  | 42 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | No training of operator, encroaching safety clearance | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available, Regular inspection of equipment, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | ERW 9 and SANS 10400
| 36 | Loading and off loading, equipment | 41 | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | Safety | NO | Not services cranes, Inadequate inspection of lifting equipment, Incorrect rigging, | Possible property damage - Injury to staff | 4 | 4 | I | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 37 | Unauthorised personnel operating lifting equipment | 38 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees | Safety | NO | Lifting machine not lock-out | Serious injuries/fatalities, property damage | 5 | 4 | I | Unauthorised use of lifting machines prohibited. Safety talks. | P | Maintain existing controls | 2 | 1 | IV | Supervision, Observations | Employer | Driven Machinery Regulation 18: (Lifting Machines and Lifting Tackles
Aerial platforms | 37 | Working at heights | 42 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | Serious injuries, fatalities, | 5 | 4 | I | Legal certificate, Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness, | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Construction Regulation 8: (Fall Protection). Working at Height Procedure 32-418.
| 38 | Falling objects | 43 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | People standing underneath the bucket, Hand tools not secured, | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Make sure safe working loads of tool and equipment (conductors, slings ext.). Visual inspections before use. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Construction Regulation 8: (Fall Protection). Working at Height Procedure 32-418.
| 39 | Close proximity with live apparatus | 44 | Exposed group/employees | Company Owner | Daily | Staff exposed to live electrical equipment | Safety | NO | Encroaching within prescribed safety clearance, | Possible property damage, Serious injury, fatalities | 5 | 4 | I | Proper PPE, Supervision, Proper training, authorisation for operator, relevant certificate for the aerial bucket, medical surveillances | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 40 | Noise | 45 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the machine, In adequate maintenance, not using PPE | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
Chain Saw / pruners ( petrol ) - Bush clearing and cutting away branches. | 41 | Vibration | 46 | Exposed group/employees | Company Owner | Daily | Hand body vibration | Health | NO | Operation of the machine | Lost time injury | 4 | 1 | IV | Rotation of operator, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 42 | Flying debris, Saw dust | 47 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases - Eye injury | Safety | NO | Operation of the machine, Not using correct PPE, | Lost time injury | 4 | 3 | III | Special Safety boots, Face shileds, Ear protection,Eye protection, Dust masks, gloves | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 43 | Petrol fumes | 48 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Making use of unserviced equipment, If the petrol mix is not correct | Respiratory discomfort or complications | 2 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 44 |  | 49 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | No proper maintenance, Petrol leaks | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available, Regular inspection of equipment, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Inspection | Employer | ERW 9 and SANS 10400
| 45 | Awkward posture | 50 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No Regular breaks, Incorrect posture | Lost time injury | 4 | 2 | IV | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 46 | Heavy lifting | 51 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | No regular breaks, No clearing your work area | Lost time injury | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 47 | Noise | 52 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the machine, maintanance of the machine, No supervision, No training, | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
Brush cutters ( petrol) -for pruning and bush cutting | 48 | Vibration | 53 | Exposed group/employees | Company Owner | Daily | Hand body vibration | Health | NO | Operation of the machine | Lost time injury | 4 | 1 | IV | Rotation of operator, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervsion | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 49 | Awkward posture | 54 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 2 | 2 | IV | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 50 | Heavy lifting | 55 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | No regular breaks, No clearing your work area | Lost time injury | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 51 | Flying debris, Saw dust | 56 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases - Eye injury |  | NO | Operation of the machine, not using PPE | Lost time injury | 4 | 3 | III | Eye protection, Dust masks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 52 | Petrol fumes | 57 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | No proper maintenance, Petrol leaks | Lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 53 |  | 58 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | No proper maintenance, Petrol leaks | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available, Regular inspection of equipment, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | ERW 9 and SANS 10400
| 54 | Noise | 59 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Lack of proper maintenance | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | NIHLR 6(1) and 7(1)
Electrical/ Hydraulic and battery Drilling machine - drilling holes on wooden poles, steel and concrete walls | 55 | Vibration | 60 | Exposed group/employees | Company Owner | Daily | Hand body vibration | Health | NO | Operation of the machine | Lost time injury | 4 | 1 | IV | Rotation of operator, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision, Medical Suivellance | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 56 | awkward posture, | 61 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regular breaks | Lost time injury | 4 | 2 | IV | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 57 | Flying debris, Dust | 62 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases - Eye injury | Safety | NO | Operation of the machine, not using PPE | Lost time injury | 4 | 3 | III | Eye protection, Dust masks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 58 | Heavy lifting | 63 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Safety | NO | Not assisting one another | Lost time injury | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 59 | Using defective electrical drilling machines | 64 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | No supervision, Lack of maintenance, no propre training | Possible fatalities - Lost time injury | 5 | 4 | I | Routine maintenance of equipment | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 60 | Driving on uneven terrain | 65 | Exposed group/employees | Company Owner | Daily | Whole body vibration, vehicle accident, | Health | NO | Driving of vehicles | Possible fatalities - Lost time injury - Damage to vehicle | 4 | 3 | II | Valid drivers licence, Pre and post trip inspections, regular breaks, Life saving rules, Dangerous goods training, Defensive driving, PDP, Driver with a co driver | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Driving of heavy vehicles (code 14/10/08) for transporting of construction, normal day to day material. | 61 | Long hours driving | 66 | Exposed group/employees | Company Owner | Daily | Fatigue, vehicle accident | Safety | NO | No Regualar breaks, Maintenance of vehicle, Driving alone | Possible fatalities - Lost time injury - Damage to vehicle | 5 | 3 | II | Valid drivers licence, regular rest stops | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 62 | Diesel, Petrol and Oil spills | 67 | Exposed group/employees | Company Owner | Daily | Ground, air and water pollution - lung irritation | Health | NO | Lack of proper maintenance | Environmental damage, lost time injury | 4 | 3 | III | Pre trip inspections, Maintanace of vehicle, | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Hazardous Chemical Substance Regulations 7
|  |  |  | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Lack of proper maintenance, Pipe burst, Vehivle accidents | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available, Regular inspection of equipment, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | ERW 9 and SANS 10400
| 63 | Using Public Roads | 68 | Exposed group/employees | Company Owner | Daily | Property damage, Injury to staff | Safety | NO | Not adhering to traffic rules, inadequate driver training, lack of maintenance of vehicles, Not adhering to life saving rules | Possible fatalities - Lost time injury - Damage to vehicle/property | 4 | 3 | II | Valid drivers licence, Pre and post trip inspections, PDP, Life saving rules | P | Maintain existing controls | 2 | 1 | IV | Incident register/coida reports/ annexure 1 forms | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 64 | Defective / broken hand tools | 69 | Exposed group/employees | Company Owner | Daily | Hand injuries, cuts and bruises , electrocution, fractures, Injuries, Fatalities | Safety | NO | No regular inspection of tools, Incorrect hand tools, | Lost time injuries | 4 | 3 | III | Medical surveillance, training, regular inspections, PPE | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Using of hand tools - day to day task | 65 | Live electricity | 70 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | Incorrect and handling of tools, Inproper storage of tools | Possible fatalities - Lost time injury | 5 | 4 | I | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 66 | Working at heights | 71 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | Not using FAS, Not medically fit, | Serious injuries, fatalities, | 5 | 4 | I | Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 67 | Tools falling from heights | 72 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | Tools not secured | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Proper training, medical surveillance. | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 68 | Noise | 73 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the manchine, Incorrect / lack of PPE, No supervision, no training, incorrect use. | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
Using of Angle grinders - Cutting of steel, stone and bricks | 69 | Vibration | 74 | Exposed group/employees | Company Owner | Daily | Hand body vibration | Health | NO | Operation of the machine, not properly maintained, | Lost time injury | 4 | 1 | IV | Rotation of operator, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Inspections | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 70 | Flying debris, Grinding Dust | 75 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases - Eye injury | Safety | NO | Making use of the machine, Not using PPE | Lost time injury | 4 | 4 | II | Eye protection, Dust masks | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspections | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 71 | Awkward posture | 76 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regular breaks | Lost time injury | 4 | 2 | IV | Regular breaks | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 72 | Heavy equipment | 77 | Exposed group/employees | Company Owner | Daily | Amputation, Fractures, Back, shoulder neck, feet injuries, Blisters. | Safety | NO | Not using correct PPE | Lost time injury | 4 | 4 | II | Leather Gloves, Overall,- Safety Boots, Keep working area safe, Proper handling technique and training, | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Using of Big Bolt cutters- cutting of steel | 73 | Falling Objects | 78 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | Not staying clear of person working overhead | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 74 | Cutting lose ends of conductor | 79 | Exposed group/employees | Company Owner | Daily | Head, hand, arm and eye injuries | Safety | NO | Not staying clear of person working overhead | Injury to staff | 3 | 4 | II | Training, correct PPE, Control cable ends | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 75 | Falling of tools from elevated positions | 80 | Exposed group/employees | Company Owner | Daily | Head injuries, Fractures, Hand, arm and eye injuries, property damage | Safety | NO | Tools not secured | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Proper training, medical surveillance. | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Use of Lifting gear / Kitos/ Turfor | 76 | Heavy equipment. | 81 | Exposed group/employees | Company Owner | Daily | Amputation, Fractures, Back, shoulder neck, feet injuries, Blisters. | Safety | NO | Lack of maintenance | Lost time injury | 3 | 4 | II | Leather Gloves, Overall, Safety Boots, Keep working area safe, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 77 | Equipment under tension/strain | 82 | Exposed group/employees | Company Owner | Daily | Equipment failure | Safety | NO | Lack of maintemnance, Not conducting routine inspections, No test certificates, Not using correct tools for the task at hand | Fatalities, Head injuries, Fractures, Hand, arm and eye injuries, Equipment falling on people in working area | 3 | 5 | II | Proper PPE, Keep safe working space around the operator. Keep working area underneath operator safe. Make sure safe working loads of tool and equipment (conductors, slings ext.). Regular testing of equipment. Visual inspections before use. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 78 | Defective lifting gears. | 83 | Exposed group/employees | Company Owner | Daily | Equipment failure | Safety | NO | Lack of maintemnance, Not conducting routine inspections, No test certificates, Not using correct tools for the task at hand | Fatalities, Head injuries, Fractures, Hand, arm and eye injuries, Equipment falling on people in working area | 3 | 5 | II | Proper PPE, Keep safe working space around the operator. Keep working area underneath operator safe. Make sure safe working loads of tool and equipment (conductors, slings ext.). Regular testing of equipment. Visual inspections before use. Proper training, medical surveillance. | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 79 | Breaking of conductors ,slings and poles under tension. | 84 | Exposed group/employees | Company Owner | Daily | Possible property damage. Injury to staff | Safety | NO | Using incorrect equipment, Inadequate training, Inadequate supervision | Fatalities, Head injuries, Fractures, Hand, arm and eye injuries, Equipment falling on people in working area | 3 | 5 | II | Proper PPE, Keep safe working space around the operator. Keep working area underneath operator safe. Make sure safe working loads of tool and equipment (conductors, slings ext.). Regular testing of equipment. Visual inspections before use. Proper training, medical surveillance |  | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 82 | Ultra violet ARC | 87 | Exposed group/employees | Company Owner | Daily | Arc eyes. Inhaling off hazardous fumes | Health | NO | Lack of proper ventilation, not using PPE, Inadequate training, Lack of supervision | Lost time injury | 3 | 4 | II | Wear welding gloves. Wear welding helmet. Medical surveillances on people that uses it regularly. Only authorised people. Training. Working area to shielded off |  | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | General Safety Regulation 9
Welding using welding machines | 83 | Welding creating heat | 88 | Exposed group/employees | Company Owner | Daily | Burn wounds |  | NO | Conducting welding activites | Lost time injury | 3 | 4 | II | Wear welding gloves. Wear welding helmet. Wear welding apron. Only authorised people. Training. Working area to shielded off | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | General Safety Regulation 9
| 84 | Defective welding machines | 89 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | Lack of proper mainenance | Possible fatalities - Lost time injury | 3 | 4 | II | Regular inspections of welding machine, cabling and clamps | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | General Safety Regulation 9
| 85 | Welding fumes | 90 | Exposed group/employees | Company Owner | Daily | Lower Respiratory diseases. |  | NO | Lack of proper ventilation, not using PPE, Inadequate training, Lack of supervision, lack of training | Lost time injury | 2 | 3 | III | Work in ventilated area. Medical surveillances on people that uses it regularly. Only authorised operators. Training. | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | General Safety Regulation 9
| 86 | Damaged power leads and incorrect earthing | 91 | Exposed group/employees | Company Owner | Daily | Electrical shock . Burning from hot metals and tools. | Safety | NO | Lack of proper maintenance | Lost time injury | 2 | 4 | III | Regular inspections of welding machine, cabling and clamps | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | General Safety Regulation 9
| 93 | Arc flash | 98 | Exposed group/employees | Company Owner | Daily | Burn wounds | Safety | NO | No training of operator, encroaching safety clearance | Possible fatalities - Injury to staff | 4 | 4 | I | Supervision - Proper PPE, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
High voltage operating (11Kv - 132 Kv) . . Maintenance and fault repairs of electrical equipment . Loading and off loading equipment or material (ladders, tool boxes, generators etc) . Climbing of ladders and structures | 94 |  | 99 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Lack of proper maintenance, Pipe burst, Vehivle accidents | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment - Training of staff | P | Maintain existing controls | 2 | 1 | IV |  | Employer | ERW 9 and SANS 10400
| 95 | Walking on uneven terrain | 100 | Exposed group/employees | Company Owner | Daily | Staff falling/tripping | Safety | NO | Environment | Lost time injury | 4 | 3 | II | Obey barricades & sign posting, PPE to be worn, be aware of where you are stepping, clean up spills immediately, Safety talks, | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 96 | Awkward positions | 101 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 3 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 97 | Falling equipment | 102 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | Not staying clear of person working overhead | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Proper training, medical surveillance. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 98 | Working at heights | 103 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | Serious injuries, fatalities, | 5 | 4 | I | Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 99 | Loading / off- loading of the equipment | 104 | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | Safety | NO | Not services cranes, Inadequate inspection of lifting equipment, Incorrect rigging | Possible property damage, Injury to staff | 4 | 4 | I | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 100 | Climbing of ladders and structures | 105 | Exposed group/employees | Company Owner | Daily | Staff falling from ladders or structures | Safety | NO | Working at heights, steps of ladder | Serious injuries, fatalities | 3 | 5 | II | Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV |  | Employer | General Safety Regulation 13A
| 101 | Electrical contact | 106 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | MAKING CONTACT WITH LIVE EQUIPMENT | Possible fatalities, Lost time injury | 5 | 4 | I | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 102 | Electrical equipment failure | 107 | Exposed group/employees | Company Owner | Daily | Electrocution. Burn wounds. Fire. | Safety | NO | Lack of maintenance | Possible fatalities, Lost time injury | 4 | 5 | II | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 103 | Working in hot weather conditions | 108 | Exposed group/employees | Company Owner | Daily | Staff becoming ill, heat stroke | Health | NO | Sun rays | Lost time injury | 4 | 3 | III | Regular breaks, Availability of adequate water | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 104 | Working in cold weather conditions | 109 | Exposed group/employees | Company Owner | Daily | Staff becoming ill | Health | NO | Cold, Wet weather conditions | Lost time | 4 | 3 | III | Regular breaks, PPE | P | Maintain existing controls | 2 | 1 | IV |  | Employer | OCcupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 105 | Heavy equipment. | 110 | Exposed group/employees | Company Owner | Daily | Amputation, Fractures, Back, shoulder neck, feet injuries, Blisters. | Safety | NO | No regular breaks, No clearing your work area .Operation of the machine, not using PPE | Lost time injury | 4 | 4 | II | Leather Gloves, Dusk Mask, Overall, Safety Boots, Keep working area safe, Proper lifting technique and training, medical surveillances. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 106 | Unauthorised personnel operating high voltage equipment | 111 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees | Safety | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 5 | 4 | I | Supervision, Disciplinary action, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 107 | Oil spill | 112 | Exposed group/employees | Company Owner | Daily | Ground, air and water pollution | Health | NO | Lack of maintenace, Faulty equipment | Environmental damage | 3 | 4 | II | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Low voltage Operating (Under 1000volts) | 108 | Unauthorised / untrained personnel operating high voltage equipment | 113 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees | Safety | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 5 | 4 | I | Supervision, Disciplinary action, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 109 | Loading / off- loading of the equipment | 114 | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | Safety | NO | Not services cranes, Inadequate inspection of lifting equipment, Incorrect rigging | Possible property damage - Injury to staff | 4 | 4 | I | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 110 | Noise from transformer | 115 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Not making use of PPE | NIHL | 4 | 4 | II | Supervision, Training, Hearing protection devices medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 111 | Arc flash | 116 | Exposed group/employees | Company Owner | Daily | Burn wounds |  | NO | No training | Possible fatalities - Injury to staff | 4 | 4 | I | Supervision - Proper PPE, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 112 |  | 117 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment - Training of staff | P | Maintain existing controls | 2 | 1 | IV |  | Employer | ERW 9 and SANS 10400
| 113 | Awkward positions | 118 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 4 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 114 | Working at heights | 119 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | Serious injuries, fatalities, | 5 | 4 | I | Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 115 | Working in hot weather conditions | 120 | Exposed group/employees | Company Owner | Daily | Staff becoming ill, heat stroke | Health | NO | Sun rays | Lost time injury | 4 | 3 | III | Regular breaks, Availability of adequate water | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 116 | Working in cold weather conditions | 121 | Exposed group/employees | Company Owner | Daily | Staff becoming ill | Health | NO | Cold, Wet weather conditions | Lost time | 4 | 3 | III | Regular breaks, PPE | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 117 | Faulty electrical equipment | 122 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | Lack of maintenace | Possible fatalities - Lost time injury | 5 | 4 | I | Regular service, maintenance and inspection of equipment | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 118 | Falling equipment | 123 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | Not staying clear of person working overhead | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 119 | Heavy lifting | 124 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Health | NO | No Regular breaks, Not assisting one another | Lost time injury | 4 | 5 | I | Regular breaks - Safety shoes | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 120 | Electrical equipment failure | 125 | Exposed group/employees | Company Owner | Daily | Electrocution. Burn wounds. Fire. | Safety | NO | Lack of maintenance | Possible fatalities, Lost time injury | 4 | 5 | II | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 121 | Hydraulic oil and diesel spills | 126 | Exposed group/employees | Company Owner | Daily | Ground, air and water pollution - lung irritation | Health | NO | Lack of maintenace, faulty equipment | Environmental damage, lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Hazardous Chemical Substance Regulations 7
Live work Medium Voltage ( 11Kv - 33Kv) 1, Inspection of the live electrical equipment . 2, Maintenance and fault repairs of live electrical equipment 3, Loading and off loading equipment or material ( ladders, tool boxes, generators etc) 4, Climbing of ladders and structures , 5, Working from the live line aerial device. |  |  | 127 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Lack of maintenace, faulty equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment - Training of staff | P | Maintain existing controls | 2 | 1 | IV |  | Employer | ERW 9 and SANS 10400
| 122 | Unauthorised / untrained personnel operating high voltage equipment | 128 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees | Safety | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 5 | 4 | I | Supervision, Disciplinary action, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 123 | Noise from the truck | 129 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the truck, lack of maintanance of the truck | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer | Noise Induced Hearing Loss Regulations 6(1) and 7(1)
| 124 | Extreme hot conditions. | 130 | Exposed group/employees | Company Owner | Daily | Staff becoming ill, heat stroke | Health | NO | Sun rays | Lost time injury | 4 | 3 | III | Regular breaks, Availability of adequate water | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 125 | Live electricity | 131 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | Incorrect and handling of tools, Inproper storage of tools | Possible fatalities - Lost time injury | 5 | 4 | I | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 126 | Diesel fumes and dust | 132 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Operation of the machine, Not making use of PPE | Lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Hazardous Chemical Substance Regulations 7
| 127 |  | 133 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment | P | Maintain existing controls | 2 | 1 | IV |  | Employer | ERW 9 and SANS 10400
| 128 | Loading / off- loading of the equipment | 134 | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | Safety | NO | Not services cranes, Inadequate inspection of lifting equipment, Incorrect rigging | Possible property damage - Injury to staff | 4 | 4 | I | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 129 | Electrical equipment failure | 135 | Exposed group/employees | Company Owner | Daily | Electrocution. Burn wounds. Fire. | Safety | NO | Lack of maintenance | Possible fatalities, Lost time injury | 5 | 4 | I | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 130 | Electrical contact | 136 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | MAKING CONTACT WITH LIVE EQUIPMENT | Possible fatalities - Lost time injury | 5 | 4 | I | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 131 | Walking on uneven terrain | 137 | Exposed group/employees | Company Owner | Daily | Staff falling/tripping | Safety | NO | Environment | Lost time injury | 4 | 3 | II | Obey barricades & sign posting, PPE to be worn, be aware of where you are stepping, clean up spills immediately, Safety talks, | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 132 | Working at heights | 138 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | Serious injuries, fatalities, | 5 | 4 | I | Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 133 | Faulty electrical equipment | 139 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | Lack of maintenace | Possible fatalities - Lost time injury | 5 | 4 | I | Regular service, maintenance and inspection of equipment | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 134 | Awkward positions | 140 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 4 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 135 | Falling equipment. | 141 | Exposed group/employees | Company Owner | Daily | Injury to personnel and property damage | Safety | NO | Not staying clear of person working overhead | Inj | 5 | 4 | I |  | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 136 | Arc flash | 142 | Exposed group/employees | Company Owner | Daily | Burn wounds | Safety | NO | No training | Possible fatalities - Injury to staff | 4 | 4 | I |  | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 137 | Unauthorised personnel operating live work on high voltage equipment | 143 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees | Safety | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 5 | 4 | I | Supervision, Disciplinary action, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 138 | Unauthorised / untrained personnel operating high voltage equipment | 144 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to bystanders/employees |  | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 3 | 5 | II | Supervision, Disciplinary action, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Live work Low Voltage ( Under 1000 Volts) |  |  |  | Exposed group/employees | Company Owner | Daily | [15 empty] | Employer
|  |  |  | Exposed group/employees | Company Owner | Daily | [15 empty] | Employer
| 139 | Noise from the truck | 145 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Operation of the truck, lack of maintanance of the truck | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer
| 140 | Extreme hot conditions | 146 | Exposed group/employees | Company Owner | Daily | Staff becoming ill, heat stroke | Health | NO | Sun rays | Lost time injury | 4 | 3 | III | Regular breaks, Availability of adequate water | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 141 | Heavy lifting, | 147 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Health | NO | No regular breaks, No clearing your work area | Lost time injury | 4 | 4 | II | Regular breaks, Safety shoes | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 142 | Electrical contact | 148 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | MAKING CONTACT WITH LIVE EQUIPMENT | Possible fatalities - Lost time injury | 5 | 4 | I | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 143 | Electrical equipment failure | 149 | Exposed group/employees | Company Owner | Daily | Electrocution. Burn wounds. Fire. | Safety | NO | Lack of maintenance | Possible fatalities, Lost time injury | 4 | 5 | II | Proper PPE, Regular testing of equipment. Proper training, medical surveillance. Authorisation. Mental alertness and physical ability. | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 144 | Walking on uneven terrain | 150 | Exposed group/employees | Company Owner | Daily | Staff falling/tripping | safety | NO | Environment | Lost time injury | 4 | 3 | II | Obey barricades & sign posting, PPE to be worn, be aware of where you are stepping, clean up spills immediately, Safety talks, | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 145 | Awkward positions | 151 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 4 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 146 | Falling equipment | 152 | Exposed group/employees | Company Owner | Daily | Objects falling on staff, other equipment | Safety | NO | Not staying clear of person working overhead | Possible property damage - Injury to staff | 5 | 4 | I | Proper PPE, Keep working area underneath operator safe. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 147 | Faulty electrical equipment | 153 | Exposed group/employees | Company Owner | Daily | Electrocution | Safety | NO | Lack of maintenace | Possible fatalities - Lost time injury | 5 | 4 | I | Regular service, maintenance and inspection of equipment | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Electrical Machinery Regulation 8: (Portable Electric Tools).
| 148 | Working at heights | 154 | Exposed group/employees | Company Owner | Daily | Falling from heights | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | Serious injuries, fatalities, | 5 | 4 | I | Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Construction Regulation 8: (Fall Protection). Working at Height Procedure 32-418.
| 149 | Diesel fumes and dust | 155 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Operation of the machine, Not making use of PPE | Lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 150 |  | 156 | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 151 | Unauthorised personnel operating live work on high voltage equipment | 157 | Exposed group/employees | Company Owner | Daily | Property/lifting equipment damage, Serious injuries/fatalities to by bystanders/employees | Safety | NO | No training, Unauthorised personel, No Supervision, Not following Safe work procedures | Serious injuries/fatalities, property damage | 5 | 4 | I | Supervision, Disciplinary action, Proper training and authorisation | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 153 | Awkward position | 158 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 3 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer
Planting of poles by hand | 154 | Underground electrical cables and other underground services | 159 | Exposed group/employees | Company Owner | Daily | Damage to services/ property - Electrocution | Safety | NO |  | Possible fatalities - Injury to staff | 3 | 4 | II | Way leave | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 155 | Lifting heavy poles | 160 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Health | NO | Not assisting one another | Lost time injury | 4 | 2 | III | Safety Boots, Gloves, Regular breaks, Proper lifting technique and training, medical surveillances | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 156 | Dust | 161 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Impact of poles on the ground | Lost time injury | 2 | 3 | III | Dust mask, Proper PPE, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer
Planting of poles using cranes | 157 | Noise | 162 | Exposed group/employees | Company Owner | Daily | Staff exposed to excessive noise | Health | NO | Truck iddling | NIHL | 4 | 2 | III | Supervision, Training, Hearing protection devices medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision/ Medical Surveillance Measurements | Employer
| 158 | Diesel fumes and dust | 163 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Operation of the machine, Not making use of PPE | Lost time injury | 4 | 3 | III | Supervision and regular breaks, dust mask, Proper PPE, proper training and authorisation, medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer
|  |  |  | Exposed group/employees | Company Owner | Daily | Fire | Safety | NO | Making use of unserviced equipment | Damage to equipment and structures, Lost time injury | 4 | 2 | III | Fire fighting equipment available - Regular inspection of equipment | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 159 | Awkward position | 164 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 4 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 160 | Defective / broken hand tools | 165 | Exposed group/employees | Company Owner | Daily | Hand/foot injuries, cuts and bruises | safety | NO | No regular inspection of tools, Incorrect hand tools, | Lost time injury | 4 | 3 | III | Regular inspections of hand tools - PPE | P | Maintain existing controls | 2 | 1 | IV |  | Employer
Falling of heavy pole | 161 | Awkward position | 166 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regular breaks | Lost time injury | 4 | 5 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 162 | Dust | 167 | Exposed group/employees | Company Owner | Daily | Air pollution - Lung irritation | Health | NO | Impact of poles on the ground | Lost time injury | 4 | 3 | III | Dust mask - Proper PPE - medical surveillance | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 163 | Heavy lifting | 168 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Health | NO | No regular breaks, No clearing your work area | Lost time injury | 4 | 5 | II | Regular breaks - Safety shoes | P | Maintain existing controls | 2 | 1 | IV |  | Employer
Handling; Climbing and working on ladders | 164 | Awkward position | 169 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort | Health | NO | No regualr breaks | Lost time injury | 4 | 4 | II | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 165 | Working at height | 170 | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Health | NO | No proper guard rails around working platforms, Not using Safety harness, | Lost time injury | 4 | 4 | II | Regular breaks - Safety shoes | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Construction Regulation 8: (Fall Protection Plan). Working at Height Procedure 32-418.
| 166 | Fall from height | 171 | Exposed group/employees | Company Owner | Daily | Fractures, Back, shoulder neck, feet injuries, | Health | NO |  | Lost time injury | 4 | 4 | II | Leather Gloves - Dusk Mask - Overall - Safety Boots - Keep working area safe - Proper lifting technique and training - medical surveillances. | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 167 | Awkward position | 172 | Exposed group/employees | Company Owner | Daily | Falling objects or personnel falling off scaffold | Safety | NO | No regualr breaks | Serious injuries, fatalities, | 5 | 4 | I | Safe working platforms, Supervision, Training of staff, Safety harnesses, Medical certificates of fitness | P | Maintain existing controls | 2 | 1 | IV |  | Employer | Construction Regulation 8: (Fall Protection Plan). Working at Height Procedure 32-418.
Erecting and working on scaffolds |  |  |  | Exposed group/employees | Company Owner | Daily | [15 empty] | Employer
|  | Working at height | 173 | Exposed group/employees | Company Owner | Daily | Wet or slippery scaffold. Falling, slipping and tripping on or from the scaffold | Safety | NO | No proper guard rails around working platforms, Not using Safety harness, | injuries and possible fatalities | 4 | 4 | II | Regular breaks - Safety shoes | P | Maintain existing controls | 2 | 1 | IV |  | Employer
|  | Heavy lifting | 174 | Exposed group/employees | Company Owner | Daily | Back, shoulder neck, feet injuries/discomfort |  | NO | No regular breaks, No clearing your work area | injuries and possible fatalities | 4 | 2 | III | Regular breaks | P | Maintain existing controls | 2 | 1 | IV |  | Employer
| 168 | Insects | 175 | Exposed group/employees | Company Owner | Daily | Insects bites | Health | NO | Insects in area | Experience burning, pain, itching, rediness, headache, rash, nausea, vomiting | 3 | 3 | II | OPERATIONAL CONTROL: Individuals to be aware of their status regarding allergies. Seek immediate emergency care for treatment. Treatment may include: Wash the area well with soap and water. Apply a cold or ice pack wrapped in a cloth, or a cold, wet washcloth to the site. Protect against infection. Give acetaminophen for pain. Elevate the site if the bite occured on an arm or leg (to help prevent swelling). PROGRAMME: SHE talks, OE, medical surveillance and situational awereness. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | OHSACT 8(1) Employer shall provide and maintain, as far as reasonably practicable, a working environment that is safe and without risk to the health of his employees.
Working in the field | 169 |  | 176 | Exposed group/employees | Company Owner | Daily | Bee Stings | Health | NO | Bee's in the area | Allergic reactions, swelling,itching, sweating, dizziness, fainting and possible fatality. | 3 | 3 | II | Safety talks, Risk assessment, Situational awareness, Individuals to be aware of their status. Share status to their collegues, Medical siuvellannce | P | Maintain existing controls | 2 | 1 | IV |  | Employer | OHSACT 8(1) Employer shall provide and maintain, as far as reasonably practicable, a working environment that is safe and without risk to the health of his employees.
| 170 | Bit by Snakes | 177 | Exposed group/employees | Company Owner | Daily | Snake bites | Safety | NO | Snakes/dogs in the area | Shock, fever, fainting, rapid pulse and breathing difficulties and worse case fatality. | 3 | 3 | II | Call for emergency assistance immediately. While waiting for emergency assistance: Wash the bite with soap and water. Immobilize the bitten area and keep it lower than the heart. Cover the area with a clean, cool compress or a moist dressing to minimize swelling and discomfort. Monitor breathing and heart rate. Remove all rings, watches, and constrictive clothing, in case of swelling. Note the time of the bite so that it can be reported to an emergency room physician if needed. Do not apply a tourniquet. Leave snakes alone. Always be aware of your surroundings. Stay out of tall grass unless you wear thick leather boots.Keep hands and feet out of areas you cannot see. SHE talks. It is very important to try and note what the snake looked like (colour, size etc).... to assist Medical Services or treating physician to establish what anti-venom to administer. | P | Maintain existing controls | 2 | 1 | IV |  | Employer | OHSACT 8(1) Employer shall provide and maintain, as far as reasonably practicable, a working environment that is safe and without risk to the health of his employees.
| 171 | Wet or slippery or uneven surfaces | 178 | Exposed group/employees | Company Owner | Daily | Slipping on wet floors or uneven surfaces | Safety | NO | Weather conditions | Injury | 4 | 3 | II | Obey barricades & sign posting, PPE to be worn, be aware of where you are stepping, clean up spills immediately, Safety talks, |  | Maintain existing controls | 2 | 1 | IV |  | Employer
| 193 | Uncontrolled usage | 201 | Exposed group/employees | Company Owner | Daily | Injuries - Cuts, bruises & wounds | Safety | NO | Failure to correctly operate, inspections and not wearing correct PPE | LTI or Medical | 4 | 2 | III | Use equipment as per safe working instructions, Wear correct PPE | F | Maintain existing controls, On Job Observations | 1 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
USING PORTABLE ELECTRICAL TOOLS | 194 | Damaged cords & equipment | 202 | Exposed group/employees | Company Owner | Daily | Electrical shocks | Safety | NO | No proper maintenance & inspections | Fatality, LTI or Medical | 5 | 3 | II | Periodical Inspections & Maintenance | F | Maintain existing controls | 1 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 195 | Using non-calibrated tools | 203 | Exposed group/employees | Company Owner | Daily | Damaging Equipment, Injuries | Safety | NO | Not calibrating equipmenmt on time as per schedule or due date |  | 5 | 3 | II | Periodical Inspections & Maintenance | F | Maintain existing controls | 1 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 196 | Rotating and moving Machinary | 204 | Exposed group/employees | Company Owner | Daily | Damaging Equipment, Injuries | Safety | NO | Failure to correctly operate and not wearing correct PPE | LTI or Medical | 4 | 3 | II | Use equipment as per safe working instructions, Wear correct PPE | F | Maintain existing controls | 1 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 8 | Physical material handling |  | Exposed group/employees | Company Owner | Daily | Equipment falling on staff, other equipment | H&S | NO | Weight and awkward material to handle | Possible property damage, Injury to staff | 4 | 3 | II | Keep safe working space around the machine, Supervision, Training of staff | P | Maintain existing controls | 2 | 1 | IV | Capturing and monitoring incidents and reported near misses | Employer | OHSACT 8(1) Employer shall provide and maintain, as far as reasonably practicable, a working environment that is safe and without risk to the health of his employees.
Stringing and Tensioning of conductors | 9 | Pinching of fingers between Trestle and conductor drun |  | Exposed group/employees | Company Owner | Daily | Hand and arm injuries | Health | NO | Poor engineering /design | Strains / sprains/leg/ back injuries | 4 | 3 | II | Redesign the brake mechanism on the conductor drum and Trestle. | P | Maintain existing controls | 2 | 2 | IV | Capturing and monitoring incidents and reported near misses | Employer | OHSACT 8(1) Employer shall provide and maintain, as far as reasonably practicable, a working environment that is safe and without risk to the health of his employees.
| 10 | Working at height |  | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot injuries | Health | NO | Working from a fall risk position and in awkward positions. | Lost time injury/Fatality | 5 | 3 | II | Inspect FAS before use,hook up to suitable anchor point. | P | Maintain existing controls | 2 | 1 | IV | Planned task observations and Behavioral Observations | Employer | Construction Regulation 8: (Fall Protection Plan). Working at Height Procedure 32-418.
| 11 | Fall from height |  | Exposed group/employees | Company Owner | Daily | Fractures, Back, shoulder neck, feet injuries, | Health | NO | Working from a fall risk position and in awkward positions. | Lost time injury/Fatality | 5 | 3 | II | Leather Gloves - Overall - Safety Boots -Hardhat - Proper training - medical surveillances. | P | Maintain existing controls | 2 | 1 | IV | Planned task observations and Behavioral Observations | Employer | Construction Regulation 8: (Fall Protection Plan). Working at Height Procedure 32-418.
| 12 | Walking on uneven terrain |  | Exposed group/employees | Company Owner | Daily | Staff falling/tripping | Health | NO | Environment | Lost time injury | 4 | 3 | II | PPE to be worn, be aware of where you are stepping, Safety talks, | P | Maintain existing controls | 2 | 1 | IV | Capturing and monitoring incidents and reported near misses | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 13 | Equipment under tension/strain |  | Exposed group/employees | Company Owner | Daily | Equipment failure | H&S | NO | Lack of maintemnance, Not conducting routine inspections, No test certificates, Not using correct tools for the task at hand | Fatalities, Head injuries, Fractures, Hand, arm and eye injuries, Equipment falling on people in working area | 5 | 3 | II | Proper PPE, Keep safe working space around the operator. Keep working area underneath operator safe. Make sure safe working loads of tool and equipment (conductors, slings ext.). Regular testing of equipment. Visual inspections before use. Proper training, medical surveillance | P | Maintain existing controls | 2 | 1 | IV | Supervision, Inspection | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
| 14 | Repetative motion |  | Exposed group/employees | Company Owner | Daily | Arm and joint injuries | Safety | NO | Awkward position/Fatigue | Arm and joint injuries | 3 | 3 | II | Take regular breaks and share the workload. | P | Maintain existing controls | 2 | 1 | IV | Supervision | Employer | Occupational Health and Safety Act, 1993 (Act No. 85 of 1993)
Workiing with climbing irons | 15 | Working at a fall risk position |  | Exposed group/employees | Company Owner | Daily | Fatigue, Back, shoulder, neck, foot, leg injuries | Safety | NO | Lack of Training,no Supervision, inadequate risk assessment | Lost time injury | 4 | 4 | I | Regular breaks - Safety shoes | P | Maintain existing controls, medical surveillances. | 2 | 1 | IV | Observations | Employer | Construction Regulation 8: (Fall Protection Plan). Working at Height Procedure 32-418.

## Consequence rating
Consequence criteria
Consequence rating | Description
Health and Safety
1 | No injuries or health effects(near misses)
2 | First-aid treatment case, and temporary discomfort case
3 | Medical treatment case; occupational disease with reversible/non-permanent effect
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
Score | Descriptor | Safety and Environment | Occupational Hygiene
|  |  | Exposure | Probability of exceeding OEL
1 | Highly unlikely | § <5% probability | Rare(once a year) | No exposure (or exposure < 10% of OEL)
§ occurrence requires exceptional circumstances
§ exceptionally unlikely, even in the long-term future
§ only occurs as a “100-year event”
2 | Unlikely | § >5% probability, or | Short periods of time, a few times per day / intermittent (once in 6, 3 or a month) | Low exposure (<50% of OEL)
§ may occur but not anticipated, or
§ could occur in “years to decades”
3 | Possible | § >20% probability, or | Continuous for between 1 and 2 hours (often / weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure >/-OEL
§ may occur shortly but a distinct probability it will not, or
§ could occur within “months to year\s”
4 | Likely | § >70% probability, or | Continuous for between 2 and 4 hours (frequent / daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ balance of probability it will occur, or
§ could occur within “weeks to months”
5 | Unavoidable | § 99% probability, or | Continuous for 8 hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C
§ impact is occurring now, or
§ could occur within “days to weeks”

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE |  | Guide
Fully effective | F | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventative and address the root causes and Management believes that they are effective and reliable at all times. Reactive controls only support preventative controls.
Partially effective | P | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or Management has doubts about operational effectiveness and reliability.
Ineffective | I | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently very effective. There may be an over-reliance on reactive controls. OR Some of the controls do not seem correctly designed in that they do not treat root causes, those that are correctly designed are operating effectively.
Totally ineffective | Ti | Significant control gaps. Either controls do not treat root causes or they do not operate at all effectively. Controls, if they exist are just reactive.
None | N | Virtually no credible control. Management has no confidence that any degree of control is being achieved due to poor control design and/or very limited operational effectiveness.

## Risk matrix
Risk matrix
Consequences | 6 | III | II | I | I | I
| 5 | III | II | II | I | I
| 4 | IV | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | 1 | 2 | 3 | 4 | 5
Likelihood
I |  | Very High
II |  | High
III |  | Medium
IV |  | Low