## Compatibility Report (hidden)
Compatibility Report for Witfontein Ext. 54 Services Payment Certificate NO 1..xls
Run on 9/27/2012 10:41
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 1

## Preambles (hidden)
MAJUBA ROADS REHABILITATION PROJECT
ECC3 Option B
Pricing assumptions: Option B
1. How work is priced and assessed for payment
Clause 11 in NEC3 Engineering and Construction Contract (ECC3) Option B states:
Identified and defined terms | 11
| 11.2 | (21) The Bill of Quantities is the bill of quantities as changed in accordance with this contract to accommodate implemented compensation events and for accepted quotations for acceleration.
(28) The Price for Work Done to Date is the total of
· the quantity of the work which the Contractor has completed for each item in the Bill of Quantities multiplied by the rate and
· a proportion of each lump sum which is the proportion of the work covered by the item which the Contractor has completed.
Completed work is work without Defects which would either delay or be covered by immediately following work.
(31) The Prices are the lump sums and the amounts obtained by multiplying the rates by the quantities for the items in the Bill of Quantities.
This confirms that Option B is a re-measurement contract and the bill comprises only items measured using quantities and rates or stated as lump sums. Value related items are not used. Time related items are items measured using rates where the rate is a unit of time.
2. Function of the Bill of Quantities
Clause 55.1 in Option B states, “Information in the Bill of Quantities is not Works Information or Site Information”. This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Bill, but in the Works Information. This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Bill of Quantities. The Bill of Quantities is only a pricing document.
3. Guidance before pricing and measuring
Employers preparing tenders or contract documents, and tendering contractors are advised to consult the sections dealing with the bill of quantities in the NEC3 Engineering and Construction Contract Guidance Notes before preparing the bill of quantities or before entering rates and lump sums into the bill.
There is no general provision in Option B for payment for materials on Site before incorporation into the works. If secondary Option X14 Advanced payment has not been used then the tendering contractor may obtain the same effect by inserting appropriate items in the method related charges where the method of measurement allows, or alternatively making allowance in the rates of the bill of quantities for the financing of Plant and Materials until they are incorporated in the works.
When compensation events arise, the default position is that the Bill of Quantities is not used to calculate the cost effect of the event. Defined Cost and the resulting Fee is used and Defined Cost includes all components of cost which the Contractor is likely to incur, including so called P & G items. Rates and lump sums from the Bill of Quantities, or from any other source, may be used instead of Defined Cost and the Fee only if the Contractor and Project Manager agree. If they are unable to agree, then Defined Cost plus Fee is used.
4. Measurement and payment
4.1. Symbols
The units of measurement described in the Bill of Quantities are metric units abbreviated as follows:
Abbreviation | Unit
% | percent
h | hour
ha | hectare
kg | kilogram
kl | kilolitre
km | kilometre
km-pass | kilometre-pass
kPa | kilopascal
kW | kilowatt
l | litre
m | metre
mm | millimetre
m2 | square metre
m2-pass | square metre pass
m3 | cubic metre
m3-km | cubic metre-kilometre
MN | mega newton
MN.m | mega newton-metre
MPa | mega pascal
No. | number
sum | Lump sum
t | tonne (1000kg)
4.2 General assumptions
4.2.1 | Unless otherwise stated, items are measured net in accordance with the drawings, and no allowance has been made in the quantities for waste.
4.2.2 | The Prices and rates stated for each item in the Bill of Quantities shall be treated as being fully inclusive of all work, risks, liabilities, obligations, overheads, profit and everything necessary as incurred or required by the Contractor in carrying out or providing that item.
4.2.3 | An item against which no Price is entered will be treated as covered by other Prices or rates in the bill of quantities.
4.2.4 | The quantities contained in the Bill of Quantities may not be final and do not necessarily represent the actual amount of work to be done. The quantities of work assessed and certified for payment by the Project Manager at each assessment date will be used for determining payments due.
4.2.5 | The short descriptions of the items of payment given in the bill of quantities are only for the purposes of identifying the items. Detail regarding the extent of the work entailed under each item is provided in the Works Information.
4.3 Amplification of or assumptions about measurement items
4.3.1 | All measured items will be priced and paid in the currency of the contract (ZAR) with no adjustments for foreign exchange variations
4.3.2 | There are no measurement items for not disestablishing the facilities that the Contractor establishes for the Project Manager’s use and not disestablish on Completion as the facilities continues to be used by the Project Manager. Ownership of such facilities passes to the Employer on Completion and the Contractor must procure and price the relevant items appropriately

## Breakdown
8 |  | SECTION 1 : NLEPDS FENCING
|  | Lethabo P/S Solar PV Plant Fence | UoM | Quantity | Rate | Amount
8.2 | SABS 1200 C | SITE CLEARANCE
8.2.1 |  | Clear & grub fence (1000mm width) | m² | 23358
8.3 | SABS 1200 DM | CIVIL WORKS
EXCAVATION
8.3.1 |  | Excavate 500x500x650mm deep Straining post pit | m3 | 381
8.3.2 |  | Excavate 200x600mm deep anti-burrowing | m3 | 2534
CONCRETE
8.3.3 |  | 20MPa Mass concrete
|  | Posts | m3 | 381
|  | Anti-burrowing | m3 | 2534 |  |  | 0
8.4 | SABS 1220 DM | FENCING
HIGH RISK SECURITY MESH FENCING
8.4.1 |  | The fence will be dressed with an Y electric wire on top
8.4.2 |  | 2,4m Post @10m c/c | no | 1558
8.4.3 |  | 2,4m Poly*** mesh fence | m | 15572
8.4.4 |  | Non-Lethal Electric fence | m | 7786 |  |  | 0
GATES
8.4.5 |  | Pedestrian gate | no. | 2
8.4.6 |  | 8m wide motorized mesh fence gate for vehicle | no. | 2 |  |  | 0
|  | TOTAL SECTION 1 |  |  |  | 0
#REF!
#REF!
#REF!
#REF!
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40mm Thick continuously graded TPA-medium asphalt surface with 60/70 Pen.Bitumen as binder (5,5% bitumen content)

## Summary
LETHABO P/S SOLAR PV PLANT NLEPDS FENCE |  |  |  | Date: 26/09/2022
Item | Description | Qty | Rate | Amount
1 | Preliminaries & General
2 | Site Clearance | 1
3 | Civil Works | 1
4 | 3-Tier Security Fence | 1
5 | Gates | 1
6 | General electric requirements | 1
7 | O&M Training | 1
8 | Spares | 1
| SUB-TOTAL |  |  | 0
9 | Add: Contingency @15% |  |  | 0
| TOTAL |  |  | 0
10 | Add : VAT @15% |  |  | 0
| GRAND TOTAL (incl. VAT) |  |  | 0 | 0