NEC3 Engineering and Construction

Short Contract (ECSC3)

| A contract between | Eskom Holdings SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and |  |  |
| for | Waterproofing repairs on the surface building roof at Drakensberg Pumped Storage Scheme |  |
| Contents: | Compiled in accordance with CIDB Standard for Uniformity in Construction Procurement (May 2010 amendments) | Page No. |
| Part C1 | Agreements & Contract Data |  |
|  | C1.1 Form of Offer and Acceptance | 2 |
|  | C1.2 Contract Data provided by the Employer | 5 |
|  | C1.2 Contract Data provided by the Contractor | 14 |
| Part C2 | Pricing Data |  |
|  | C2.1 Pricing assumptions | 15 |
|  | C2.2 Price List | 16 |
| Part C3 | Scope of Work |  |
|  | C3.1 Works Information | 17 |
| Part C4 | Site Information | 15 |
| Documentation prepared by: | Zandile Mnukwa |  |

C1 Agreements & Contract Data

# C1.1 Form of Offer and Acceptance

## Offer

The Employer, identified in the Acceptance page signature block on the next page, has solicited offers to enter into a contract for the procurement of:

# Waterproofing repairs on the surface building roof at Drakensberg Pumped Storage Scheme

The tenderer, identified in the signature block below, having examined the documents listed in the Tender Data and addenda thereto as listed in the Tender Schedules, and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the Contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| The offered total of the Prices exclusive of VAT is | R[●] |
| --- | --- |
| Value Added Tax @ 15% is | R[●] |
| The offered total of the Prices inclusive of VAT is | R[●] |
| (in words) [●] |  |

This Offer may be accepted by the Employer by signing the form of Acceptance overleaf and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: | (Insert name and address of organisation) |  |  |  |
| Name & signature of witness |  |  | Date |  |
| Tenderer’s CIDB registration number: |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an Agreement between the Employer and the tenderer upon the terms and conditions contained in this Agreement and in the Contract that is the subject of this Agreement.

The terms of the Contract, are contained in:

Part 1	Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part 2	Pricing Data

Part 3	Scope of Work: Works Information

Part 4	Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule, which must be signed by the duly authorised representative(s) for both parties.

The tenderer shall within one week of receiving a completed copy of this Agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this Agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this Agreement.

Notwithstanding anything contained herein, this Agreement comes into effect on the date when the tenderer receives one fully completed and signed copy of this document, including the Schedule of Deviations (if any) together with all the terms of the contract as listed above.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer | (Insert name and address of organisation) Eskom Holdings SOC Ltd c/o Peaking Generation 15 Pasita Street Rosenpark Bellville |  |  |  |
| Name & signature of witness |  |  | Date |  |

Note: 	If a tenderer wishes to submit alternative tender offers, further copies of this document may be used for that purpose, duly endorsed, ‘Alternative Tender No. _____ ‘

## Schedule of Deviations

Note:

- To be completed by the Employer prior to award of contract.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) Eskom Holdings SOC Ltd c/o Peaking Generation 15 Pasita Street Rosenpark Bellville |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

# C1.2 Contract Data

## Data provided by the Employer

Completion of the data in full is essential to create a complete contract.

| ## Clause |  |  | ## Statement |  | ## Data |
| --- | --- | --- | --- | --- | --- |
|  |  |  | ## General |  |  |
| 10.1 |  |  | The Employer is (Name): |  | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |
|  |  |  | Address |  | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |
| 10.1 & 14.4 |  |  | The Employer’s representative to whom the Employer in terms of clause 14.4 delegates his actions is (Name): |  | Zandile Mnukwa |
|  |  |  | Address |  | Drakensberg Pumped Storage Scheme Jagersrust 3354 |
|  |  |  | Tel No. |  | 036 438 2034 |
|  |  |  | Fax No. |  | N/A |
|  |  |  | E-mail address |  | MnukwaCN@eskom.co.za |
| 11.2(11) |  |  | The works are |  | Waterproofing repairs on the surface building roof at Drakensberg Pumped Storage Scheme |
| 11.2(13) |  |  | The Works Information is in |  | the document called ‘Works Information’ in Part 3 of this contract. |
| 11.2(12) |  |  | The Site Information is in |  | the document called ‘Site Information’ in Part 4 of this contract. |
| 11.2(12) |  |  | The site is |  | Drakensberg Pumped Storage Scheme |
| 30.1 |  |  | The starting date is. |  | TBC |
| 11.2(2) |  |  | The completion date is. |  | TBC |
| 13.2 |  |  | The period for reply is |  | 2 working days |
| 40 |  |  | The defects date is |  | 52 weeks after Completion |
| 41.3 |  |  | The defect correction period is |  | 1 week |
| 50.1 |  |  | The assessment day is the |  | Completion date |
| 50.5 |  |  | The delay damages are |  | 5% per day up to a maximum of 20% of the full contract value. (Penalties will kick in if the works are not provided as per the agreed schedule completion date |
| 50.6 |  |  | The retention is |  | 5 % of contract value (maximum 12 months after completion date) |
| 51.2 |  |  | The interest rate on late payment is |  | 0.5 % per week |
| 80.1 |  |  | The Contractor is not liable to the Employer for loss of or damage to the Employer’s property in excess of |  | the amount of the deductibles relevant to the event |
|  |  |  | Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) apply? |  | No |
| 93.1 |  |  | The Adjudicator is |  | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |
| 93.2(2) |  |  | The Adjudicator nominating body is: |  | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body |
| 93.4 |  |  | The tribunal is: |  | arbitration. |
|  |  |  | The arbitration procedure is |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |
|  |  |  | The place where arbitration is to be held is |  | Johannesburg, South Africa |
|  |  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |
|  |  |  | The conditions of contract are the NEC3 Engineering and Construction Short Contract (April 2013) and the following additional conditions Z1 to Z14which always apply: |  |  |
| Z1 |  | Cession delegation and assignment |  |  |  |
| Z1.1 |  | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |
| Z1.2 |  | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |
| Z2 |  |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |
| Z2.1 |  |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |
| Z2.2 |  |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer. |  |  |
| Z2.3 |  |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the starting date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |
| Z2.4 |  |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |  |
| Z3 |  | Confidentiality |  |  |  |
| Z3.1 |  | The Contractor does not disclose or make any information arising from or in connection with this contract available to others except where required by this contract. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to others where required by this contract the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |
| Z3.2 |  | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Employer. |  |  |  |
| Z3.3 |  | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |
| Z3.4 |  | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Employer. All rights in and to all such images vests exclusively in the Employer. |  |  |  |
| Z3.5 |  | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |
| Z4 |  | Waiver and estoppel: Add to clause 12.2: |  |  |  |
| Z4.1 |  | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties or their delegates or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |
| Z5 |  |  | Health, safety and the environment |  |  |
| Z5.1 |  |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and - undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |
| Z5.2 |  |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |
| Z6 |  | Provision of a Tax Invoice and interest. Add to clause 50 |  |  |  |
| Z6.1 |  | The Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the correctly assessed amount due for payment. |  |  |  |
| Z6.2 |  | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |
| Z6.3 |  | The Contractor is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |
| Z7 |  | Notifying compensation events |  |  |  |
| Z7.1 |  | Delete from the last sentence in clause 61.1, “unless the event arises from an instruction of the Employer.” |  |  |  |
| Z8 |  | Employer’s limitation of liability; Add to clause 80.1 |  |  |  |
| Z8.1 |  | The Employer liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand). |  |  |  |
| Z9 |  | Termination: Add to clause 90.2, after the words "or its equivalent": |  |  |  |
| Z9.1 |  | or had a business rescue order granted against it. |  |  |  |
| Z10 |  | Addition to Clause 50.5 |  |  |  |
| Z10.1 |  | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data (if any), the Employer may terminate the Contractor’s obligation to Provide the Works. |  |  |  |
|  |  | If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the works. |  |  |  |
| Z11 | Ethics |  |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |  |
| Affected Party |  |  |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subconsultants or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |  |
| Coercive Action |  |  |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |  |
| Collusive Action |  |  |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |  |
| Committing Party |  |  |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees, |  |
| Corrupt Action |  |  |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |  |
| Fraudulent Action |  |  |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |  |
| Obstructive Action |  |  |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |  |
| Prohibited Action |  |  |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |  |
| Z11.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |  |  |  |
| Z11.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |  |  |  |
| Z11.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |  |  |  |
| Z11.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |  |  |  |

Z12		Insurance

Z _12.1	Replace core clause 82 with the following:

| Insurance cover | 82 |  |  |  |
| --- | --- | --- | --- | --- |
|  | 82.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |  |  |
|  | 82.2 | The Contractor provides the insurances stated in the Insurance Table A, from the starting date until the earlier of Completion and the date of the termination certificate. |  |  |
|  |  |  | INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity; Cover provided until. Loss of or damage to the works; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance; The Employer’s certificate of Completion has been issued. Loss of or damage to Equipment, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance; The Defects Certificate has been issued. The Contractor’s liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Works; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by the applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law.. |  |
|  | 82.3 |  | The Employer provides the insurances as stated in the Insurance Table B - INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document.. |  |

| Z13 | Nuclear Liability |  |
| --- | --- | --- |
| Z13.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z13.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z13.3 | Subject to clause Z13.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z13.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z13.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z14 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z14.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z14.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z14.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z14.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z14.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z14.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z14.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

## Data provided by the Contractor (the Contractor’s Offer)

The tendering contractor is advised to read both the NEC3 Engineering and Construction Short Contract (April 2013) and the relevant parts of its Guidance Notes (ECSC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on page 31 of the ECSC3 April 2013 Guidance Notes.

Completion of the data in full is essential to create a complete contract.

| 10.1 | The Contractor is (Name): | [●] |
| --- | --- | --- |
|  | Address | [●] |
|  | Tel No. | [●] |
|  | Fax No. | [●] |
|  | E-mail address | [●] |
| 63.2 | The percentage for overheads and profit added to the Defined Cost for people is | [●]% |
| 63.2 | The percentage for overheads and profit added to other Defined Cost is | [●]% |
| 11.2(9) | The Price List is in | the document called ‘Price List’ in Part 2 of this contract. |
| 11.2(10) | The offered total of the Prices is [Enter the total of the Prices from the Price List]: | R[●] excluding VAT [in words] [●] excluding VAT |

C2 Pricing Data

# C2.1 Pricing assumptions

Entries in the first four columns in the Price List are made either by the Employer or the tendering contractor

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered.

All Prices are to be shown excluding VAT unless instructed otherwise by the Employer in Tender Data or in an instruction the Employer has given before the tenderer enters his Prices.

If there is insufficient space in the Price List which follows, state in which document the Price List is contained.

# C2.2 Price List

The Price List is as follows

| Item no. | Description | Unit | Quantity | Rate | Price |
| --- | --- | --- | --- | --- | --- |
| 1 | Preliminary and General |  |  |  |  |
| 1.1 | Site Establishment | Sum | 1 |  |  |
| 1.2 | Contractor’s obligation in respect of the Occupational Health and Safety Act and Construction Regulations. Health and Safety file preparation and submission. | Sum | 1 |  |  |
| 1.3 | Staff medicals and induction | Sum | 1 |  |  |
| 1.4 | Site De-establishment | Sum | 1 |  |  |
| 1.5 | Storeroom/Office Container | Sum | 1 |  |  |
| 1.6 | Transport, Accommodation etc. (Please specific) |  |  |  |  |
| 1.7 | Other (specify and list with quantities) | Sum | 1 |  |  |
| 2 | Waterproofing Surface Building Roofs- The tendered rate shall include full compensation for all labour, materials, equipment, preparation, UV coating etc. that is required including the primer and all layers to provide a waterproofing system. |  |  |  |  |
| 2.1 | Inspect and assess roof and provide a report | Sum | 1 |  |  |
| 2.2 | Cleaning drainage system- Full bore inlets Outlets | Sum | 1 |  |  |
| 2.2 | Repair of screed (30mm thickness)- (cracks, damage spalling etc) | m2 | 50 |  |  |
| 2.3 | Sealing of joints | m | 50 |  |  |
| 2.4 | Remove existing waterproofing and dispose off-site | m2 | 256 |  |  |
| 2.5 | Prepare surface | m2 | 256 |  |  |
| 2.6 | Replace waterproofing | m2 | 256 |  |  |
|  | The total of the Prices (excluding VAT): |  |  |  |  |

C3:  Scope of Work

# C3.1 Works Information

1. Description of the works

The works make provision for waterproofing repairs to the Surface Building Roofs at Drakensberg Pumped Storage Scheme (DPSS). This includes the investigation into the root cause of the roof leaks, preparation, appropriate selection of waterproofing system, sealing and a providing a watertight roof.

Background

DPSS straddles the Drakensberg escarpment in the vicinity of the Olivierhoek Pass on the road between Bergville and Harrismith. The KwaZulu Natal/ Free State border crosses the headrace tunnels between the intake and the surge shafts. The Scheme is situated on the farms Metz, Poccolan and Kilburn, but the area of the site is restricted to servitudes on the farms Metz and Kilburn.

The surface building roofs that requires remedial work is typically used by Eskom Employees as office space. Access to the surface building is via access. The existing waterproofing appears to have aged and require repairs.  Water ingress from the roof has resulted in damage to the paint on the inside of the buildings.

Employer’s Objective

- The Employer’s objective is for a competent Contractor to perform remedial works to the Surface Building Roofs to prevent leaks.

- The waterproofing maintenance work to ensure water tightness as intended to achieve the useful design life of the building.

- Employer’s Philosophy

- The works should have optimal structural strength as required.

- The works must be properly executed and provide high quality and technical performance.

- The works must be safe and fit for purpose.

- The execution and construction methods of the works to be as per the relevant standards.

Engineering Philosophy

The Engineering Philosophy which includes the selection of materials of the structures and the application is performed in accordance with latest accepted standards. A competent Contractor will be required to provide the works as stated in the Works Information.

Maintenance Philosophy

Maintenance of the works is kept at a minimum. Maintenance includes ease of inspection and replacement. Maintenance philosophy is to ensure long-term structural health.

Operating Philosophy

Perform maintenance and replacement of civil infrastructure to maintain and increase the design and operating life of civil structures.

Scope of work

The Scope must be read in conjunction with the specifications as stipulated in Section 3 Discrepancies or ambiguities are to be reported to the Employer prior to submission of tender.  The Contractor must submit all work methods, procedures and specifications to the Employer for acceptance. The Scope of works entails the provision of services to waterproof the roof and prevent water ingress into the building in accordance with the Works Information.

The works comprises the following:

| Applicable Structure | Scope |
| --- | --- |
| Surface Building Roofs | - Submission of all work methods and procedures to the Employer for acceptance. - The Contractor to provide resources, equipment and services in compliance with the OSH Act. This includes all working at heights requirements, certification, equipment and compliance needed to perform the works. - The Contractor to supply and deliver all necessary materials, machinery, tools and equipment required for the repairs as stated in the Works Information. - Inspect the condition of the roof and provide a report, check the slope and drainage requirements, clean drainage system. - Remove existing waterproofing system, perform repairs (repair screed/concrete, sealing cracks, preparation of substrate and testing) and install accepted waterproofing system that will ensure that the roof is watertight. - Remove from site and safely discard the old waterproofing system and all the other waste generated during the works |

The Contractor assesses the full scope of work at the site inspection meeting and submits tender accordingly. The Contractor shall check and verify the as built condition. The scope is read in conjunction with specifications and the pricelist.

Disciplines in which services sought:

Civil Engineering, Buildings, Structures and Maintenance in waterproofing.

2.  Drawings

| Drawing number | Revision | Title |
| --- | --- | --- |
| 0.48/1781 | 5 | Surface Building- Roof Layout and Concrete Details |
| 0.48/1149 | 2 | Drakensberg Pump Storage Scheme Surface Building Structural Details |
| 0.48/4884 | 0 | Drakensberg Pump Storage Scheme Surface Building Extension Structural Details |

The drawings provided by the Employer are for reference and pricing only. The Contractor verifies the correctness of these drawings against the As Built condition prior to commencing with the Works. Nothing in the drawings lessens the Contractor’s obligations as detailed in any other documents forming part of the Contract.

3. Specifications

| Title | Date or revision | Tick if publicly available |
| --- | --- | --- |
| General Specifications: |  |  |
| Health and Safety requirements: OHSA No 85 of 1993 |  |  |
| Environmental requirements: National Environmental Management Act of 1988 |  |  |
| Site regulations and access control |  | * |
| Eskom’s Procurement and Supply Chain Management Procedure 32-1034 |  | * |
| Plant Safety Regulations: GGR 0992 | Rev 1 | * |
| Technical specifications: |  |  |
| - Inspections and assessments must comply with the following specifications. The following SANS specifications for Civil Engineering is applicable to the work. |  |  |
| 1200 series specification for civil work - SANS 1200 |  |  |
| Construction Works - SANS 2001 |  |  |
| The application of the National Building Regulations - SANS 10400 |  |  |
| Roof paints - SANS 683 |  |  |
| The waterproofing of buildings (including damp-proofing and vapour barrier installation) - SANS 10021 |  |  |
| Accuracy in buildings - SANS 10155 |  |  |
| Inspection Manual for Civil Works at Eskom Power Station - 240-99527377 |  | * |
| Standard drawing practice - GGS 0315 |  | * |
| Drawing record system GGS 0441 |  | * |
| Quality requirements for engineering and construction works - GGG 0462 |  | * |
| Eskom Life Saving Rules - 32/421 |  | * |
| The Occupational Health and Safety Act No. 85 of 1993 and Regulations |  | * |
| - The Compensation for Occupational Injuries and Diseases Act No.130 of 1993, amended by government notices to 30 April 2004 or Equivalent |  | * |

- * The revisions and amendments of the Specification documents that apply are the latest revisions and amendments in force at the time of the Contract authorisation. Nothing in the Specification documents lessens the Contractor’s obligations as detailed in any other documents forming part of the Contract.

### Particular specifications and Performance Requirements

### Materials and Workmanship

- Materials and workmanship are of the best of their respective kinds.  Only labour skilled in their trade is employed. Only new and undamaged materials are used in the works. Materials to be permanently installed are not used for any temporary purposes on site. Works are for the acceptance of the Supervisor and are executed in accordance with the relevant manufacturer's written recommendations and instructions. The Contractor to perform a detailed site inspection to note the existing features and as built condition. The Contractor takes cognisance of the surroundings that may potentially impact the works during implementation.

### Proprietary Product

- For the purpose of submission of tenders, rates for items described in the bills of quantities by trade names, catalogue references, etc., are for the particular type and manufacture specified.

- Once the Contract has been signed the acceptance of the Supervisor is obtained prior to any substitution and where products or materials, etc., other than those specified are used, adjustments in the rates are made, if deemed necessary.

### Waterproofing

- Damp proofing and waterproofing comply with the Specifications and requirements given in the table below. Waterproofing materials are applied in accordance with SANS 10021.

| Material | SANS | Type and/or Additional Requirements |
| --- | --- | --- |
| Bituminous damp-proof course to wall, sills, etc. | 248 | Type FV |
| Polyethylene sheet for the waterproofing of flat roofs | 952 | Type A |
| Polyethylene sheet in damp-proof course to walls, sills etc. | 952 | Type B |
| Ditto to floors and basements | 952 | Type C |
| Mastic asphalt for roofing | 297 | - |
| Mastic asphalt for damp-proof coursed and Tanking | 298 | - |
| Bituminous roofing felt | 92 | Type 60 |
| Chloroprene rubber sheet (for waterproofing) | 580 | At least 2.5 mm thick and 1200 mm wide |
| Sealing compounds with two-component polysulphide base | 110 | Type 2 Gun Grade/ as specified on the drawings |

- Roofs must be durable and must not allow the penetration of rainwater or any other surface water to the interior. Additionally, the roofs must not allow the accumulation of water on its surface. All the surfaces are to be checked for adequacy of slopes to ensure adequate drainage of the roof.

- The waterproofing system must allow for movement of concrete elements where this may occur ensuring that the waterproofing system is not damaged or comprised in anyway.

- The concrete/screed surfaces that are damaged or defective (cracking, spalling etc.) must be repaired with suitable repair products. The substrate must be stable before the waterproofing is applied. This includes structural and non-structural crack repairs.

- Cracks are to be repaired using crack injection for structural repairs or routing the cracks and filling with suitable concrete repair mortars.

- It is a requirement of the Contractor that an unconditional 5 year guarantee is provided. The guarantee must be provided by the Contractor and the Suppliers. The comprehensive pro forma guarantee must be submitted with the tender. If an additional coating or any maintenance interventions are required to ensure that the system is UV stable, it should be stated. Any maintenance requirements for the above 5-year guarantee shall be clearly indicated in the Contractor’s guarantee.

The proposed waterproofing system must provide the following characteristics:

    - Durable

    - Bonding with substrate

    - Bridge over minor cracks in concreteF

    - UV stable

    - Maintainable

    - Provide a guarantee

- The tendered rates to include the following:

    - Supplying material

    - Testing

    - Surface preparation- sealing, cleaning, priming etc.

    - Construction and installation

    - Supply of equipment to perform the works

    - Clearing, trimming, disposing of material, tidying and all other work to be done for finishing of the roof.

### People restrictions on site, hours of work, conduct and records

- Restrictions and hours of work may apply.  The Contractor is required to keep records of his people on site, including those of his Subcontractors which the Project Manager or Supervisor has access to, at any time. The Contractor is required to manage the interface between his Subcontractors and ensure access is granted prior to establishing and commencing work.

- The Contractor takes into consideration the site working hours and must align to work hours on site. The Contractor to include this in the construction programme. Normal hours of work for site are from 7H00 to 16H15 Mondays to Thursdays and 7H00 to 12H00 on Fridays

#### Supplier Documentation

Documentation and information (specific to this project) to be provided by the Supplier for works includes:

- A Quality Management Policy.

- A Quality Management System that meets or exceeds the requirements of ISO 9001. Relevant and applicable certification and the quality management policy to be submitted.

- Name of company, facility, web address, e-mail address, contact telephone number and physical address.

- Provide verifiable/auditable evidence that the Contractor has experience in waterproofing of buildings and waterproofing systems for similarly sized projects in comparable environments.

- Provide an organogram, specific to this particular supply, detailing all the positions and individuals responsible for technical expertise and logistic support. Curriculum vitaes of these key personnel shall be included with the submission. Suitably qualified technical supervisors and inspectors are considered key in the process. In this regard details of personnel number, qualification type, level and experience to be provided as part of the organogram.

The organogram submitted at tender stage is required to contain the following persons as a minimum:

    - Site Agent/ Supervisor/ Foreman

    - SHEQ Supervisor

    - Project Manager

    - Site Construction Manager

    - Site Manager

- In addition, the tenderer must submit the following information and documentation with his/her tender:

    - Detailed qualifications of any deviation from the contents of this specification.

    - Evidence of the tenderer’s capability of undertaking that he has successfully completed similar contracts of like size and scope. Additionally provide certification proving competency.

    - Provide protection and support to existing equipment where applicable.

    - A Quality Control Plan (QCP).

    - Method statements

    - Protection plan to existing equipment while work is carried out.

    - A guarantee of the installed/commissioned work for a period as specified in the specification from the date of issue of the Certificate of Completion.

    - A quality assurance document which includes control and management procedures.

    - A manual detailing installation care and maintenance procedures where applicable.

    - Cleaning and protection during the progress of the works, the Contractor shall clean the work area as well as protect his/her work area in strict accordance with the particular standards for such works.

    - A technical construction project programme.

    - The Contractor should be well established and reputed Contractor (Waterproofing- Building Maintenance) and should have a minimum of 3 years’ experience in construction of similar Works as well as key personnel with adequate experience and competency to perform work specific to the scope of this project. The key capability is related waterproofing and building works.

#### Pre-job Meeting

- A pre-job meeting to discuss and analyse the procedures and processes to be used on the project shall be held prior to commencement of the work. The purpose of the pre-job meeting would be to ascertain specifics in relation to this specification. Attendance shall include the Employer, Suppliers, manufacturers, Contractors and all key role players.

#### Contractor Skills and Competency

### The Contractor shall ensure that there are at all times sufficient suitably qualified, experienced and skilled staff to carry out and supervise all activities. The skills and competency is referenced to waterproofing of buildings, general building maintenance and construction work.

#### Quality Assurance

### Supplier Capability

- The Employer may, at his discretion, require a Quality Audit of the Supplier to ensure that he has the management, facilities and skilled staff to carry out the work in accordance with the specification.

- The Supplier shall retain full responsibility for the quality of his work and of materials used, irrespective of any quality surveillance that may be carried out by the Employer

### Quality Control

- The Supplier shall have the necessary equipment and qualified staff to carry out the quality control required to ensure compliance with the specification.

- Quality control shall be carried out by qualified individuals. Quality control cannot be carried out by the site supervisor, or any member of staff involved in production and programming.

- These records shall be kept in a format that meets the approval of the Employer.

- The cost of quality control shall be included in the Supplier’s tender price.

- Before the commencement of the contract, the Supplier shall prepare the following:

(i)	A Quality Plan detailing each activity to be carried out during the execution of the works. Each activity shall be supported by a detailed Works Procedure/Method Statement for that activity.  The Quality Plan will also detail the inspection requirements of each specific activity, listing whether it is a review, witness or hold point, and defining the responsibilities of the various parties at each stage of the works.

(ii)	The Safety File

- The Supplier shall provide the necessary documentation to be used during all quality control inspections. Such documentation shall be reviewed and approved by the Employer before work commences.

- The Supplier shall produce evidence that he has copies of, and understands, all reference documents listed under Section 3 ‘Specifications’.

## Clean working Conditions

- The site is kept and left in a clean and orderly condition as the work progresses and upon completion thereof.

- The Supplier stores equipment, materials and plant for which he is responsible in an orderly manner.

## Quality management

- The quality requirements are captured in the Supplier Quality Management Specification QM 58 (240-105658000), which specify and describe the minimum quality criteria for the selection, evaluation, registration, monitoring and auditing of suppliers.  This specification as provided during tender will be seen as part of the works.  It will work hand in hand with (Form A) Tender & Contract Quality Requirements for QM58 and Quality requirements for ISO 9001 Standard.  A Quality Control Plan / Inspection and Test Plan template as well as a Template for a Typical Contract Quality Plan will be provided.

- The Supplier defines the level of QA/QC or inspection imposed on his Sub-contractors and Suppliers.

- The programming of inspections, hold and witness points is agreed between the Employer and the Supplier prior to undertaking any work.

### Safety and Occupational Health Management

### General Safety

- The Contractor must submit a detailed and comprehensive Safety Health and Environmental Plan as required by amongst others the Construction Regulations, Hazardous Chemical Substances Regulations, General Administration Regulations, General Safety Regulations of the Occupational Health and Safety Act 85 of 1993, Eskom’s SHEQ Policy 32-727, 167A/271: Health and Safety Requirements for Contractors, etc. which will include amongst others:

- The safety file needs to be signed off by the client before any work can commence.

- Method statements for all activities should be part of the safety file and plan.

- A Letter of Good Standing (compulsory):

- Appropriate statutory appointments;

- Medical Certificates of Fitness issued by registered Occupational Health Practitioners;

- Method Statements/Procedures for all tasks as identified in the Risk Assessments;

- The Contractor and his personnel will attend an induction meeting on site and sign the attendance sheet provided as proof of attendance.

- The Supplier shall ensure that adequate precautions are taken to avoid fire hazards, as required by the General Safety Regulations, Construction Regulations of the Act, and any Eskom requirement related to fire risks.

4. Constraints on how the Contractor Provides the Works

  - Access

- The Employer will provide access to the site for the Contractor to conduct repair works. The site can be accessed via the main access road at DPSS.

- Working space may sometimes be restricted. General access to the power station complex is controlled and it is mandatory that the Contractor adheres to all security regulations in force at all times.

- The Contractor notes that the Site is a National Key Point and complies with the associated requirements of the National Key Point Act, 102 of 1980.

  - Functional Requirements

- The Contactor must provide sufficient Equipment and tools to carry out the work. The Contractor shall have all the necessary ancillary Equipment and hand tools available for the work. The Engineer shall be entitled to request reserve plant should there be any doubt as to the efficiency or capability of the Equipment provided.

- It is mandatory that the Contractor be certified (in terms of the South African Occupational Health and Safety Act of 1993 and Construction Regulations 2014), and has the necessary skills to carry out the works as per the Works Information. The structures are safe for use and are structurally sound.

- The Contractor shall provide detailed procedures that shall be employed, describing systematically how the Contractor performs the works.

- The Contractor shall provide an organogram, specific to this particular supply, detailing all the positions and individuals responsible for technical expertise and logistic support. Curriculum Vitaes of these key personnel (e.g. person leading the inspection team, rope access supervisor, corrosion applicators etc.), shall be included with the Safety Plan. Suitably qualified technical backup or support, Quality Assurance and Quality Control personnel are considered key in the execution process. In this regard, details of the personnel number, qualification type, level and experience to be provided as part of the organogram.

  - Modifications

The Contractor does not modify any plant or materials unless accepted by the Employer prior to site execution.

  - Start of Works

A site inaugural meeting is held between the Contractor and the Employer, where details of the Works are discussed and clarified prior to site execution. The start of Works shall be as per the contract documentation.

  - Transporting of Employees

The Contractor is in all respects responsible for the housing and transporting of employees, and for the arrangement thereof, and no extension of time due to any delays resulting from this, will be granted.

  - Others

The Contractor notes that there may be other work taking place during the period when he is providing the Works. The Contractor liaises with others in this regard.

4.7	Subcontracting

All Work done by specialist Contractor is the responsibility of the Principal Contractor. The Employer shall accept works as provided by the Contractor.

4.8	Debris

The Contractor must remove all debris generated from and transports it to a designated spoil site. All spoil material generated by the Works, is disposed of by the Contractor at the municipal designated dumping site and the Contractor must provide proof or certification thereof.

4.9	Medical facilities

No medical facilities are available on site.

4.10	 Security of Works

The Contractor is entirely responsible for the security of all the Works, materials, equipment and lighting and other precautions as necessary to ensure security against theft, loss or damage. The Contractor is advised to visit site to familiarize with the nature and position of the site.

4.11 	Tool and Equipment

The Contractor supplies all tools and Equipment for the Works including safety harnesses approved by the Employer and step ladders with their inspection records.

4.12 	Meetings

Before any work can commence on site, the Contractor and all staff is to attend site induction.  The Contractor is to allow 2 hours for this.

The Contractor will be required to sign on to the workers register each morning and sign out each afternoon.  A responsible person (RP) will be appointed by site and will be responsible for the area where the works is taking place.  The RP will be responsible for ensuring that everyone signs on and off the register, ensure that everyone is aware of the Eskom rules and will confirm that the area is still safe for work. The Contractor must notify the RP of the daily work plan prior to execution of works.

The Contractor is to hold a toolbox talk each morning before commencing with the Works to discuss the previous day’s work and to ensure that everyone understands what is required of them.

When required, the Contractor must have a representative at each daily morning meeting.

4.13	Contractor representation

The Contractor’s Site Supervisor is on site for the entire duration of the Works.

4.14	Facilities to be provided by the Contractor

- If required, the Contractor is required to provide his own containers to be used as an office or for storage.

- The Contractor supplies all tools and Equipment for the Works.

- The Contractor is entirely responsible for the security of all the Works for 24-hour period.

4.15	Title to material

The Contractor has no title to plant and/or materials resulting from him carrying out the Works.

4.16	Design by the Contractor

The Contractor does not design any of the work.

4.17	Quality Management

The quality requirements are as per Eskom standard ESKASAAU7: QUALITY REQUIREMENTS FOR THE PROCUREMENMT OF ASSET GOODS AND SERVICES. The Contractor utilizes the Employer’s forms for requesting access, etc. These request forms are submitted to the supervisor at least one week prior to the requested date.

The onus to produce work that conforms in quality and accuracy of detail to the requirements of the specifications and drawings rests with the Contractor, and the Contractor shall institute a quality control system and provide suitably qualified staff to ensure adequate supervision and positive control of the works at all times.

The programming of inspections, hold and witness points of the repairs is to be agreed between the Employer and the Contractor prior to undertaking any work.

The Contractor’s attention is drawn to the provisions of the various Standardized Specifications regarding the minimum frequency of testing required. The Contractor shall, at his own discretion, increase this frequency where necessary to ensure adequate control.

On completion and submission of every part of the work to the Employer for inspection, the Contractor shall furnish to the Employer the results of the relevant tests, measurements and levels to demonstrate the achievement of compliance with the specifications.

4.18	Clean working conditions

Progressive and systematic finishing and tidying will form an essential part of this contract. The Contractor must undertake to dispose of the building rubble as there is no capacity on site to dispose. Materials of value belong to the Employer and not the Contractor.

Under no circumstances shall materials, Equipment or unfinished operations be allowed to accumulate unnecessarily and in the event of this occurring the Employer shall have the right to withhold payment for as long as necessary in respect of the relevant works in the area(s) concerned.

The Contractor is responsible for Clean Working Conditions, for the duration of the work, and uses the Employer’s Standard Reference no 167A-139, as a minimum requirement.

The Contractor is responsible to establish and maintain a protected environment around the work area. Only persons authorized by the Employer have access to the work area. Precautions are enforced by the Contractor to ensure that no foreign objects are lying around at any stage of the work.

The Contractor stores materials and Equipment for which he is responsible in an orderly manner.

The Contractor ensures that the working area remains clean for the duration of the works.

4.19	Health and Safety requirements

Health, safety and the environment

The Contractor shall submit a detailed and comprehensive Safety, Health and Environmental Plan as required by amongst others the Construction Regulations, General Administration Regulations, General Safety Regulations of the Occupational Health and Safety Act 85 of 1993, Eskom’s SHEQ Policy 32-727, Eskom’s Permit to Work System, 32-418 - Work at Height, 167A/271: Health and Safety Requirements for Contractors, etc. which will include amongst others:

- A valid and verified Letter of Good Standing (mandatory):

- Risk Assessments including a Fall Protection Plan that must include a detailed fall rescue plan, especially since work at height will be required; mitigation of slip and fall hazards in the Surge Shaft or waterways; Personal Protective Equipment, etc.;

- Appropriate statutory appointments specific to the risks of the tasks, e.g. a competent fall protection plan developer, competent risk assessment developer, rescuers, first aiders supervisor, etc.;

- Medical Certificates of Fitness issued by a registered occupational health practitioner or occupational medicine practitioner;

- Method Statements/Procedures that specifically address the tasks and their hazards.

- Competencies specific to the tasks, e.g. training in fall arrest systems, maintenance of fall protection equipment, fall rescue, emergency management, risk assessment methods, supervisory skills, etc., issued by accredited safety training service providers;

The Contractor and his personnel will attend an induction meeting on site that will detail site health and safety requirements and expectations during the contract, e.g. actions required during an emergency, incident accident reporting, worker identification, security requirement, etc. Contractor employees will be required to sign the attendance sheet provided as proof of attendance.

The Contractor is responsible for the medical treatment of his/her personnel should it be required and must adhere strictly to the requirements of COID and the contract.

## 4.21	Environmental Management

The Contractor’s attention is drawn to the fact that the Power Station is situated in a highly sensitive area with respect to the environment.

The Contractor acquaints himself with all statutory and local environment regulations and adheres to these without exception, especially the requirements of the National Environmental Act, Number 107 of 1998 and its Regulations.

Any waste that is generated shall be stored, labelled and disposed in the manner prescribed in the applicable legislation governing the management of waste.

The required SHE Plan must be submitted for evaluation before any work commences, and no contractor or his/her personnel will be allowed to conduct any work with a duly approved SHE Plan.

4.22	Site Clearance

The Contractor removes all his equipment, plant and waste generated during the Works on takeover of the Works.

## 4.23	 Invoicing and payment

In terms of core clause 50 the Contractor assesses the amount due and applies to the Employer for payment.  The Contractor applies for payment with a tax invoice addressed to the Employer as follows:

The Contractor includes the following information on each tax invoice:

- Name and address of the Contractor

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- The total Price for Work Done to Date which the Contractor has completed;

- Other amounts to be paid to the Contractor;

- Less amounts to be paid by or retained from the Contractor;

- The change in the amount due since the previous payment being the invoiced amount - excluding VAT, the VAT and including VAT;

- (add other as required)

The Contractor attaches the detail assessment of the amount due to each tax invoice showing the Price for Work Done to Date for each item in the Price List for work which he has completed.

### How to submit invoices

- General Submission Information

- The subject line on your email should only contain your Eskom vendor number

- Each invoice in PDF should be named with your invoice number only

- Ensure that the Eskom task order number is clearly indicated on your invoice together with the line number you are billing for

- Ensure you comply with the SARS tax requirements for submitting invoices electronically

- Each PDF files should contain one invoice, one debit note or one credit note only. Ou may submit more than one invoice per email

- All electronic invoices must be sent in PDF format only

- Attach proof of delivery to your invoice (eg assessment certificate)

- Where applicable, supporting documents must be attached to the scanned PDF invoice as one attachment

- Assessment Certificate / delivery note

- Retention certificates where it is a retention invoice

- Any other appropriate documents

All invoices to be accompanied by the Payment Assessment Certificate as issued by the Service Manager.  Invoices to be submitted electronically as PDF documents to: Invoiceseskomlocal@eskom.co.za

### Payment Queries

For all queries and follow-ups on invoice payments, kindly contact the Finance Shared Services Contact Centre

- Tel: 011 800 5060

- Email: fss@eskom.co.za

## 4.24	 Records of Defined Cost

In order to substantiate the Defined Cost of compensation events, the Employer may require the Contractor to keep records of amounts paid by him for people employed by the Contractor, Plant and Materials, work subcontracted by the Contractor and Equipment.  [See clause 11.2(5) and 63.2].  State in what form these records are to be kept and how accessed by the Employer

## 4.25 Supplier Development and Localisation (SD&L)

### Supplier Development Localisation & Industrialisation (SDL&I) undertaking

Will be inserted here at contract award based on the tender returnables submitted by Contractor to Eskom and as agreed by Eskom. Information inserted here is based on tender returnables schedules for SDL& requirements indicated in Enquiry documents.

- Local content

Will be inserted here at contract award based on the tender returnables submitted by Contractor to Eskom and as agreed by Eskom. Information inserted here is based on tender returnables schedules for SDL& requirements indicated in Enquiry documents.

## 4.26	BBBEE and preferencing scheme

As per clause Z3.

- Requirements for the programme

The Contractor submits a bar (Gantt) chart programme in PDF format, detailing how the Works is executed within the stipulated dates, including weekends and public holidays. The programme must include the following:

- Lead time from Contract start date to Site Establishment

- Proposed time to complete each activity as per the scope of work.

- Resources needed per activity

- Links between activities indicating predecessors and successors.

- Site establishment and de-establishment duration.

- Health, Safety and Environmental considerations including 2 hours for Induction training.

- Float per activity.

- Quality verification and testing activities.

- Key deliverable dates.

The programme will be subject to acceptance by the Employer and must be within the offered timeframes during tender stage.

The schedule needs to be updated on a daily basis and be available to the Employer when required.   The updated schedule must be presented to the Employer by each Friday of each week during the execution phase of the Works.  An Early Warning must be tabled every time the updated schedule indicates lateness of any activities on the critical path.

The Contractor must stick to the agreed programme and any changes to it need to be approved by the Employer.

- Services and other things provided by the Employer

Electrical Supply

- 220V supply is available.

- Note:  The Contractor provides his own extension leads and equipment needed to carry out the works.

Potable Water Supply

- All points of supply are provided in terms of availability and location.

- The Employer indicates which supply points may be used.

Lightning

- Contractor to provide own lighting where required.

Designated smoking areas

- Personnel to smoke only at designated smoking areas.

Ablution facilities

- Ablution facilities are available at the work area, Employer to indicate this to the Contractor

C4:  Site Information

The site is reached from Harrismith via the R49 to Kestel. The R74 turn-off to Bergville is 2.8 km along the R49. Turn left after 8.7 km and travel 23.5 km to the Natal/Free State boundary at the top of the Oliviershoek Pass. From there, travel 13.1 km down the pass and turn left. Follow the signposted directions to the power station for approximately 9.5 km. The total distance from Harrismith is approximately 60 km.

GPS Co-ordinates

| Site | Latitude | Longitude |
| --- | --- | --- |
| Drakensberg power station | -28.564689187276056 | 29.084088524999807 |

# C4.1: Information about the site at time of tender which may affect the work in this contract

## 1. Access limitations

Access to the Power Station is restricted to authorized personnel only. The Contractor will be required to submit ID copies of all their staff well in advance for security clearance. ID copies must be sent to the Service Manager. The Contractor to take note that security clearance turnaround time is 24 hours.

All Contractors will be tested for the use of alcohol.  Any persons found to be above Eskom’s legal limit will not be allowed on site.

## 2.  Ground conditions in areas affected by work in this contract

The Contractor is to assess the ground condition and work area at the site meeting.

## 3.  Hidden and other services within the site

The Contractor is to assess the area to confirm the presents of services. Prior to commencement of any works, the Contractor shall ascertain from the relevant authorities the exact position, depth and level of all existing services in the area and shall make whatever provisions may be required by the authority concerned for the support, maintenance and protection of such services.

## 4.  Details of existing buildings / facilities which Contractor is required to work on

The Contractor will not be working on any building when there are the presence of pylons in the area, the Contractor is to take caution not to undermine or disturb its foundation in any way.

Except those actions which can only be done by the Employer as a Party to the contract.

5

to be obtained from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za.