Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Scope |  |
| C3.2 | Consultant’s Scope (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

C3.1: Employer’s scope

Contents

When the document is complete, insert a ‘Table of Contents’.  To do this go to:  Insert, → Reference, → Index and tables → Table of Contents.  Three levels and the title (but not the subtitle) may be shown if the formats used in this template are retained.

Otherwise insert list of contents manually.

# Description of the services

## Executive overview

The successful tenderer is required to conduct specialised power system studies associated with series compensation on the planned Perseus – Zeus 765 kV Line. This study is critical in determining the sizing and configuration of the series compensation along this line. In addition, there are significant time constraints associated to the studies required to be conducted. The successful tenderer is required to ensure that adequate resources are assigned to these deliverables in ensuring that the tasks are completed timeously.

## Interpretation and terminology

If required include here definitions additional to those used in the conditions of contract which are required only for the purpose of making the Scope easier to draft and read.  Also list abbreviations used and provide a full interpretation of each one, for example:

The following abbreviations are used in this Scope:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| ECSA | Engineering Council of South Africa |
| SACPCMP | South African Council for Project and Construction Management Professionals |

# Specification and description of the services

The scope of work for this contract is as follows:

- Sizing (impedance), optimization of the series capacitors, thermal rating and overload requirements as per IEC147 standard and end-to-end voltage profiles of the series compensated line and existing Zeus – Mercury – Perseus 765 kV line and maximum voltage of the series capacitors. Skills and knowledge transfer must be provided to at least 2 Eskom planners (grid planners and/or operations planners). Presentation/s of assumptions and results to Eskom technical review committee/s. Detailed technical report that document the studies undertaken and the findings and recommendations thereof in electronic formats.

- Investigation and identification of possible sub-synchronous resonance (SSR) node problem areas in the Eskom network before and after the series compensation (including but not limited to Koeberg, Ankerlig and Gourikwa, Tutuka and Majuba i.e. generation closely linked / coupled to the Cape Corridor). In the event of a substantial change in the frequency scan results under system healthy, N-1 and N-2 conditions, additional sites over and above those listed above must be identified and included. Skills and knowledge transfer must be provided to at least 2 Eskom planners (grid planners and/or operations planners). Presentation/s of assumptions and results to Eskom technical review committee/s. Detailed technical report that document the SSR study undertaken and the findings and recommendations thereof in electronic formats.

- Transient recovery voltage (TRV) [and Rate of Rise of Recovery Voltage (RRRV)] to determine the worst voltage rating on both sides of the series capacitor and at the remote substations for fault conditions and switching operations. Skills and knowledge transfer must be provided to at least 2 Eskom planners (grid planners and/or operations planners). Presentation/s of assumptions and results to Eskom technical review committee/s. Detailed separate technical reports that document the studies undertaken and the findings and recommendations thereof in electronic formats. Detailed technical report that document the TRV study undertaken and the findings and recommendations thereof in electronic formats.

- Provision of the PSS®E / PowerFactory / PSCAD / EMTDC (or any other power systems simulation tool) files used in electronic and editable/unlocked/unprotected format; where possible converted into working and solving PSS®E files as well.

## Stage 1 Preparation

A kick-off meeting will be scheduled within one week of contract award where the consultant will be inducted into the requirements stipulated by the employer. This meeting will also offer an opportunity for clarification.

## Stage 2 Concept

Consultant’s conceptual approaches to be agreed with the Employer’s Technical Expert. More clearly defined in the Technical Scope Document

## Stage 3: Design development

The study parameters are explained in detail in the Technical Scope Document.

## Stage 4: Production information

More clearly defined in Technical Scope Document

## Stage 5: Manufacture, Installation and Construction Information:

Outputs more clearly defined in Technical Scope Document

## Stage 6: Post Practical Completion

Outputs more clearly defined in Technical Scope Document

# Constraints on how the Consultant Provides the Services.

## Management meetings

Once a month, on Teams recorded. Consultant to compile presentation and present progress to date, areas of concern and way forward. Remaining activities and timelines.

Regular meetings of a general nature may be convened and chaired by the Employer’s Agent as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | Every Two Weekly basis | [●] MS Teams | [●]Employer’s Agent , Consultant and Eskom technical lead. |
| Overall contract progress and feedback | Monthly on _____ at ___ | [●] | Employer’s Agent , Consultant and [●]__ |

Meetings of a specialist nature may be convened as specified elsewhere in this Scope or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the services.  Records of these meetings shall be submitted to the Employer’s Agent by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Consultant’s key persons

Refer to Technical Tender Evaluation Strategy for Professional Services: Zeus – Perseus 765 kV Line Series Compensation Annexure A.

## Provision of bonds and guarantees

Not Applicable.

## Documentation control and retention

### Identification and communication

Grid Planning and/or Engineering will provide a standard template for the report which can be adapted for the study. Sections that are not applicable may be removed at the discretion of the consultant. Eskom reference numbers will be issued to the consultant for reports submitted.

### Retention of documents

Refer to Technical Tender Evaluation Strategy for Professional Services: Zeus – Perseus 765 kV Line Series Compensation Section 6.

## Records and forecasting of expenses

Not applicable

## Records and forecasting of the Time Charge

Not Applicable.

## Invoicing and payment

Consultant submits an assessment. Employer reviews and issues a progress payment certificate. Consultant submits invoice.

The following details shall be shown on or attached to each Invoice to show how the amount due has been assessed:

[List them]

The Consultant shall address the tax invoice to _________________________ and include on it the following information:

- Name and address of the Consultant and the Employer’s Agent.

- The contract number and title;

- Consultant’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

- (add other as required)

Email address to be confirmed on contract award

## Contract change management

Consultant will be required to submit a change request followed by the employer granting concession to the request if accepted

## Inclusions in the programme

Contract key dates; completed activities; outstanding activities and forecasted start and completion dates

## Quality management

### System requirements

More clearly defined in Technical Scope Document

### Information in the quality plan

More clearly defined in Technical Scope Document

## The Parties use of material provided by the Consultant

### Employer’s purpose for the material

The purpose of the material provided by the consultant  will be used to inform the network and technical requirements for the series compensation on the planned Perseus – Zeus 765 kV Transmission line.

### Restrictions on the Consultant’s use of the material for other work

Employer has the sole rights to Intellectual Property and copy rights arising from this study

### Transfer of rights if Option X 9 applies

Employer retains the sole intellectual and copy rights arising from the study. the format of documentation generated from the study is more clearly defined in the Technical Scope Document. Transfer of documents includes all reports, diagrams, drawings, analytical reference documentation used in the study.

.

## Management of work done by Task Order

Not Applicable.

## Health and safety

Not applicable. Consultant will not be travelling to Eskom sites as all activities are expected to be conducted from own offices.

The Consultant shall at all times comply with the health and safety requirements prescribed by law as they may apply to the services.

[If the Consultant may be required to work on Eskom premises, such as a power station, where health and safety requirements additional to those prescribed by law apply, specify these here or state,

The Consultant shall comply with the health and safety requirements contained in Annexure ___________ to this Scope.]

## Procurement

### BBBEE and preferencing scheme

Not Applicable.

### Other constraints

Not Applicable.

### Preferred subconsultants

Not applicable

### Subcontract documentation, and assessment of subcontract tenders

Not Applicable.

### Limitations on subcontracting

Not Applicable.

### Attendance on Subconsultants

Not Applicable.

## Working on the Employer’s property

Not applicable.

### Employer’s entry and security control, permits, and site regulations

Sites such as Koeberg Nuclear Power Station have very strict entrance requirements which tendering consultants need to allow for in their prices, and the Consultant has to comply with.  State these or similar requirements here.  In addition to the above there may be other restrictions once on the site.

### People restrictions, hours of work, conduct and records

Restrictions and hours of work may apply on some sites.  It is very important that the Consultant keeps records of his people working on the Employer’s property, including those of his Subconsultants.  State that the Employer’s Agent shall have access to these records at any time.  These records may be needed when assessing compensation events.

## Cooperating with and obtaining acceptance of Others

This sub-paragraph could be used to deal with two issues.

1) The cross reference from core clause 23.1 about cooperation generally as well as details about Others with whom the Consultant may be required to work. See clause 11.2(7) for the definition of Others.

2) Requirements for liaison with and acceptance from statutory authorities or inspection agencies.

## Things provided by the Employer

Not Applicable.

## Cataloguing requirements by the Consultant

Not Applicable.

# List of drawings

## Documentation and Data issued by the Employer

This is the list of documentation and data issued by the Employer after the Contract Date and which apply to this contract. Data in the form of Case files will only be provided to successful bidder and only once Non-Disclosure Agreements etc., are signed.

| Description | Revision | Title |
| --- | --- | --- |
| Scenario 1 Case File | 0 | One KBG unit in operation for peak load |
| Scenario 2 Case File | 0 | One KBG unit in operation for midday load |
| Scenario 3 Case File | 0 | One KBG unit in operation for light load |
| Scenario 4 Case File | 0 | Two KBG units in operation for peak load |
| Scenario 5 Case File | 0 | Two KBG units in operation for midday load |
| Scenario 6 Case File | 0 | Two KBG units in operation for light load |
| Transmission Network Changes | 0 | Description/summary of the Transmission network changes leading up to those years; |