NEC3 Term Service Contract (TSC3)

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________ ) |  |
| for | The Provision of Civil Maintenance Services and spares at Majuba Power Station for 60 months Insert title of the service |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | [●] |
| Part C2 | Pricing Data | [●] |
| Part C3 | Scope of Work | [●] |
| CONTRACT No. |  |  |

PART C1:	AGREEMENTS & CONTRACT DATA

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance | [●] |
| C1.2a | Contract Data provided by the Employer | [●] |
| C1.2b | Contract Data provided by the Contractor | [●] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

The Provision of Civil Maintenance Services and civil spares at Majuba Power Station for 60 months

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

Delete the row for the Options which do not apply

| Options A or C | The offered total of the Prices exclusive of VAT is | R |
| --- | --- | --- |
|  | Value Added Tax @ 15% is | R |
|  | The offered total of the amount due inclusive of VAT is | R |
|  | (in words) |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number: |  | N/A |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Service Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed and signed original copy of this document, including the Schedule of Deviations (if any).

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 TSC3 Contract Data

# Part one - Data provided by the Employer

| Clause |  | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  | ## General |  |  |  |  |
|  |  | The conditions of contract are the core clauses and the clauses for main Option: |  |  |  |  |
|  |  |  | A: Priced contract with price list |  |  |  |
|  |  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |
|  |  | and secondary Options |  |  |  |  |
|  |  |  | X1: Price adjustment for inflation |  |  |  |
|  |  |  | X2 Changes in the law |  |  |  |
|  |  |  | X17: Low service damages |  |  |  |
|  |  |  | X18: Limitation of liability |  |  |  |
|  |  |  | X19: Task Order |  |  |  |
|  |  |  | Z: Additional conditions of contract |  |  |  |
|  |  | of the NEC3 Term Service Contract April 2013 (TSC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |
| 10.1 |  | The Employer is (name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |
|  |  | Tel No. |  |  |  |  |
|  |  | Fax No. |  |  |  |  |
| 10.1 |  | The Service Manager is (name): | N Mthembu |  |  |  |
|  |  | Address | Majuba Power Station Private Bag x 9001 Volksrust 2470 |  |  |  |
|  |  | Tel | 017 799 3755 |  |  |  |
|  |  | Fax | N/A |  |  |  |
|  |  | e-mail | sibiyain@eskom.co.za |  |  |  |
| 11.2(2) |  | The Affected Property is | Majuba Power Station |  |  |  |
| 11.2(13) |  | The service is | The Provision of Civil Maintenance Services and civil spares at Majuba Power Station for 60 months |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register | None |  |  |  |
| 11.2(15) |  | The Service Information is in | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |
| 12.2 |  | The law of the contract is the law of | the Republic of South Africa |  |  |  |
| 13.1 |  | The language of this contract is | English |  |  |  |
| 13.3 |  | The period for reply is | 02 weeks |  |  |  |
| ## 2 |  | ## The Contractor’s main responsibilities | Data required by this section of the core clauses is also provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data |  |  |  |
| 21.1 |  | The Contractor submits a first plan for acceptance within | N/A |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |
| 30.1 |  | The starting date is. | ASAP |  |  |  |
| 30.1 |  | The service period is | 60 Months |  |  |  |
| ## 4 |  | ## Testing and defects |  |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |
| 50.1 |  | The assessment interval is | between the 20 to the 25th day of each successive month. |  |  |  |
| 51.1 |  | The currency of this contract is the | South African Rand |  |  |  |
| 51.2 |  | The period within which payments are made is | Four weeks. |  |  |  |
| 51.4 |  | The interest rate is | the publicly quoted prime rate of interest (calculated on a 365 day year) charged by from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter (and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |  |  |  |
| ## 6 |  | ## Compensation events | None |  |  |  |
| ## 7 |  | ## Use of Equipment Plant and Materials |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |
| 80.1 |  | These are additional Employer's risks | 1. None |  |  |  |
| 83.1 |  | The Employer provides these insurances from the Insurance Table | as stated for “Format TSC3” available on http://www.eskom.co.za/live/content.php?Item_ID=9248 (See Annexure A for basic guidance). |  |  |  |
| 83.1 |  | The Employer provides these additional insurances | as stated for “Format TSC3” available on http://www.eskom.co.za/live/content.php?Item_ID=9248 (See Annexure A for basic guidance) |  |  |  |
| 83.1 |  | The Contractor provides these additional insurances: | N/A |  |  |  |
| 83.1 |  | The minimum amount of cover for insurance against loss and damage caused by the Contractor to the Employer’s property is | the amount of the deductibles relevant to the event described in the “Format TSC3” insurance policy available on http://www.eskom.co.za/live/content.php?Item_ID=9248 |  |  |  |
| 83.1 |  | The insurance against loss of or damage to the works, Plant and Materials is to include cover for Plant and Materials provided by the Employer for an amount of | [●] |  |  |  |
| 83.1 |  | The minimum amount of cover for insurance in respect of loss of or damage to property (except the Employer’s property, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Service for any one event is: | whatever the Contractor deems necessary in addition to that provided by the Employer. |  |  |  |
| 83.1 |  | The minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract for any one event is: | As prescribed by the Compensation for Occupational Injuries and Diseases Act No. 130 of 1993 and the Contractor’s common law liability for people falling outside the scope of the Act with a limit of Indemnity of not less than R500 000 (Five hundred thousand Rands).. |  |  |  |
| ## 9 |  | ## Termination | There is no Contract Data required for this section of the conditions of contract. |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |
| A |  | Priced contract with price list |  |  |  |  |
| 20.5 |  | The Contractor prepares forecasts of the final total of the Prices for the whole of the service at intervals no longer than | Four weeks. |  |  |  |
| ## 11 |  | ## Data for Option W1 |  |  |  |  |
| W1.2(3) |  | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the Institution of Civil Engineers (London) (see www.ice-sa.org.za ) or its successor body. |  |  |  |
| W1.4(2) |  | The tribunal is: | arbitration |  |  |  |
| W1.4(5) |  | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |
|  |  | The place where arbitration is to be held is | As mutually agreed within the boundaries of South Africa |  |  |  |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |
| ## 12 |  | ## Data for secondary Option clauses |  |  |  |  |
| X1 |  | Price adjustment for inflation | On each anniversary of the contract date contract manager and the contractor must confirm the increase/ decrease with the QS department before the revised prices are stated on the invoice. The QS and the contract Manager must confirm the escalation with the financial department before it may be implemented. The CPA adjustment calculated will be the 12 months and will be adjusted on the contract anniversary date. The first 12 months the rates are without escalation. |  |  |  |
| X1.1 |  | The base date for indices is | 1 month before contract start date |  |  |  |
|  |  | The proportions used to calculate the Price Adjustment Factor are: | proportion | linked to index for | Index prepared by |  |
|  |  |  | 0.45 0.30 0.10 | Labour Material Transport | SEIFSA Table C3 (All hourly paid employees) SEIFSA Table G-1 (Building and Construction) SEIFSA Table L2 |  |
|  |  |  | 15% | non-adjustable |  |  |
|  |  |  | 100% |  |  |  |
| X2 |  | Changes in the law | No data is required for this Option |  |  |  |
| X17 |  | Low service damages |  |  |  |  |
| X17.1 |  | The service level table is in | C3:Scope of work |  |  |  |
| X18 |  | Limitation of liability |  |  |  |  |
| X18.1 |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to | R0.0 (zero Rand) |  |  |  |
| X18.2 |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to | the amount of the deductibles relevant to the event described in the “Format TSC3” insurance policy available on http://www.eskom.co.za/live/content.php?Item_ID=9248 |  |  |  |
| X18.3 |  | The Contractor’s liability for Defects due to his design of an item of Equipment is limited to | The greater of - the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s insurance (other than the resulting physical damage to the Employer’s property which is not excluded) plus the applicable deductibles in the Employer’s assets and works / maintenance policies available on http://www.eskom.co.za/live/content.php?Item_ID=9248 |  |  |  |
| X18.4 |  | The Contractor’s total liability to the Employer, for all matters arising under or in connection with this contract, other than the excluded matters, is limited to | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for - Defects due to his design, plan and specification, - Defects due to manufacture and fabrication outside the Affected Property, - loss of or damage to property (other than the Employer’s property, Plant and Materials), - death of or injury to a person and - infringement of an intellectual property right. |  |  |  |
| X18.5 |  | The end of liability date is | One month after the end of the service period. |  |  |  |
| X19 |  | Task Order |  |  |  |  |
| X19.5 |  | The Contractor submits a Task Order programme to the Service Manager within | No programme is to be submitted |  |  |  |
| Z |  | The additional conditions of contract are | Z1 to Z11 always apply. |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Service Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |
| Z2.3 | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Service Manager within thirty days of the notification or as otherwise instructed by the Service Manager. |  |  |  |  |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Service. |  |  |  |  |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P4 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Service Manager. |  |  |  |  |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the Affected Property or any portion thereof, in the course of Providing the Service and after the end of the service period, requires the prior written consent of the Service Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Service Manager or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the service. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Affected Property; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of the service; and - undertakes, in and about the execution of the service, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |
| Z6.2 |  | The Contractor, in and about the execution of the service, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |
| Z7.1 | Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Service Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |
| Z8 | Notifying compensation events |  |  |  |  |  |
| Z8.1 | Delete the last paragraph of core clause 61.3 and replace with: If the Contractor does not notify a compensation event within eight weeks of becoming aware of the event, he is not entitled to a change in the Prices. |  |  |  |  |  |
| Z9 | Employer’s limitation of liability |  |  |  |  |  |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |
| Z9.2 | The Contractor’s entitlement under the indemnity in 82.1 is provided for in 60.1(12) and the Employer’s liability under the indemnity is limited to compensation as provided for in core clause 63 and X19.11 if Option X19 Task Order applies to this contract. |  |  |  |  |  |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |
| Z10.1 | or had a business rescue order granted against it. |  |  |  |  |  |
| Z11 | Ethics |  |  |  |  |  |

For the purposes of this Z-clause, the following definitions apply:

Affected Party	means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends,

Coercive Action	means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally,

Collusive Action	means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally,

Committing Party	means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees,

Corrupt Action	means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party,

Fraudulent Action	means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation,

Obstructive Action	means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action and

Prohibited Action	means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action.

Z 11.1 	A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof.

Z 11.2 	The Employer may terminate the Contractor’s obligation to Provide the Service if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Service for this reason.

Z 11.3 	If the Employer terminates the Contractor’s obligation to Provide the Service for this reason, the procedures and amounts due on termination are respectively P1, P2, P3 and P4, and A1 and A3.

Z 11.4 	A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation.

# Annexure A:	Insurance provided by the Employer

These notes are provided as guidance to tendering contractors and the Contractor about the insurance provided by the Employer. The Contractor must obtain its own advice. Details of the insurance itself are available from the internet web link given below.

- Services provided in a TSC3 contract could include some element of construction or refurbishment as well as a continuous maintenance or operational service activity.  If an event occurs which causes loss or damage, a claim could be made either against the Employer’s “works” type policy which may be in place for the Employer’s portion of the Affected Property concerned or against the Employer’s assets policy which may be in place for the Employer’s portion of the Affected Property concerned, or both.

- The cover provided and the deductibles under the works policy are different to those under the assets policy.   Each policy has a range of applicable deductibles depending on the location of the Affected Property and the nature of the insurable event.

- The Contractor is required in terms of Contract Data for clause 83 to provide cover for the deductibles in the insurance provided by the Employer.  This can be provided from his own resources on a ‘self insured’ basis or obtained by him from his own insurers.   In order to assess the extent of this cover, tendering contractors and their brokers should consult the internet web link given below and scroll to ‘Format TSC3’ to establish both the cover and the deductibles in relation to the service provided in terms of this contract.

- Tendering contractors should note that cover provided by the Employer is only per the policies available on the internet web link listed below and may not be the cover required by the tendering contractor or as intended by each of the listed insurances in the left hand column of the Insurance Table in clause 83.2.  In terms of clause 83.1 “the Contractor provides the insurances stated in the Insurance Table except any insurance which the Employer is to provide”.  Hence the Contractor provides insurance which the Employer does not provide and in cases where the Employer does provide insurance the Contractor insures for the difference between what the Insurance Table requires and what the Employer provides.

- If Marine Insurance is required the Contractor needs to obtain a copy of the latest edition of Eskom’s Marine Policies Procedures found at internet website given below.

- Further information and full details of all Eskom provided policies and procedures may be obtained from:

http://www.eskom.co.za/Tenders/InsurancePoliciesProcedures/Pages/EIMS_Policies_

From_1_April_2014_To_31_March_2015.aspx

C1.2 Contract Data

# Part two - Data provided by the Contractor

Notes to a tendering contractor:

- Please read both the both the NEC3 Term Service Contract April 2013 and the relevant parts of its Guidance Notes (TSC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.

- The number of the clause which requires the data is shown in the left hand column for each statement however other clauses may also use the same data.

- Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |
| --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |
|  | Address |  |
|  | Tel No. |  |
|  | Fax No. |  |
| 11.2(8) | The direct fee percentage is | % |
|  | The subcontracted fee percentage is | % |
| 11.2(14) | The following matters will be included in the Risk Register |  |
| 11.2(15) | The Service Information for the Contractor’s plan is in: |  |
| 21.1 | The plan identified in the Contract Data is contained in: |  |
| 24.1 | The key people are: |  |
|  | 1 Name: |  |
|  | Job: |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  | 2 Name: |  |
|  | Job |  |
|  | Responsibilities: |  |
|  | Qualifications: |  |
|  | Experience: |  |
|  |  | CV's (and further key person's data including CVs) are in . |
| A | Priced contract with price list |  |
| 11.2(12) | The price list is in |  |
| 11.2(19) | The tendered total of the Prices is | R |

# Part 2: Pricing Data

TSC3 Option A

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A |  |
| C2.2 | The price list |  |

C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Term Service Contract (TSC3) core clauses and Option A states:

| Identified and defined terms | 11 11.2 | (12) The Price List is the price list unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (17) The Price for Services Provided to Date is the total of - the Price for each lump sum item in the Price List which the Contractor has completed and - where a quantity is stated for an item in the Price List, an amount calculated by multiplying the quantity which the Contractor has completed by the rate. |
|  |  | (19) The Prices are the amounts stated in the Price column of the Price List. Where a quantity is stated for an item in the Price List, the Price is calculated by multiplying the quantity by the rate. |

This confirms that Option A is a priced contract where the Prices are derived from a list of items of service which can be priced as lump sums or as expected quantities of service multiplied by a rate or a mix of both.

# Function of the Price List

Clause 54.1 in Option A states: “Information in the Price List is not Service Information”.  This confirms that instructions to do work or how it is to be done are not included in the Price List but in the Service Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Service in accordance with the Service Information”. Hence the Contractor does not Provide the Service in accordance with the Price List.   The Price List is only a pricing document.

# Link to the Contractor’s plan

Clause 21.4 states “The Contractor provides information which shows how each item description on the Price List relates to the operations on each plan which he submits for acceptance”.  Hence when compiling the price list, the tendering contractor needs to develop his first clause 21.2 plan in such a way that operations shown on it can be priced in the price list  and result in a satisfactory cash flow in terms of clause 11.2(17).

# Preparing the price list

Before preparing the price list, both the Employer and tendering contractors should read the TSC3 Guidance Notes pages 14 and 15.  In an Option A contract, either Party may have entered items into the price list either as a process of offer and acceptance (tendering) or by negotiation depending on the nature of the service to be provided.  Alternatively the Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in the price list to be prepared and priced by him.

It is assumed that in preparing or finalising the price list the Contractor:

- Has taken account of the guidance given in the TSC3 Guidance Notes relevant to Option A;

- Understands the function of the Price List and how work is priced and paid for;

- Is aware of the need to link operations shown in his plan to items shown in the Price List;

- Has listed and priced items in the price list which are inclusive of everything necessary and incidental to Providing the Service in accordance with the Service Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate item within the Prices or rates of other listed items in order to fulfil the obligation to complete the service for the tendered total of the Prices.

- Understands there is no adjustment to items priced as lump sums if the amount, or quantity, of work within that item later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the (lump sum) Prices is as a result of a compensation event.

## Format of the price list

(From the example given in an Appendix within the TSC3 Guidance Notes)

Entries in the first four columns in the price list in section C2.2 are made either by the Employer or the tendering contractor.

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tendering contractor enters the amount in the Price column only, the Unit, Expected Quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for an item of work which is the rate for the work multiplied by the quantity completed, the tendering contractor enters the rate which is then multiplied by the Expected Quantity to produce the Price, which is also entered.

If the Contractor is to be paid a Price for an item proportional to the length of time for which a service is provided, a unit of time is stated in the Unit column and the expected length of time (as a quantity of the stated units of time) is stated in the Expected Quantity column.

C2.2 the price list

  - General assumptions

    - Unless otherwise stated, items are measured net in accordance with the drawings, and no allowance has been made in the quantities for waste.

    - The Prices and rates stated for each item in the Bill of Quantities shall be treated as being fully inclusive of all, risks, liabilities, obligations, consumables, overheads, profit and everything necessary as incurred or required by the Contractor in carrying out or providing that item.

    - An item against which no Price is entered will be treated as covered by other Prices or rates in the bill of quantities.

    - Unless other wise stated, all prices will include the removal of the     defected material/work and must be included in the price quoted for replacing, installing etc.

Prices must include for all profits, consumables, equipment, products, labour and transport etc:

Price List One:

Plumbing Price List:

| Item No. | Description | Unit | QTY | Rate | Price |
| --- | --- | --- | --- | --- | --- |
| 1 | Replacing Of Pipes In Roofs |  |  |  |  |
| 1.1 | Install Copper Tube Class (O) Plus Capillary Fittings 15MM. | M | 1 |  |  |
| 1.2 | Install Copper Tube Class (O) Plus Capillary Fittings 22mm. | M | 1 |  |  |
| 1.3 | Replace ½’’Galv. Pipes In Roof With 15mm Copper Pipes Class (O) Plus Capillary Fittings | M | 1 |  |  |
| 1.4 | Replace ¾" Galv. Pipes In Roof With 22mm Copper Pipes Class (O) Plus Capillary Fittings | M | 1 |  |  |
| 1.5 | Replace 15mm Polycop Pipes In Roof With 15mm Copper Pipes Class (O) Plus Capillary Fittings. | M | 1 |  |  |
| 1.6 | Replace 22mm Polycop Pipes In Roof With 22mm Copper Pipes Class (O) Plus Capillary Fittings | M | 1 |  |  |
| 1.7 | Replace ½" Galv. Pipes In Roof With ½" Galvanised Pipes Plus Fittings | M | 1 |  |  |
| 1.8 | Replace ¾" Galv. Pipes In Roof With ¾" Galvanised Pipes Plus Fittings | M | 1 |  |  |
| 2 | Pipes In Wall |  |  |  |  |
| 2.1 | Replace ½"Galv. Pipes In Walls With 15MM Copper Pipes Class (O) Plus Capillary Fittings (Cavity).To Make Good With Matching Face Bricks Or Plaster. Note: A Paint Defect To Be Issued For Painting | M | 1 |  |  |
| 2.2 | Replace ¾" Galv. Pipes In Walls With 22MM Copper Pipes Class (O) Plus Capillary Fittings (Cavity).To Make Good With Matching Face Bricks Or Plaster. Note: A Paint Defect To Be Issued For Painting | M | 1 |  |  |
| 2.3 | Replace ½" Galv. Pipes In Walls With 15mm Copper Pipes Class (O) Plus Capillary Fittings (Chased).To Make Good With Matching Face Bricks Or Plaster. Note: A Paint Defect To Be Issued For Painting | M | 1 |  |  |
| 2.4 | Replace ¾"Galv. Pipes In Walls With 22mm Copper Pipes Class (O) Plus Capillary Fittings (Chased).To Make Good With Matching Face Bricks Or Plaster. Note: A Paint Defect To Be Issued For Painting and service provider to supply paint. | M | 1 |  |  |
| 2.5 | Replace ½" Galv. Pipes In Wall With ½" Galv. Pipes With Galv. Fittings (Asbestos Panels) And To Make Good | M | 1 |  |  |
| 2.6 | Replace ¾" Galv. Pipes In Walls With ¾" Galv. Pipes Galv. Fittings (Asbestos Panels) And To Make Good | M | 1 |  |  |
| 2.7 | Replace ½" Galv. Pipes Against Wall With ½"Galv. Pipes And Fittings And To Make Good | M | 1 |  |  |
| 2.8 | Replace ¾" Galv. Pipes Against Wall With ¾"Galv. Pipes And Fittings And To Make Good | M | 1 |  |  |
| 2.9 | Replace ½" Galv. Standpipe | M | 1 |  |  |
| 2.10 | Replace ¾" Galv. Standpipe With Existing | M | 1 |  |  |
| 2.11 | Install 15mm Copper Pipes Class (O) With Fittings, Brass Holder BATS 1.2m Apart | M | 1 |  |  |
| 2.12 | Install 22mm Copper Pipes Class (O) With Fittings, Brass Holder BATS 1.2m Apart | M | 1 |  |  |
| 2.13 | Install ½" Galv. Pipe With Fittings And Galv. Holder BATS 1.2m Apart | M | 1 |  |  |
| 2.14 | Install ¾"Galv. Pipe With Fittings And Galv. Holder BATS 1.2m Apart | M | 1 |  |  |
| 3 | Gutters |  |  |  |  |
| 3.1 | Install An Outlet 100mm X 75mm X 0.78 Gauge | Ea | 1 |  |  |
| 3.2 | Blank Off Existing Outlet 100mm X 75mm X 0.75 Gauge | Ea | 1 |  |  |
| 3.3 | Replace An Offset (Crimped) 100mm X 75mm X 0.75 Gauge | Ea | 1 |  |  |
| 3.4 | Replace A Downpipe (Crimped) With Shoe 100mm X 75mm X 0.75 Gauge | Ea | 1 |  |  |
| 3.5 | Replace A Downpipe Holder Bat 100mm X 75mm X 0.75 Gauge Sq | Ea | 1 |  |  |
| 3.6 | Replace 125mm X 100mm X 0.75 Gauge Gutters | M | 1 |  |  |
| 3.7 | Remove Gutters | M | 1 |  |  |
| 3.8 | Cleaning of gutters | M | 1 |  |  |
| 3.9 | Painting of gutters | M | 1 |  |  |
| 4 | Fittings and Valves |  |  |  |  |
| 4.1 | Replace 15mm Copper Capillary Elbow | Ea | 1 |  |  |
| 4.2 | Replace 22MM Copper Capillary Elbow | Ea | 1 |  |  |
| 4.3 | Replace ½" Galvanised Elbow | Ea | 1 |  |  |
| 4.4 | Replace ¾"Galv Elbow | Ea | 1 |  |  |
| 4.5 | Replace 25MM Plasson Elbow | Ea | 1 |  |  |
| 4.6 | Replace 1" Galvanised Elbow | Ea | 1 |  |  |
| 4.7 | Replace ½"Galv Tee | Ea | 1 |  |  |
| 4.8 | Replace ¾"Galv Tee | Ea | 1 |  |  |
| 4.9 | Replace 15MM Copper Capillary Tee | Ea | 1 |  |  |
| 4.10 | Replace 22MM Copper Capillary Tee | Ea | 1 |  |  |
| 4.11 | Replace 1" Galvanised Tee | Ea | 1 |  |  |
| 4.12 | Replace 25MMPLASON Tee | Ea | 1 |  |  |
| 4.13 | Replace ½" Galvanised Socket | Ea | 1 |  |  |
| 4.14 | Replace ¾" Galvanised Socket | Ea | 1 |  |  |
| 4.15 | Replace 15MM Copper Capillary Coupler CXC | Ea | 1 |  |  |
| 4.16 | Replace 22MM Copper Capillary Coupler CXC | Ea | 1 |  |  |
| 4.17 | Replace 25mm Plasson Adapter | Ea | 1 |  |  |
| 4.18 | Replace ½" Galv. Holder BAT | Ea | 1 |  |  |
| 4.19 | Replace ¾" Galv. Holder BAT | Ea | 1 |  |  |
| 4.20 | Replace 15mm Brass Holder BAT | Ea | 1 |  |  |
| 4.21 | Replace 22mm Brass Holder BAT | Ea | 1 |  |  |
| 4.22 | Fit And Supply ½’ Nipple | Ea | 1 |  |  |
| 4.23 | Fit And Supply ¾’ Nipple | Ea | 1 |  |  |
| 4.24 | Fit And Supply ½’ Socket | Ea | 1 |  |  |
| 4.25 | Fit And Supply ¾’ Socket | Ea | 1 |  |  |
| 4.26 | Replace ½" Galv. Union | Ea | 1 |  |  |
| 4.27 | Replace 3/4" Galv. Union | Ea | 1 |  |  |
| 4.28 | Replace Flexi Connector 300MM X 15MM | Ea | 1 |  |  |
| 4.29 | Replace ¾" Ballostop | Ea | 1 |  |  |
| 4.30 | Replace ½" Ballostop | Ea | 1 |  |  |
| 4.31 | Clean & Repair ½"Ball Valve | Ea | 1 |  |  |
| 4.32 | Clean & Repair ¾" Ball Valve | Ea | 1 |  |  |
| 4.33 | Replace ½" Ball Valve - Cobra Type | Ea | 1 |  |  |
| 4.34 | Replace ¾"Ball Valve – Cobra Type | Ea | 1 |  |  |
| 4.35 | Supply & Install Kwikflow Repair Kit | Ea | 1 |  |  |
| 4.36 | Replace Kwikflow 400 KPA | Ea | 1 |  |  |
| 4.37 | Install Kwikflow 400 KPA | Ea | 1 |  |  |
| 4.38 | Replace Masterflo 400 KPA | Ea | 1 |  |  |
| 4.39 | Install Masterflow 400 KPA | Ea | 1 |  |  |
| 4.40 | Replace Latco Valve Twin Pack | Ea | 1 |  |  |
| 4.41 | Replace Safety Valve | Ea | 1 |  |  |
| 5 | Ground Pipes |  |  |  |  |
| 5.1 | Replace ¾" Galvanised Pipe With 25mm Plasson Pipe Aqua FLOW (Hdpe) Pe80 Class 10 Type 5 & Including Plasson Fittings Excavations 700mm Deep & Backfilling Concrete Etc. (Shortest Route – No Extra Taps – 1 At The Front & 1 At The Back). | M | 1 |  |  |
| 5.2 | 1" 32MM | M | 1 |  |  |
| 5.3 | 1 ¼" 40MM | M | 1 |  |  |
| 5.4 | 1 ½" 50MM | M | 1 |  |  |
| 5.5 | 2" 63MM | M | 1 |  |  |
| 5.6 | 3" 75MM | M | 1 |  |  |
| 5.7 | 4" 90MM | M | 1 |  |  |
| 5.8 | 5" 110MM | M | 1 |  |  |
| 6 | Sewer Drains |  |  |  |  |
| 6.1 | Replacing Of 4" Sewer Drain With 110mm P.V.C Pipe Drains Must Be Fixed, Compact And Backfilled And Lawns Must Be Made Good | M | 1 |  |  |
| 6.2 | Replacing Of 6" Sewer Drain With 150MM P.V.C Pipe Drains Must Be Fixed, Compact And Backfilled And Lawns Must Be Made Good | M | 1 |  |  |
| 6.3 | Replacing Of A 1/4 , 1/8 , 1/16 Bend With 110mm P.V.C | M | 1 |  |  |
| 6.4 | Open Blocked Drains during Normal Working Hours | Ea | 1 |  |  |
| 6.5 | Open Blocked Drains After Hours | Ea | 1 |  |  |
| 7 | Excavation Of Ground |  |  |  |  |
| 7.1 | Excavate | M3 | 1 |  |  |
| 7.2 | Replacing Of Gully Traps 4" With 110mm P.V.C Gully Trap & Installation Of Gully Top (Concrete) Drains Must Be Fixed , Backfilled And Lawns Must Be Made Good | Ea | 1 |  |  |
| 7.3 | Replace Broken Gully Top (Concrete) | Ea | 1 |  |  |
| 7.4 | Lift Gully Top & Gully Tops Must Be Installed With Concrete | Ea | 1 |  |  |
| 7.5 | Re-Install Leaking Gully Top | Ea | 1 |  |  |
| 7.6 | Install New Rodding Eye 110mm P.V.C Drains Must Be Fixed, Backfilled And Lawns Must Be Made Good | Ea | 1 |  |  |
| 7.7 | Replace Rodding – Eye 110mm P.V.C Drains Must Be Fixed, Backfilled And Lawns Must Be Made Good | Ea | 1 |  |  |
| 7.8 | Replace 4" Junction With 110mm P.V.C Drains Must Be Fixed, Backfilled And Lawns Must Be Made Good | Ea | 1 |  |  |
| 7.9 | Laying Of New Drain 110mm. Drains Must Be Fixed, Backfilled And Lawns Must Be Made Good (Fall 1:40) | M | 1 |  |  |
| 7.10 | Excavating Machine | Ea | 1 |  |  |
| 7.11 | Compacting Machine | Ea | 1 |  |  |
| 8 | Fire Equipment |  |  |  |  |
| 8.1 | Replacing Of Existing Fire HOSE Reel Supplied By Eskom (Damaged) | Ea | 1 |  |  |
| 8.2 | Replace Fire Hose Reel Nozzle Supplied By Eskom | Ea | 1 |  |  |
| 8.3 | Replacing Of Fire Hose Complete Eskom To Supply | Ea | 1 |  |  |
| 8.4 | Replace Fire Hose Reel Stop Cocks Supplied By Eskom | Ea | 1 |  |  |
| 9 | Waste Pipes |  |  |  |  |
| 9.1 | Replacing Of 1 ½" Galvanised Waste Pipe With 50MM S.A.B.S. Pvc Pipe (Making Use Of Pvc Glue With Necessary Pipe Clips (1 ½ M Apart ) | M | 1 |  |  |
| 9.2 | Replacing Of 1 ¼" Galvanised Waste Pipe With 40MM S.A.B.S. Pvc Pipe (Making Use Of Pvc Glue With Necessary Pipe Clips (11/2 M Apart) | M | 1 |  |  |
| 9.3 | Installation Of New Waste Pipes 50MM Pvc S.A.B.S. With Necessary Pipe Clips (1 1/2M Apart) | M | 1 |  |  |
| 9.4 | Installation Of New Waste Pipes 40MM Pvc S.A.B.S. With Necessary Pipe Clips (1 1/2M Apart) | M | 1 |  |  |
| 9.5 | Replacing Of Waste Pipes 2" Galvanised | M | 1 |  |  |
| 11 | Basins |  |  |  |  |
| 11.1 | Replacing Of A Wash Hand BASIN (Fit & Supply Complete (2 X Cobra C.P. Heavy Duty, Star Pattern 1/2" Taps And I X Heavy Duty Basin Waste Fitting Brass C.P.) | Ea | 1 |  |  |
| 11.2 | Remove Of Basin And Refit | Ea | 1 |  |  |
| 11.3 | Replacing Of Under TILE Stopcocks (15mm Cp. Fxf Stopcock Under Tile Fig 128 ,Cobra Heavy Duty) In Showers. Tile And Make Good | Ea | 1 |  |  |
| 11.4 | Replacing Of Shower MIXERS In Showers With (15mm Cp. FXF Stopcock Under Tile Fig 128, Cobra Heavy Duty).Tile And Make Good | Ea | 1 |  |  |
| 11.5 | Fit & Supply Of Sink Mixers Cobra Type – Star Pattern C.P. Heavy Duty, Wall Mount Fig 166/041 | Ea | 1 |  |  |
| 11.6 | Fit & Supply Of Bath Mixers Cobra Type Star Pattern C.P. Heavy Duty ¾” Fig 249 | Ea | 1 |  |  |
| 11.7 | Replacing Of A Cast Iron High Level CISTERN With A Low Level P.V.C. Cistern 11 Litres Fit And Supply | Ea | 1 |  |  |
| 11.8 | Replacing Of A Cast Iron Low Level Cistern With A Porcelain Cistern – 11 Litres Fit And Supply | Ea | 1 |  |  |
| 11.9 | Fit And Supply Porcelain 11L Toilet Cistern (White) With Similar Type. | Ea | 1 |  |  |
| 12 | Traps |  |  |  |  |
| 12.1 | Replacing Of Sink P-Trap 1 ½" X 1½"(Flexi) | Ea | 1 |  |  |
| 12.2 | Replacing Of Basin P-Trap 1 ½" X 1 ¼" (Flexi) | Ea | 1 |  |  |
| 12.3 | Replacing Of Basin P-Trap 1 ¼" X 1 ¼" (Flexi) | Ea | 1 |  |  |
| 12.4 | Replacing Of Basin S-Trap 1 ½" X 1 ¼" (Flexi) | Ea | 1 |  |  |
| 12.5 | Replacing Of Basin S-Trap 1 ¼" X 1 ¼" (Flexi) | Ea | 1 |  |  |
| 12.6 | Replacing Of Double Sink -Trap 1 1/2" X 1 1/2" (Flexi) | Ea | 1 |  |  |
| 13 | Geysers |  |  |  |  |
| 13.1 | Drain Geyser | Ea | 1 |  |  |
| 13.2 | Replace Vacuum Breaker – 22MM | Ea | 1 |  |  |
| 13.3 |  |  |  |  |  |
| 13.4 | Remove SQ Geyser And Taps | Ea | 1 |  |  |
| 13.5 | Replace 50l Geysers (Horizontal/ Vertical) Kwikot with 5 year guarantee Geyser To Be Supplied By Contractor. Own Pressure Valve, Vacuum Breakers And Overflows To Be Supplied By Contractor | Ea | 1 |  |  |
| 13.6 | Replace 100l Geysers (Horizontal/ Vertical) Kwikot with 5 year guarantee Geyser To Be Supplied By Contractor. Own Pressure Valve, Vacuum Breakers And Overflows To Be Supplied By Contractor | Ea | 1 |  |  |
| 13.7 | Replace 150l Geyser (Horizontal/Vertical) Kwikot with 5 year guarantee Geyser To Be Supplied By Contractor. Own Pressure Valve, Vacuum Breakers And Overflows To Be Supplied By Contractor | Ea | 1 |  |  |
| 14 | Install Geyser Overflow Pipes With Copper Pipes Class (O) And Capillary Fittings To Fit Valve Specifications. The Pipe Must Protrude On The Outside Wall By 150mm | M | 1 |  |  |
| 14.1 | Install Geyser Valve Overflow With 15MM Copper Pipe Class O With Capillary Fittings | M | 1 |  |  |
| 14.2 | Install Geyser Safety Valve Overflow Pipe With 22mm Copper Pipe & Capillary Fittings | M | 1 |  |  |
| 14.3 | Install Geyser Tray, Including Overflow Pipe S.A.B.S. 50MM P.V.C Fittings, With A Slight Fall To Outlet. To Be Glued With P.V.C Glue, Tray Outlet Fitting To Be Sealed Watertight With Silicone Sealant. | Ea | 1 |  |  |
| 15 | Sink Tops (Various) |  |  |  |  |
| 15.1 | Replace Double Sink Top | Ea | 1 |  |  |
| 15.2 | Replace Single Sink Top | Ea | 1 |  |  |
| 15.3 | Fit Single Zink (Sit-On, Drop-In) With Similar. | Ea | 1 |  |  |
| 15.4 | Fit Double Zink (Sit-On, Drop-In) With Similar. | Ea | 1 |  |  |
| 15.5 | Replace Rubber Cone On Water Inlet From Cistern | Ea | 1 |  |  |
| 15.6 | Replace Beta Valve Complete (Pvc Dpi) | Ea | 1 |  |  |
| 15.7 | Replace Beta Valve Washer | Ea | 1 |  |  |
| 15.8 | Replace Flush PIPE | Ea | 1 |  |  |
| 15.9 | Reseal Flush PIPE | Ea | 1 |  |  |
| 15.10 | Replace Leaking Pan Connector 110mm | Ea | 1 |  |  |
| 15.11 | Repair Leaking Pan Connector 110mm | Ea | 1 |  |  |
| 15.12 | Replace Vanity Basin With Similar Type- Same Taps – New Waste Fittings And Finish Off With Mosaic Tiles | Ea | 1 |  |  |
| 15.13 | Install P.V.C Boss Adapter 110MM X 50MM | Ea | 1 |  |  |
| 15.14 | Replace P.V.C Boss Adapter 110MM X 50MM | Ea | 1 |  |  |
| 15.15 | Replace T-Piece 50MM P.V.C Plain | Ea | 1 |  |  |
| 15.16 | Replace Elbow 900 50MM P.V.C Plain | Ea | 1 |  |  |
| 15.17 | Replace Roof Flashings On Tile Roofs (Similar Type) | M | 1 |  |  |
| 15.18 | Replace Toilet Pan – White P-Trap | Ea | 1 |  |  |
| 15.19 | Replace Toilet Pan – White P – Trap Close Couple | Ea | 1 |  |  |
| 15.20 | Replace 110MM P.V.C Junction I.E Above Ground | Ea | 1 |  |  |
| 15.21 | Replace 110MM P.V.C I .E Bends Above Ground | Ea | 1 |  |  |
| 15.22 | Install 110 Mm P.V.C Kimberly Socket | Ea | 1 |  |  |
| 15.23 | Install Garden Tap ½" Cobra Heavy Duty 108/15 Supply And Fit | Ea | 1 |  |  |
| 15.24 | Replace ½" Garden Tap Cobra Heavy Duty 108/15 Supply And Fit | Ea | 1 |  |  |
| 15.25 | Remove And Blank-Off Garden Taps (Taps To Be Delivered To Cmd Workshop) | Ea | 1 |  |  |
| 15.26 | Remove Blanks And Install Garden Taps. | Ea | 1 |  |  |
| 15.27 | Install Tap ½" Mount ¾” Hose Fitting Plastic Type Cobra Heavy Duty 108/15 Supply And Fit | Ea | 1 |  |  |
| 15.28 | Install Tap ¾”Mount ¾” Hose Fitting Plastic Type Cobra Heavy Duty 108/15 Supply And Fit | Ea | 1 |  |  |
| 15.29 | Replace Tap Washers As Per Defect | Ea | 1 |  |  |
| 15.30 | Install Waste Fitting Cobra 1 ½" (40MM) | Ea | 1 |  |  |
| 15.31 | Replace Waste Fitting Cobra 1 ½" (40MM) | Ea | 1 |  |  |
| 15.32 | Install Basin Waste Fitting 1 ¼" (32MM) | Ea | 1 |  |  |
| 15.33 | Replace Basin Waste Fitting 1 ¼" (32MM | Ea | 1 |  |  |
| 15.34 | Replace Bung Rubber | Ea | 1 |  |  |
| 15.35 | Install 110MM P.V.C End Cap To Blank Off | Ea | 1 |  |  |
| 15.36 | Install 150MM P.V.C End Cap To Blank Off | Ea | 1 |  |  |
| 15.37 | Replace Toilet Seat With Similar Type service provider To Supply | Ea | 1 |  |  |
| 15.38 | Fit And Supply Toilet Seat With Similar Type. | Ea | 1 |  |  |
| 15.39 | Fit And Supply Toilet Pan With Similar Type | Ea | 1 |  |  |
| 16 | Labour |  |  |  |  |
|  | Qualified Plumber – Artisan |  |  |  |  |
|  | Work Done During Working Hours Not Specified by Eskom (Material Supplied By Eskom) Not Specified In Contract. | P/H | 1 |  |  |
| 16.1 | Overtime Rate: 2.00 | Per Hour | 1 |  |  |
| 16.2 | Overtime Rate: 1.50 | Per Hour | 1 |  |  |

Note:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs, which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts, supply of new parts and installation of new parts.

Electrical Price List:

| Item No. |  | Description |  | Unit | QTY | Rate /Including Labour, transport etc. |  | Price |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | To determine the cost to test, remove defective part, supply new part and install new parts. |  |  |  |  |  |  |  |
|  |  | GEYSER |  | Unit | QTY | Rate /Including Labour, transport etc. |  | Price |  |
| 119 |  | Disconnect Geyser as per Plumber Request |  | each | 1 |  |  |  |  |
| 120 |  | Connect Geyser as per Plumber Request |  | each | 1 |  |  |  |  |
| 121 |  | Re-Wiring Geyser |  | each | 1 |  |  |  |  |
|  |  | KWIKOT |  | Unit | QTY | Rate /Including Labour, transport etc. |  | Price |  |
| 122 |  | 150L MKI Kwikot Element + Pocket 3Kw (els-114) |  | each | 1 |  |  |  |  |
| 123 |  | 50L Kwikot Element + Pocket 2Kw (els-112) |  | each | 1 |  |  |  |  |
| 124 |  | 150L VKFII Kwikot Thermostat with leads - TH202 |  | each | 1 |  |  |  |  |
| 125 |  | 50L VKFII Kwikot Thermostat with leads - TH202 |  | each | 1 |  |  |  |  |
| 126 |  | Kwikot Element Flange |  | each | 1 |  |  |  |  |
| 127 |  | Kwikot Element Flange Gasket |  | each | 1 |  |  |  |  |
| 128 |  | C.O.C Certificate Issue |  | Each | 1 |  |  |  |  |
| 129 |  | Testing of Earth Leakages |  | each | 1 |  |  |  |  |
|  |  |  | The total of the Prices (excluding VAT): |  |  |  |  |  |  |

Note:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs, which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts, supply of new parts and installation of new parts.

Brick Layer Price List:

|  | Item No. | Description | Unit | Estimate Quantities | Rate |  |  | Price |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Demolishing of existing concrete slab & casting of a new 25m.p.a concrete slab remove rubble and dump at a registered dumping site | M2 | 1 |  |  |  |  |  |
|  | 2 | Remove existing plaster work & apply new plaster to walls15mm thick RATIO:2 sand x 1 cement | M2 | 1 |  |  |  |  |  |
|  | 3 | Plaster of raw walls | M2 | 1 |  |  |  |  |  |
|  | 4 | Replace of 110mm steel door frame supply and fit | EA | 1 |  |  |  |  |  |
|  | 5 | Replace of 230mm steel door frame supply and fit | EA | 1 |  |  |  |  |  |
|  | 6 | Replace SQ door frame 230mm complete with louver on top. supply and fit | EA | 1 |  |  |  |  |  |
|  | 7 | Replace glass door frame with door complete supply and fit excluding glass and paint | EA | 1 |  |  |  |  |  |
|  | 8 | Replace of double door steel cupboard frame supply and fit | EA | 1 |  |  |  |  |  |
|  | 9 | Replace of single door steel cupboard frame. supply and fit | EA | 1 |  |  |  |  |  |
|  | 10 | Replace of window frame – steel SABS | M2 | 1 |  |  |  |  |  |
|  | 11 | Replace of white glazed wall tiles 150mm² x 150mm² | M2 | 1 |  |  |  |  |  |
|  | 12 | Install of ceramic tiles Install ceramic floor tiles supllied by service provider | M2 | 1 |  |  |  |  |  |
|  | 13 | Replace of ceramic tiles | M2 | 1 |  |  |  |  |  |
|  | 14 | Install mosaic floor tiles | M2 | 1 |  |  |  |  |  |
|  | 15 | Building of 110mm face brick wall on the outside and stock brick on the inside | M2 | 1 |  |  |  |  |  |
|  | 16 | Building of 230mm face brick walls both sides to be face brick (Eskom too supply) | M2 | 1 |  |  |  |  |  |
|  | 17 | Building of 110mm stock brick walls | M2 | 1 |  |  |  |  |  |
|  | 18 | Building of 230mm stock brick walls (both sides to be stock bricks) | M2 | 1 |  |  |  |  |  |
|  | 19 | Apply one layer of glass stone to plastered walls | M2 | 1 |  |  |  |  |  |
|  | 20 | Apply 1 layer of pavelite to floors | M2 | 1 |  |  |  |  |  |
|  | 21 | Cast in situ concrete slab 25MPA. 80mm thick | M2 | 1 |  |  |  |  |  |
|  | 22 | Excavate & cast concrete foundations of brick walls 600mm x 220mm thick 25 MPA | M3 | 1 |  |  |  |  |  |
| Item No. |  | Description | Unit | Estimate Quantities |  | Rate | Price |  |  |
| 23 |  | Excavate and casting of concrete 25MPA | M3 | 1 |  |  |  |  |  |
| 24 |  | Repair of concrete of 25MPA. 80mm Thick | M2 | 1 |  |  |  |  |  |
| 25 |  | Strip ridging completely, replace, SABS approved damp coarse and repair with new mortar solid and oxide to match exciting roof color. By using the existing ridge tiles and replace only the broken tiles. Wash down roof clean working area | M | 1 |  |  |  |  |  |
| 26 |  | Replace of ridging tiles Supply and replace | M | 1 |  |  |  |  |  |
| 27 |  | Replace of roof sheeting IBR Supply and replace | EA | 1 |  |  |  |  |  |
| 28 |  | Replace pre cast pole 4 feet | EA | 1 |  |  |  |  |  |
| 29 |  | Replace pre cast pole 6 feet | EA | 1 |  |  |  |  |  |
| 30 |  | Replace pre cast slab with existing type | EA | 1 |  |  |  |  |  |
| 31 |  | Remove Precast walls 4 feet | M | 1 |  |  |  |  |  |
| 32 |  | Remove Precast walls 6 feet | M | 1 |  |  |  |  |  |
| 33 |  | Erecting of Precast walls 4 feet | M | 1 |  |  |  |  |  |
| 34 |  | Erecting of pre cast wall 6 feet | M | 1 |  |  |  |  |  |
| 35 |  | Breaking down of existing brickwork & remove rubble from sight, dump at registered dumping site | M2 | 1 |  |  |  |  |  |
| 36 |  | Repair window sill asbestos. | M | 1 |  |  |  |  |  |
| 37 |  | Replace window sill asbestos. Supply and fit. | M | 1 |  |  |  |  |  |
| 38 |  | Install window sill, brick. | M | 1 |  |  |  |  |  |
| 39 |  | Install window sill, brick. Fit and supply | M | 1 |  |  |  |  |  |
| 40 |  | Prepare and patch plaster work | M2 | 1 |  |  |  |  |  |
| 41 |  | Preparation and laying of interlocking blocks using exiting blocks | M2 | 1 |  |  |  |  |  |
| 42 |  | Remove existing shower floor slash floor with cement and water before commencing new floor | M2 | 1 |  |  |  |  |  |
| 43 |  | Preparation of cracks in walls up to 5mm with polyfilla to suit existing finishing | M | 1 |  |  |  |  |  |
| 44 |  | Supply and lay paving (interlocking bricks size 65mm thick) | M2 | 1 |  |  |  |  |  |
| 45 |  | Supply & lay paving (interlocking bricks size 85mm thick) | M2 | 1 |  |  |  |  |  |
| 46 |  | Prepare cracks in walls more that 5mm repair with plaster (cement) | M | 1 |  |  |  |  |  |
| 47 |  | Replace soap dish (porcelain with existing type) fit and supply | EA | 1 |  |  |  |  |  |
| 48 |  | Replace toilet paper roll holder – ceramic (porcelain with existing type) fit and supply | EA | 1 |  |  |  |  |  |
| 49 |  | Replace off air bricks – interior , Supply and fit | EA | 1 |  |  |  |  |  |
| 50 |  | Replace of air bricks – exterior, Supply and fit | EA | 1 |  |  |  |  |  |
| 51 |  | Patching of tar roads with tar, Hot and Cold mix | M2 | 1 |  |  |  |  |  |
| 52 |  | Replace Garage floor | EA | 1 |  |  |  |  |  |

|  | The total of the Prices (excluding VAT): |  |
| --- | --- | --- |

Note:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts, supply of new parts and installation of new parts.

Fencing and Welding Price List:

Contractor to include all costs to test, remove defective parts/material, supply of new parts/material and installation of new parts/material.

| item no. | Description | Unit | QTY | Rate Material | Rate Labor | Total Price |
| --- | --- | --- | --- | --- | --- | --- |
| A) INSTALL & ERECT OF FENCING, SINGLE GATE, MOTOR GATE, REWIRING OF fence |  |  |  |  |  |  |
| 1 | Remove & replace Fence 1.2m diamond mesh with 3 strands | M | 1 |  |  |  |
| 2 | Remove & replace corner post 1.800mm x 0.76mm | Ea. | 1 |  |  |  |
| 3 | Remove & Replace Standard Y- Section post | Ea. | 1 |  |  |  |
| 4 | Remove & replace Stay pipe 1.830mm x 50 mm | Ea. | 1 |  |  |  |
| 5 | Remove & replace garden gate 1.200mm x 900mm x 3mm | Ea. | 1 |  |  |  |
| 6 | Supply and install catch on garden gate | Ea. | 1 |  |  |  |
| 7 | Remove & replace double leaf motor gate 1.300mm | Ea. | 1 |  |  |  |
| 8 | Supply and install catch on motor gate on parameter fence | Ea. | 1 |  |  |  |
| Palisade and Palisade Fence Repair Work: |  |  |  |  |  |  |
| 1 | Supply and Install Palisade Section with existing Installed Type / 3m Section | Ea. | 1 |  |  |  |
| 2 | Repair Bend Palisade Fence | Ea. | 1 |  |  |  |
| 3 | Replace Palisade Post 75mm x 75mm | Ea. | 1 |  |  |  |
| Steel Doors and Gates |  |  |  |  |  |  |
| 11 | Supply & Install Of Steel SQ Doors (0,755mm x 1,970mm) | Ea. | 1 |  |  |  |
| 12 | Supply & Install Steel Courtyard Gate (0,895mm x 1,850mm x 25mm) | Ea. | 1 |  |  |  |
| 13 | Supply & Install Steel Courtyard Gate (0.930mm x 1.860mm x 25mm) | Ea. | 1 |  |  |  |
| 14 | Supply & Install Courtyard Steel Gate Handles | Ea. | 1 |  |  |  |
| 15 | Supply & Install Courtyard Steel Gate Hinge + Bracket |  | 1 |  |  |  |
| 16 | Supply & Install Locks on Steel Security Doors A) Ultra Lock Small (120mm x 85mm x 28mm) B) Toolmaster HL0556 C) Dejuca HL160 | Ea. | 1 |  |  |  |
| 17 | Supply & Install Steel Security Doors complete with Lock | Ea. | 1 |  |  |  |
| Steel Window Frames |  |  |  |  |  |  |
| 18 | Install Steel Burglar Proofing | m2 | 1 |  |  |  |
| 19 | Supply & Install Window Handle | Ea. | 1 |  |  |  |
| 20 | Supply & Install Window Slides | Ea. | 1 |  |  |  |
| 21 | Supply & Install Window Peg Stays | Ea. | 1 |  |  |  |
| Steel Downpipes and Channels |  |  |  |  |  |  |
| 22 | Supply & Install Veranda Downpipe with Existing Type (2.500mm x 75mm x 4mm) | m | 1 |  |  |  |
| 23 | Supply & Install Veranda Rain Channel with Existing Type (0.020mm x 0.030mm x 0.075mm x 0.120mm x 0.020mm x 3mm) See Drawing: 20mm 20mm 120mm 30mm 75mm | m | 1 |  |  |  |
| Repair and Re-Fit |  |  |  |  |  |  |
| 6 | Re-Fitment of Courtyard Door Handles | Ea. | 1 |  |  |  |
| 7 | Repair Hinge + Bracket on Courtyard Gate | Ea. | 1 |  |  |  |
| 8 | Repair Bend Steel Security Doors | Ea. | 1 |  |  |  |
| 9 | Repair Locks on Steel Security Doors | Ea. | 1 |  |  |  |
| 10 | Repair Steel Burglar Proofing | Ea. | 1 |  |  |  |
| 11 | Repair Window Handle Bracket | Ea. | 1 |  |  |  |
| 12 | Repair Window Sliding Stay Bracket | Ea. | 1 |  |  |  |
| 13 | Repair Window Peg Stay Bracket | Ea. | 1 |  |  |  |
| 14 | Repair Bend Window Frame | Ea. | 1 |  |  |  |
| 15 | Repair Bend Glass Door Frame | Ea. | 1 |  |  |  |
| 16 | Rectify Steel Glass Door Frame | Ea. | 1 |  |  |  |
| 17 | Rectify Steel Window Frame | Ea. | 1 |  |  |  |
| 18 | Remove excessive steel alterations from standard steel railings and bring back to Standard Specification | Ea. | 1 |  |  |  |
|  |  |  |  |  | TOTAL: |  |

Notes:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts/material, supply of new parts/material and installation of new parts/material.

Carpet and Tiles Price List:

| Item nr | Description | Unit | QTY | Rate | Price |
| --- | --- | --- | --- | --- | --- |
| 1 | Supply and install Belgotex Berber point 920 Carpets | M² | 1 |  |  |
| 2 | Supply and install Belgotex “Portrait Earth” | M2 | 1 |  |  |
| 3 | Repair screeding | M2 | 1 |  |  |
| 4 | Fit new quarter round | M | 1 |  |  |
| 5 | Install new black plastic skirting MCB70 Black | M | 1 |  |  |
| 6 | Install 2mm thick Marley tiles color 682 | M2 | 1 |  |  |
| 7 | Stretching per room | EA | 1 |  |  |
| 8 | Supply and fit tiles: Killimanjaro African Slate | M2 | 1 |  |  |
| 9 | Supply and fit tile skirting | M | 1 |  |  |
| 10 | Supply and fit PVC corner strip color light gray | M | 1 |  |  |
|  |  |  |  | Total: |  |

Notes:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts/material, supply of new parts/material and installation of new parts/material.

Painting Price List:

| Item | Description | Unit | Quantity | RATE | TOTAL |
| --- | --- | --- | --- | --- | --- |
| 1 | EGGSHELL ENAMEL IVORY PLASCON/IVORY (WALLS INSIDE) | M² | 1 |  |  |
| 2 | PVA PLASCON (CEILINGS) | M² | 1 |  |  |
| 3 | WHITE VELVAGLO PLASCON (CEILINGS) | M² | 1 |  |  |
| 4 | WHITE ENAMEL PLASCON/STEELPRIMER PLASCON (WINDOW FRAMES INSIDE) | EA | 1 |  |  |
| 5 | WHITE ENAMEL PLASCON/STEELPRIMER PLASCON (WINDOW FRAMES OUTSIDE) | EA | 1 |  |  |
| 6 | MUSHROOM ENAMEL PLASCON (DOORS IF PAINTED) | EA | 1 |  |  |
| 7 | MUSHROOM ENAMEL PLASCON (STEEL DOORS ) | EA | 1 |  |  |
| 8 | VARNISH UV RESISTANT (DOORS IF NOT PAINTED) | EA | 1 |  |  |
| 9 | PWD BLACK ENAMEL PLASCON (SKIRTING) | M | 1 |  |  |
| 10 | BLACK ENAMEL PLASCON (DRAINS/STEPS/DRAIN PIPES) | M | 1 |  |  |
| 11 | BLACK ENAMEL PLASCON (Steps and floors) | M² | 1 |  |  |
| 12 | CREAM ENAMEL PLASCON (PELMETS) | EA | 1 |  |  |
| 13 | GARAGE WALLS PVA PLASCON | M² | 1 |  |  |
| 14 | NEW ROOF PLASCON (GARAGE DOOR/FRAME) | M² | 1 |  |  |
| 15 | NEW ROOF PLASCON/GALVANIZED PRIMER PLASCON (GUTTERS) | M | 1 |  |  |
| 16 | NEW ROOF PLASCON/GALVANIZED PRIMER PLASCON (DOWN PIPES) | M | 1 |  |  |
| 17 | NEW ROOF PLASCON (FACIA BOARDS and BARGE BOARDS) | M | 1 |  |  |
| 18 | SILVERSHINE PLASCON (OUTSIDE GATES) | EA | 1 |  |  |
| 19 | SILVERSHINE PLASCON (FENCE POLES) | EA | 1 |  |  |
| 20 | MICATEX PLASCON EXTERIOR | M² | 1 |  |  |
| 21 | MUSHROOM ENAMEL PLASCON/STEEL PRIMER (SAFETY DOOR) | EA | 1 |  |  |
| 22 | BLACK ENAMEL (WINDOW SILLS) | EA | 1 |  |  |
| 23 | NEW ROOF PLASCON (COURTYARD GATE) | EA | 1 |  |  |
| 24 | CUPBOARD WALLS INSIDE (Bedroom) | m² | 1 |  |  |
| 25 | CUPBOARD (Kitchen) Steel | m² | 1 |  |  |
| 26 | WALLS INSIDE (KITCHEN/BATHROOMS) | M² | 1 |  |  |
| 27 | WHITE ENAMEL PLASCON BATHROOM CABINET | EA | 1 |  |  |
| 28 | MUSHROOM ENAMEL PLASCON DOOR FRAMES | EA | 1 |  |  |
| 29 | INDUSTRIAL PPE WORK PAINTING | M² |  |  |  |

| The total of the Prices |  |
| --- | --- |

Notes:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts/material, supply of new parts/material and installation of new parts/material.

Glazing Price List:

| Item nr | Description | Unit | QTY | Rate | Price |
| --- | --- | --- | --- | --- | --- |
| 1. | Supply and install 3mm clear float glass | M² | 1 |  |  |
| 2. | Supply and install 4mm clear float glass | M² | 1 |  |  |
| 3. | Supply and install 4mm obscure glass | M² | 1 |  |  |
| 4. | Supply and install 5mm clear float glass | M² | 1 |  |  |
| 5. | Supply and install 6.38 mm shatterproof glass | M² | 1 |  |  |
| 6. | Supply and install 3mm mirror | M² | 1 |  |  |
| 7. | Supply and install shower door Pivot | EA | 1 |  |  |
| 8. | Supply and install shower door Tri Glide doors | EA | 1 |  |  |
| 9. | Supply and install putty | M | 1 |  |  |

| The total of the Prices |  |
| --- | --- |

Notes:

The quantities as listed in the Contract Price List are based on visual inspections done by the Employer’s Contract Supervisor, hence they are only estimates. The Contractor should thus not take this as final. The works required will be confirmed by the Employer’s Contract Supervisor or Employer’s Representative at an ad-hoc basis during the course of the Contract.

Road maintenacne price list and unblocking

| Item | Description | Unit | Quantity | RATE | TOTAL |
| --- | --- | --- | --- | --- | --- |
| 1 | Roller | EA | 1 |  |  |
| 2 | Excavator | EA | 1 |  |  |
| 3 | TLB | EA | 1 |  |  |
| 4 | Tipper truck | EA | 1 |  |  |
| 5 | Vacuum truck | EA | 1 |  |  |
| 6 | Rope excess | EA | 1 |  |  |
| 7 | High pressure | EA | 1 |  |  |
| 8 |  | EA | 1 |  |  |
| 9 |  | M | 1 |  |  |
| 10 |  | M | 1 |  |  |
| 11 |  | M² | 1 |  |  |
| 12 |  | EA | 1 |  |  |
| 13 |  | M² | 1 |  |  |
| 14 |  | M² | 1 |  |  |
| 15 |  | M | 1 |  |  |
| 16 |  | M | 1 |  |  |
| 17 |  | M | 1 |  |  |
| 18 |  | EA | 1 |  |  |
| 19 |  | EA | 1 |  |  |
| 20 |  | M² | 1 |  |  |
| 21 |  | EA | 1 |  |  |
| 22 |  | EA | 1 |  |  |
| 23 |  | EA | 1 |  |  |
| 24 |  | m² | 1 |  |  |
| 25 |  | m² | 1 |  |  |
| 26 |  | M² | 1 |  |  |
| 27 |  | EA | 1 |  |  |
| 28 |  | EA | 1 |  |  |

core crew to be on site full timE

| Item No. | Description | UoM | Qty | No. of people | Rate per Hr | Rate per Month | Total Amount |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Maintenance Services: |  |  |  |  |  |  |
| 1.1 | Engineer | Mon | 60 | 1 |  |  |  |
| 1.2 | Supervisor | Mon | 60 | 1 |  |  |  |
| 1.3 | Technicians | Mon | 60 | 2 |  |  |  |
| 1.4 | Carpenter | Mon | 60 | 1 |  |  |  |
| 1.5 | Plumber | Mon | 60 | 1 |  |  |  |
| 1.6 | Assistance | Mon | 60 | 5 |  |  |  |
| 2 | Other: |  |  |  |  |  |  |
| 2.1 | Standby Costs | Mon | 60 |  |  |  |  |
| 2.2 | Medical Test | Year | 5 |  |  |  |  |
| 2.3 | Site Establishment | sum | 1 |  |  |  |  |
| 2.4 | Site de establishment | sum | 1 |  |  |  |  |
| 3 | Transport: |  |  |  |  |  |  |
| 3.1 | Travelling | Mon | 60 |  |  |  |  |
|  | The total of the Prices (excluding VAT): |  |  |  |  |  |  |

Note:

Tenderers shall allow in their rates for the cost of all materials, labour, transport, profit, supervision and all other costs, which may be incurred in the proper execution of the works (access, compressed air, water, electricity etc). This could also include, but not be limited to levies payable to any industrial councils, associations, etc that may be due by the tenderer, the cost of compliance to legislation, for instance regarding Health and Safety, compliance with Labour Legislation, etc. and all costs to test, remove defective parts, supply of new parts and installation of new parts.

Part 3: Scope of Work

| Document reference | Title |
| --- | --- |
|  | This cover page |
| C3.1 | Employer’s Service Information |
| C3.2 | Contractor’s Service Information (insert at award stage or delete if not applicable) |

C3.1: Employer’s service Information

Table of Contents

Part 3: Scope of Work	1

C3.1: Employer’s service Information	2

1.	Description of the service	5

1.1	Executive overview	5

1.2	Interpretation and terminology	6

1.3	Employer’s requirements for the service	6

1.3.1	Specific Building and Civil works description	6

1.3.2	Roles and responsibilities	12

1.3.3	Manpower requirements for the service	14

1.3.4	Maintenance Philosophy	15

1.3.5	Outage and Opportunity Work	16

1.3.6	Shift and Standby	16

1.3.7	Modifications	16

1.3.8	Working Hours	16

1.3.9	Spillages and leaks	16

1.3.10	House keeping	17

1.3.11	Maintenance Planning	17

1.3.12	Quality Control	18

1.3.13	Welding and Rigging Service related to the Execution of Work	18

1.3.14	Strike Action	18

1.3.15	KPIs	19

1.3.16	Procedures	19

1.3.17	Contract Conclusion	19

1.4	Meetings	19

1.5	Contractor’s management, supervision and key people	20

1.6	Documentation control	21

1.7	Invoicing and payment	21

2.	Health and safety, the environment and quality assurance	21

2.1	Health and safety risk management	21

2.1.1	Eskom Life Saving Rules	21

i.	Plant Safety Regulations	22

ii.	Fire Precautions	22

iii.	Reporting of incidents	22

iv.	Vehicle Safety	22

v.	Barricading / Screens and Scaffolding	23

vi.	Health and Safety Arrangements	23

vii.	Company Branding	24

viii.	Special requirements	24

ix.	Exposure to Silica	24

2.2	Environmental constraints and management	24

2.2.1	Work carried out in terms of:	24

2.2.2	New Environmental Legislation	25

2.2.3	Existing Environmental Legislation	25

2.2.4	Liability	25

2.2.5	Hazardous substances	25

2.3	Quality control and assurance requirements	25

2.3.1	Personal Competency	25

2.3.2	Quality Requirements	25

2.3.3	Quality Control Documents	25

3.	Procurement	26

3.1	Subcontracting	26

3.2	Plant and Materials	26

3.2.1	Correction of defects	26

3.2.2	Plant & Materials provided “free issue” by the Employer	26

4.	Working on the Affected Property	26

4.1	Employer’s site entry and security control, permits, and site regulations	26

4.1.1	Security and Access Arrangements	26

4.2	People restrictions, hours of work, conduct and records	27

4.2.1	Only authorised persons may have site access and perform work.	27

4.2.2	Majuba Power Station normal working hours are:	27

4.2.3	Working Hours	27

4.2.4	Removal from Site	27

4.3	Health and safety facilities on the Affected Property	27

4.4	Cooperating with and obtaining acceptance of others	28

4.5	Records of Contractor’s Equipment	28

4.6	Equipment provided by the Employer	28

4.6.1	Scaffolding	28

Scaffolding can be supplied after notification and call-out of the relevant scaffolding service provider.  Other equipment such as forklift and cranes may be supplied upon request and if available at the time on site.	28

4.6.2	Rigging	28

4.7	Site services and facilities	28

4.7.1	Provided by the Employer	28

4.7.2	Provided by the Contractor	28

4.7.3	Contractor’s yard	28

4.8	Control of noise, dust, water and waste	29

4.8.1	Waste Disposal	29

4.8.2	Noise	29

4.9	Tests and inspections	29

5.	Service Level Table	29

6.	List of Documents	30

6.1	Drawings issued by the Employer	30

# Description of the service

Majuba Power Station is ageing. The older the power station gets, the more the civil structures, buildings and components deteriorate. There is a need for maintenance on all civil components at Majuba power station, for infrastructure to be restored to an acceptable state by means of repair work, replacement and site expansion as and when required.

## Executive overview

The contract services required are for the civil maintenance. This consists of but not limited to, planned and corrective maintenance as per the approved civil maintenance strategy. The delivery of this service includes all spares required to execute the works.

The services include the following:

- The Contractor provides a core site crew and logistics to manage and perform daily, routine maintenance, breakdown/ emergency maintenance activities and outage work.

- The Contractor performs planned, corrective, preventative, opportunity and Outage Maintenance. Corrective maintenance will involve standby and overtime hours worked.

- Preventative & corrective maintenance involves job cards that will be printed, filled and submitted daily after work is done.

- The Contractor supply all spares required to execute works.

- The Contractor provides tools and equipment required by the site crew.

- The Contractor implements minor projects and modifications as required by the Employer.

- The Contractor service and refurbish civil structures in house.

- The Contractor drives the availability of spares and co-ordinate supply of maintenance items to execute the job just on time.

- The Contractor performs all planning and scheduling associated with the Plant in line with the Eskom Work Management Process.

- The Contractor provides qualified and competent teams with all the necessary equipment to provide the Service.  The Contractor’s teams must always be led and Supervised by Qualified, Competent and experienced supervisor.

- The Contractor ensures that the contracted service is performed regardless of strike and industrial action.

- The Contractor establishes his own yard with all the relevant facilities on the site indicated by the Employer.

- The Contractor’s responsibility is to keep the plant running at 95% availability regardless of any challenges they may arise, the Contractor will be deemed competent to help Eskom maintain availability.

- The Contractor performs quality control and risk assessments on all activities

- The Contractor perform maintenance activities to the SHEQ requirements, including Plant Safety Regulations

- The Contractor maintain a safe and hygiene working environment and culture

- In conjunction with the Employer,  the Contractor perform continuous improvement and cost reduction initiatives

## Interpretation and terminology

The following abbreviations are used in this Service Information:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| FPG | Functional Plant Group |
| INO | Initial Notification of Occurrence |
| OEM | Original Equipment Manufacturer |
| PSR | Plant Safety Regulations |
| RBO | Reliability Based Optimisation |
| SAP | System Application Product |
| NEC | New Engineering Contract |
| KPI | Key Performance Indicators |
| SMP | Standard Maintenance Package |
| QCP | Quality Control Plan |

## Employer’s requirements for the service

### Specific Building and Civil works description

Job Specific tools and material/spares shall be provided by the Contractor

#### Painting

- Interior  and External wall

- Ceiling

- IBR Roofs

- Concrete roof

- Gutters

- Fencing

- Steel Palisade

- Building signage

- Road Marking

- Barriers

- Carports

- Carport roof

- Carport post and support structure

#### Plumbing

- All plumbing to comply with SANS 10400-P.

- All plumbing to be carried out by a registered plumber.

##### Portable water pipes repair and replacement

- New portable water pipes

- Unblocking pipes

##### Drainage Systems

- Sewer and drainage

- Waste pipes

- Roofs

- Wall pipes

- Ground pipes

##### Gutters and downpipes

Existing galvanised gutters and downpipes:

- Where damages are identified, repairs are to be performed or replaced when recommended and authorised.

##### Geysers

- New geyser

- New geysers need to be installed with complete plumbing and valves as and when required.

- Replace the defective geyser components.

##### Valves

- Replacement of Isolating Ball valves.

- Replacing under tile stopcock (15mm cp. FXF stopcock cobra heavy duty)

##### Kitchen sink and wash basin

Repair and replacement of kitchen sink and wash basin components.

##### Toilet

Repair and/ or replacement of toilet components

##### Showers

Repair and replace shower components as and when required.

##### Urinals

Repair or/ and replacement of urinal flush master system and its components.

##### Blockages

- Job Specific Tools shall be provided by the Contractor.

- Pipe, drain and sewerage blockages are to be attended to by unblocking where there is a problem with

- the flow through the pipes

- Excavation is a required service for underground systems access to work on pipes.

- Gully trap access work is a required service from Contractor

- Unblock sub-soil drains, including breaking of concrete and digging to open drains

- Drains should be unblocked using rods, jetting machines or pressure system.

- Solid objects should be removed manually and overgrown vegetation should be removed, avoiding

- blockage and flow ‘resistance

- Pipe replacement should be as per existing diameter and material not unless instructed by the

- Engineer/Civil Maintenance Supervisor.

- Cleaning of catch pits and manholes should be done manually and to ensure proper drainage is restored

- Vacuum truck/machine to be used on drains and septic tanks where necessary

#### Masonry

- Bricklaying

- Plastering

- Foundations

- Tiling

- Wall and floor

- Ceramic and vinyl

- Excavate and backfilling

- Wall chasing

- Demolition work

- Cement slabs

- Paving

- Door frames replacement

- Window frame replacement

#### Glazing

Job Specific Tools shall be provided by the Contractor.

Types of glass include:

- Frosted

- Tinted

- Clear

- All glazing will be done with safety glass

- Mirrors 4mm clear float glass

- 4mm obscure glass (pacific)

- 6mm Georgian glass

- 6mm clear float glass

- Standard shower door glass, including door frame (+/-900mm)

- 3 panel sliding door (including frame+/- 900mm).

- Re-install glass

#### Carpentry

Job Specific Tools shall be provided by the Contractor. Contractor is to repair or replace the following as and when required.

- All types of wood doors, hinges, locks, handles, air-vents

- Auto door closer adjustments

- Facier boards

- Ceilings- nutec boards 3mm

- Bishop strips- 6mm and 3mm

- Shelves

- Wood boxes

- Notice boards

- Counter tops (marble-lite)

- Hung Picture frames	'

- Hung ceilings

- Skirting- quarter round skirting

- Hand rails, Shower Curtain rails and Towel rails (chrome)

- Soap Dishes (chrome)

- Shower plastic skirting

- Shower and toilet indicator locks (chrome)

- Barrel bolts- 15mm to 100mm

- Broken roof tiles

- Remove and replace 38mm x 38mm SA pine

- Remove and replace 38mm x 152mm SA pine

- Remove and replace 50mm x 76mm SA pine

- Remove and replace 75mm x 228mm

- Supply and install SA pine block board, 22mm

- Remove and replace Merante skirting

- Remove and replace ¼ rouund Merante

- Supply and install 6mm tampered hard board

- Remove and replace ceiling board with Nu Tee, 3-4-6mm

- Remove and replace cornice (cladded cove)

- Remove and replace bishop strips, 3-4-6mm

- Remove and replace facia board (NuTee)

- Remove and replace big striking plate

- Remove and replace small striking plate

- Remove and replace half moulded striking plate

- Remove and replace brass goose neck barrel bolt, 50mm; 76mm; 100mm

- Remove and replace Chrome round handle, 30mm; 50mm

- Remove and replace'i1at lock, 64mm; 75mm

- Remove and replace'-interior wooden door (sapele)

- Remove and replace exterior wooden door (meranti close back)

- Remove and replace'butt hinge

- Remove and replace oval cylinder lock

- Remove and replace 4 and 2 lever union locks

- Remove and replace night latch lock union

- Remove and replace push button lock chrome union xliv

- Remove and replace 3 lever lock

#### Fencing

Job Specific Tools shall be provided by the Contractor. Repair, removal and replacement of fencing include all components that comprise a fence structure i.e. upright sections and support poles and corner sections. Where Fencing is identified as damaged, it is to be repaired or a section replaced as per requirement.

Fence types include the following:

- Wire Mesh fence

- Diamond Mesh fence

- Steel and Concrete Palisades

- Gate

- Remove and replace diamond mesh fence

- Remove and replace corner post (included where necessary concrete re-enforcement)

- Remove and replace standard Y section post (included where necessary concrete re- enforcement)

- Remove and replace diamond mesh gate, 900mm

- Remove and replace diamond mesh gate, 3000mm (double gate)

- Supply and replace 3 spike palisade fencing

- Supply and replace 3m palisade gate

#### Reinforced concrete works

- Repairs to concrete structural cracks, spooling and other associated failures

- Casting  of plinths, beams, slabs, and etc

- Concrete waterproofing application/ repairs

### Roles and responsibilities

#### Roles and responsibilities

- The Contractor is to execute scope as laid out within this document in order to fulfil the maintenance requirements within the entire Majuba Power station Site on a day to day basis.

- The Contractor shall plan 12 weeks in advance on scope of work to be carried out and lock down weekly scope of work every week in a weekly lockdown meeting in order facilitate proper planning and work management. Within the lockdown meeting there shall be an agreement with employer to lockdown scope for the week ahead and ensure availability of all necessary material spares and access for work execution in compliance with the Employers SAP system process.

- The onus is with the Contractor to use all relevant SANS standards and Eskom Procedures to    execute the works.

#### Supervisor minimum duties

- Work/task planning and co-ordination

- Functional Plant Group (FPG) co-ordination

- Liaise with other supervisors, engineers, etc

- Make recommendations regarding spares stock holding

- Give input into the Life Cycle planning process

- Attend daily production planning and other relevant meetings

- Responsible person for safety, as per Majuba Power Station requirements, and compliance to

- Eskom affiliated safety system requirements

#### Other personnel involvement

- The writing up and/or revising and registering of plant and work related procedures in the Eskom system.

- The writing and/or revising and registering of quality control documents and programs in the Eskom system.

- Trouble shooting and problem solving.

- Attend Reliability Cantered maintenance (RBO) sessions.

- Outage related work including preparing scopes of work, planning, execution, report writing and meeting attendances etc

- Responding to call-outs

#### Process for monitoring

It shall be necessary to have;

- Weekly meetings - scope discussion and lockdown meetings

- Weekly inspections where the employer shall inspect and sign-of the Contractors work or initiate rework

on defective work.

- Other meetings shall be initiated as and when required.

### Manpower requirements for the service

Minimum manpower required:

| Skilled required | Number of people | Minimum Qualification | Related Experience (Years) | Eskom Task grading |
| --- | --- | --- | --- | --- |
| Technical supervisor | 1 | National Diploma Civil Engineering + 3yrs related experience+ NEC3/ECC | 3 | T13 |
| Technician | 3 | ND Civil Diploma | 3 | T11 |
| Artisan Plumber | 1 | Grade 12 + Trade test | 3 | T7 |
| Artisan Carpenter | 1 | Grade 12 + Trade test | 3 | T7 |
| Artisan Masonry | 1 | Grade 12 + Trade test | 3 | T7 |
| Painter | 2 | Qualified painter | 3 | T5 |
| Semi-skilled | 5 | Grade 12 | 3yrs civil maintenance/ construction | T5 |
| Safety officer | 1 | Safety diploma + 2yrs experience | 2 | T11 |
| Engineer | 1 | BSC/ B-COM in Civil Engineering + 3yrs related experience+ NEC3/ECC ECSA Registration | 3 | P13 |

### Maintenance Philosophy

#### Running Maintenance

Running maintenance inspections is seen as the Daily walk downs that will be done by the Contractor.  During these walk downs qualified & experienced artisans will do inspections while the plant is in operation.  All defects or potential failures will be recorded in SAP as a basis for planning and history capturing.  The Inspections will be documented by the Contractor.

The defects will be listed and corrective actions will be planned according to the priority of the defects. The detailed planning of critical/major activities, together with, Standard Maintenance Package (SMP) including QCP’s and risk assessments will be done by the Contractor and approved by the Service Manager.  Where Permits to Work are required, the work will be planned with the Production Manager of Majuba P/S via the Service Manager.

#### Planned Maintenance

Planned maintenance schedules initiated by Employer will be followed to prevent any potential breakdowns or failures of civil structures/components.

#### Corrective and Breakdown Maintenance

All unpreventable and unforeseen plant failure occurrences, replacement of damaged structure/ components are included.

The Authority for determining the criticality of Work rest with the Production Managers , repairs to plant on breakdown are to start as soon as the plant is ready for access where safety is been declared green and continue until the plant is back in operation on a 24hr cycle unless discussed with Eskom authorities that single day shift is sufficient.  Except for safety reasons the Service manager’s permission is required to postpone breakdown work.

#### Daily Plant Inspections

Defects that put the plant and personnel at risk are to be reported to the Eskom Supervisor or Service Manager immediately and action taken to correct the fault as soon as possible.

It is expected that all plant deterioration or faults be identified and corrected by the Contractor before they become a major risk to the plant or a break down.

#### Repair Times

Eskom’s Works Management process requires that work be prioritised and that corrective action be taken as follows:

- Priority 1 – 24 hours to affect the repair

- Priority 2 – 72 hours to affect the repair

- Priority 3 – planned and completed within 5 weeks

#### Revision of Maintenance Scope

The Maintenance Schedule is reviewed annually as part of the Reliability Basis Optimising process.

Improvements to the Preventative Maintenance Strategy in line with the RBO process are expected during the duration of the contract. This is regarded as an opportunity for the contractor to contribute to the strategy for a positive change

The Contractor makes experienced personnel available for the revision of Maintenance Strategies throughout the RBO process.

### Outage and Opportunity Work

Maintenance Opportunities are sometimes provided on short notice. When a Unit comes down for repairs it is expected that all outstanding work on the units is planned, in readiness for execution on short notice and that when the Unit returns to service that there are no outstanding Work orders on planned or Corrective actions.

### Shift and Standby

This Contract makes allowance for Standby:

- The Contractor should have at least two person on stand-by after hours.

- If a person was called-out and is not available the next day, a backup person should be provided to

cover the key person’s duties during normal hours, if an emergency breakdown occurs.

- The person providing standby duties, should know the plant.

- In case of a call-out, the person on stand-by should be on site within 45 min.

- Standby roster should be submitted to EOD and should be up-to-date.

### Modifications

Only approved modifications with the appropriate Drawings and documentation authorised by the Eskom modifications committee through the plant system engineer or a recognised alternative engineer will be allowed on the affected plant.

### Working Hours

The Contractor’s personnel including the Supervisors will be on site during Eskom working hours as specified in 4.2.3 below.

### Spillages and leaks

The Prevention of Spillages is viewed to be very important for ensuring plant housekeeping and should be actioned as one of the top priorities.

Any leak must be attended to Immediately, It is acceptable that a Short term repair is instituted immediately and then a permanent repair be effected on a planned opportunity.

Any spillage caused as a direct result of the Contractor will be cleaned by the Contractor at Their Cost.

### House keeping

#### General Plant

The Contractor is to ensure that the Plant area where work is to be performed is clean before and during the maintenance process.  Possible sources of contamination are to be addressed by the contractor Before Work Starts.

All materials, consumables and spares (new, used or damages) etc. are to be removed from the Plant and deposited in the appropriate areas.

These are unless otherwise directed by the Employer:

- All Spares whether Damaged, Repaired or New are to be Booked into the Majuba Store.

- Scrap steel is to be deposited in the allocated metals Bins at the Africa Store.

- Domestic waste is to be deposited in rubbish bins or a Domestic waste skip.

- Oil used or new is to be returned to the oil Store.

- Hazardous and contaminated Material or waste is to be deposited in the Skips provided for this purpose,    usually at the Fuel oil offloading Station.

It is important that when stripping nuts and bolts in the plant the contractor must provide for themselves designated containers to keep such during work progress. Hence it is prohibited to leave bolts on the ground or floor

It is prohibited to cut bolts & nuts during stripping of plant unless it can be proven that it is not practical to loosen without cutting off which in this case the plant supervisor/technician or artisan must be informed.

#### Work Shop

The allocated Work shop area is to be kept neat and managed according to good housekeeping practices.

### Maintenance Planning

#### General Planning`

The Employer requires that all civil structures and components be maintained according to a defined maintenance programme developed by the Employer. With each and every system the planned maintenance activities are listed with periods at which stage the activity is to be carried out. The scope of work will focus on a specific plant area.

The Employer has a planning system called SAP PM, which records all corrective maintenance identified and all planned maintenance schedules.

All of the Employer’s documentation will be used in each and every activity performed on the respective plant with accurate information of the required actions undertaken to restore the plant back to working condition.

All work orders completed to be verified and approved by Contractors Supervisor and submitter to the Planning Department on the same day that the work is complete. All man-hours, staff used, material used, corrective or planned actions taken must be recorded on the corrective maintenance (CM) or planned maintenance (PM) documentation which is forwarded to the Planning Division for recording.

The failure mode and correction action taken must be written on the work order in order to permit smooth history capturing.

The Contractor will be responsible for planning and scheduling all Work being executed in the Affected Area. The Planning work will be done by competent and qualified Planners in line with the Employers Work Management principles, Including Scoping of all Work categories, the Writing of Standard Maintenance packages.

#### Qualification

The Planning personnel are to be Qualified as Per the Eskom Job Profile for a Planner/scheduler Gen 030109.

The Employer will provide the required SAP and Works Management training.

All scheduling activities will be undertaken by the Contractor’s planning schedulers - corrective maintenance is also catered for in the same way.

### Welding and Rigging Service related to the Execution of Work

All welding and rigging to be requested in advance from Eskom supervisor’s to  perform all the rigging and welding work required to execute the work and will ensure that the work is performed by competent and Qualified Personnel and that all work is executed safely and in accordance with Eskom Procedures and regulations.

### Strike Action

Majuba Power Station is a National Key Point and as such strike action and the associated intimidation and other activities associated with industrial action place the power station at risk.  The Contractor is to ensure that the contracted service is performed regardless of strike and industrial action.

The Contractor is to take all possible steps to ensure that strike action and the associated intimidation and other activities associated with industrial action do not take place on the premises of the Power Station.

The Contractor is required to provide an action plan for approval on how this situation is going to be mitigated.

### KPIs

The Employer uses KPI’s to determine the successful performance of the plant area.  The Contractor is required to perform maintenance in order to meet these targets.  The KPI’s are Subject to change on an Annual basis.  The Service Level Table in Section 5 Below contains Penalties that are Tied to theses KPI’s.

The Current KPI:

| Scheduled Compliance | More than 95% |
| --- | --- |
| PM compliance | More than 98% |
| Statutory work order violation | No violations |
| P1 work order not closed within 24 hours | Less than 1 outstanding |
| P2 work order not closed within 24 hours | Less than 3 outstanding |
| Civil plant availability | More than 95% |
| Safety Work orders not attended to within 24 hours | No violations |
| Work order back log | No more than 10 outstanding |
| Planned & breakdown jobs | Committed target completion |
| Unit trip due to civil defected plant | No trips |

### Procedures

In the event that an Eskom policies and Procedures should change, the Contractor is required to adopt the replaced or revised Procedure.

### Contract Conclusion

The Contractor Provides Safety File on conclusion of the contract to the Service Manager

The Safety fine contains Excite medical certificates for all employees associated with the contract including persons leaving employment of the Contractor before the end of the contract.

## Meetings

Meetings of a specialist nature may be convened at times and locations to suit the Parties, the nature and the progress of the service.  Records of these meetings shall be submitted to the Service Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

Meetings will be convened and chaired by the Service Manager as and when required, including the following:

Meeting Schedule

| Name | Frequency | Attendance by relevant Employer’s personnel: | Attendance by relevant Contractor’s personnel: |
| --- | --- | --- | --- |
| Contract kick-off | Once off | Service manager, Plant supervisor/manager and/or other necessary representatives. | Site manager, Site supervisor and/or other necessary representatives. |
| Early Warning | As and when notified by either party | Service manager and Plant supervisor/manager and other relevant personnel. | Site manager and Site supervisor/manager and other relevant personnel. |
| Technical and/or non- conformance | At least once every 3 months | Service manager, Plant supervisor and technical representative. | Site manager, Site supervisor and technical representative. |
| Safety Incidents | For each occurrence | Safety Representative, Service manager and Plant supervisor and others involved. | Safety Representative, Site manager and Site supervisor and others involved. |
| Section Meeting | Daily | Plant Maintenance manager and supervisor, Engineer, and others involved. | Site manager, Site supervisors Safety Representative and planner. |
| Scope freeze meeting | weekly | Contract Supervisor, planning Supervisor | Planner, Site Supervisor |
| Planning meeting | weekly | Contract Supervisor, planning Supervisor | Planner, Site Supervisor |
| Prioritization meeting | Daily | Contract Supervisor, planning Supervisor, Production Manager and others involved | Planner, Site Supervisor |
| Outage Progress Meeting | Daily | Contract Supervisor, planning Supervisor, Production Manager and others involved | Planner, Site Supervisor |
| Contractor Safety meeting | Monthly | Plant Maintenance Manager | Site manager, Site supervisors Safety Representative |
| Outage planning meeting | When Required | Service manager and supervisor, Engineer, and others involved. | Site manager, Site supervisors Safety Representative and planner. |

Additional ad-hoc meetings may be convened as required by either party.  All meetings on site shall be recorded using the Employer’s attendance register and minutes taken.  Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Contractor’s management, supervision and key people

The key persons of the Supplier are to be identified and approved by the Employer prior to contract start for all skills.

The Employer may, having stated reasons, instruct the Contractor to remove a key person. The Contractor then arranges that, after one day, the key person has no further connection with the work included in this contract.

The Contractor may not replace any of the key persons, without prior written request and approval thereof from the Employer.

The Contractor shall ensure that his Supervisor/s become authorized as Authorised Supervisor/s (AS), in terms of the Eskom Plant Safety Regulations (PSR) within 2 Months of the contract start date.  This authorisation is obtained by attending a course which includes written evaluations (allow 10 days duration) and undergoing a verbal evaluation (1 to 2 hours) within three months after course results indicate that the Supervisor has passed.  As authorisations are valid for two years only, the Contractor must ensure that Supervisors are re-authorised before the authorisation lapses.  The necessary training and evaluations will be provided by Majuba free of charge and the Contractor’s Supervisors must be available to attend, when the course is scheduled.  If the Contractor’s Authorised Supervisor/s is not available on site, this implies that work may not be done and therefore Low Service Damages will be charged

## Documentation control

Procedures, Records and Reports

The Contractor implements the following procedures or paperwork over the first month of this Contract:

- Safety procedures

The following policies, procedures and specifications will be complied by at all times

- Site Regulations – Majuba site Regulations

- BIA/RM/STD/01 – Safety, health and environmental requirements to be met by Contractors

- All specifications produced via the RCM or Majuba maintenance process

- Eskom Majuba Site transport requirements

- Construction Regulations

- Majuba Maintenance Quality Manual

- Occupational, Health and Safety Act

- Eskom Cardinal Rules

- BIA/QA/STD/01 – Quality requirements for engineering and construction works

- All Relevant Majuba Power Station standards, policies and procedures

All quality, health, environmental and safety costs are included in the contract price

## Invoicing and payment

Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Service Manager’s payment certificate.

Invoices are to be submitted as per the attached e-invoicing letter.

# Health and safety, the environment and quality assurance

## Health and safety risk management

The Contractor shall comply with the health and safety requirements that follow:

### Eskom Life Saving Rules

Five Life Saving Rules have been developed that will apply to all Eskom employees, agents, consultants and Contractors.

- Rule 1:	Open, Isolate, Test, Earth, Bond, And/Or Insulate before touch - that is any plant operating above 1000 V.

- Rule 2:	Hook up at heights - no person may work at height where there is a risk of falling.

- Rule 3:	Buckle up – no person may drive any vehicle on Eskom business and/or on Eskom premises: unless the driver and all passengers are wearing seat belts.

Eskom takes a "ZERO TOLERANCE" attitude to drivers and passengers who do not wear safety belts when driving in any vehicle on Eskom Business and/or on Eskom premises.  The violation of this very important safety rule as well as any safety rule while performing work for or on behalf of Eskom may result in Eskom terminating your obligation to perform work in terms of your contract with Eskom.

- All occupants must wear their safety belts properly, and must never put the shoulder belt under their arm or behind their backs.  Drivers and all passengers must buckle-up at all times for the sake of themselves and their families.

- No Person may be on or within a Vehicle that is in any way in motion with our wearing a safety belt

- Rule 4:	Be sober -no person is allowed to work under the influence of drugs and alcohol.

- Rule 5:	Use a permit to work – where an authorization limitation exists, no person shall work without the required permit to work.

    - Plant Safety Regulations

  - The Employer shall arrange the isolation of the plant from all sources of danger as described in the Plant Safety Regulations.  The Permit to Work shall be issued to the Responsible Person (RP) (site Maintenance staff/client) and be shown to the Contractor with the risk assessment, indicating which plant has been isolated and any special conditions applicable.

  - The RP Shall conducts a pre job Brief on the job site before the work commences.

  - The RP shall ensure that all of the Contractors workers sign in on the Worker’s Register in order to declare that they understand the work requirements and dangers.

  - The Employer shall, on request, make available a copy of the latest revision of the Plant Safety Regulations to the Contractor.

  - All work on plant is governed by the Plant Safety Regulations and Contractors must comply fully No permit to Work available implies that no work may be done.

  - Each of the Contractor’s teams performing work most have its own  Authorised Supervisor.

  - This contract includes for the PTW requirements for outside Contractors doing specialized work or upgrades/projects for the Fuel Oil Plant.  Continuous supervision of outside Contractors must be provided for and cost must be included in the monthly contract amount.

  - The Employer is to supply all their RP and AP persons with Arc flash suits as per the PC requirements.  These are to be supplied at the contractors cost.

    - One Suit per RP every 2 Years

    - Fire Precautions

  - Any tampering with the Employer’s fire equipment is strictly forbidden.

  - All exit doors, fire escape routes, walkways, stairways and stair landings and access to electrical distribution boards must be kept free of obstruction and is not be used for work or storage at any time. Fire fighting equipment must remain accessible at all times.

  - In case of fire, report the location and extent of the fire to Electrical Operating Desk at 017 799 3803 and it is expected that the Contractor shall take the necessary action to safeguard the work area in order to prevent injury and spreading of fire.

  - All Hot Work on site must be done as per the Hot Work Procedure, SERV/FIRE02.

    - Reporting of incidents

- The Employer follows an incident prevention policy which includes the investigation of all incidents involving personnel and property.  This is done with the intention of introducing control measures to prevent a recurrence of the same incident.  The Contractor is expected to co-operate fully to achieve this objective and have his own incident reporting system which is compatible to the site system.  The Employer's Representative (Plant Supervisor) and Service Manger must be informed immediately of all safety incidents including fatalities, medicals and first aids and near misses. Any damage to property or equipment must be reported to the Employer's Representative as soon as reasonably practicable but not later than 4 hours after the incident.  A Summary of the Incident is to be Submitted to the Employer’s Representative and Service Manger within 4 hours of the Incident.

- NOTE: The above-mentioned reporting does not relieve the Contractor of his legal obligation to report incidents to the Department of Labour, or to keep records in terms of the Occupational Health and Safety Act, and Compensation for Occupational Injuries and Diseases Act and to perform investigations of all incidents.

- The Contractor must provide the Safety Risk Officer with a monthly safety statistics report by the first working day of every month, even if no incidents have occurred.

    - Vehicle Safety

  - Drivers, passengers and pedestrians must obey safety requirements in terms of the National Road Traffic Act, No 93 of 1996, as amended, including other relevant provincial or local requirements.

  - All drivers must possess a valid, national driver’s licence of the correct category/class, must not be under the influence of alcohol or other drugs which will impair the senses and must be authorised by the Contractor to drive the company vehicle.

  - All vehicles must be roadworthy and vehicle specifications must include at least front airbags for the driver and the front passenger and an anti-lock braking system (ABS).

  - All vehicles must be driven with due consideration for personnel and property. A maximum speed limit of 40 km/hour will be adhered to on the premises at all times.

  - Transportation of passengers on the back of open or closed light delivery vehicles (LDVs), trailers, trucks or any other form of transportation is not allowed.  It is a legal requirement for all Employers to provide safe transportation of all employees both on and off site.

  - No person may be transported in the back of vehicles closed by means of canopies, unless provided with factory-fitted or manufactured-approved, proper seating and safety belts, i.e. crew cabs.

  - Drivers and others entering Majuba Power Station will be subjected breathalyser testing.

  - The driver/s must ensure that their passengers are seated and wear seatbelts at all times.

  - Tools and equipment in vehicles must always be properly secured.

    - Barricading / Screens and Scaffolding

- The Contractor shall be responsible to adequately barricade off of working areas and display warning signs to ensure that people and plant are not exposed to danger or to prevent access to work areas.

- The Employer will supply scaffolding and barricading if with at least 24 hour notice given.  Tampering, adjustment, moving or dismantling of any approved scaffold is not allowed – this may only be done by the scaffolding service provider.

    - Health and Safety Arrangements

- The Contractor shall comply with the guidelines set out in the Eskom Standard  23-726 titled SHE REQUIREMENTS FOR ESKOM COMMERCIAL PROCESS, 32-136 titled CONTRACTOR HEALTH AND SAFETY REQUIREMENTS and 32-296 titled INTEGRATED SHE ORGANISATION; ROLES AND RESPONSIBILITIES AND STATUTORY APPOINTMENTS

- The Contractor must ensure that all his personnel attend a Health and Safety Induction Course prior to starting with the works.  A one hour course will be provided free of charge by the Employer and will be valid for the duration of one year.  It is the Contractor’s responsibility to make an appointment for the induction and ensure that re-induction is done timeously.

- Safety Risk Management has the right and authority to visit and inspect the Contractor’s workplace or site establishment to ensure that tools, machinery and equipment comply with the minimum safety requirements.

- The Employer's Representative shall be entitled to instruct the Contractor to stop work, without penalty to the Employer, where the Contractor’s personnel fail to conform to safety standards or contravene health and safety regulations.  The Employer's Representative is entitled to instruct the Contractor to discipline his employees, to enforce disciplinary action and to submit a report to the Employer's Representative.  The Contractor shall implement additional health and safety precautions wherever necessary.

- The following Health & Safety requirements should be complied with:

  - The Contractor is required to supply a Certificate of Competency for his/her employees if the work will be done under the following conditions:

    - Confined Spaces

    - Heights

    - Heat stresses

    - Cold stresses

  - The Contractor to provide the Employer with a signed register as proof of free issue of adequate Personal Protective Equipment (PPE) to be used by his/her employees (preferably SABS approved).  Additionally, the Contractor shall provide overalls for his staff with clearly identifying motifs depicting the company name.

  - Sub-contractors - the principal contractor must request approval for the use of any sub-contractor.  Proof must be given to Eskom that the sub-contractor/s have the necessary competence and resources to carry out the work safely and to ensure that due care of the environment will be exercised.

  - Medical certificate of fitness shall be issued by a Registered Occupational Health Medical Practitioner only.

- The Contractor appoints a person, qualified in accordance with the SHE Requirements, as the liaison with the Eskom Safety Officer for all matters related to health and safety and this person shall be contactable telephonically 24 hours a day.

- The Contractor confirms that it has been provided with sufficient written information regarding the health and safety arrangements and procedures applicable to the Services to ensure compliance with it and all employees, agents, Subcontractors or mandatories with the SHE Requirements while providing the Works in terms of this contract.  As such, the Contractor confirms that this contract and the relevant Eskom Regulations referred to in this contract constitute written arrangements and procedures between the Contractor and the Employer regarding health and safety for the purposes of section 37(2) of the OHSA.

    - Company Branding

The Contractor shall provide all overalls (when needed) for his staff with clearly identifying motifs depicting the company name.

    - Special requirements

The Contractor Allows for staffing based on a full running Station of Which some of the Unit may two Shift.  The Light up Requirement will vary depending on National electricity Demand.

The Contractor seeks Employees from the local Seme Districts as per “ANCYL PROTEST Majuba Actions “.

    - Exposure to Silica

The Risk of exposure to Silica and coal dust is High

The Contractor is responsible for ensuring that ALL employees working in the Boiler Area wear appropriate SABS approved dust mask and that they are used correctly.

The Contractor is to ensure that Lung X-rays are performed on an annual basis and that the reports are issued by a Medical Doctor Qualified to recognise Silica related dust Lung ailments or Diseases.

## Environmental constraints and management

All Legislative, Eskom and Majuba environmental policies are to be adhered to:

### Work carried out in terms of:

The Contractor will be required to ensure that all works are carried out as per the ISO 14001 standard and Majuba’s Environmental Policy, BIA/ENV/04 and Waste management Policy, BIA/ENV/01.  The following environmental requirements are complied with at all times:

- Zero liquid effluent discharge.

- No chemicals will be dumped into the station drains or on the premises.

- No oil or waste will be dumped in an unauthorised area or unlicensed waste site.

- Asbestos will be handled and stored according to Act 15 of 1973 (Hazardous Substances Act).

- No materials or waste will be burnt on site.  Hazardous substances shall be handled and stored according to the hazardous substances Act no 15 of 1973.  No effluent shall be discharged into the public streams.

- Contractors’ activities/ services shall be carried out as per the above procedures and BIA/RM/STD/01

### New Environmental Legislation

The Contractor will be responsible for complying with any new environmental requirements, relevant to the Services Information that may come into effect as part of Majuba Power Station’s Environmental Management System (EMS) during the duration of this contract.

### Existing Environmental Legislation

In order to protect Eskom's environmental interests whenever a product or service is provided by a Contractor, the Contractor complies with all relevant and appropriate environmental legal requirements contained in governmental notices, laws and regulations promulgated by the central and provincial governments.

### Liability

The Contractor also accepts all responsibilities, accountabilities and liabilities associated with such legal requirements, unless specifically excluded from a contract by a mutually acceptable written agreement.

### Hazardous substances

If product is classified as a hazardous substance, material safety data sheets (MSDS) must accompany delivery/use. In accordance with the Occupational Health and Safety Act (OHSA), Act 85 of 1993 section 10 and 11.  If any hazard is identified by the Contractor, he must immediately inform the Employer.

## Quality Management  requirement [QM 58( 240-105658000)]

The Contractor must possess an accredited Quality Management System.  A pre-approved Quality Control Plan (QCP) is to be used for the tasks at hand.

### Personal Competency

Proof of the Contractor’s personnel competency in terms of Regulation 18 (5 and 6) of the OHS Act is required by the Employer.

### Quality Control

Majuba Power Station reserves the right to do quality checks at any time.  It will be the philosophy of this contract that if a problem is identified while carrying out an inspection, a defect is raised to rectify the problem as corrective maintenance.

The Contractor is required to be certified in accordance to ISO9001.

### QCP’s

The Contractor is responsible for creating QCP documents for all jobs and having them approved by the Eskom plant engineer, Eskom plant supervisor and viewed by the project manager on requested

The Contractor will ensure that all critical work will be performed using a Procedure and QCP.  Where no procedure exists the Contractor will write the procedure and have it approved by the Employer.

The Employer’s agent will witness the work and a results report (hardcopy) will be provided to the Employer and uploaded into the SAP system.

All specifications and actions stipulated within plant specific procedures shall be strictly adhered to with exception of any changes stated within the Service Information or an approved Eskom document.  Further exceptions to the above procedures must be approved by Eskom authorities the before it may be implemented.

### Quality Requirements

The Contractor will additionally comply with the Employer’s Quality Requirements as specified in Standard QM58.  This includes the Contractor’s ISO 9001 Registration Certification of Compliance

### Quality Control Documents

All quality control documentation must be submitted to the Project Manager/ Employer's Representative/ Employer's Agent within two weeks after contract award for written approval.

# Procurement

## Subcontracting

The Contractor may not use a Subcontractor unless a written request is made to the Employer and approval is given.  All terms and conditions applicable to the Contractor, will also apply to the approved Subcontractors e.g. legal requirements, appointments, authorisations, safety, quality and therefore all relevant documentation must be submitted in order for the Employer to consider the Subcontractor for approval.

Additionally, the prices listed in the price list will remain unchanged if any Subcontractors are used

## Plant and Materials

### Correction of defects

Defects to be treated as a matter of urgency and should be attended in minimum possible time.

### Plant & Materials provided “free issue” by the Employer

Scaffolding, forklifts and/or cranes will be provided without cost to the Contractor upon the Contractor’s request, if available at the time.  These may only be installed /operated by persons who have authorisation to do so.

The Contractor will at his cost ensure that his employees are authorised for the use of all lifting equipment including folk lifts.

The Contractor will provide the Spares and Materials required for maintaining the Plant.

# Working on the Affected Property

Whilst working on site the Contractor will adhere to all Eskom and Majuba Power Station site regulations.

## Employer’s site entry and security control, permits, and site regulations

The Contractor shall prepare and submit the safety plan and other documents in a file within one week of the contract start date and which shall be corrected if necessary to be approved within one week thereafter.  Safety induction is provided subject to the safety file being approved by one of the Safety Risk Officers of Majuba Power Station and thereafter, the file must always be available when work is done on site.

Access to site is dependent on the all workers undergoing a short (1 hour) safety induction and then only will access permits be issued for workers and construction vehicles to enter.  Work will not be allowed without induction provided by the Employer for each and every worker.

Medical certificates of workers can only be issued by Occupational Health Practitioners and includes hearing, sight and lung-function tests and may include psychological evaluations for workers who work at heights and/or any other requirement stipulated by the Safety Risk Officers.

See BIA/RM/STD/01 for all relevant details or contact the Safety Risk Officers at 017 799 3121

or 017 799 3445.

### Security and Access Arrangements

a. The Contractor may apply for a temporary or permanent photo permit (if on site for longer than two months) as well as vehicle permits at the Security office, after completing induction.

- The following information is required for permits to be approved (temporary permit forms will be provided by the Safety Risk Officer conducting the safety induction):

- Employee name and ID Number

- Company

- Contract validity date

- Employer's Representative signature

- Copy of the first page of the ID book of each employee

- The Contractor’s personnel will be required to be in possession of their access permit at all times and will produce them at the security gate on every occasion or whenever requested.  All Contractors’ permits must be returned to Protective Services when the relevant personnel leave the site permanently and upon Completion of the services.  Any lost photo permits will be paid for by the Contractor.

- The Contractor’s visitors and all personnel shall conform at all times, to the security arrangements in force at the time.  Application forms for visitors must be completed by the Contractor’s Site Manager and approved by the Employer's Representative at least one day before the visit and submitted to the Protective Services office.  Visitors will not be allowed on site if the necessary forms are not in the possession of security staff.

- Protective Services may with valid cause, remove any of the Contractor’s personnel from the site, either temporarily or permanently.  Access may be denied to site to any person, whom in the opinion of Protective Services, constitutes a security risk. No compensation is claimable by the Contractor if this occurs.

- No unauthorised vehicles will be allowed on site.  Only Contractor’s vehicles with contract vehicle permit disks will be allowed on site.  Contract Vehicle Permit Applications should be directed to the Employer's Representative.

- The Contractor will be restricted to the working areas associated with his place of work.  The Contractor is forbidden to enter any other area, and must ensure that his employees abide by these regulations.

- Parking inside the Power Station buildings or in front of driveways, doors and gates is strictly forbidden, except for loading purposes.

- No recruiting of casual labour may be done on the Employer’s premises, including the area outside the Power Station security gate.

## People restrictions, hours of work, conduct and records

### Only authorised persons may have site access and perform work.

### Majuba Power Station normal working hours are:

- Monday to Thursday – 07:30 to 16:45

- Friday – 07:30 to 12:30

The Contractor will however, provide the services during all hours.

### Working Hours

As per the Labour Regulations Act and the Basic Conditions of Employment Act, no person is allowed to work more than 12 continuous hours per shift.  The Contractor shall ensure that workers are relieved from duty after working twelve hours.

### Removal from Site

The Employer reserves the right to have any of the Contractor’s personnel removed off site if, in the Employer’s opinion, it is warranted.

## Health and safety facilities on the Affected Property

There is a medical station on site and a fire and rescue service for assistance with serious incidents and treatment of all serious injuries during normal working hours.  Emergency services are available during normal working hours by dialling 9222 from any site phone or else 017 799 2138 (medical centre) 017 799 3192 (fire and rescue) and also available after hours by dialling 9222 from any site phone or else contacting the Electrical Operating Desk (EOD) at 017 799 3803 (all hours).  However, the Contractor is expected to handle all minor incidents in-house by providing a first aider and a first aid kit.

## Cooperating with and obtaining acceptance of others

Proper co-ordination and work planning must be done when working in any area where others are performing work or activities.  Interfacing may be required with the site maintenance personnel and others.

## Records of Contractor’s Equipment

The Contractor will bring a typed list of all his equipment and tools (with serial numbers, wherever possible).  This list needs to be approved by the Security office before the items are taken onto site on each occasion. Equipment that is not listed on a tool/equipment list cannot be removed from site.  Equipment and vehicles left on site is done so at the Contractor’s own risk.

## Equipment provided by the Employer

### Scaffolding

### Scaffolding can be supplied after notification and call-out of the relevant scaffolding service provider.  Other equipment such as forklift and cranes may be supplied upon request and if available at the time on site.

### Rigging

Rigging Equipment, lights, hand tools and other equipment will not be provided by the Employer and The Contractor is to conduct his operation is such a way as to make lending of tools from the Employer or other contractors on Site unnecessary.

The Contractor will provide all rigging equipment, for performing the services  All the Contractor’s equipment must be serviceable and on a planned maintenance schedule and must be inspected each time before being used on the Plant.  All the Contractor’s Rigging equipment must comply with the Relevant Legal requirements.

## Site services and facilities

### Provided by the Employer

Sanitary services, water, compressed air and electricity shall be provided by Eskom at fixed points on the plant.  There is also a site kitchen which serves lunch only and meal tickets may be purchased at the Petty Cash Office in the Finance Building.  Furthermore there is also a tuck-shop on site but both of these operate only on week days and are for the Contractor’s own cost.

### Provided by the Contractor

The Contractor is to supply all the personal protective equipment, transport, accommodation, tools, equipment and consumables to perform all the required tasks on site.

### Contractor’s yard

The Contractor is to establish a Site yard in the location indicated by the Employer.  Permission will be granted once the Contractor provides an accepted layout plan. Expected site yard size 40 by 40 meters.

The Contractor will be responsible for supplying all the required buildings including separate venues for eating ablution and office work, etc.

The Contractor will ensure that all the required services are connected and that the relevant building codes and by laws are adhered to.

Site Establishment will only be assessed for payment once a Certificate of Compliance issued by a duly Authorised person is provided to the Service Manager.

## Control of noise, dust, water and waste

### Waste Disposal

Waste is to be disposed of in bins supplied by Eskom – yellow bins for general waste and red bins for hazardous waste.  However, the Contractor is expected to remove all his own waste from site, as far as possible.

### Noise

Noisy equipment and tools emitting noise more than 105dB (A) may not be supplied/utilised by the supplier.

## Tests and inspections

The site maintenance staff or Quality Control personnel shall inspect the Contractor’s work and sign off all relevant documentation, if the work is satisfactory.  Thereafter, plant shall be test run and the Contractor informed of any defects.  The Contractor may be present for any test running.

# Service Level Table

The following table depicts the level of performance required of the Contractor.  Should the Contractor be unable to meet these requirements, Low Service Damages will be claimed from the Contractor.

The total Low Service Damages will be limited to 10% per month.

Table 6:  Service Level Table for Low Service Damages

| No. | Description | Employer’s Requirement | Damages payable by Contractor |
| --- | --- | --- | --- |
| 1 | Approval of safety file | 2 weeks Before Contract Commences | R500.00 per day without approved safety file. |
| 2 | Approval of Quality Management System | Within 2 weeks of contract start date. | R500.00 per day without approved quality file. |
| 3 | Authorisation of Supervisors | Within 2 months of contract start date. | R750.00 per day without an Authorised Supervisor. |
| 4 | Arrival on site for call-out | Within 1 hours of call-out. | R1,000.00 per hour of delay or part thereof. |
| 5 | Non Attendance of meetings | Every listed meeting to be attended | R500.00 per incident. |
| 6 | Excessive Task Duration | Within the time specified by Contractor’s plan as approved By the Service Manager. | R500.00 per hour of extended Duration or 10% of the monthly contract value whichever value is lower |
| 7 | Scheduled Compliance | More than 95% | 1% of monthly contract value |
| 8 | PM compliance | More than 98% | 1% of monthly contract value |
| 9 | Statutory work order violation | No violations | 5% of monthly contract value |
| 10 | P1 work order not closed within 24 hours | Less than 1 outstanding | R1000 for each one per month |
| 11 | P2 work order not closed within 24 hours | Less than 3 outstanding | R1000 for each one per month |
| 12 | Safety Work orders not attended to within 24 hours | No violations | 1% of monthly contract value |
| 13 | Work order back log | No more than 60 outstanding | R100 for each outstanding |
| 14 | Major break downs not identified and actioned | All failure that put the plant or redundant plant at risk must be prevented | 1% of monthly contract value |
| 15 | Planning information not submitted as required | Work executed without Approved Plan | 1% of monthly contract value |
| 16 | Work Not Executed as Planned | Work committed By the contractor not executed | R250 per Job per day of not complying up to 10% of the monthly contract value. |
| 17 | Plant Failure after returning from Maintenance work and rework | No Delays when returning plant to service or rework | R500.00 per hour of extended Duration or 10% of the monthly contract value whichever value is lower |
| 18 | Standby team arrive to site late on callout | Standby team to start with repair work within 1.5 hours of being called | R1000 per Hour or 10% of the monthly contract value whichever value is lower |
| 19 | Reaction to Breakdowns | Permit must be requested within 30 minutes and be correct. | R500.00 per hour of delay in requesting permit 10% of the monthly contract value whichever value is lower |
| 20 | Maintenance crew on work site in time | Maintenance crews to be on the job within 30 minutes of permit issue. With all the correct tools. | R500.00 per hour of delay in team being on site, 10% of the monthly contract value whichever value is lower |
| 21 | Supervision | No Supervision and Management during high Risk break downs | As per Major Plant Break Down in 1.3.above. limited to 10% of the contract value |
| 22 | Safety File not Submitter for Monthly Audit on time | Safety File must be Submitted Monthly to the Employers Safety Department For Audit. | 5% of Monthly Contract Value. |
| 23 | COID and SARS Letter of Good Standing | Letters not Provided to the Service Manager before the previous year expires | 15% of Monthly contract Value. |
| 24 | Exit Medical | All excite medical certificates not included in the Safety File | Final contract payment. |

# List of Documents

## Drawings issued by the Employer

The following drawing will be issued to the appointed Contractor.

| Drawing number | Revision | Title |
| --- | --- | --- |
| 0,66/1 | 14 | Majuba Power Station - Site Layout |
| 0,66/2 | 17 | Majuba Power Station - Station Layout |

Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Service Information |  |
| C3.2 | Contractor’s Service Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

C3.1: Employer’s service Information

Contents

When the document is complete, insert a ‘Table of Contents’.  To do this go to:  Insert, → Reference, → Index and tables → Table of Contents.  Three levels and the title (but not the subtitle) may be shown if the formats used in this template are retained.

Otherwise insert list of contents manually.

Part 3: Scope of Work	1

C3.1: Employer’s service Information	2

1	Description of the service	4

1.1	Executive overview	4

1.2	Employer’s requirements for the service	4

1.3	Interpretation and terminology	4

2	Management strategy and start up.	5

2.1	The Contractor’s plan for the service	5

2.2	Management meetings	5

2.3	Contractor’s management, supervision and key people	6

2.4	Provision of bonds and guarantees	6

2.5	Documentation control	6

2.6	Invoicing and payment	6

2.7	Contract change management	6

2.8	Records of Defined Cost to be kept by the Contractor	7

2.9	Insurance provided by the Employer	7

2.10	Training workshops and technology transfer	7

2.11	Design and supply of Equipment	7

2.12	Things provided at the end of the service period for the Employer’s use	7

2.12.1	Equipment	7

2.12.2	Information and other things	7

2.13	Management of work done by Task Order	8

3	Health and safety, the environment and quality assurance	9

3.1	Health and safety risk management	9

3.2	Environmental constraints and management	9

3.3	Quality assurance requirements	9

4	Procurement	10

4.1	People	10

4.1.1	Minimum requirements of people employed	10

4.1.2	BBBEE and preferencing scheme	10

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	10

4.2	Subcontracting	10

4.2.1	Preferred subcontractors	10

4.2.2	Subcontract documentation, and assessment of subcontract tenders	10

4.2.3	Limitations on subcontracting	11

4.2.4	Attendance on subcontractors	11

4.3	Plant and Materials	11

4.3.1	Specifications	11

4.3.2	Correction of defects	11

4.3.3	Contractor’s procurement of Plant and Materials	11

4.3.4	Tests and inspections before delivery	11

4.3.5	Plant & Materials provided “free issue” by the Employer	12

4.3.6	Cataloguing requirements	12

5	Working on the Affected Property	13

5.1	Employer’s site entry and security control, permits, and site regulations	13

5.2	People restrictions, hours of work, conduct and records	13

5.3	Health and safety facilities on the Affected Property	13

5.4	Environmental controls, fauna & flora	13

5.5	Cooperating with and obtaining acceptance of Others	13

5.6	Records of Contractor’s Equipment	13

5.7	Equipment provided by the Employer	14

5.8	Site services and facilities	14

5.8.1	Provided by the Employer	14

5.8.2	Provided by the Contractor	14

5.9	Control of noise, dust, water and waste	14

5.10	Hook ups to existing works	14

5.11	Tests and inspections	14

5.11.1	Description of tests and inspections	14

5.11.2	Materials facilities and samples for tests and inspections	14

6	List of drawings	15

6.1	Drawings issued by the Employer	15

Description of the service

Executive overview

Put yourself in the position of the Contractor’s senior management who need a high level overview of what is involved – the scope of work - so that they can decide when tendering whether they have the resources and capability to undertake the work.  Include a description of the different services and disciplines of work involved within the service and the location where most of the work will be carried out.

Employer’s requirements for the service

Either

Describe in detail what the Employer requires the Contractor to do and how he is to do it if the Contractor is mainly providing labour and tools to carry out the Employer’s requirements

Or

Provide the Employer’s operating philosophy / user requirement specification (URS) / performance specification giving deliverables and constraints for the service from which the Contractor is to plan in detail how he is to achieve the required deliverables.

Reference could be made to an Annexure for a detailed classification of services or to the Price List in the case of Option A or C and if the Price List descriptions are complete.

Interpretation and terminology

If required include here definitions additional to those used in the conditions of contract which are required only for the purpose of making the Service Information easier to draft and read.  Also list abbreviations used and provide a full interpretation of each one, for example:

The following abbreviations are used in this Service Information:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| OBL | Outside battery limits |

Management strategy and start up.

The Contractor’s plan for the service

In the TSC3 the Contractor’s plan is his “design” for performing the service throughout the service period. Section 2 of the conditions of contract describes what the Contractor is to show in his plan both in the core clauses and some additional requirements in each of the main Options.

The extent of the Contractor’s plan will depend on whether the Contractor is required to develop a plan in accordance with the Employer’s broad outline of the service or whether the Employer has provided a plan for the Contractor to follow.  Read the TSC3 Guidance Notes pages 21 and 22 for more information on the Contractor’s plan.

Use this section to describe any particulars which must be taken into account by the Contractor in developing his plan as required by clause 21.2.   For example information about the order and timing or method of carrying out particular items of work.

List technical reporting and scheduling requirements which are to be incorporated into the Contractor’s plan.

Management meetings

The conditions of contract (e.g. Clause 16.2) and other sections of the Service Information (e.g. safety risk management) may require that a meeting shall be held.  However the intention of all NEC contracts is that the Parties and their agents use the techniques of partnering to manage the contract by holding meetings designed to pro actively and jointly manage the administration of the contract with the objective of minimising the adverse effects of risks and surprises for both Parties.

Depending on the size and complexity of the service, it is probably beneficial for the Service Manager to hold a weekly risk register meeting (Clause 16.2).  This could be used to discuss safety, compensation events, subcontracting, overall co-ordination and other matters of a general nature.  Separate meetings for specialist activities such as planning and activities of a technical nature may also be warranted.

Describe here the general meetings and their purpose. Provide particulars of approximate times, days, location, and attendance requirements, stipulating that attendees shall have the necessary delegated authority to make decisions in respect of matters discussed at such meetings.

The following text could be used as a model for this section:

Regular meetings of a general nature may be convened and chaired by the Supply Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | Weekly on ________ at ___ |  |  |
| Overall contract progress and feedback | Monthly on _____ at ___ |  | Employer, Contractor and ___ |

Meetings of a specialist nature may be convened as specified elsewhere in this Service Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the service.  Records of these meetings shall be submitted to the Service Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

Contractor’s management, supervision and key people

State any additional constraining requirements on Contractor’s supervision and key people that are not already stated in other sections such as for Health and Safety.  This section could be used to solicit an organogramme from the Contractor showing his people and their lines of authority / communication.  This would be essential if the Contractor is a Joint Venture.

Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Service Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

Documentation control

Specify how documentation will be identified with an alpha numeric which indicates source, recipient, communication number etc.  Provide details of any particular format or other constraints; for example that all contractual communications will be in the form of properly compiled letters or forms attached to e mails and not as a message in the e mail itself.  State any particular routing requirements but note from TSC3 who issues what to whom.

Invoicing and payment

The Z clauses make reference to invoicing procedures stated here in this Service Information. Also include a list of information which is to be shown on an invoice.

Within one week of receiving a payment certificate from the Service Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Service Manager’s payment certificate.

The Contractor shall address the tax invoice to

_________________________

and include on each invoice the following information:

Name and address of the Contractor and the Service Manager;

The contract number and title;

Contractor’s VAT registration number;

The Employer’s VAT registration number 4740101508;

Description of service provided for each item invoiced based on the Price List;

Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

(add other as required)

Add procedures for invoice submission and payment (e. g. electronic payment instructions)

Contract change management

This section is intended to deal with any additional requirements to the compensation event clauses in section 6 of the core clauses; such as the use of standard forms.  Not the same thing as documentation control.

Records of Defined Cost to be kept by the Contractor

If Option C or E applies first read clause 52.2 and then state whether the Contractor is required to keep any other records.  Include any other constraint which may be required in regard to format and filing of the records, and whether access for the Service Manager shall be provided in hard copy or electronically.

Could delete if Option A applies unless the Employer requires some form of control over the Contractor’s record keeping for the purpose of compensation event management.

Insurance provided by the Employer

First read TSC3 Core Clause 86.1 and then add anything necessary for the management of insurance related issues such as a cross reference to where procedures for making claims can be found.  Also provide contact details for persons capable of being able to answer any insurance related queries the Contractor may have, as well as to whom the information required by Marine Insurance (if any) may be addressed.

Training workshops and technology transfer

Describe type and frequency of any on job training workshops, as well as any obligation for technology transfer being included as part of the service or at the end of the service period.

Design and supply of Equipment

On some complex services (e. g. nuclear) it could be in the Parties best interests that some details of the design of Equipment are shared with the Service Manager, not necessarily for his acceptance but as an assurance that the Equipment will be able to allow the Contractor to Provide the Service efficiently and without delay.  For example specialised handling Equipment for a particular maintenance operation.  Clause 23.1 is always available to the Service Manager if this paragraph is not used.

Also the Employer may wish to exercise constraints or include witness and hold points during manufacture, assembly or delivery of such Equipment.   Include these constraints here.

Draft in such a way that there is no doubt that the liability for such design supply and use of the Equipment remains with the Contractor.

Things provided at the end of the service period for the Employer’s use

Equipment

The Employer may wish to use some of the Equipment used by the Contractor after the end of the service period.  Clause 70.2 requires that details of such requirement be stated in the Service Information.   Complete here or if not applicable retain the heading and state ‘None’.

Information and other things

Clause 70.2 requires that information and other things which the Contractor is to provide at the end of the service period be stated in the Service Information.

Management of work done by Task Order

Only use this heading if Option X19 applies to this contract.

In some cases all work may be done in terms of Task Orders in which case it may be logical to move this section closer to the start of this part 2 of the Service Information.   In some cases only parts of the service may require to be handled by Task Order, for example a major repair which has become necessary during a continuous maintenance service contract.

Please read Option X19 before drafting requirements here as much of the procedure for the administration of Task Orders is already provided in X19, for example X19.2 specifies what a task Order should include

A Task Order format could be provided in an Annexure to this Service Information.

Many considerations can apply to Task Orders, such as availability of resources, arrangements for emergency work, Task Order reporting (work carried out and service results), assessment of additional Prices for service not included in the Price List etc.

Clause X19.6 requires information which should be included on a Task Order programme.

Further requirements for Task Orders include things to be provided by the Employer under a Task Order and the conditions under which the Employer or Others are to work.

Health and safety, the environment and quality assurance

Health and safety risk management

In addition to the requirements of the laws governing health and safety, Eskom may have some additional requirements particular to the service and the Affected Property for this contract.  The text below provides for these being attached as an Annexure to this Service Information. PLEASE ALSO READ CORE CLAUSE 27.4 TOGETHER WITH Z7 IN THE ADDITIONAL CONDITIONS OF CONTRACT TO MAKE SURE THAT WHATHEVER IS INCLUDED IN THE ANNEXURE FOLLOWS ON FROM THOSE CLAUSES.

The Divisional/Regional Safety Risk Manager or his representative having jurisdiction over the service must provide the relevant safety, health and environmental (SHE) criteria for incorporation into this Service Information. The SHE specification / scope must be signed off by the Divisional/Regional Safety Risk Manager or his representative confirming that the applicable safety criteria have been taken into account.

The Commodity Manager / Buyer must refer the tender to the Divisional/Regional Safety Risk Manager or his representative in order to evaluate against enquiry-specific safety criteria.

The Divisional Safety Risk Managers who will be responsible for the allocation of resources to assist P&SCM with the above processes are as follows:

·         Generation: Roley McIntyre

·         Transmission: Tony Patterson

·         Distribution: Alex Stramrood

·         Enterprises: Jace Naidoo

·         Corporate: Kerseri Pather

The Contractor shall comply with the health and safety requirements contained in Annexure ___________ to this Service Information.

Environmental constraints and management

Describe or cross refer to environmental constraints applicable to the Contractor’s plan and his activities on the Affected Property and how they should be managed.  Include here or cross refer to an Annexure to the Service Information.

The Contractor shall comply with the environmental criteria and constraints stated in Annexure ________

Quality assurance requirements

Specify minimum requirements for the Contractor’s Quality Plan and Work Procedures or provide the Employer’s Quality Plan if that is to be used.  Make sure witness and hold points are identified generally and describe any particular requirements for QA outside the Affected Property.  Indicate how the Contractor’s QA documentation is to be submitted for acceptance and any conditions that need to be imposed relating to acceptance.  State whether ISO compliance is a condition and if so which ISO standard shall apply.

Procurement

There is a cross reference from the core clause 11.2(6) definition of Disallowed Cost to the Service Information regarding procurement procedures.  This part of the Service Information MUST include any such procedures to be able to administer Disallowed Cost.

People

Minimum requirements of people employed

Specify any constraints relating to people employed to Provide the Service; for example permits for foreigners, training (other than H & S), use of labour from designated areas and industrial relations.

BBBEE and preferencing scheme

Specify constraints which Contractor must comply with after contract award in regard to any Broad Based Black Economic Empowerment (B-BBEE) or preferencing scheme measures.

Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

If the ASGI-SA requirements are to be included in this contract specify constraints which Contractor must comply with after contract award in regard to any ASGI-SA requirements.  The ASGI-SA Compliance Schedule completed in the returnable tender schedules is reproduced here.  If ASGI-SA does not apply, delete this paragraph.

The Contractor complies with and fulfils the Contractor’s obligations in respect of the Accelerated and Shared Growth Initiative - South Africa in accordance with and as provided for in the Contractor’s ASGI-SA Compliance Schedule stated below

.

[Insert the agreed ASGI-SA Compliance Schedule here]

The Contractor shall keep accurate records and provide the Service Manager with reports on the Contractor’s actual delivery against the above stated ASGI-SA criteria.   [Elaborate on access to and format of records and frequency of submission etc.]

The Contractor’s failure to comply with his ASGI-SA obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract.

Subcontracting

Preferred subcontractors

TSC3 does not make use of nominated subcontracting, but the Employer may list which subcontractors or suppliers the Contractor is required to enter into subcontracts with.  This is usually only required where specialist services need to be obtained from a particular supplier or group of suppliers in order to comply with operational standards.

Subcontract documentation, and assessment of subcontract tenders

Specify any constraints on how the Contractor is to prepare subcontract documentation, whether use of the NEC system is compulsory or not (compulsory is recommended) and how subcontract tenders are to be issued, received, assessed (using a joint report?) and awarded.

Limitations on subcontracting

The Employer may require that the Contractor must subcontract certain specialised work, or that the Contractor shall not subcontract more than a specified proportion of the whole of the contract.

Attendance on subcontractors

State requirements for attendance on Subcontractors, if any

Plant and Materials

Specifications

Plant and Materials are defined as items intended to be included in the Affected Property.  This will refer to replacement of worn or defective parts, routine replacement as part of regular preventative maintenance and supply of spare parts.  Quality is usually designed in or specified in the technical specifications.  However to cover circumstances where quality may not be prescribed, this sub-paragraph could also be used to state an overarching default requirement – fitness for purpose etc.

Either specify here or provide a list of the applicable specifications and attach them as Annexure or state where they can be obtained from.

Correction of defects

State any constraints when dealing with defective Plant and Materials such as how repairs are carried out - can the item be fixed up or must it be replaced by a new one.

Contractor’s procurement of Plant and Materials

Specify any constraints on how the Contractor is to order, codify, expedite, freight, import, transport to the Affected Property and any other requirements for delivery and storage before installation.  The Employer may require warranties from suppliers to be in favour of the Employer and not just to the Contractor.   The Employer may also need schedules of vendor data for his own use after the end of the service period.

Tests and inspections before delivery

Core Clause 41.1 makes reference to the Service Information stating which Plant and Materials are to be inspected and tested before delivery.  Specify any requirements particularly if such tests and inspections are to be carried out by agents of the Employer overseas.

Plant & Materials provided “free issue” by the Employer

List any Plant and Materials which are to be provided by the Employer.

State arrangements for collection by Contractor or delivery by others on behalf of the Employer, off loading, inspection, storage, care custody and control, return of unused Plant and Materials, etc.   Always include a statement to the effect that ‘all other Plant and Materials are to be provided by the Contractor’.

Cataloguing requirements by the Contractor

State whether cataloguing is applicable, if it is, reference the requirements for cataloguing that need to be satisfied by the Contractor (consult Procurement Instruction Number 1 of 2018 – Incorporating Cataloguing into the Procurement Environment, Unique Identifier 240-1289988974).

Working on the Affected Property

This part of the Service Information addresses constraints, facilities, services and rules applicable to the Contractor whilst he is doing work on the Affected Property.

Employer’s site entry and security control, permits, and site regulations

Sites such as Koeberg Nuclear Power Station have very strict entrance requirements which tendering contractors need to allow for in their prices, and the Contractor has to comply with.  State these or similar requirements here.

In addition to the above there may be other restrictions once on the site, plus rules relating to roads, walkways and the provision of barricades

People restrictions, hours of work, conduct and records

Restrictions and hours of work may apply on some sites.  It is very important that the Contractor keeps records of his people working on the Affected Property, including those of his Subcontractors.  State that the Service Manager shall have access to them at any time.  These records may be needed when assessing compensation events.

Health and safety facilities on the Affected Property

Section 3 deals with contractual H & S requirements in addition to those of the OHSA Act.  This section allows the Employer to state what measures are to be taken on the Affected Property by describing where First Aid facilities provided by the Employer are located and any other emergency arrangements.  Do not use if already addressed in 2.3.

Environmental controls, fauna & flora

This sub-paragraph may not be required in a service contract or if these matters are dealt with in the general environmental requirements referred to in section 3 above.

Cooperating with and obtaining acceptance of Others

This sub-paragraph could be used to deal with two issues.

1) The cross reference from core clause 25.1 about cooperation generally as well as details about Others with whom the Contractor may be required to share the Affected Property. See clause 11.2(9) for the definition of Others.

2) Requirements for liaison with and acceptance from statutory authorities or inspection agencies.

Records of Contractor’s Equipment

This sub-paragraph is intended to address how records are to be kept of Equipment on Site including whether it is owned or hired.  Include any constraints about scaffolding, rigs, heavy lifts and cranes, including removal from the Affected Property.

Equipment provided by the Employer

Provide details of equipment (e.g. overhead cranes) made available for use by the employer and set out conditions relating thereto.

Site services and facilities

Provided by the Employer

This is a mandatory cross reference form clause 25.2 in TSC3.  State what the Employer will provide in the way of power, water, waste disposal, telecomms, ablutions, fire protection and lighting (etc) on the Affected Property.  Give hook up locations and any constraints on how the hook up is to be done.  Always conclude by stating that the Contractor shall provide everything else necessary for Providing the Service.

Provided by the Contractor

Describe what the Contractor is to provide in the way of accommodation, laboratories, storage, vehicles and office equipment for the Service Manager and any restrictions or minimum requirements concerning the Contractor’s own facilities.  Also state what happens to these facilities upon completion of the contract.

Control of noise, dust, water and waste

State requirements, if any.

Hook ups to existing works

State any constraints

Tests and inspections

Description of tests and inspections

Describe the tests and inspections to be carried out by the Contractor and the Service Manager and others [40.1].

Materials facilities and samples for tests and inspections

State what materials facilities and samples for tests and inspections the Contractor and the Employer are to provide, per core clause 40.2.

List of drawings

Drawings issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

| Drawing number | Revision | Title |
| --- | --- | --- |

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008 Fax 086 539 1902 www.ecs.co.za

Available from Engineering Contract Strategies Tel 011 803 3008 Fax 086 5391902 or www.ecs.co.za