NEC3 Term Service

Short Contract (TSSC3)

| A contract between | Eskom Holdings SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and |  |  |
| for |  |  |
| Contents: | Compiled in accordance with CIDB Standard for Uniformity in Construction Procurement (May 2010 amendments) | Page No. |
| Part C1 | Agreements & Contract Data |  |
|  | C1.1 Form of Offer and Acceptance | [2] |
|  | C1.2 Contract Data provided by the Employer | [5] |
|  | C1.2 Contract Data provided by the Contractor | [14] |
| Part C2 | Pricing Data |  |
|  | C2.1 Pricing assumptions | [15] |
|  | C2.2 Price List | [16] |
| Part C3 | Scope of Work |  |
|  | C3.1 Service Information | [18] |
|  | Pro Forma Task Order |  |
| ENQUIRY NUMBER | OLT205526 |  |

C1 Agreements & Contract Data

# C1.1 Form of Offer and Acceptance

## Offer

The Employer, identified in the Acceptance page signature block on the next page, has solicited offers to enter into a contract for the procurement of:

Inspection and repairs to the concrete lining of Drakensberg Waterway Units 1 & 2

The tenderer, identified in the signature block below, having examined the documents listed in the Tender Data and addenda thereto as listed in the Tender Schedules, and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the Contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| The offered total of the Prices exclusive of VAT is | R[●] |
| --- | --- |
| Value Added Tax @ 15% is | R[●] |
| The offered total of the Prices inclusive of VAT is | R[●] |
| (in words) |  |

This Offer may be accepted by the Employer by signing the form of Acceptance overleaf and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: | (Insert name and address of organisation) |  |  |  |
| Name & signature of witness |  |  | Date |  |
| Tenderer’s CIDB registration number: |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an Agreement between the Employer and the tenderer upon the terms and conditions contained in this Agreement and in the Contract that is the subject of this Agreement.

The terms of the Contract, are contained in:

Part 1	Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part 2	Pricing Data

Part 3	Scope of Work: Service Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule, which must be signed by the duly authorised representative(s) for both parties.

The tenderer shall within one week of receiving a completed copy of this Agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this Agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this Agreement.

Notwithstanding anything contained herein, this Agreement comes into effect on the date when the tenderer receives one fully completed and signed copy of this document, including the Schedule of Deviations (if any) together with all the terms of the contract as listed above.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) | Avi Singh |  |  |  |
| Capacity | General Manager: Peaking Power Stations |  |  |  |
| for the Employer | (Insert name and address of organisation) Eskom Holdings SOC Ltd c/o 15 Pasita Street Rosenpark 7530 |  |  |  |
| Name & signature of witness | M Bester Procurement Manager |  | Date |  |

Note: 	If a tenderer wishes to submit alternative tender offers, further copies of this document may be used for that purpose, duly endorsed, ‘Alternative Tender No. _____ ‘

## Schedule of Deviations

Note:

- To be completed by the Employer prior to award of contract.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  | Avi Singh |
| Capacity |  |  | General Manager: Peaking Power Stations |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) Eskom Holdings SOC Ltd c/o 15 Pasita Street Rosenpark 7530 |
| Name & signature of witness |  |  | M Bester Procurement Manager |
| Date |  |  |  |

# C1.2 Contract Data

## Data provided by the Employer

| ## Clause |  | ## Statement | ## Data |
| --- | --- | --- | --- |
|  |  | ## General |  |
| 10.1 |  | The Employer is (Name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |
|  |  | Tel No. | 011 800 8111 |
|  |  | Fax No. | N/A |
|  |  | E-mail address | N/A |
|  |  | If the Employer appoints an Employer’s Agent , the Employer’s Agent is: |  |
| 14.5 |  | Name | Zandile Mnukwa |
|  |  | Address | Drakensberg Pumped Storage Scheme Off R74 between Harrismith and Bergville Jagersrust 3354 |
|  |  | Tel No. | 046 438 2034 |
|  |  | Fax No. | None |
|  |  | E-mail address | MnukwaCN@eskom.co.za |
|  |  | The authority of the Employer’s Agent is | To carry out all the actions of the Employer in this contract |
| 11.2(5) |  | The service is | Inspection and repairs to the concrete lining of Drakensberg Waterway Units 1 & 2 |
| 11.2(6) |  | The Service Information is in | the document called ‘Service Information’ in Part 3 of this contract. |
| 30.1 |  | The starting date is. | 06th January 2023 |
| 30.1 |  | The service period is. | 15 days |
| 13.2 |  | The period for reply is | Planning phase – 2 calendar days Execution phase – 5 hours |
| 50.1 |  | The assessment day is the | On completion of the task order |
| 51.2 |  | The interest rate on late payment is | 0% per complete week of delay |
| 80.1 |  | The Contractor is not liable to the Employer for loss of or damage to the Employer’s property in excess of | the amount of the deductibles relevant to the event |
|  |  | Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) apply? | No |
| 93.1 |  | The Adjudicator is | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |
| 93.2(2) |  | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body |
| 93.4 |  | The tribunal is: | arbitration. |
|  |  | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |
|  |  | The place where arbitration is to be held is | Johannesburg, South Africa |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |
|  |  | The conditions of contract are the NEC3 Term Service Short Contract (April 2013) and the following additional conditions Z1 to Z11 which always apply: |  |
| Z1 | Cession delegation and assignment |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |
| Z2 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |
| Z2.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |
| Z2.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer. |  |
| Z2.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the starting date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Service. |  |
| Z2.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the service. |  |
| Z3 | Confidentiality |  |  |
| Z3.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to others except where required by this contract. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to others where required by this contract the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |
| Z3.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Employer. |  |  |
| Z3.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |
| Z3.4 | The taking of images (whether photographs, video footage or otherwise) of the Employer’s property or any portion thereof, in the course of Providing the Service and after the end of the service period, requires the prior written consent of the Employer. All rights in and to all such images vests exclusively in the Employer. |  |  |
| Z3.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |
| Z4 | Waiver and estoppel: Add to clause 12.2: |  |  |
| Z4.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties or their delegates or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |
| Z5 |  | Health, safety and the environment |  |
| Z5.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the service. Without limitation the Contractor: - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of service; and - undertakes, in and about the execution of the service, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |
| Z5.2 |  | The Contractor, in and about the execution of the service, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |

| Z6 |  | Provision of a Tax Invoice and interest. Add to clause 50 |  |  |
| --- | --- | --- | --- | --- |
| Z6.1 |  | The Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Service Information, showing the correctly assessed amount due for payment. |  |  |
| Z6.2 |  | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |
| Z6.3 |  | The Contractor is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |
| Z7 |  | Notifying compensation events |  |  |
| Z7.1 |  | Delete from the last sentence in clause 61.1, “unless the event arises from an instruction of the Employer.” |  |  |
| Z8 |  | Employer’s limitation of liability; Add to clause 80.2 |  |  |
| Z8.1 |  | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand). |  |  |
| Z9 |  | Termination: Add to clause 90.2, after the words "or its equivalent": |  |  |
| Z9.1 |  | or had a business rescue order granted against it. |  |  |
| Z10 |  | Addition to Clause 50.4 |  |  |
| Z10.1 |  | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in a Task Order (if any), the Employer may terminate the Contractor’s obligation to Provide the Service. |  |  |
| Z10.2 |  | If the Employer terminates in terms of this clause, the procedures on termination are those stated in Clause 91.1 and the amount due on termination includes amounts listed in Clause 92.1 less a deduction of the forecast additional cost to the Employer of completing the service. |  |  |
| Z11 | Ethics |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |
| Affected Party |  |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |  |
| Coercive Action |  |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |  |
| Collusive Action |  |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |  |
| Committing Party |  |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractors or the Subcontractor’s employees, |  |
| Corrupt Action |  |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |  |
| Fraudulent Action |  |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |  |
| Obstructive Action |  |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |  |
| Prohibited Action |  |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |  |
| Z11.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |  |  |
| Z11.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |  |  |
| Z11.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |  |  |
| Z11.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |  |  |

Z12	Insurance

Z __12.1	Replace condition of contract 82 with the following:

| Insurance cover |  | 82 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 82.1 |  | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |  |  |
|  |  | 82.2 |  | The Contractor provides the insurances in the Insurance Table A, from the starting date until the until the earlier of Completion and the date of the termination certificate. |  |  |
|  |  |  |  | INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage caused by the Contractor to the Employer’s property; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance. Loss of or damage to equipment, plant and materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible as at contract date, where covered by the Employer’s insurance. The Contractor’s liability for loss of or damage to property (except the Employer’s property, equipment and other things used to Provide the Service) and for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Service; Loss of or damage to property The replacement cost Bodily injury to or death of a person The amount required by the applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
|  |  | 82.3 |  | The Employer provides the insurances stated in the Insurance Table B |  |  |
|  |  |  |  | - INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

| Z13 | Nuclear Liability |
| --- | --- |
| Z13.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |
| Z13.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |
| Z13.3 | Subject to clause Z13.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |
| Z13.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |
| Z13.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |
| Z14 | Asbestos |

| For the purposes of this Z-clause, the following definitions apply: |  |  |
| --- | --- | --- |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z14.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z14.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z14.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z14.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z14.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z14.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z14.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

## Data provided by the Contractor (the Contractor’s Offer)

The tendering contractor is advised to read both the NEC3 Term Service Short Contract (April 2013) and the relevant parts of its Guidance Notes (TSSC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on page 24 of the TSSC3 Guidance Notes.

Completion of the data in full is essential to create a complete contract.

| 10.1 | The Contractor is (Name): | [●] |
| --- | --- | --- |
|  | Address | [●] |
|  | Tel No. | [●] |
|  | Fax No. | [●] |
|  | E-mail address | [●] |
| 63.2 | The percentage for overheads and profit added to the Defined Cost for people is | [●]% |
| 63.2 | The percentage for overheads and profit added to other Defined Cost is | [●]% |
| 11.2(4) | The Price List is in | the document called ‘Price List’ in Part 2 of this contract. |
| 11.2(4) | The offered total of the Prices for part of the service in Part 1 of the Price List is [Enter the total of the Prices from the Price List]: | R[●] excluding VAT [in words] [●] excluding VAT |
| 11.2(4) | The offered total of the Prices for part of the service in Part 2 of the Price List is [Enter the total of the Prices from the Price List]: | R[●] excluding VAT [in words] [●] excluding VAT |

C2 Pricing Data

# C2.1 Pricing assumptions

The Price List is in two parts.  Part 1 is for work described in the Service Information not requiring the Employer to issue a Task Order.  Part 2 is for work to be carried out within a stated period of time on a task by Task basis and instructed by Task Order.  The service may comprise work under Part 1 only or Part 2 only or a mix of both.

Entries in the first four columns of Part 1 of the Price List are made either by the Employer or the tenderer.  Entries in the first four columns of Part 2 of the Price List would normally be made by the Employer as the Party most likely to know the kind of work which will be instructed by the issue of Task Orders.  The tenderer then enters a rate for each item and multiplies it by the Expected quantity to produce the Price to be entered in the final column.

If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only, the Unit, Expected quantity and Rate columns being left blank.

If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters a rate for each item and multiplies it by the Expected quantity to produce the Price, to be entered in the final column.

If the Contractor is to be paid a Price for an item proportional to the length of time for which a service is provided, a unit of time is stated in the Unit column and the expected length of time (as a quantity of the stated units of time) is stated in the Expected quantity column.

The rates and Prices entered for each item includes for all work and other things necessary to complete the item.

# C2.2 Price List

Part 1

The rates and Prices entered for each item includes for all work and other things necessary to complete the item.

| ITEM | DESCRIPTION | QTY | UNIT | RATE | TOTAL |
| --- | --- | --- | --- | --- | --- |
| 1 | P&Gs |  |  |  |  |
| 1.1 | Site Establishment(offices, storage shed) | 1 | sum |  |  |
| 1.2 | Transport | 10 | days |  |  |
| 1.3 | Accomodation | 12 | days |  |  |
| 1.4 | PortableToilets | 1 | sum |  |  |
| 1.5 | Compliance with Employers Safety requirements, Compile Health & Safety File | 1 | sum |  |  |
| 1.6 | Plant, tools & Equipment.(Provide all necessary certified rigging and rope access equipment for execution of the work) | 1 | sum |  |  |
| 1.7 | Site De-establishment(offices, storage shed) | 1 | sum |  |  |
| 2 | Concrete Repairs | 1 | No |  |  |
| 2.1 | SIKA Top Armatech 110 EpoCem bonding agent (or similar approved) | 25 | m² |  |  |
| 2.2 | Sika Rep LW cementitious grout (or similar approved) | 5 | m³ |  |  |
| 2.3 | Sika Rep LW cementitious grout with bulking stone (or similar approved) | 5 | m³ |  |  |
| 2.4 | Crack injection repair | 20 | m |  |  |
| 2.5 | Epoxy injection repair | 30 | No. |  |  |
| 2.6 | Drill drain holes at strategic locations through 400mm thick reinforced concrete walls and into rock, install 75mm diameter HDPE perforated pipes wrapped in suitable filter fabric in the hole (all the way to the back end of the wall). Allowance to be made for 10 No. weep holes, 1410mm long. The valve pit has an octagonal shape and is approximately 12.5m deep with wall to wall distance of 9m. The anticipated positions is approximately 9m from the bottom (below an expansion joint) and 3,5m from the top level of the pit. Access to execute the work can either be by means of scaffolding or rope access. The exact details and specifications to be confirmed. | 10 | No. |  |  |
| 2.7 | Install aluminium box gutters 125mm wide x 100mm deep below the weep holes. Install aluminium down pipes to suit gutters and drain water to valve pit sump. Include all brackets and fixings to concrete walls. Gutters to be flush with concrete walls. Allowance to be made for 1 gutter ring and 2 no. down pipes. | 1 | sum |  |  |

|  | Total of the Prices for Part 1 |  |
| --- | --- | --- |

Part 2

The rates and Prices entered for each item includes for all work and other things necessary to complete the item.

| Item no. | Description | Unit | Quantity | Rate | Price |
| --- | --- | --- | --- | --- | --- |

|  | The total of the Prices for Part 2 |  |
| --- | --- | --- |

C3:  Scope of Work

# C3.1 Service Information

Units 1 and 2 which are served by waterway 1/2 were commissioned in 1981. The waterway serving units of 1 and 2 were last dewatered and inspected in 2020. The forthcoming outage will be the fifth inspection in the life of the structure. Waterway 1/2 is to be dewatered in January 2023 to perform inspections and effect repairs to the concrete lined pressure tunnel and headrace tunnel.

The waterway is a high-pressure system consisting of a concrete pre-stressed lining. During the outage the concrete lining will be inspected and repaired if required.

PRESSURE TUNNEL

During the inspection of waterway 1/2 in 2009 a number of defects were detected in the reinforced concrete liner comprising the pressure tunnel. Localized areas of surface concrete were identified as having lost strength and have been repaired in previous outages. Generally, the affected zones of concrete can be related to repairs of spalled concrete undertaken during the pre-stressing of the waterway liner during the construction stage. With the waterway outage in 2020, the concrete lining was re-inspected and repaired where required.

The pressure tunnel has an internal diameter of 5.5 m (section BB in drawing 0.48/4837) and a slope of 1 in 10. The overall length of the pressure tunnel 1/2 is 1343 m with the concrete lined section approximately 821 m. Stainless steel hand holds are installed in the invert of the tunnel lining at approximately 50 m intervals (refer drawing 0.48/4836). The nominal thickness of the concrete lining is 750 mm and is reinforced with 25mm diameter high tensile reinforcing bars at 200 mm centres in the longitudinal and circumferential directions. The minimum cover to the reinforcement is 50 mm and the maximum, 90 mm. Although the cube strength of the concrete was measured to be in the order of 40 MPa at 28 days, the conditions under which the concrete has cured are likely to result in much higher strengths. This should be taken into account when determining appropriate methods for preparing the substrate prior to the application of any repair.

Due to leakage through the headrace gate seals, a continual minor leakage of water along the invert can be expected. On either side of this leakage, the presence of a silt layer on the tunnel lining makes the surface slippery Access into the pressure tunnel is via a 740 mm diameter manhole in the penstock. All equipment, plant materials and personnel are required to enter and exit via this manhole. The orientation of the manhole in relation to the surrounding concrete works is given in drawing 0.48/1302 (Section AA and Detail H). The access to the manhole door is via a 3.0 m high pre-cast culvert (Section CC).

HEADRACE TUNNEL

There were zones identified during previous inspection in 2009 of the headrace tunnel where ground water was flowing under pressure into the waterway, these were repaired in 2020 with crack seal, epoxy injection and concrete repair. These occur in the low pressure section of the waterway where the maximum water pressure was in the order of 170 m. It is possible that since this inspection other leaks could have developed. The extent of the leaks will be inspected and the contractor should plan his operation to repair such leaks in the time available.

It will only be confirmed after the inspection of the headrace tunnel by the Employer whether these, and other, leaks of ground water through the tunnel lining need to be grouted. The Contractor is therefore required to have the equipment for such repairs on standby prior to the inspection. The repair materials should be readily available for purchase. However, the equipment and repair materials are only mobilised on the Employer’s instruction.

Details of the headrace tunnel and the headrace intake tower through which access to the tunnel is gained, are given in “2  Drawings”.The headrace tunnel has a horse shoe shape with an approximate diameter of 6 m, as indicated in the sections of drawing 0.48/4832. The slope of the tunnel varies between 1 in 100 to 1 in 8 and has an overall length of 1490 m. Stainless steel hand holds are installed in the invert of the tunnel lining at approximately 50 m intervals (refer drawing 0.48/4836). The nominal thickness of the concrete lining varies between 650 mm and 750 mm at its crown.   Thickest section viz. at the bottom corners, the thickness of the concrete is 1270 mm in the horizontal direction and 1420 mm in the vertical. However, considering the likelihood of over break of the tunnel excavation, it is recommended that the maximum thickness of the concrete lining as determined above be increased by 0.5 m.

Although the cube strength of the concrete was measured to be in the order of 40 MPa at 28 days, the conditions under which the concrete has cured are likely to result in much higher strengths. Due to leakage through the headrace gate seals, a continual minor leakage of water along the invert can be expected. On either side of this leakage, the presence of a silt layer on the tunnel lining makes the surface slippery.

Access into the headrace tunnel is via the intake tower (drawing 0.48/4829). The power station staff will provide personnel access via a number of permanent and temporary ladders /scaffolding. Equipment is lowered down the intake structure from level 1706 m to level 1660 m (a total height of 46 m) via a manually operated block and tackle supplied by the power station having a maximum carrying capacity of 100 kg. The size of any plant and equipment is restricted to the size of the openings at 1706m – the maximum width of openings at this level is 1700m

1. Description of the service

Scope of work for the Pressure Tunnel

The following work is planned to be undertaken:

- The Contractor is to provide and erect a demountable access platform which will enable a thorough inspection of the concrete lining and the identification and marking of localized areas which are in need of repair. The access platform is to be designed by the Contractor and must have the capability to be safely moved and stopped along the length of the pressure tunnel.

- Where necessary, the Contractor provides an additional platform(s) which can be used in breaking out the identified areas of deteriorated concrete, the preparation of the substrate and the application of the repair material in accordance with the specification.

- The Contractor inspects the concrete lining together with the Employer and/or his representative and identifies areas of deteriorated concrete. These areas are marked for repair. The method of inspection of the lining should include for the removal of any layers of silt or other deposits, mechanical testing or tapping with steel hammers and sufficient battery powered lighting for a visual assessment.

- The Contractor affects repairs to the concrete lining by the removal of deteriorated concrete, preparation of the concrete substrate and the repair of these areas in accordance with the specifications. Any requirements for the curing   the repair materials are to be strictly implemented. The Contractor ensures that the time between the re-watering of the tunnel and the time of the last repair is greater than the minimum curing period specified.

- The Contractor removes all debris from the tunnel and transports it to a designated spoil dump. All materials, plant and equipment are removed and all personnel evacuated from the tunnel prior to the specified time for closure of the tunnel as indicated in this document and later, more specifically defined by the power station during the course of the outage.

Based on previous repairs, typical dimensions of the zones of concrete which are to be repaired are approximately 300 x 300 x 50 to 75mm deep. It is estimated that a maximum volume of concrete to be repaired will be in the order of 0.5 m3 to 1.0 m3.

The Contractor is required to grout up areas where ground water leakage through the tunnel lining has been identified by the Employer, in accordance with the specifications. It is required that the interface between the concrete lining and the rock mass be grouted locally to permanently seal off any leakage paths and stem the leakage of water into the rock mass during operating conditions and in the reverse direction when the waterway is dewatered. All drill holes and existing leakage paths in the concrete lining are to be repaired such that they form a second barrier to the leakage paths.

Under no circumstances is the Contractor to drill through the lining or damage the rebar. All repair work is to be limited to the surface concrete.

Scope of work for the Headrace Tunnel

The following work is planned to be undertaken:

- The Contractor is to provide and erect a demountable access platform which will enable access to zone identified for grouting. The access platform is to be designed by the Contractor and must have the capability to be easily and safely moved and stopped along the length of the tunnel.

- The Contractor erects a safety barrier 50 m upstream of the intersection of the headrace tunnel and the pressure shaft. The pressure shaft is some 275 m deep and will be emptied during the contract. It is the Contractor's responsibility to ensure that his workmen are at all times kept upstream of this barrier. This barrier is removed on completion of the grouting.

- The Contractor is required to grout up areas where ground water leakage through the tunnel lining has been identified by the Employer, in accordance with the specifications. It is required that the interface between the concrete lining and the rock mass be grouted locally to permanently seal off any leakage paths and stem the leakage of water into the rock mass during operating conditions and in the reverse direction when the waterway is dewatered. All drill holes and existing leakage paths in the concrete lining are to be repaired such that they form a second barrier to the leakage paths.

- The leakages identified in the previous inspection occurred 240 m downstream from the 1:8/1:100 junction and 680 m upstream of the 1:100/1:13 junction.

- The Contractor removes all debris from the tunnel and transports it to a designated spoil dump. All materials, plant and equipment are removed and all personnel evacuated from the tunnel prior to the specified time for closure of the tunnel as indicated in this document and later, more specifically, as defined by the power station during the course of the outage.

2. Specifications

Particular Specifications

Repair of Deteriorated Surface Concrete in the Pressure Tunnel

Preparation of the Concrete Surface

Prior to breaking out of any concrete which has been identified for repair in the inspection, the surface of the concrete at and around the repair is to be cleaned such that it is free of any dust, dirt or deleterious material. This is to ensure that the repair area, once broken out, will not be contaminated.

The equipment and methods used to break out the concrete are such that no reinforcing steel or other embedded items such as lifting sockets etc. are loosened, damaged or removed unless otherwise agreed by the Employer. Any damage is brought to the attention of the Employer and replaced by the Contractor at his own cost.

The pockets broken out are profiled such that entrapment of air during the process of placing the repair material is avoided The perimeter of the void is incised to a depth of at least 10mm causing good arises to be formed at the outer edges and so eliminate any occurrence of feather edging. Preferably, these edges should be undercut to for 'dovetailed' edges. Such undercutting should not however, result in acute angles which could weaken the edge.

All exposed concrete surfaces to receive repair materials are to comprise sound concrete having a rough nature in which the aggregate is exposed. All saw/disc cut edges are to be lightly roughened.

This preparation should result in a sound (i.e. no flaking or cracked concrete), exposed concrete substrate free of dust, loose particles, cement paste, laitance covering the aggregate and any deleterious matter or contaminants. Repairs are to be implemented immediately after the cleaning process.

It is essential, during the break out and repair phases that any standing water be removed and prevented from entering the broken out pockets and that the surface be maintained in a dry condition after cleaning.

The concrete lining will be in a saturated condition on dewatering but no water seepage is expected from the lining. The Contractor is to take the necessary measurements of air and concrete temperature and relative humidity to ensure that the substrate temperature is above dew point and that no condensation occurs on the surface prior to applying the repair material.

Mixing & Application

The mixing and application of the repair material(s) are to be performed in accordance with the recommendations of the manufacturer and as may be discussed and agreed with the Employer and manufacturer on site.

The repair material is to be mixed and applied to the voids without delay. Any material not used within the specified pot life will be discarded and not paid for by the Employer. Where deep repairs are necessary, the repair material is applied in layers of specified thickness and any bond coats, as recommended by the manufacturer of the repair material, applied. Any such bond coats are to have a wet consistency when the next layer of repair material is applied to prevent the development of bond breakers forming between layers. The surface between layers should not be smooth.

Curing

The Contractor ensures that repaired areas are adequately cured and that no drying of the repair surface occurs. A minimum cure period is specified between the application of the repair and the recommissioning of the waterway. This minimum cure period must be taken into account by the Contractor in planning his repair activities.

Acceptance Tests

The sections of concrete broken out are inspected by the Employer prior to the application of the repair material.

The Contractor ensures that, where necessary, access is provided to enable the undertaking of inspections and taking of samples for test purposes.

The Contractor takes samples of the repair material and prepares 12 No. cubes for compression strength testing. These tests are conducted such that 4 No. samples are tested at 3, 7 and 28 days after casting.

Repair Material Specification

Sika Top Armatech 110 EpoCem, bonding agent and anti-corrosive coating.

Sika Rep LW cementitious, non-sag patching and repair mortar is applied to within 5 mm of the finished surface.

The contractor to provide the material specifications for grouting of any water leaks.

3. Constraints on how the Contractor Provides the Service

The Contractor provides

- Proof of security Screening

Acceptance of this tender is subject to the condition that both the contracting company’s management and its employees will provide Eskom with a clear criminal record not older than thirty (30) days from a reputable screening company. If the principal contractor appoints a subcontractor, the same provisions and measures will apply to the subcontractor. Acceptance of the tender is also subject to the condition that the contractor will implement all such security measures for the safe performance of the work as required in the scope of the contract

- Accommodation and Transport

The Contractor provides accommodation and transport for all his staff

- Telephone facilities

Telephone facilities are not provided. The Contractor shall make arrangements for his telephone facilities

Items to be supplied by the Contractor in his tender

- Lead time to site establishment after order is placed

- Method statement and QCP

- Reference to similar work with contact details of the references

- Bar chart program detailing how he is to execute the works within the stipulated timeframes

3.1  Meetings

Before ay work can commence on site the Contractor and all staff to attend site induction. The Contractor is to allow 2 hours for this. Contractors are required to submit the SAPS Clearance certificate obtained by the employee along with a copy of his/her identity document or passport.

The Contractor will be required to sign on to the workers register each morning and sign out each afternoon. A responsible person (RP) will be appointed by site and will be responsible for the area where the works is taking place. The RP will be responsible for ensuring that everyone signs on and off the workers register, ensure that everyone is aware of the Eskom rules and will confirm that the area is still safe for work. The Contractor must notify the RP of the daily work plan prior to execution of works.

The Contractor is to hold a toolbox talk each morning before commencing with the works to discuss the previous day’s work and to ensure that everyone understands what is required of them.

When required, the Contractor must have a representative at each daily morning Outage meeting.

3.2 Use of standard forms

Standard forms to be used by the Contractor in the administration of the contract, for example early warning and compensation event notifications.

## 3.3 Invoicing and payment

In terms of core clause 50 the Contractor assesses the amount due and applies to the Employer for payment.  The Contractor applies for payment with a tax invoice addressed to the Employer as follows:

______________________________________________________________________

The Contractor includes the following information on each tax invoice:

- Name and address of Contractor;

- Contractor’s VAT registration number if applicable;

- Contractor’s company registration number if applicable;

- Contractor’s banking details;

- Name and address of recipient ;

- Tax invoice number and date of issue;

- Description of goods/services provided;

- Period time for which the Tax invoice is being rendered;

- Contract Number (commencing with a 46 prefix);

- Relevant Task Number (commencing with a 45 prefix);

- Relevant Task Order line item number;

- Relevant good receipt/service entry number received from the Employer’s Service Manager;

- Statement whether value added tax is included or excluded

- Invoices to be made out to Eskom Holdings SOC Ltd

The Contractor attaches the detail assessment of all work done for each item in the Price List to each tax invoice showing

- the Price for each lump sum item in the Price List or Task Order which the Contractor has completed and

- where a quantity is stated for an item in the Price List or Task Order, an amount calculated by multiplying the quantity which the Contractor has completed by the rate.

All invoices to be accompanied by the Payment Assessment Certificate as issued by the Service Manager invoices to be submitted electronically as PDF documents to:

invoiceseskomlocal@eskom.co.za

### 3.3.1	Eskom information

- Eskom Tax clearance and BBBEE certificate is available at: https://www.eskom.co.za/Tenders/BBBEECertificate/Pages/Eskom_BBBEE_Certificate.aspx

- Eskom VAT Number is 4740101508

3.4 Records of Defined Cost

In order to substantiate the Defines Cost of compensation events, the Employer requires that the Contractor keeps records of amounts paid by him for people employed by the Contractor, Plant and Materials, work subcontracted by the Contractor and equipment. [See clause 11.2(2) and 63.2].  These records need to be available on a spreadsheet in case a compensation event is agreed on.

### 3.5 Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

Not applicable in this instance

### 3.6 BBBEE and preferencing scheme

Contractor to ensure Employer has an updated valid certified copy of BBBEE certificate or sworn affidavit during contract period. Failure to do so, could result in Eskom Vendor Management Dept blocking the vendor details on Eskom vendor management system which affects payment processing of invoices.

3.7 Cataloguing requirements by the Contractor

Not applicable

4.  Requirements for the plan

The Contractor is to submit a bar chart program detailing how he is to execute the works within the stipulated dates. The program must indicate the start and completion dates and duration of all activities. Take full cognizance of the contractor risk and obligations in terms of the contract. The program will be subject to acceptance by the Project Manager.

If the program has to be revise because the contractor is falling behind, the Contractor shall submit a revised program showing how he intends to meet the completion date. Any proposal by the contractor to increase the tempo or work must incorporate positive steps to increase production either by the provision of more labour and plant on the site or by using the available labour and plant in a more efficient manner.

The Contractor must submit with his tender, daywork rates for al personnel, materials and equipment to be used in execution of the works.

5. Services and other things provided by the Employer

| Item | Date by which it will be provided |
| --- | --- |
| - Water Supply The nearest potable water connections will be indicated but it is the Contractor’s responsibility to arrange for all such services required in the execution of the works. No warranty is offered or given by the Employer that the existing available water supply will be necessarily adequate for the contractor’s purposes nor that such supply is in any way guaranteed. All water for construction purpose shall be clean, free from undesirable concentrations of deleterious salts and other materials. |  |
| - Potable Water |  |
| The Contractor makes his own connections from the location as indicated on site |  |
| - Electricity Supply 220V and 380V electrical supply are generally available in the power station complex. The nearest electrical power supply will be indicated but it is the Contractor’s responsibility to arrange for all such services required in the execution of the works. No warranty is offered or given by the Employer that the existing available electrical supply will necessarily be adequate for the contractor’s purposes nor that such supply is in any way guaranteed. The distribution of electricity shall be carried out by the contractor strictly in accordance with the applicable laws and regulations. |  |
| - Ablution facilities Only available at the power station complex |  |
| - Telephone facilities none |  |
| - Area for Contractors Site Establishment An area in which the contractor may erect its offices, workshop, stores and other facilities, which it requires for the purposes of the contract, will be identified and pointed out at the site meeting. If, the contractor finds the area unsuitable for his requirements, he shall, at his own cost, be responsible for locating and making all arrangements necessary in securing an area suitable to meet its needs Security to the Contractors storage or site yard is the responsibility of the Contractor |  |
| - Storage yard A storage yard will be indicated to the Contractor |  |
| - Spoil Area A spoil area will be indicated to the Contractor |  |
| - Compressed Air No compressed air is available. |  |

6. Property affected by the service

Off R74 between Bergville and Harrismith

is reached from Harrismith via the R49 to Kestel. The R74 turn-off to Bergville is 2,8 kms along the R49. Turn left after 8,7 kms and travel 23,5 kms to the Natal/Free State boundary at the top of the Oliviershoek Pass. From there, travel 13,1 kms down the pass and turn left. Follow the signposted directions to the power station for approximately 9,5 Kms. The total distance from Harrismith is approximately 60 kms

GPS Co-ordinates

| Site | Latitude | Longitude |
| --- | --- | --- |
| Drakensberg Power Station | -28.564689187276056 | 29.084088524999807 |

Task Order

| Task Order form for use when work within the service is instructed to be carried out within a stated period of time on a Task by Task basis |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task Order No. | [●] |  | service | .[●] |
| To: [●]....................................................................................................................................................... .......................................................................................................................... (Contractor) |  |  |  |  |
| I propose to instruct you to carry out the following task: |  |  |  |  |
| Description |  | [●] |  |  |
| Starting date |  | [●] |  |  |
| Completion Date |  | [●] |  |  |
| Delay damages per week |  | [●] |  |  |
| Please submit your price and programme proposals below. |  |  |  |  |
| Signed: |  |  | Date |  |
| (for Employer) |  |  |  |  |
| Total of Prices for items of work on the Price List (details attached) |  |  | R.___________________________________ |  |
| Total of Prices for items of work not on the Price List (details attached). |  |  | R.___________________________________ |  |
| Total of the Prices for this Task Order |  |  | R ___________________________________ |  |
| The programme for the Task is |  |  | ........................................... [ref] (attached) |  |
| Signed: |  |  | Date |  |
| (for Contractor) |  |  |  |  |
| I accept the above price and programme and instruct you to carry out the Task |  |  |  |  |
| Signed: |  |  | Date: |  |
| (for Employer) |  |  |  |  |

If the previous edition applies change ‘April 2013’ for ’September 2009’.

State whether attached as a ‘PDF’ file in terms of Eskom’s licence, or to be obtained from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902 or www.ecs.co.za

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 086 539 1902, or www.ecs.co.za.