NEC3 Engineering & Construction Contract

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________ ) |  |
| for | Replacement of Consumables FFP bags and cages as and when required Insert title of the works |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | [22] |
| Part C2 | Pricing Data | [6] |
| Part C3 | Scope of Work | [16] |
| Part C4 | Site Information | [7] |
| CONTRACT No. | [Insert at award stage] |  |

Part C1: Agreements & Contract Data

| Contents: |  | No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance [to be inserted from Returnable Documents at award stage] | [●] |
| C1.2a | Contract Data provided by the Employer | [●] |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] | [●] |
| C1.3 | Proforma Guarantees | [●] |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Replacement of consumables FFP bags and cages as and when required.

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

Delete the Options which do not apply

| Options A | The offered total of the Prices exclusive of VAT is | R [●] |
| --- | --- | --- |
|  | Sub total | R [●] |
|  | Value Added Tax @ 15% is | R [●] |
|  | The offered total of the amount due inclusive of VAT is | R [●] |
|  | (in words) [●] |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number (if applicable) |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 | [●] | [●] |
| 2 | [●] | [●] |
| 3 | [●] | [●] |
| 4 | [●] | [●] |
| 5 | [●] | [●] |
| 6 | [●] | [●] |
| 7 | [●] | [●] |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer

| ## Clause |  | ## Statement | ## Data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | ## General |  |  |  |  |  |  |
|  |  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |  |  |
|  |  |  | A: Priced contract with activity schedule |  |  |  |  |  |
|  |  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |  |  |
|  |  | and secondary Options |  |  |  |  |  |  |
|  |  |  | X1: Price adjustment for inflation |  |  |  |  |  |
|  |  |  | X2 Changes in the law |  |  |  |  |  |
|  |  |  | X7: Delay damages |  |  |  |  |  |
|  |  |  | X18: Limitation of liability |  |  |  |  |  |
|  |  | of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |  |  |
| 10.1 |  | The Employer is (Name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |  |  |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |
| 10.1 |  | The Project Manager is: (Name) | Phephisani Dlamini |  |  |  |  |  |
|  |  | Address | Hendrina Power Station Impala road Private bag X1003 Pullenshope 1096 |  |  |  |  |  |
|  |  | Tel | 013 296 3973 |  |  |  |  |  |
|  |  | Fax | N/A |  |  |  |  |  |
|  |  | e-mail | dlaminpe@eskom.co.za |  |  |  |  |  |
| 10.1 |  | The Supervisor is: (Name) | Nqatyiswa Nkabinde |  |  |  |  |  |
|  |  | Address | Hendrina Power Station Impala road Private bag X1003 Pullenshope 1096 |  |  |  |  |  |
|  |  | Tel No. | 013 296 3722 |  |  |  |  |  |
|  |  | Fax No. | N/A |  |  |  |  |  |
|  |  | e-mail | nkabinnq@eskom.co.za |  |  |  |  |  |
| 11.2(13) |  | The works are | Replacement of Consumables FFP bags and cages as and when required |  |  |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register | 1. Risk: Flammable bags Action: Take precautionary measures by ensuring that there is full proof access control in place around the working area 2. Risk: Availability of plant Action: Parties to adapt to the shifting of the outage dates by ensuring that there is enough duration within the contract dates to execute work without raising compensation events or delay damages 3. Risk: Outage duration Action: The contractor ensures that enough provision is made to execute the works within the required time by managing time risk allowances and floats 4. Risk: Availability of spares from both parties Action: Have pre-outage meeting to ensure all spares are in place before the go-ahead is given to execute the works 5. Risk: Authorization under Plant Safety Regulations (PSR). 6. Inclement weather conditions. Action: Contractor to provide someone who is authorised under PSR to ensure no time is lost when plant is available for execution of works Any other matter posing a risk to the project/ contract will be discussed amongst the Parties and agreed upon before inserted on the Risk Register. |  |  |  |  |  |
| 11.2(15) |  | The boundaries of the site are | The location is the Fabric Filter plant at FFP landing |  |  |  |  |  |
| 11.2(16) |  | The Site Information is in | Part 4: Site Information |  |  |  |  |  |
| 11.2(19) |  | The Works Information is in | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |  |  |
| 12.2 |  | The law of the contract is the law of | the Republic of South Africa |  |  |  |  |  |
| 13.1 |  | The language of this contract is | English |  |  |  |  |  |
| 13.3 |  | The period for reply is | 2 Working days |  |  |  |  |  |
| ## 2 |  | ## The Contractor's main responsibilities | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |  |  |
| 11.2(3) |  | The completion date for the whole of the works is | 31/12/2026 |  |  |  |  |  |
| 11.2(9) |  | The key dates and the conditions to be met are: | Condition to be met |  |  |  |  | key date |
|  |  |  | 1 | Submission of Health and safety documents for audit approval |  |  |  | Withing one week of contract award date |
|  |  |  | 2 | Site establishment |  |  |  | Within one week of contract award date |
| 30.1 |  | The access dates are: | Part of the Site |  |  |  | Date |  |
|  |  |  | 1 | As required by site during outages |  |  |  |  |
|  |  |  |  | Should any of the above-mentioned units not be available for execution, no penalties are incurred by either Parties upon termination. The access will only be granted by the Project Manager |  |  |  |  |
| 31.1 |  | The Contractor is to submit a first programme for acceptance within | 2 days of the Contract Date. |  |  |  |  |  |
| 31.2 |  | The starting date is |  |  |  |  |  |  |
| 32.2 |  | The Contractor submits revised programmes at intervals no longer than | 1 day A revised programme submitted on a daily basis during the executions of the works |  |  |  |  |  |
| 35.1 |  | The Employer is not willing to take over the works before the Completion Date. |  |  |  |  |  |  |
| ## 4 |  | ## Testing and Defects |  |  |  |  |  |  |
| 42.2 |  | The defects date is | 52 weeks after Completion of the whole of the works. |  |  |  |  |  |
| 43.2 |  | The defect correction period is | 1 day after notification |  |  |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |  |  |
| 50.1 |  | The assessment interval is | On completion of activities as assessed and agreed upon on the assessment date as per task order/activity schedule |  |  |  |  |  |
| 51.1 |  | The currency of this contract is the | South African Rand. |  |  |  |  |  |
| 51.2 |  | The period within which payments are made is | 4 weeks after assessment and tax invoice submission |  |  |  |  |  |
| 51.4 |  | The interest rate is | the publicly quoted prime rate of interest (calculated on a 365 day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and (ii) the LIBOR rate applicable at the time for amounts due in other currencies. LIBOR is the 6 month London Interbank Offered Rate quoted under the caption “Money Rates” in The Wall Street Journal for the applicable currency or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of The Standard Bank of South Africa Limited, whose appointment it shall not be necessary to prove. |  |  |  |  |  |
| ## 6 |  | ## Compensation events |  |  |  |  |  |  |
| 60.1(13) |  | The place where weather is to be recorded is: | Hendrina Power Station Control Rooms |  |  |  |  |  |
|  |  | The weather measurements to be recorded for each calendar month are, | the cumulative rainfall (mm) |  |  |  |  |  |
|  |  |  | the number of days with rainfall more than 10 mm |  |  |  |  |  |
|  |  |  | the number of days with minimum air temperature less than 0 degrees Celsius |  |  |  |  |  |
|  |  |  | the number of days with snow lying at 09:00 hours South African Time |  |  |  |  |  |
|  |  |  | and these measurements: |  |  |  |  |  |
|  |  | The weather measurements are supplied by | Hendrina Power Station Control Rooms |  |  |  |  |  |
|  |  | The weather data are the records of past weather measurements for each calendar month which were recorded at: | Hendrina Power Station Control Rooms |  |  |  |  |  |
|  |  | and which are available from: | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer |  |  |  |  |  |
| 60.1(13) |  | Assumed values for the ten year return weather data for each weather measurement for each calendar month are: | As stated in Annexure A to this Contract Data provided by the Employer. Note: If this arrangement is used, delete the rows above for 60.1(13) and delete this note. |  |  |  |  |  |
| ## 7 |  | ## Title | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |  |  |
| 80.1 |  | These are additional Employer's risks | As referenced by the Risk Register during works execution |  |  |  |  |  |
| ## 9 |  | ## Termination | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |  |  |
| A |  | Priced contract with activity schedule | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |
| ## 11 |  | ## Data for Option W1 |  |  |  |  |  |  |
| W1.1 |  | The Adjudicator is | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |  |  |
|  |  | Address |  |  |  |  |  |  |
|  |  | Tel No. |  |  |  |  |  |  |
|  |  | Fax No. |  |  |  |  |  |  |
|  |  | e-mail |  |  |  |  |  |  |
| W1.2(3) |  | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body. |  |  |  |  |  |
| W1.4(2) |  | The tribunal is: | arbitration. |  |  |  |  |  |
| W1.4(5) |  | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |
|  |  | The place where arbitration is to be held is | South Africa |  |  |  |  |  |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |
| ## 12 |  | ## Data for secondary Option clauses |  |  |  |  |  |  |
| X1 |  | Price adjustment for inflation |  |  |  |  |  |  |
| X1.1(a) |  | The base date for indices is | [●]. |  |  |  |  |  |
| X1.1(c) |  | The proportions used to calculate the Price Adjustment Factor are: | proportion |  | linked to index for | Index prepared by |  |  |
|  |  |  | 0. [●] |  | [●] | [●] |  |  |
|  |  |  | 0. [●] |  | [●] | [●] |  |  |
|  |  |  | 0. [●] |  | [●] | [●] |  |  |
|  |  |  | 0. [●] |  | [●] | [●] |  |  |
|  |  |  | 0. [●] |  | [●] | [●] |  |  |
|  |  |  | [●] |  | non-adjustable |  |  |  |
|  |  | Total | 1.00 |  |  |  |  |  |
| X2 |  | Changes in the law | There is no reference to Contract Data in this Option and terms in italics are identified elsewhere in this Contract Data. |  |  |  |  |  |
| X7 |  | Delay damages (but not if Option X5 is also used) |  |  |  |  |  |  |
| X7.1 |  | Delay damages for Completion of the whole of the works are | 5% of the total contract value per day up to a limit of 20% of the total contract value |  |  |  |  |  |
| X18 |  | Limitation of liability |  |  |  |  |  |  |
| X18.1 |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: | Total contract value per unit |  |  |  |  |  |
| X18.2 |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: | the amount of the deductibles relevant to the event |  |  |  |  |  |
| X18.3 |  | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to | The greater of - the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date. |  |  |  |  |  |
| X18.4 |  | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for - Defects due to his design which arise before the Defects Certificate is issued, - Defects due to manufacture and fabrication outside the Site, - loss of or damage to property (other than the works, Plant and Materials), - death of or injury to a person and - infringement of an intellectual property right. |  |  |  |  |  |
| X18.5 |  | The end of liability date is | (i) 0.5 years after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |  |  |  |  |  |
| Z |  | The Additional conditions of contract are | Z1 to Z15 always apply. |  |  |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |  |  |
| Z2.3 | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |  |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |  |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |  |  |  |  |  |  |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |  |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |  |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. |  |  |  |  |  |  |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |  |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and - undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |
| Z6.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |  |  |
| Z7.1 | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |  |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |  |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |
| Z8 | Notifying compensation events |  |  |  |  |  |  |  |
| Z8.1 | Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”. |  |  |  |  |  |  |  |
| Z9 | Employer’s limitation of liability |  |  |  |  |  |  |  |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |
| Z9.2 | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited. |  |  |  |  |  |  |  |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |
| Z10.1 | or had a business rescue order granted against it. |  |  |  |  |  |  |  |
| Z11 | Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |  |
| Z11.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |  |  |  |  |  |  |  |

| Z12 | Ethics |  |
| --- | --- | --- |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| Affected Party |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |
| Coercive Action |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |
| Collusive Action |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |
| Committing Party |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees, |
| Corrupt Action |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |
| Fraudulent Action |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |
| Obstructive Action |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |
| Prohibited Action |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |
| Z12.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |
| Z12.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |
| Z12.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |
| Z12.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |
| Z13 | Insurance |  |
| Z 13.1 | Replace core clause 84 with the following: |  |

| Insurance cover | 84 |  |
| --- | --- | --- |
|  | 84.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |
|  | 84.2 | The Contractor provides the insurances stated in the Insurance Table A. |
|  | 84.3 | The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate. |
|  |  | ### INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage to the works, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance. Loss of or damage to Equipment; The replacement cost. Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
| Z 13.2 |  | Replace core clause 87 with the following: The Employer provides the insurances stated in the Insurance Table B. |
|  |  | - INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

| Z14 | Nuclear Liability |  |
| --- | --- | --- |
| Z14.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z14.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.3 | Subject to clause Z14.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z14.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z15 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4 hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z15.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z15.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z15.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z15.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |
| Z15.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z15.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z15.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

# Annexure A:	 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Cumulative rainfall (mm) | Number of days with rain more than 10mm | Number of days with min air temp < 0 deg.C | Number of days with snow lying at 08:00 CAT | [Other measurements if applicable] |
| January | [●] | [●] | [●] | [●] |  |
| February | [●] | [●] | [●] | [●] |  |
| March | [●] | [●] | [●] | [●] |  |
| April | [●] | [●] | [●] | [●] |  |
| May | [●] | [●] | [●] | [●] |  |
| June | [●] | [●] | [●] | [●] |  |
| July | [●] | [●] | [●] | [●] |  |
| August | [●] | [●] | [●] | [●] |  |
| September | [●] | [●] | [●] | [●] |  |
| October | [●] | [●] | [●] | [●] |  |
| November | [●] | [●] | [●] | [●] |  |
| December | [●] | [●] | [●] | [●] |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.

C1.2 Contract Data

# Part two - Data provided by the Contractor.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |  |  |
| --- | --- | --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |  |  |
|  | Address |  |  |  |
|  | Tel No. |  |  |  |
|  | Fax No. |  |  |  |
| 11.2(8) | The direct fee percentage is | % |  |  |
|  | The subcontracted fee percentage is | % |  |  |
| 11.2(18) | The working areas are the Site and |  |  |  |
| 24.1 | The Contractor's key persons are: |  |  |  |
|  | 1 Name: |  |  |  |
|  | Job: |  |  |  |
|  | Responsibilities: |  |  |  |
|  | Qualifications: |  |  |  |
|  | Experience: |  |  |  |
|  | 2 Name: |  |  |  |
|  | Job |  |  |  |
|  | Responsibilities: |  |  |  |
|  | Qualifications: |  |  |  |
|  | Experience: |  |  |  |
|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |  |  |
| 11.2(3) | The completion date for the whole of the works is |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register |  |  |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: |  |  |  |
| 31.1 | The programme identified in the Contract Data is |  |  |  |
| A | Priced contract with activity schedule |  |  |  |
| 11.2(20) | The activity schedule is in |  |  |  |
| 11.2(30) | The tendered total of the Prices is | (in figures) (in words), excluding VAT |  |  |

Part 2: Pricing Data

ECC3 Option A

| Document reference | Title Replacement of Consumables FFP bags and cages as and when required | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A | 2 |
| C2.2 | The activity schedule | 6 |

C2.1 Pricing assumptions: Option A

# How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

| Identified and defined terms | 11 11.2 | (20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (27) The Price for Work Done to Date is the total of the Prices for - each group of completed activities and - each completed activity which is not in a group. A completed activity is one which is without Defects which would either delay or be covered by immediately following work. |
|  |  | (30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract. |

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

# Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.

# Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

# Preparing the activity schedule

Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

It is assumed that in preparing his activity schedule the Contractor:

- Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

- Understands the function of the Activity Schedule and how work is priced and paid for;

- Is aware of the need to link the Activity Schedule to activities shown on his programme;

- Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event.

An activity schedule could have the following format:

| No. | QTY. | Activity description. | Price. |
| --- | --- | --- | --- |
| 1 | 1 | Site Establishment |  |
| 2 | 14 | Skips disposal rental and disposal of FFP bags to Springs |  |
| 3 | 132 | PPE |  |
| 4 | 12 tonnes in 25kg bags | Lime coating material |  |
| 5 | 2 | Transport |  |
| 6 | 1 | DB Board 220-380V |  |
| 7 | 8 | Mechanical toolbox |  |
| 8 | 4 | Welding Machines |  |
| 9 | 400 | Grinding Discs |  |
| 10 | 8 | Electric Grinders |  |
| 11 | 16 | Mechanical toolbox |  |
| 12 | 200 | Welding rods |  |
| 13 | 100 | Lights and torches |  |

Labour

Normal working time: Monday to Friday

| Labour | QTY | Hours | Rate/Hour | Total amount |
| --- | --- | --- | --- | --- |
| Site Manager | 1 | 180 |  |  |
| Site Supervisor | 1 | 180 |  |  |
| Safety officer | 1 | 180 |  |  |
| Planner | 1 | 180 |  |  |
| Quality controller | 1 | 180 |  |  |
| Mechanical Fitter | 6 | 180 |  |  |
| Riggers | 4 | 180 |  |  |
| Boilermaker | 2 | 180 |  |  |
| B Class welder | 2 | 180 |  |  |
| Semi-skilled | 10 | 180 |  |  |
| Hot work monitor | 10 | 180 |  |  |
| Assistants | 26 | 180 |  |  |
| Storeman | 1 | 180 |  |  |

Overtime hours Saturday

| Labour | QTY | Hours | Rate/Hour | Total amount |
| --- | --- | --- | --- | --- |
| Site Manager | 1 | 128 |  |  |
| Site Supervisor | 1 | 128 |  |  |
| Safety officer | 1 | 128 |  |  |
| Planner | 1 | 128 |  |  |
| Quality controller | 1 | 128 |  |  |
| Mechanical Fitter | 6 | 128 |  |  |
| Riggers | 4 | 128 |  |  |
| Boilermaker | 2 | 128 |  |  |
| B Class welder | 2 | 128 |  |  |
| Semi-skilled | 10 | 128 |  |  |
| Hot work monitor | 10 | 128 |  |  |
| Assistants | 26 | 128 |  |  |
| Storeman | 1 | 128 |  |  |

Overtime hours Sunday

| Labour | QTY | Hours | Rate/Hour | Total amount |
| --- | --- | --- | --- | --- |
| Site Manager | 1 | 48 |  |  |
| Site Supervisor | 1 | 48 |  |  |
| Safety officer | 1 | 48 |  |  |
| Planner | 1 | 48 |  |  |
| Quality controller | 1 | 48 |  |  |
| Mechanical Fitter | 6 | 48 |  |  |
| Riggers | 4 | 48 |  |  |
| Boilermaker | 2 | 48 |  |  |
| B Class welder | 2 | 48 |  |  |
| Semi-skilled | 10 | 48 |  |  |
| Hot work monitor | 10 | 48 |  |  |
| Assistants | 26 | 48 |  |  |
| Storeman | 1 | 48 |  |  |

C2.2 the activity schedule

Use this page as a cover page to the Contractor’s activity schedule.

Part 3: Scope of Work

| Document reference | Title Replacement of Consumables FFP bags and cages as and when required | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Works Information |  |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) |  |
|  | Total number of pages |  |

C3.1: Employer’s works Information

Contents

Part 3: Scope of Work	1

C3.1: Employer’s works Information	2

1	Description of the works	5

1.1	Executive overview	5

1.2	Employer’s objectives and purpose of the works	5

1.3	Interpretation and terminology	5

2	Management and start up.	5

2.1	Management meetings	5

2.2	Documentation control	6

2.3	Health and safety risk management	6

2.4	Environmental constraints and management	7

2.5	Quality assurance requirements	7

2.6	Programming constraints	7

2.7	Contractor’s management, supervision and key people	7

2.8	Invoicing and payment	7

2.9	Insurance provided by the Employer	8

2.10	Contract change management	8

2.11	Provision of bonds and guarantees	8

2.12	Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor	8

2.13	Training workshops and technology transfer	8

3	Engineering and the Contractor’s design	9

3.1	Employer’s design	9

3.2	Parts of the works which the Contractor is to design	9

3.3	Procedure for submission and acceptance of Contractor’s design	9

3.4	Other requirements of the Contractor’s design	9

3.5	Use of Contractor’s design	9

3.6	Design of Equipment	9

3.7	Equipment required to be included in the works	10

3.8	As-built drawings, operating manuals and maintenance schedules	10

4	Procurement	11

4.1	People	11

4.1.1	Minimum requirements of people employed on the Site	11

4.1.2	BBBEE and preferencing scheme	11

4.1.3	Accelerated Shared Growth Initiative – South Africa (ASGI-SA)	11

4.2	Subcontracting	11

4.2.1	Preferred subcontractors	11

4.2.2	Subcontract documentation, and assessment of subcontract tenders	11

4.2.3	Limitations on subcontracting	12

4.2.4	Attendance on subcontractors	12

4.3	Plant and Materials	12

4.3.1	Quality	12

4.3.2	Plant & Materials provided “free issue” by the Employer	12

4.3.3	Contractor’s procurement of Plant and Materials	12

4.3.4	Spares and consumables	12

4.4	Tests and inspections before delivery	13

4.5	Marking Plant and Materials outside the Working Areas	13

4.6	Contractor’s Equipment (including temporary works).	13

4.7	Cataloguing requirements	13

5	Construction	14

5.1	Temporary works, Site services & construction constraints	14

5.1.1	Employer’s Site entry and security control, permits, and Site regulations	14

5.1.2	Restrictions to access on Site, roads, walkways and barricades	14

5.1.3	People restrictions on Site; hours of work, conduct and records	14

5.1.4	Health and safety facilities on Site	14

5.1.5	Environmental controls, fauna & flora, dealing with objects of historical interest	14

5.1.6	Title to materials from demolition and excavation	14

5.1.7	Cooperating with and obtaining acceptance of Others	15

5.1.8	Publicity and progress photographs	15

5.1.9	Contractor’s Equipment	15

5.1.10	Equipment provided by the Employer	15

5.1.11	Site services and facilities	15

5.1.12	Facilities provided by the Contractor	15

5.1.13	Existing premises, inspection of adjoining properties and checking work of Others	15

5.1.14	Survey control and setting out of the works	16

5.1.15	Excavations and associated water control	16

5.1.16	Underground services, other existing services, cable and pipe trenches and covers	16

5.1.17	Control of noise, dust, water and waste	16

5.1.18	Sequences of construction or installation	16

5.1.19	Giving notice of work to be covered up	16

5.1.20	Hook ups to existing works	16

5.2	Completion, testing, commissioning and correction of Defects	17

5.2.1	Work to be done by the Completion Date	17

5.2.2	Use of the works before Completion has been certified	17

5.2.3	Materials facilities and samples for tests and inspections	17

5.2.4	Commissioning	17

5.2.5	Start-up procedures required to put the works into operation	17

5.2.6	Take over procedures	18

5.2.7	Access given by the Employer for correction of Defects	18

5.2.8	Performance tests after Completion	18

5.2.9	Training and technology transfer	18

5.2.10	Operational maintenance after Completion	18

6	Plant and Materials standards and workmanship	19

6.1	Investigation, survey and Site clearance	19

6.2	Building works	19

6.3	Civil engineering and structural works	19

6.4	Electrical & mechanical engineering works	20

6.5	Process control and IT works	20

6.6	Other [as required]	20

7	List of drawings	21

7.1	Drawings issued by the Employer	21

C3.2	Contractor’s Works Information	22

# Description of the works

The works entails to remove and replace the complete set of used filter bags and cages from the Fabric Filter Plants at Hendrina Power Station and related activities as stipulated below.

## Executive overview

The aim of this project is to execute a complete bags and cages replacement on Units 7 and 10 to ensure the particulate emission limit of 50 mg/Nm3 is not exceeded and to ensure compliance to the Atmospheric Emission Licence (AEL) AEL no: 17/4/AEL/MP313/11/16. The currently installed bags at Unit 7 and 10  are reaching their end of operational life and need replacement.  The works will consist of replacing the cages and bags on all 16 modules (8 modules per boiler) of Units 7 and 10 Fabric Filter Plant (FFP).

The works for each boiler consist of:

- Site Establishment for bag change.

- Medicals and inductions part of site establishment.

- Transport Bags and Cages to boiler using vehicle (Part of Site establishment).

- Move cages and bags from bottom of ash hoppers to Top of FFP plant (Part of site establishment).

- Remove rotating manifold arms where necessary before bag and cage removal.

- Carry out bag removal on all 16 modules (LH and RH) Specialised bag tools such as a spikes, small forks and big forks to be made available from approved manufacturing drawing.

- Carry out cage removal on all 16 modules (LH and RH).

- Carry out bag and cage Replacement for on all the 16 modules (LH and RH). High temperature bags (PPS) and new cages to be supplied by Eskom.

- Re-install removed rotating manifold arms.

- Clean dust hoppers and ensure no blockages on the hydrovacs.

- Clean any clinkers found inside the hoppers and below the tube plate.

- Remove old bags and cages to the bottom level.

- Dispose all the removed bags and cages.  Contractor to supply the environmental bins.

- Contractor to provide proof of disposal site certificate and supply disposal certificate.

- Clean top of tube plate, surrounding areas and report water leaks (Clean any debris and water)

- Carry out Pre-Coating. The supply of the lime to be included.

- Final Inspection to ensure that there is no debris around the plant (Good Housekeeping).

- Open and close the inspection door seal. Replace inspection door seal. Seal to be supplied by Contractor.

- Open and close inspection doors for structural inspection. Replace access door seals with new seals. New door seal to be supplied by Contractor.

- Site De-establishment.

## Employer’s objectives and purpose of the works

The goals of this project may then be summarised as follows.

- The project is needed to achieve compliance with air quality legislation and licences.

- The Emmisions Compliance Limits for particulate Matter is at 50 mg.Nm3. The currently installed bags at Unit 7 and 10 are reaching their end of operational life and need replacement .

- This calls for maintenace interventions to avoid legal contraventions of Atmospheric Emmission Licences (AEL‘s). AEL No: 17/4/AEL/MP313/11/16

The purpose of the works is to replace the existing FFP bags and cages when replacement is due.

1.2.1.    Removal of bags

1.2.1.1 The Contractor removes the old bags from their installed position in the plant.

1.2.1.2 The Contractor carefully strips the old bags from the cages.

1.2.1.3. The Contractor removes the old bags to disposal bins, which the Contractor provides, via the    disposal chutes installed at the rear of the FFP between the top walkway and the ground level

Method of bag removal:

Remove the cage and old bags by pulling them out together, tear the bag off the cages, and dispose the old bag through the clean-air side to the bag disposal chute. The bag is 8 meters long and the cage is in three sections. The removal is done in three phases. The first phase is to lift the first section of the cage and the bag out, cut off the bag from the top cage, split the top cage from the middle cage, pull out the middle cage and remove the bag from the middle section, split the middle section from the bottom cage, pull out the bottom section and remove the bag from the bottom cage. Existing bags are removed carefully by the Contractor to minimise damage to the cages.

1.2.2    Cages

1.2.2.1 The works include the replacement of the currently installed top, middle and bottom section cages.

1.2.2.2 The Contractor stores the removed support cages in a safe place for later re-use during the fitting of the new bags if we run out of new cages.

1.2.2.3 Special attention is given to ensure that the cages are in a sound condition.

1.2.2.4 The cage is inspected for any type of damage.

1.2.2.5 The Contractor does minor repairs to damaged cages on site during the re-bag activity.  Should any type of damage be found then the cage is repaired before it is re-used.

1.2.2.6 The Contractor removes all cages damaged beyond repair and disposes it to an approved disposal site.

1.2.3    Fitting of bags

1.2.3.1 The Contractor transports the bags from the storage place to the plant.

1.2.3.2 The Contractor inspects the new bags prior to installation.

1.2.3.3 The Contractor fits the new bags onto the cages and installs it in its position in the casing.

Method of bag installation:

The contractor will install the bags starting from the inside of the bag module and working towards the outer row of the module. Bags and cages are to be installed simultaneously.

1.2.4    Inspection doors

The Contractor opens and closes the inspection doors that give access to the tube plate support hangers.

1.2.5     Inspection door seals

The Contractor replaces the seals of these doors with asbestos free door seals.

1.2.6    Access door seals

1.2.6.1 The Contractor replaces the seals of these doors with new.

1.2.6.2 The Contractor adjusts the doors to seal properly.

1.2.7      General

1.2.7.1. No objects are dropped from the top of the FFP except via these disposal chutes.

1.2.7.2. The tube plate and seal are inspected for damage and the damage is repaired before re-bagging commences.

1.2.7.3. The Contractor calls the Employers Representative to inspect the cell before re-bagging commences

1.2.7.4. The Contractor calls the Employers Representative to inspect the cell before signing off the permit to work inside this cell.

1.2.7.5. The Contractor supplies a work method statement for the work to be performed, as part of the tender documentation.

1.2.7.6. The Contractor transports the bags from the on-site bag store to the FFP.

1.2.7.7. The Contractor cleans each of the four cell chambers and inspects the filter casing and bag plate for damage (like holes or indications of dust leaks).  All damage found is repaired before re-bagging commences.

1.2.7.8. Any bags or other objects dropped into the filter plant hoppers are removed before re-commissioning the cell.

1.2.7.9. The Contractor employs methods (e.g. covering the waste bins or employing water sprays) to keep dust pollution into the nearby environment to the minimum during the bag replacement process.

1.2.7.10. The Contractor makes provision in his work plan and quality control document for a final inspection of fitted bags by the Employer, before a cell is de-isolated for pre-coating.

1.2.7.11. The Contractor provides adequate lighting and ventilation inside the cell during the re-bag process.

1.2.7.12. The Contractor must make provision for other Contractors who may be working in the same area.

1.2.7.13. The Contractor is responsible for all free issue material control functions, including but not limited to receipt, checking, off-loading, taking temporary possession and proper storage of all materials, as well as returning any unused or refurbishable items to the Supervisor.

1.2.8     Pre-coating

1.2.8.1. The Contractor provides the lime and labour for this pre-coating activity. 4 tons (2 tons per boiler) of hydrated lime will be used, 1 ton for the Left hand FFP and 1 ton for the Right hand FFP.

1.2.8.2. During re-commissioning of the newly bagged cell, the Contractor pre-coats the bags with hydrated lime as per the method approved by the Employer.

1.2.8.3. Supply, delivery and unloading of the lime are the responsibility of the Contractor.

## Interpretation and terminology

The following abbreviations are used in this Works Information:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| AFC | Approved for construction |
| OBL | Outside battery limits |
| FFP | Fabric Filter Plant |
| NEC | New Engineering Contract |
| PM | Project Manager |
| OEM | Original Equipment Manufacturer |
| QIP | Quality Inspection Plan |
| ETD | Education and Training Department |
| N/A | Not Applicable |
| QC | Quality Control |

# Management and start up.

## Management meetings

Regular meetings of a general nature may be convened and chaired by the Project Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Overall contract progress and feedback | Daily at 07:30 am | Project Manager’s Office | Project Manager and Contractor Site Manager or Site Supervisor |
| Kick off meeting | 3rd working day after contract placement | Projects Boardroom | Project Manager, System Engineer, Contractor Site Manager, Contractor Site Supervisor and Others |
| Early warning (Risk reduction meeting) | As and when required | Projects Boardroom | Project Manager, System Engineer and Contractor Site Manager or Site Supervisor |
| Outage meeting | Daily at 8H00 | Umcebo boardroom | Project Manager and Contractor Site Manager or Site Supervisor |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Documentation control

All communication and decisions must be in writing and must be signed. Email correspondence is an acceptable and legal form of communicating. All correspondence in letters, reports and email must be stored in a project communication file. The sequence of which will be in dates.

## Health and safety risk management

The Contractor shall comply with the health and safety requirements contained in Annexure ___________ to this Works Information.

The following Hendrina Safety Standard is to be adhered to: - HSSMS004 rev 2

## Environmental constraints and management

The Contractor shall comply with the environmental criteria and constraints stated in Annexure ________

## Quality assurance requirements

The supplier shall provide a Quality Plan and Work Procedure.  Before any work commence the quality control plan and work procedure shall be approved by the employer’s engineering and quality departments.

## Programming constraints

The supplier will submit a bar-chart indicating the start date, milestones, critical path and completion date in line with the given time to implement the project. The bar chart to be in MS projects.

## Contractor’s management, supervision and key people

The supplier must submit an Organogram and a list of people on site to the project manager.

## Invoicing and payment

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor shall address the tax invoice to Eskom Holdings SOC Ltd and include on each invoice the following information:

- Name and address of the Contractor and the Project Manager;

- The contract number and title;

- Contractor’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- Description of service provided for each item invoiced based on the Price List;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

- (add other as required)

Add procedures for invoice submission and payment (e. g. electronic payment instructions)

## Insurance provided by the Employer

All insurance related queries should be communicated with the project manager. The project manager is responsible for communicating with the employer’s insurer.

## Contract change management

As per NEC

## Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Contractor is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

## Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor

The contractor should keep records of documents, communication correspondents and payment history.

## Training workshops and technology transfer

Not applicable since the OEM is responsible for plant maintenance. An in-house simulation and training will be provided for operating personnel by ETD.

# Engineering and the Contractor’s design

N/A

## Employer’s design

N/A

## Parts of the works which the Contractor is to design

N/A

## Procedure for submission and acceptance of Contractor’s design

N/A

## Other requirements of the Contractor’s design

N/A

## Use of Contractor’s design

N/A

## Design of Equipment

N/A

## Equipment required to be included in the works

N/A

## As-built drawings, operating manuals and maintenance schedules

N/A

# Procurement

As per Eskom procurement procedure

## People

### Minimum requirements of people employed on the Site

As deemed necessary to complete the works.

### BBBEE and preferencing scheme

As per Employer’s procurement procedures

### Accelerated Shared Growth Initiative – South Africa (ASGI-SA)

The Contractor complies with and fulfils the Contractor’s obligations in respect of the Accelerated and Shared Growth Initiative - South Africa in accordance with and as provided for in the Contractor’s ASGI-SA Compliance Schedule stated below

The Contractor shall keep accurate records and provide the Project Manager with reports on the Contractor’s actual delivery against the above stated ASGI-SA criteria.   [Elaborate on access to and format of records and frequency of submission etc.]

The Contractor’s failure to comply with his ASGI-SA obligations constitutes substantial failure on the part of the Contractor to comply with his obligations under this contract.

## Subcontracting

### Preferred subcontractors

N/A

### Subcontract documentation, and assessment of subcontract tenders

All work to be carried by the Contractor

### Limitations on subcontracting

N/A

### Attendance on subcontractors

N/A

## Plant and Materials

### Quality

QUALITY MANAGEMENT HSP / PA006

### Plant & Materials provided “free issue” by the Employer

The supplier provides all material and tools to complete the works.

### Contractor’s procurement of Plant and Materials

N/A

### Spares and consumables

N/A

## Tests and inspections before delivery

N/A

## Marking Plant and Materials outside the Working Areas

N/A

## Contractor’s Equipment (including temporary works).

N/A

## Cataloguing requirements by the Contractor

N/A

# Construction

## Temporary works, Site services & construction constraints

### Employer’s Site entry and security control, permits, and Site regulations.

Covered by the “Induction” process, and Protection Services

### Restrictions to access on Site, roads, walkways and barricades.

This is covered by the “Induction” process.

### People restrictions on Site; hours of work, conduct and records

The same process as in outage meetings shall be followed in to keep records of contractor employees on site.

### Health and safety facilities on Site

The medical centre is used by all people on site for injuries and first aid related issues. The Fire Department is also available for fire and other related emergencies. Their respective contact details to be provided during induction.

### Environmental controls, fauna & flora, dealing with objects of historical interest

Waste Management Procedure HSPPIN003

Disposal of bags

5.1.5.1 The Contractor removes the old bags and disposes to an approved, Class 1, disposal site.

5.1.5.2 The Contractor regularly removes the filled disposal containers from site to a class 1 disposal site.

5.1.5.3 The Contractor provides the Employer with a disposal certificate as proof of compliance.

5.1.5.4 The Contractor supplies the waste bins for the storage and transport of the material to be disposed of.

5.1.5.5 The bags are disposed in a manner that assures that no bags are lost in the transportation process nor cause any pollution of the environment in the process.

5.1.5.6 The use of a compactor waste transport vehicle is recommended.

5.1.5.7 The subcontracting of the waste disposal to a reputable waste disposal company such as Waste Tech, EnviroServe or Roshcon is recommended

Hazardous substances HSPHO / 058

It is required in terms of the General Administrative Regulation (Regulation 7) that the Contractor of hazardous chemical substance shall supply the receiver, free of charge, with sufficient information for the user.  This is to enable the user to introduce the necessary measures as regards the protection of the health and safety of persons.  It is therefore the responsibility of the supplier (dealing directly with Employer) to supply the information as per attached list.  If information is not available, for whatever reason, the Supplier must indicate on the form and give the reasons in writing to Employer.

Waste Disposal HSPHO / 058 and HSPPIN003

All waste introduced to and / or produced on Employer Premises by the Contractor for this contract, is handled in accordance with the minimum requirements for the handling and disposal of Hazardous waste in terms of Government Legislation as proclaimed by the department of Water Affairs and Forestry Act 1994 Ref. ISBN0621-16296-5.

(A copy of this document is available from Employers Representative).

### Title to materials from demolition and excavation

N/A

### Cooperating with and obtaining acceptance of Others

N/A

### Publicity and progress photographs

Pictures of the work in progress may be taken for the purpose of reporting in meetings.

### Contractor’s Equipment

All contractors’ equipment list should be kept for all equipment that will leave site after completion of the project

### Equipment provided by the Employer

Only scaffolding shall be made available for use by the employer. The contractor must report to project manager any scaffolding requirements two days in advance.

### Site services and facilities

The employer shall provide power, water, waste disposal areas, lighting and ablution. Any additional lighting requirements around the work area shall be provided by the contractor. The Contractor shall provide everything else necessary for completing the works.

### Facilities provided by the Contractor

N/A

### Existing premises, inspection of adjoining properties and checking work of Others

N/A

### Survey control and setting out of the works

A signed off quality inspection plan (QIP) of the employer must be adhered to at all times, to ensure the job is performed to the employer’s satisfaction.

### Excavations and associated water control

N/A

### Underground services, other existing services, cable and pipe trenches and covers

N/A

### Control of noise, dust, water and waste

N/A

### Sequences of construction or installation

N/A

### Giving notice of work to be covered up

N/A

### Hook ups to existing works

N/A

## Completion, testing, commissioning and correction of Defects

### Work to be done by the Completion Date

On or before the Completion Date the Contractor shall have done everything required to Provide the Works except for the work listed below which may be done after the Completion Date but in any case before the dates stated.  The Project Manager cannot certify Completion until all the work except that listed below has been done and is also free of Defects which would have, in his opinion, prevented the Employer from using the works and Others from doing their work.

|  | Item of work | To be completed by |
| --- | --- | --- |
|  | QIP’s to be signed off | All relevant parties |

On or before the Completion Date the Contractor shall have done everything required to provide the Works.

### Use of the works before Completion has been certified

N/A

### Materials facilities and samples for tests and inspections

N/A

### Commissioning

The works is to be implemented on the identified units in line with Hendrina power station outage philosophy.

During re-commissioning of the newly bagged cell, the Contractor pre-coats the bags with hydrated lime as per the method approved by the Employer.

### Start-up procedures required to put the works into operation

The plant will be handed over to the operating department one all the commissioning and testing documentation has been signed off on completion of each unit.

### Take over procedures

N/A

### Access given by the Employer for correction of Defects

PSR (Permit to Work System)

### Performance tests after Completion

N/A

### Training and technology transfer

N/A

### Operational maintenance after Completion

N/A

# Plant and Materials standards and workmanship

## Investigation, survey and Site clearance

See 5.1.5

## Building works

N/A

## Civil engineering and structural works

N/A

## Electrical & mechanical engineering works

N/A

## Process control and IT works

N/A

## Other [as required]

N/A

# List of drawings

## Drawings issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

Note:  Some drawings may contain both Works Information and Site Information.

| Drawing number | Revision | Title |
| --- | --- | --- |

Part 4: Site Information

| Document reference | Title Replacement of Consumables FFP bags and cages as and when required | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C4 | Site Information |  |
|  | Total number of pages | 6 |

Part 4: Site Information

Core clause 11.2(16) states

Part 4: Site Information

# C4.1: Information about the site at time of tender which may affect the work in this contract

## Access limitations

  - Site location and Security

- The Site is Hendrina Power Station which is located approximately 35km from Middelburg N4/N11 offramp along the Middelburg – Hendrina road (N11). Taking the Pullenshope turn-off, about 23 km south from N4/N11 offramp, and continue about 8km you will get to a sign Hendrina Power Station & turn left to the security gates. Access to the site will be via the main security gate only.

- The Employer will inform the Contractor of the access procedures, and it should be expected that such procedures may change depending on the prevailing security situation.

- The Contractor to allow in his price and program for delays at the security gate.
The Employer reserves the right for its Security personnel to search persons or vehicles entering or leaving the premises. This includes but is not limited to briefcases and toolboxes.

- All Contractor employees to provide proof clearance before access permits are issued.

  - Access limitations

Normal working hours are Eskom working hours:

- Monday to Thursday 	07:00 - 16:15

- Fridays			07:00 - 12:00

All Timesheets and workers register are to be kept for records purposes i.e. man-hours worked safely     etc. Daily time sheet must be kept up to date of normal and overtime worked at all times.

  - Temporary Gate Permits

- The Contractor provides the Employer with the personal details of their staff at least two days prior to the occupation date. All names and details to be submitted to the Employer who arranges for all gate permits.

  - Occupational Health and Safety Induction Course

- All the employees of the Contractor must attend a health and safety induction course provided by the Employer at the security offices before they will be allowed to work on the Site. It is the responsibility of the Contractor to ensure that all employees have attended the health and safety induction.

- The Induction course includes an awareness on the Error prevention and Improvement tools and techniques to ensure familiarisation and use of these error-prevention tools/techniques inclusive of, Pre and Post-job briefs, Risk Assessments, Self-checks (STAR principle), Peer Checks, Job observations, Accountability, Effective communications e.g. 3- way, Questioning attitude, Procedural adherence, Hand overs and other.

- A list of employees requiring safety induction must be submitted at least 2 days in advance arrival so that the details of the safety and health induction course can be communicated.

  - Health and Safety Requirements

The Contractor and his sub-Contractors ensure at all times compliance with safety regulations imposed by any Act of Parliament, ordinance or any regulation or by-law of any local or statutory authority. The Contractor acts in accordance with the health and safety requirements stated in the Works Information.

- In carrying out its obligations to the Employer in terms of this contract; in providing the Works; in using Plant, Materials and Equipment; and while at the Site for any reason, the Contractor complies and procures and ensures the compliance by its employees, agents, Sub-Contractors and mandataries with:

- the provisions of the Occupational Health and Safety Act 85 of 1993 (as amended) and all regulations in force from time to time in terms of that Act (“the OHSA”); and the Eskom “Health, Safety and Environmental specifications for Contractors” document attached to the Works Information (as amended from time to time) and such other Eskom Safety Regulations as are applicable to the Works and are provided in writing to the Contractor (collectively “the Eskom Regulations”). The Eskom Regulations may be amended from time to time by the Employer and all amendments will be provided in writing to the Contractor. The Contractor complies with the provisions of the latest written version of the Eskom Regulations with which it has been provided; and the health and safety plan prepared by the Contractor in accordance with the SHEQ Requirements

(The OHSA and the Eskom Regulations are collectively referred to as the “SHEQ Requirements”.)

- The Contractor, at all times, considers itself to be the “Employer” for the purposes of the OHSA and shall not consider itself under the supervision or management of the Employer with regard to compliance with the SHEQ Requirements, the Contractor shall furthermore not consider itself to be a subordinate or under the supervision of the Employer in respect of these matters. The Contractor is at all times responsible for the supervision of its employees, agents, Sub-Contractors and mandataries and takes full responsibility and accountability for ensuring they are competent, aware of the SHEQ Requirements and execute the Works in accordance with the SHEQ Requirements.

- The Contractor acknowledges that it is fully aware of the requirements of all the above and undertakes to employ only people who have been duly authorized in terms thereof and who have received sufficient training to ensure that they can comply therewith.

- The Contractor ensures that all statutory appointments and appointments required by any Eskom Regulations are made and that all appointees fully understand their responsibilities and is trained and competent to execute their duties. The Contractor supervises the execution of their duties by all such appointees.

- The Contractor shall appoint a person who will liaise with the Eskom Safety Officer responsible for the premises relevant to this contract. The person so appointed shall, on request: supply the Eskom Safety Officer with copies of minutes of all Health And Safety Committee meetings, whenever he is required to do so; supply the Eskom Safety Officer with copies of all appointments in respect of employees employed on this contract, in terms of the Act and Regulations and shall advise the Eskom Safety Officer of any changes thereto.

The Employer, or any person appointed by the Employer, may, at any stage during the duration of this contract:

- conduct health and safety audits regarding all aspects of compliance with the SHEQ Requirements, at any off-site place of work, or the site establishment of the Contractor;

- refuse any employee, Sub Contractor or agent of the Contractor access to the premises if such person has been found to commit an unsafe act or any unsafe working practice or is found not to be qualified or authorised in terms of the SHEQ Requirements;

- Issue the Contractor with a stop order should the Employer become aware of any unsafe working procedure or condition or any non-compliance with any provision of the SHEQ Requirements.

- The Contractor immediately reports any disabling injury as well as any threat to health or safety of which it becomes aware at the Works or on the Site to the Employer’s Representative.

- The Contractor undertakes not to do, or not to allow anything to be done which will contravene any of the provisions of the Act, Regulations or Safety and Operating Procedures.

- The Contractor appoints a person, qualified in accordance with the SHEQ Requirements, as the liaison with the Eskom Safety Officer for all matters related to health and safety, this person shall be contactable 24 hours a day.

- The Contractor confirms that it has been provided with sufficient written information regarding the health and safety arrangements and procedures applicable to the Works to ensure compliance by it and all employees, agents, Sub-Contractors or mandataries with the SHEQ Requirements while providing the Works in terms of this contract. As such, the Contractor confirms that this contract and the relevant Eskom Regulations referred to in this contract constitute written arrangements and procedures between the Contractor and the Employer regarding health and safety for the purposes of section 37(2) of the OHSA.

- The Contractor agrees that the Employer is relieved of any and all of its responsibilities and liabilities in terms of Section 37(1) of OHSA in respect of any acts or omissions of the Contractor, and the Contractor’s employees, agents or Sub-Contractors, to the extent permitted by the OHSA.

- The Contractor hereby indemnifies the Employer and holds the Employer harmless in respect of any and all loss, costs, claims, demands, liabilities, damage, penalties or expense that may be made against the Employer and/or suffered or incurred by the Employer(as the case may be) as a result of, any failure of the Contractor, its employees, agents, Sub-Contractors and/or mandataries to comply with their obligations in terms of clause 16, and/or the failure of the Employer to procure the compliance by the Contractor , its employees, agents, Sub-Contractors and/or mandataries with their responsibilities and/or obligations in terms of or arising from the OHSA.

- In carrying out his obligation as the mandatory to the Employer for this contract in terms of the National Environmental Management Act No.107 of 1998, the Contractor ensures that he complies with the Act when Providing the Services or using plant, materials or equipment.

- The following hierarchy of controls has to be observed on any activity that is above ground level:

- When considering work at height, a risk assessment must be conducted, form part of the health and safety plan to be applied on site and must include:

- The identification of the risks and hazards to which persons may be exposed to.

- An analysis and evaluation of the risks and hazards identified based on a documented method.

- A documented plan and applicable safe work procedures to mitigate, reduce or control the risks and hazards that have been identified.

- Have a monitoring and a review plan in place.

- When working at height, risk assessments shall take into account factors such as, the necessity for the work to be done in an elevated position as opposed to on the ground and precaution measures to be taken to mitigate incidents.

- Any lesson occurred from working at heights must be reported and shared among the team.

  - Permit to Work System

- NO work shall be carried out without a "PERMIT TO WORK"

- The Contractor’s Responsible Person must satisfy himself that all sources of possible danger are isolated. Details of the Permit to Work system can be found in the Plant Safety Regulations for Hendrina Power Station, Eskom. The Contractor must also make provision for sufficient Authorise Supervisor(s) depending on the contractual obligations. The Authorised Supervisor will need to undergo a week’s training, which will be arranged at a suitable Eskom facility. This person must also pass an exam to verify his understanding of the procedure, after which he/she will need to be interviewed by a panel to discuss the practical understanding of being appointed as an Authorised Supervisor.

- Plant with a prohibitive sign attached may only be operated by appointed Eskom personnel. Any Contractor employee found tampering with such plant will be permanently removed from Site.

  - Transportation of passengers: open LDV’s:

No Eskom employee or Contractor would be allowed to transport passengers on the back of open light delivery vehicles (LDV’s). It is a legal requirement to provide safe transportation of Eskom and Contractor employees – therefore the following will be enforced:

- All passengers must be transported in a closed vehicle with proper and adequate

Seating, fitted with safety belt for the number of passengers to be transported.

- Tools and equipment must be properly secured.

- Only authorised drivers may transport passengers.

- Proof must be submitted on request in terms of valid roadworthiness of all vehicles

- The above must apply to on site and off site transportation of passengers.

  - Eskom Life Saving Rules:

Life Saving Rules have been developed that will apply to all Eskom Employees, agents, consultants and Contractors.

- Rule 1: Open, Isolate, Test, Earth, Bond, and/or Insulate before touch - that is any plant operating above 1 000 V.

- Rule 2: Hook up at heights - no person may work at height where there is a risk of falling.

- Rule 3: Buckle up – no person may drive any vehicle on Eskom business and/or on Eskom premises: unless the driver and all passengers are wearing seat belts.

- Rule 4: Be sober (no person is allowed to work under the influence of drugs and alcohol.

- Rule 5: Use a permit to work – where an authorization limitation exists, no person shall work without the required permit to work.

  - Local Safety Procedures

The Contractor adheres to all local procedures. A list of local procedures is available on request from the Employer.

  - Incidents / Accidents

- Incidents and accidents must be reported and investigated as detailed in OHS Incident Management Procedure 32-95. All incidents must also be reported to the Employer within 24 hours.

- First aid must be made available either by the Contractor or use can be made of the Hendrina medical centre. The availability of the Contractor’s own first aid does not relieve the Contractor of his obligation to report and investigate the incident in accordance with Hendrina Procedure.

- The Employer will accompany the Contractor to hospital in the case of serious injury.

  - Fire Prevention

- Fire prevention and protection requirements to which Contractors must comply are detailed in HSPHO/059 Emergency Response Procedure

  - Protective Equipment and Clothing

- The Contractor supplies his own personal protective equipment necessary to carry out the Works and the Contractor shall ensure that all overalls for his staff have clearly identifying company LOGO's

- The Contractor is also responsible to inspect and maintain such equipment as required in terms of the OHS Act and local procedures.

  - Inspection of Equipment

- The Contractor’s equipment is inspected by an authorised Eskom employee on arrival at the site.

- The following documentation is required to accompany the equipment where applicable: copies of all test certificates and maintenance records.

- Lifting equipment and electrical equipment must be marked with a unique number, code or colour code for identification. If the equipment is found to be in an unsatisfactory condition or if insufficient maintenance has been carried out on the equipment then it will not be approved for use on Site. A list of all lifting equipment and electrical equipment must be submitted to the Employer at least 2 days prior to the occupation date. This list must indicate the unique number and description of the equipment.

- Training requirements must comply with the Works Information and statutory requirements.

  - Environmental Policy and Waste Handling

The Contractor shall submit an Environmental Management Plan (EMP) to be reviewed and approved by Eskom environmental officer, one week before the commencement of Works if required as per the Works Information.

  - Disposal of Waste

Waste shall be removed promptly to the designated disposal area as per below requirements:

- Domestic waste to the bins marked Domestic waste

- No stockpiling will be permitted

- Production waste in the marked bins

- Paper in its recycling bin

- Contact the Project Manager for the disposal of building rubble

Scrap metal, Wood & Rubber, Redundant Valves, Pipes, and Equipment etc. to be placed in the marked bins scrap bins.

  - Hazardous Waste Disposal and Handling

- Any new hazardous waste that comes to the temporary hazardous waste site must be accompanied by an SDS; all other hazardous waste can be delivered without the SDS.

- An inventory is signed by the person who delivers the hazardous waste and the waste coordinator must acknowledge the receipt of the waste.

- A 210Ɩ drum with lid will be issued to the person who has delivered the waste after the inventory is signed.

- Drums with incorrect colour coding or drums without lids will not be accepted at the temporary hazardous waste site.

## Additional Information

Contractors are accountable for taking all the necessary steps to protect all persons (including employees, visitors, and the general public), to protect the environment and property against any harm during the course of performing work or services in relation to their contractual obligations. In addition, all work procedures and equipment will be carried out in accordance with Eskom and legislative requirements.

Eskom’s contractors have the fundamental accountability and responsibility for executing on-site safety, health, and environment issues for their activities, services, products, and work. Each Contractor is responsible for ensuring that its employees and the employees of any appointed contractors comply with all occupational safety, health, and environmental (SHE) statutory requirements and the policies and procedures of Eskom Holdings SOC Limited.

This procedure is supplementary to the requirements of relevant legislation and the conditions of the contract.

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.