## Guideline
GUIDELINE FOR COMPLETING THE BASELINE RISK ASSESSMENT TEMPLATE
Notes: | 1. To be able to complete a baseline risk assessments you need to attend Hazard Identification and Risk assessment training(HIRA).
2. All affected stakeholders should be involved in the development of a baseline risk assessment i.e. Project mangers, SHE department(including Occupational Hygienist and/or Occupational health practitioners), Engineering, etc.
3. The OHS risk assessment procedure 32-520 should be used as a reference when completing this asse3ssment.
4. This document should be reviewed as per the requirements of the 32-520 procedure.
1. List activity |  | Here you have to list different types of activities that will be performed and consider the site or environment the activity will take place. The activity can have different hazards and tasks linked to it.
Hazard number |  | This is a number that has to be given to the hazards associated to the activity. Each activity can have various hazards attached to it and therefore need to be numbered 1,2,3 etc. See example below
Hazard Identification |  | A hazard is anything that is likely to lead to an event that will have an adverse impact on achieving an objective. A hazard can pose more than one risk. Hazards are generally tangible and can be seen, heard, felt, measured, smelt, or determined through the use of one’s senses. Hazards can be classified into the following categories: Physical e.g. heat, cold, vibration Chemical e.g. poisons, vapours, acid Biological e.g. bacteria, parasites, blood Mechanical/electrical e.g. working from heights or plant and equipment Ergonomic e.g. posture, weight, or repetition Psychological e.g. stress, repetitive work.
Risk Nr |  | This is a number given to a risk that a hazard pose. One hazard can have more than one risks. The numbering of the risks should be linked to the hazard i.e. if the hazard was 1 then the risks should be numbered 1.1, 1.2 etc. See example below
Associated risk (Risk identification) |  | List the risks associated with the hazard and list them according to the example above.
Risk type |  | This is the risk type which could be Safety or Health. Safety when the consequence of the risk has effect on the physical body of the person e.g. cut and health when the effects are on the persons health e.g. coughing
Exposed group/employees |  | The exposed group represents people who are exposed to the risk either employees, visitors or members of the public. Also in terms of Occupational Hygiene it means exposure groups such as individual exposure or homogenous exposure group.
Exposure patterns |  | Exposure patterns means the frequency and duration the person/group is exposed to the hazard e.g. Exposed to noise for 3 hours daily. This will help to determine the extent of exposure and the kind of harm that the hazard can inflict to the person/group.
Cause(s) of the risk |  | List what causes the risk to come into effect.
Risk Owner |  | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness.
Conditions(Normal/Abnormal) |  | In this section you have to say if it routine and non-routine activity as required by OHSAS 18001. Routine activities are activities that are performed regularily and non-routine are those that occur due to unplanned circumstance e.g. a risk assessment for an emergency situation or work that is not part of planned activities.
What are the Consequences? |  | List the consequence that the exposure to risk pose.
Existing Controls |  | These are existing controls for the risks and hazards identified.
Consequence |  | Utilise the consequence criteria tab to determine the impact the risk has or may have.
Likelihood |  | Utilise the likelihood tab to determine the impact the risk has or may have.
Risk Priority Rating |  | The risk priority is determined by plotting the consequence rating and likelihood rating on the risk matrix to determine the priority rating. E.g. if the Consequence is 1 and likelihood is 3 then the risk rating is III
RCE Risk Control Effectiveness |  | This is to determine how effect are your current or existing controls.
Additional Controls or Tasks Aimed at improving Existing Controls |  | If the existing controls were not effective include additional controls that can minimise the impact of the risk. These are additional controls that should be added to manage the risk. The hierarchy of controls shall be considered.
Consequence |  | This is to determine the consequences the risk pose. The consequence shall be determined using consequence rating tab.
Likelihood |  | This is to determine the likelihood of the risk producing effects. The likelihood shall be determined using likelihood rating tab.
Risk Priority Rating |  | The risk priority is determined by plotting the consequence rating and likelihood rating on the risk matrix to determine the priority rating. E.g. if the Consequence is 1 and likelihood is 3 then the risk rating is III
Monitoring Mechanisms |  | This is a measurement that is used to determine the success of controls in reducing the impact of the risk.
Control Owner |  | Person allocated the responsibility for implementing the agreed controls.
Legal and Other Requirements |  | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control.
Initial Target Date |  | These are the dates for the implementation of the controls
Revised Target Date |  | These are the dates for the implementation of the controls. Used if, for any reason, a Target Date is revised. Use the Comments field to explain.
Current Status |  | This means the current status on the implementation of the controls
Verification (i.e. Confirmation that the objectives have been met) |  | This means any type of verification or assessment done to check if objectives of the controls and assessment are met.
Comments |  | Any comments that you wish to input as part of the Risk assessment.

## Risk template
#DIV/0!
Occupational Health and Safety Baseline risk assessment template
Project/Dept: | [16 empty] | Next Review Date: |  |  |  |  | Unique identifier | 240-70044602
Date: | [8 empty] | Prepared by: | [12 empty] | Revision: | 0
[22 empty] | Revision date: | 2019-04-01
Refer to Occupational Health and Safety Risk assessment procedure 32-520
1: List activity | 2: Hazard identification |  | 3: Risk identification | [7 empty] | 4: Assess & Analyse Risks | [6 empty] | 4: Evaluate Risk | [5 empty] | 5: Reduce & Eliminate Risk
List activity | Hazard nr | Hazard Identification | Risk Nr | Associated risk (Risk identifation) | Risk type | Exposed group/employees | Exposure patterns | Cause(s) of the risk | Risk Owner | Conditions(Normal/Abnormal) | What are the Consequences? | Existing Controls | First determine Consequence and then the Likelihood of that Consequence. |  |  | Risk Priority Rating |  | Additional Controls or Tasks Aimed at improving Existing Controls | First determine Consequence and then the Likelihood of that Consequence. |  |  | Risk Priority Rating | Monitoring Mechanisms | Control Owner | Legal and Other Requirements | Initial Target Date | Revised Target Date | Current Status | Independent Verification (i.e. Confirmation that the objectives have been met) |  | Comments
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | # | A hazard is anything that is likely to lead to an event that will have an adverse impact on achieving an objective. A hazard can pose more than one risk. | # | A physical event occurs or could occur in relation to the hazard | Safety or health | Who is exposed to the hazard i.e. Employees, visitors, members of the public, etc. | The frequency and duration the person/group is exposed to the hazard e.g. Daily for 3 hrs. | What causes the risk to come into effect? | Who is accountable for making sure the controls and monitors are: - in place, - implemented, - regularly reviewed for effectiveness. | Indicate Yes or No. These short-term changes to conditions that could not be reasonably anticipated e.g. Emergencies | What is the expected adverse impact on the objective? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) | Consequence | Consequence | Likelihood |  | RCE Risk Control Effectiveness | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) | Consequence | Consequence | Likelihood |  | How we know if we are succeeding. Include comments on effectiveness. This may include i.e. measurements, inspections, supervision where necessary. | Person allocated the responsibility for implementing the agreed controls | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control. | Once a date has been agreed to, this can not be changed | Used if, for any reason, a Target Date is revised. Use the Comments field to explain. | Pending, In Progress, Complete | Date Done: | By whom:

## Consequence rating
Consequence criteria
Consequence rating | Description
Health and Safety
1 | No injuries or health effects(near misses)
2 | First-aid treatment case, and temporary discomfort case
3 | Medical treatment case; occupational disease with reversible/non-permanent effect
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence
5 | Fatality or life threatening health effects
6 | Multiple fatalities

## Likelihood rating
Likelihood criteria
Score | Descriptor | Safety and Environment | Occupational Hygiene
|  |  | Exposure | Probability of exceeding OEL
A | Highly unlikely | § <5% probability | Rare(once a year) | No exposure (or exposure < 10% of OEL)
§ occurrence requires exceptional circumstances
§ exceptionally unlikely, even in the long-term future
§ only occurs as a “100-year event”
B | Unlikely | § >5% probability, or | Short periods of time, a few times per day / intermittent (once in 6, 3 or a month) | Low exposure (<50% of OEL)
§ may occur but not anticipated, or
§ could occur in “years to decades”
C | Possible | § >20% probability, or | Continuous for between 1 and 2 hours (often / weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure >/-OEL
§ may occur shortly but a distinct probability it will not, or
§ could occur within “months to year\s”
D | Likely | § >70% probability, or | Continuous for between 2 and 4 hours (frequent / daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ balance of probability it will occur, or
§ could occur within “weeks to months”
E | Unavoidable | § 99% probability, or | Continuous for 8 hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C
§ impact is occurring now, or
§ could occur within “days to weeks”

## Risk control effectiveness
RISK CONTROL EFFECTIVENESS GUIDE
RCE |  | Guide
Fully effective | F | Nothing more to be done except review and monitor the existing controls. Controls are well designed for the risk, are largely preventative and address the root causes and Management believes that they are effective and reliable at all times. Reactive controls only support preventative controls.
Partially effective | P | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or Management has doubts about operational effectiveness and reliability.
Ineffective | I | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently very effective. There may be an over-reliance on reactive controls. OR Some of the controls do not seem correctly designed in that they do not treat root causes, those that are correctly designed are operating effectively.
Totally ineffective | Ti | Significant control gaps. Either controls do not treat root causes or they do not operate at all effectively. Controls, if they exist are just reactive.
None | N | Virtually no credible control. Management has no confidence that any degree of control is being achieved due to poor control design and/or very limited operational effectiveness.

## Risk matrix
Risk matrix
| Consequences | 6 | III | II | I | I | I
|  | 5 | III | II | II | I | I
|  | 4 | IV | III | II | I | I
|  | 3 | IV | III | II | II | I
|  | 2 | IV | IV | III | II | II
|  | 1 | IV | IV | III | III | III
|  |  | 1 | 2 | 3 | 4 | 5
Likelihood
|  |  | Priority | Risk ranking | Action required
|  |  | I | Very high | Immediate action required
|  |  | II | High | Strong mandatory action required
|  |  | III | Medium | Action required, possibly at administrative level
|  |  | IV | Low | Minor or no action required
A1 | IV | A1 | IV |  | Yes | Safety | A | 1 | F | I
B1 | IV | B1 | IV |  | No | Health | B | 2 | P | II
C1 | IV | C1 | IV |  |  |  | C | 3 | I | III
D1 | IV | D1 | IV |  |  |  | D | 4 | Ti | IV
A2 | IV | A2 | IV |  |  |  | E | 5 | N
B2 | IV | B2 | IV |  |  |  | F | 6
E1 | III | E1 | III
F1 | III | F1 | III
C2 | III | C2 | III
D2 | III | D2 | III
A3 | III | A3 | III
B3 | III | B3 | III
A4 | III | A4 | III
A5 | III | A5 | III
E2 | II | E2 | II
F2 | II | F2 | II
E3 | II | E3 | II
D3 | II | D3 | II
C3 | II | C3 | II
C4 | II | C4 | II
B4 | II | B4 | II
B5 | II | B5 | II
F3 | I | F3 | I
D4 | I | D4 | I
E4 | I | E4 | I
F4 | I | F4 | I
C5 | I | C5 | I
D5 | I | D5 | I
E5 | I | E5 | I
F5 | I | F5 | I

## Risk matrix (2) (hidden)
Risk matrix | [6 empty] | A1 | IV | A1 | #N/A
Consequences | 6 | III | II | I | I | I | B1 | IV | B1 | #N/A
| 5 | III | II | II | I | I | A2 | IV | A2 | #N/A
| 4 | IV | III | II | I | I | B2 | IV | B2 | #N/A
| 3 | IV | III | II | II | I | A3 | IV | A3 | #N/A
| 2 | IV | IV | III | II | II | A4 | IV | A4 | #N/A
| 1 | IV | IV | III | III | III | C1 | III | C1 | #N/A
|  | 1 | 2 | 3 | 4 | 5 | D1 | III | D1 | #N/A
|  | Likelihood |  |  |  |  | E1 | III | E1 | #N/A
[7 empty] | C2 | III | C2 | #N/A
|  | Priority | Risk ranking | Action required |  |  | B3 | III | B3 | #N/A
|  | I | Very high | Immediate action required |  |  | A5 | III | A5 | #N/A
|  | II | High | Strong mandatory action required |  |  | A6 | III | A6 | #N/A
|  | III | Medium | Action required, possibly at administrative level |  |  | B4 | III | B4 | #N/A
|  | IV | Low | Minor or no action required |  |  | B6 | II | B6 | #N/A
[7 empty] | B5 | II | B5 | #N/A
[7 empty] | C5 | II | C5 | #N/A
[7 empty] | C4 | II | C4 | #N/A
[7 empty] | C3 | II | C3 | #N/A
[7 empty] | D3 | II | D3 | #N/A
[7 empty] | D2 | II | D2 | #N/A
[7 empty] | E2 | II | E2 | #N/A
[7 empty] | E3 | I | E3 | #N/A
[7 empty] | D4 | I | D4 | #N/A
[7 empty] | E4 | I | E4 | #N/A
[7 empty] | D5 | I | D5 | #N/A
[7 empty] | E5 | I | E5 | #N/A
[7 empty] | C6 | I | C6 | #N/A
[7 empty] | D6 | I | D6 | #N/A
[7 empty] | E6 | I | E6 | #N/A

## HIRA comments (hidden)
HAZZARD IDENTIFICATION & RISK ASSESSMENT (HIRA)
|  |  | DOC NO: | ETFM 1589 |  | REV NO: 4
Section: |  | ESKOM TELECOMMUNICATIONS |  |  | Date of last revision: | 2013-12-18
1: Identify Hazards | [7 empty] | 2: Analyse Risks |  | 3: Evaluate Risks | [5 empty] | 4: Treat Risks
Hazard No. | Area | Operation Activity | Routine/ Non Routine | Internal/ Outsourced | Sub- Activity | Hazard/Activity | Consequence | Risk | What causes the risk to come into effect? | Likelihood | Safety Consequence | Health Consequence | Max Cons | Likelihood + Consequence | Risk Rating | Include: - Preventative Controls (actions taken to eliminate hazards or reduce the likelihood of the hazard occurring), and - Reactive Controls (action taken to reduce the immediate impact of the hazard occurring) | Likelihood | Safety Consequence | Health Consequence | Max Cons | Likelihood + Consequence | Risk Rating | Risk Control Effectiveness | Person allocated the responsible for implementing the agreed controls | Where relevant, list the relevant legislative/municipal by-laws requirements that prescribe the control. (Reference to the ET Legal Register) | Where relevant, list the relevant Eskom and other Requirements that prescribes the control. | Applicable Section of Legislation | Additional Control Include: - Preventative Controls (actions taken to eliminate hazards or reduce the likelihood of the hazard occurring), and - Reactive Controls (action taken to reduce the immediate impact of the hazard occurring)
ET001 | Road | Maintenance | Routine | Internal | Travelling | Fatigue | Falling asleep while driving, Motor Vehicle accident, | Injury/Fatality | Travelling long distances without resting, partying for long hours and not getting enough rest, studying for long hours without getting any rest | D | 5 |  | 5 | D5 | I | Safety Awareness on fatigue Management, Availability of fatigue Management Procedure (ETTB 1517), Availability of travelling Procedure (ETPR 1541 in line with 32-93), MVA reports are analysed on a monthly basis to determine trends on excessive km travelled | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETTB 1517, ETPR1541, 32-93
ET002 | [5 empty] | Mechanical failures | Motor Vehicle accident | Injury/Fatality | Lack of road maintenance, adverse weather conditions, spillages, poor road construction | C | 4 |  | 4 | C4 | II | Vehicle planned maintenance,pre-trip inspection, driver evaluation | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR1541, 32-93
ET003 | [5 empty] | Wild/stray animals | Damaged Vehicle or motor vehicle accident | Injury/Fatality, damage to vehicle | Obscured view, Speeding, | C | 3 |  | 3 | C3 | II | Defensive driving, driver awareness, being vigilant, obeying traffic rules | C | 2 |  | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | 32-93, ETPR1541
ET004 | [5 empty] | Over speeding | Possible MVA, | Injury/Fatality | Intoxication, obscured view, Driver incompetence, ignorance | C | 4 |  | 4 | C4 | II | OBC installed in Pool Vehicles, driver awareness, disciplinary measures | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 54.1 and line 55.3, Line 55.4, 55.5 | NRTA, ETPR 1541 and 32-93, OHS Act
ET005 | [5 empty] | Poor planning | Possible MVA, | Injury/Fatality | Doing things in haste with no due consideration, long hours, not enough sleep, not enough eating | B | 4 |  | 4 | B4 | III | processes are in place to encourage proper planning such as specific Task risk assessment conducted daily and Tool box talks conducted on a weekly basis | A | 4 |  | 4 | A4 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR0364, ETFM1038, ETFM0594
ET006 | [5 empty] | Long Distance Travelling | fatigue and falling asleep while driving, leading to MVA | Injury/Fatality | driving long distances without taking rest periods as prescribed | D | 4 |  | 4 | D4 | I | Safety Awareness on fatigue Management, Availability of fatigue Management Procedure (ETTB 1517), Availability of travelling Procedure (ETPR 1541 in line with 32-93), MVA reports are analysed on a monthly basis to determine trends on excessive km travelled | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETTB 1517, ETPR1541, 32-93, Communication Procedure
ET007 | [5 empty] | Hijacking | Possible assault, rape, stress, trauma, being shot | Injury, fatality | Crime, driving alone, Lack of security at site, working at night | D | 3 |  | 3 | D3 | II | Risk Assessment done for every task, Training on advanced and Defensive driving, Awareness on Hijacking, | C | 2 |  | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR0364, 32-93
ET008 | [5 empty] | Poor Road conditions | Possible MVA, | Injury, damage to vehicle | stones, unclear signs, ignorance, narrow roads, Invisible road markings | E | 4 |  | 4 | E4 | I | Awareness on safe driving, training on advance driving, 4x4 training for specific employees | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR1541 and 32-93,
ET009 | [5 empty] | 4X4 Terrain | Possible MVA, | Injury/ Fatality | Lack of training, Fatigue, Wrong type of vehicle | B | 3 |  | 3 | B3 | III | 4x4 training by employees using 4x4, driver awareness, availability of suitable type of vehicle, permit issued on 4x4 driving | A | 2 |  | 2 | A2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR0364 and 32-93
ET010 | [5 empty] | Adverse weather conditions | Possible MVA, | Injury, Fatality | Poor Visibility, non adherence to safe working procedures, Speeding, reckless driving | C | 4 |  | 4 | C4 | II | Procedures prohibiting work in bad weather condition(travelling Procedure 32-93), Awareness on travelling during bad weather conditions, training on advance driving, 4x4 training | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Procedure 32-93, ET Communication Plan
ET011 | [5 empty] | Gravel Road | Possible MVA, | Injury, Fatality | Lack of driving experience, fatigue, condition of the road, Speeding | C | 4 |  | 4 | C4 | II | Advanced driver training, driver awareness, availability of a gravel road Practice note(ETPN1249) used to manage driving, Incident Monitoring | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Procedure 32-93, ET Fleet Policy, ETPN1249
ET012 | [5 empty] | Pedestrians, | Damage to the vehicle and Possible MVA, | Injury, Fatality | Intoxication, road markings, designated road usage by public, lack of knowledge, ignorance by the driver, Speeding | C | 3 |  | 3 | C3 | II | Defensive driving, safe driver awareness, Awareness on safe driving(Put headlights on, limit night time driving), Incident monitoring | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 54.18 | Procedure 32-93, ET Fleet Policy
ET013 | [5 empty] | Other road users | possible motor vehicle pile-up | Injury, Fatality | Fatigue, medication, inexperience, intoxication, bad driving behaviour | D | 3 |  | 3 | D3 | II | Continuous risk assessment, Safe Driver awareness(Road rage, avoiding reckless drivers, Giving way irrespective of being right) | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | line 32.3, Line 54.22 | Procedure 32-93, ET Fleet Policy,
ET014 | [5 empty] | Unsafe driving | Possible MVA, | Injury, Fatality | Use of a cell phone while driving, Fatigue, eating while driving, Using medication which alters your concentration, inexperience, ignorance, intoxication, reckless driving | D | 3 |  | 3 | D3 | II | Awareness raised on dangers of using means of communication while driving, Pool Vehicle Management through Introduction of OBC's, driver training & awareness, apply disciplinary measures for any transgressions to OBC | C | 2 |  | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 54,14 | Procedure 32-93, ET Fleet Policy, OHSAS 18001
ET015 | [5 empty] | Night driving | Possible hijacking and MVA | Injury, Fatality | Bad planning, lack of driving experience, lack of visibility, night blindness. | D | 3 |  | 3 | D3 | II | Better planning, Awareness through ETPN1249, Risk assessment, buddy system. | C | 2 |  | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | National Road Traffic Act, ETDR0389 Road Safety Directive; Procedure 32-94
ET016 | [5 empty] | Unroadworthy vehicle | Vehicle breakdown and Possible MVA | Injury, Fatality, Property Damage | Ignorance, poor vehicle maintenance. | D | 3 |  | 3 | D3 | II | Pre-trip inspection, vehicle service | B | 3 |  | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 54.10 | National Road Traffic Act, ETDR0389 Road Safety Directive; Procedure 32-95
ET017 | [5 empty] | Road Works | Possible MVA, | Injury, Fatality | Obstruction on the road, unclear signs, ignorance, narrow roads, poorly visible road markings | C | 4 |  | 4 | C4 | II | Training Defensive driving, Safe driver awareness(obeying traffic rules, Report road works in toolbox talk) | B | 3 | 3 | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | line 32.3, Line 54.19 | Procedure 32-93
ET018 | [5 empty] | Sand dunes | Possible MVA, or Damage to vehicle | Injury, Fatality | Bad planning, lack of driving experience | B | 3 |  | 3 | B3 | III | Training & awareness, driver training, risk assessment | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETDR0389 Road Safety Directive; Procedure 32-100
ET019 | Radio Site, Substation |  |  | Internal/ External | Working at heights | Adverse weather conditions | Possible Slipping and falling due to heavy winds or wet Tower | minor and major injury, fatality | Bad weather condition, not following safe working procedure | C | 3 |  | 3 | C3 | II | Procedure availability for working at heights, Awareness raised on the procedure, Behavioural Safety Observation conducted to monitor unsafe acts such as climbing a Tower when the weather is not conducive, | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 46.6 | (6), ETPR0647, ETPR0641
ET020 | [5 empty] | Actions and conditions leading to Slip and fall | Possible slipping and falling | Minor and major injury, fatality | Not wearing proper PPE, complacency, wet surfaces, lack of concentration, Height Phobia, wet surface, over-reaching, poor house-keeping, Psychological unfitness | C | 3 |  | 3 | C3 | II | Correct use of proper PPE, Availability of a fall protection plan, plan implemented, Periodic psychological fitness done on relevant employees, Monthly monitoring of statistics. | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | line 46.6, line 46.7, Line 34.2 | ETPR0647, ETPR0647, ETPL1233
ET021 | [5 empty] | Incorrect use of PPE | Possible falling due to not hooking up | Minor and major injury, fatality | PPE not comfortable, ignorance, lack of awareness, correct PPE not available | C | 4 |  | 4 | C4 | II | PPE issued to all employees, Awareness on use of PPE, PPE inspected on a monthly basis | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 34.2 | ETFM1129, ETFM1564
ET022 | [5 empty] | Inadequate training | Possible falling due to incompetence | Minor and major injury, fatality | Training need analysis not in place, no training plan in place, Poor training management, No IDP's in place | E | 4 | 4 | 4 | E4 | I | Training analysis done and included in the IDP's, SHEQ Training and awareness procedure in place, Training matrices in place and implemented, Fall arrest training included as an accreditation which assist with ensuring that competence is monitored | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.7 | OHSAS 18001, ETPR0369, ETPR0607, Workplace accreditations
ET023 | [5 empty] | Medically and psychological unfitness | possible falling from jumping (Wanting to commit suicide) | Minor and major injury, fatality | Not being physically and mentally fit, No man-job-specifications, | C | 4 |  | 4 | C4 | II | Medical(Physical and psychological) surveillance in place, Man-job-specifications done, Medical fitness included as part of the accreditations | A | 4 | 4 | 4 | A4 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 46.7 | ETGL 1277, Medical Surveillance, Fall protection Plan (ETPL1233)
ET024 | [5 empty] | Poorly maintained Ladders | Possible falling | minor and major injury, fatality | Improper use of ladders, Ladders not well maintained, | C | 4 |  | 4 | C4 | II | Procedure on ladder management is in place, monthly inspection of ladder are conducted, | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 34.10 | ETPR1119, ETFM 1032
ET025 | [5 empty] | Exposure to Electromagnetic Radiation | Possible radiation poisoning | Occupational Disease | working in the close proximity of an operating microwave dish | A | 2 | 2 | 2 | A2 | IV | Monitoring of radiation has been done, for any work to be done on the dish, there power is switched off | A | 1 | 1 | 1 | A1 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETRE1331
ET026 | [5 empty] | Structural failure | Possible Falling or being hit by collapsed structure and flying objects | injury, fatality, property damage | Structural Analysis not conducted, Poor maintenance of structure, overloading, Not conducting visual inspections, not reporting visible defects | D | 4 |  | 4 | D4 | I | Structural Analysis conducted, Action plans developed to implement recommendations, Periodic audits conducted for structure maintenance, | D | 2 |  | 2 | D2 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.8 | ETSP0158, ETSP0383, ETSP0422
ET027 | [5 empty] | Incorrect Climbing | Possible falling | injury, fatality, property damage | Not hooking up when ascending the structure, Not competent in tower climbing, lack of concentration and experience, improper construction, No following Safe working Procedures, taking shortcuts | D | 4 |  | 4 | D4 | I | Training attended on tower climbing and rescue, approved full safety harnesses issued as part of PPE, PPE Inspections done on a Monthly basis, working at heights procedure available and implemented, Continuous awareness raised, behavioural Safety Observations conducted on a continuous basis. Monthly reports analysed | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3. line 34.9, Line 46.11, line 46.7 | ETPR0647, ETPL1233
ET028 | [5 empty] | Structure overloading | Possible collapse of the structure | injury, fatality, property damage | Installing too many equipment not according to weight limitations, not implementing recommendations from structural analysis results | D | 4 |  | 4 | D4 | I | Structural analysis done and recommendations implemented. Pre Engineering and Design done | C | 4 | 4 | 4 | C4 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 46.8 | ETSP0158, ETSP0383, ETSP0422
ET029 | [5 empty] | Incorrect Equipment hauling | Possible falling of equipment or person hauling or both | Injury, Fatality | not following the correct procedure, not competent in hauling of equipment, Taking shortcuts, exceeding safety tolerances of hauling equipment. | C | 3 | 3 | 3 | C3 | II | Safe hauling procedure in place. Training available for personnel doing hauling, Hauling equipment inspections | C | 2 | 2 | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Safe Hauling Procedure (ETPR0745), Inspection and maintenance of Hauling kit (ETFM1041)
ET030 | [5 empty] | Ergonomics | Possible body strain and twisting | Injury | Not following safe working procedure, Bad posture, repetitive movements | C | 3 | 3 | 3 | C3 | II | Awareness raised on ergonomics, Continuous risk assessment conducted for specific task | C | 2 | 2 | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Manual Handling Guideline (ETGL0611)
ET031 | [5 empty] | Falling/moving objects | Struck by a free falling object | Injury, Fatality | incorrect use of PPE (Hard hat), ignorance, lack of training, lack of supervision, improper demarcation | C | 3 | 3 | 3 | C3 | II | Specific Task Risk Assessment conducted for specific work, Chin strap hard hat issued to relevant employees who gains access to site, awareness raised on the use of hard hats when under the Tower | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, | Tower construction Specification ETSP0386
ET032 | Radio Site & Substation access road and surroundings |  |  | Internal/ External | Site access and security | Unauthorised persons on site | Theft, vandalism, public injury through slipping or falling if access to the tower is gained | property damage or theft | lack of security | E | 5 |  | 5 | E5 | I | Site security Matrix, Security project in progress to improve site security based on the rating of the matrix per site | C | 1 | 1 | 1 | C1 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Site access procedure, Incident Management Procedure ETPR0736
ET033 | [5 empty] | Actions and Conditions leading to Hijacking, kidnapping, robbery, assault, rape | Possible assault, rape, stress, trauma, being shot | Injury, Fatality | Lack of Security, driving alone, Crime | C | 5 |  | 5 | C5 | II | Site security Matrix, Security project in progress to improve site security based on the rating of the matrix per site | B | 4 | 4 | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Site access procedure (ETPR 0578), Incident Management Procedure ETPR0737
ET034 | [5 empty] | Poor Road Conditions | Possible MVA | Injury, damage to vehicle | Lack of road maintenance, adverse weather conditions, Fuel spillages, poor road construction, Incompetence | B | 3 | 3 | 3 | B3 | III | Advanced driver training, 4x4 Training, Safe driver awareness | B | 3 | 3 | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | line 32.3 | Risk Assessment Procedure, ETPR0364 and 32-93
ET035 | [5 empty] | Raptors/Insects/Reptiles | Possible venomous bites and stings | minor and major injury, fatality | Location of the site, Poor site maintenance, seasonal dangers | C | 3 | 3 | 3 | C3 | II | Awareness, snake bite protection, risk assessment, continuous awareness | B | 4 | 4 | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency Plan in case of bees, wasps and tick stings (ETPN1730)
ET036 | [5 empty] | Actions and conditions leading to Veld Fire | Possible burns | injury, fatality, property damage | Lighting, strong winds, equipment failure, electric short circuit | B | 3 | 3 | 3 | B3 | III | Protection system, restrict access, emergency preparedness procedure, awareness, Site maintenance & emergency preparedness drills | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency Preparedness Procedure ETPR 363
ET037 | [5 empty] | Actions and conditions leading to Vandalism | Theft, vandalism, public injury | property damage/loss / Minor or major injury | Location of the site, vulnerability, Lack of Security | E | 5 |  | 5 | E5 | I | Secure site in accordance to site security matrix. | C | 4 | 4 | 4 | C4 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, | Site access Procedure (ETPR0578), Incident Management Procedure ETPR0737
ET038 | Radio site yard |  |  | Internal | Site maintenance | Improper use of PPE | Body exposed to hazards at site | injury, | PPE not comfortable, ignorance, lack of awareness, Negligence | C | 2 | 2 | 2 | C2 | III | Awareness, pre-task risk assessment, SMAT observation, correct PPE issued | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 34.2 | ETFM1129, ETFM1564
ET039 | [5 empty] | Exposure to chemical substances | Possible Skin contact and inhalation of HCS | Occupational Disease (Damage to the lungs or skin irritation) | Not using correct PPE, not following manufacturer specification | C |  | 2 | 2 | C2 | III | Herbicide procedure in place and implemented, Awareness given on safe use of herbicides, correct PPE issued, Chemical inventory in place, MSDS's in place | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 41.9, line 41.10, line 41.11 | ETPR0730, ETFM1039, ETTB1520
ET040 | [5 empty] | Raptors/Insects/Reptiles | Possible exposure to venomous bites and stings | minor and major injury, fatality | Seasonal Dangers, inadequate risk assessment, | C | 4 | 4 | 4 | C4 | II | Portable first aid kits with minimum content issued to all employees accessing the site, Risk assessment conducted, Availability of bite and sting kit, Level 2 first training attended, continuous awareness, Issue/use PPE | B | 3 | 3 | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency Plan in case of bees, wasps and tick stings (ETPN1730)
ET041 |  |  |  | External | Installation of an Electric Fence | Exposure to Electrocution or Electric shock | Electrocution or Electric Shock | Minor, Major Injury, Fatality | Touching the electric fencing, trying to damage the fence | C | 4 | 4 | 4 | C4 | II | Warning signage's available on the fence, | B | 3 | 3 | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 5.1, Line 5.2 and Line 5.3 | Specification for security Fences at Radio Sites (ETSP0426)
ET042 | Equipment Room |  |  |  | Working in a building made with Asbestos/ with Asbestos Roofing | Possible exposure to Asbestos fibres | Inhalation of asbestos fibre | Occupational Disease (Asbestosis) | No inspections done on the roof condition, roof not well maintained, no monitoring system in place ensure that the limits are not above | C | 4 | 4 | 4 | C4 | II | Asbestos inventory list in place, contract underway for the identification of buildings/ containers with asbestos. | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 48.10 | ETFM1256
ET043 |  |  |  | Internal/ External | Use of instruments and equipment | Incorrect lifting and Loading | Body strain and muscle pull | Injury, Damage to property | Improper position, incorrect manual handling, Incorrect lifting techniques, lack awareness, ergonomics, lack of SOP's, Lack of proper lifting equipment | C | 3 | 3 | 3 | C3 | II | Availability of a Manual Handling guideline Awareness, Training and awareness, equipment casing allocated in pool vehicles | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Manual Handling Procedure ETGL0611
ET044 | [5 empty] | Ergonomics | Body strain and muscle pull | injury, fatality, | Poor designs, lack of awareness, assuming bad postures when lifting | B | 3 | 3 | 3 | B3 | III | Risk assessment, awareness, inspections | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Manual Handling Procedure ETGL0611
ET045 | [5 empty] | Incompetence in the use of equipment | Possible Pricks, Stabbing, and punctures | injury, Damage to property | Awareness not raised on proper lifting techniques, guideline not followed, taking shortcuts | B | 3 | 3 | 3 | B3 | III | IDP'S, Training procedure, skills management training, Skills matrix | A | 2 | 2 | 2 | A2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | OHSAS 18001, Equipment installation procedures
ET046 | [5 empty] | Faulty equipment | Possible electrical Shock | Damage to property, loss of income | Poor maintenance, no calibration, no inspection, poor quality of equipment | D | 4 |  | 4 | D4 | I | Procedure on calibration of equipment in place, Planned maintenance scheduled, calibration of equipment done, equipment register in place to monitor calibration | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR0719, ETFM 1196
ET047 | Substation site |  |  | Internal/ External | HV environment | Actions and Conditions leading to Electrocution | Possible Electrocution | minor and major injury, fatality | Not following Operating Regulation for High Voltage System (ORHVS), Non Adherence to Life Saving Rule (Permit to work) | C | 4 |  | 4 | C4 | II | Monitoring of life saving rules in place, process of work permit followed, ORHVS training listed as accreditations | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Life Saving Rules, ORHVS
ET048 | [5 empty] | Actions and Conditions leading to Explosion | Possible explosion | damage to property, Injury, fatality | Equipment failure, not following SOP's, electric short | C | 4 |  | 4 | C4 | II | Protection system, restrict access, emergency preparedness procedure, contingency plan, awareness | C | 4 | 4 | 4 | C4 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | OHSA, Environmental regulation (9), ETPR1149
ET049 | [5 empty] | Actions and Conditions leading to Fire | Possible burns | damage to property, Injury, fatality | Equipment failure, not following SOP's, electric short circuit | C | 4 |  | 4 | C4 | II | Protection system, restrict access, emergency preparedness procedure, contingency plan, awareness | C | 4 | 4 | 4 | C4 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.8, Line 40.6 | OHSA, Environmental regulation (9), ETPR1150
ET050 | [5 empty] | Actions and Conditions leading to Veld fires | Possible burns of individuals or building | damage to property, Injury, fatality | Smoking, Braaing, poor yard maintenance, No fire breaks, extremely hot weather | C | 4 |  | 4 | C4 | II | Vegetation management, Emergency preparedness procedure, signage's | A | 4 | 4 | 4 | A4 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.8, Line 40.6 | OHSA, Environmental Regulation (9)
ET051 | Battery Room |  |  | Internal/ External | DC environment | Exposure to Battery Acid | Possible skin contact with acid | Acid burns | incorrect handling of batteries, overfilling, overcharging, faulty test equipment | B | 3 |  | 3 | B3 | III | Battery handling procedure in place, emergency preparedness procedure, Procedure for accidental spills outlined in the procedure | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 41.8, 41.9 | Battery maintenance (ETPR0800)
ET052 | [5 empty] | Improper use of PPE | Part of the body may be exposed to injury from batteries falling or contact with acid | injury, fatality, | PPE not comfortable, ignorance, lack of awareness | B | 4 |  | 4 | B4 | III | Correct PPE issued to relevant employees, Awareness raised on the correct use, Periodic Safety Observations conducted to monitor the use thereof, | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 41.10 | ETTB1696, ETFM1129, ETFM1564
ET053 | [5 empty] | Incompetence in battery maintenance | accidental falling of batteries or acid spilling | injury, Acid burns / fatality | Lack of resources, Poor management, No IDP's in place | B | 3 |  | 3 | B3 | III | training provided on handling of Hazardous Substances, Training provided on battery maintenance, awareness procedure in place | A | 2 | 2 | 2 | A2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | line 32.3, Line 41.2 | ETPR0800
ET054 | [5 empty] | Conditions leading to Possible Explosion | Possible Explosion from short circuiting | injury, fatality, environmental damage, damage to property, | Poor battery maintenance with poor connection, electric short circuit | C | 3 |  | 3 | C3 | II | Planned battery maintenance schedule in place and implemented, alarm systems that signals if any fault detected, awareness, emergency preparedness procedure in place | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, line 41.9, line 41.10, line 41.11 | ETPR0800, ETFM1203
ET055 | [5 empty] | Exposure to Fumes | Inhalation of HCS fumes | Occupational Disease (Damage to the lungs) | Not wearing correct PPE(Respirator), prolonged exposure, poor ventilation, not following correct safe working procedure | C | 3 | 3 | 3 | C3 | II | ventilation (air vents and extraction fans), alarm systems, maintenance of chargers | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 41.5 | ETPR0800, ETTB1674
ET056 | Equipment and Battery room |  |  | External | AC environment | Conditions leading to Electrocution | Electrocution | injury, fatality | contact with AC through earth mats and charger connections, not following safe working procedure, no isolation, lack of training, lack of knowledge and supervision, improper guarding/barricading, lack of SOP's | D | 4 | 4 | 4 | D4 | I | contractor management in relation to SHEQ specification and plan evaluation in relation to competence through education in electrical connections, training on charger installations and other electrical connections, spefication availability, Eskom Life Saving Rules in place and monitored | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Eskom Life Saving Rules(32-421)
ET057 | [5 empty] | Incompetence in handling AC | Possible electrocution or shock | injury, fatality, environmental damage, damage to property, | Training needs not analysed, Training matrix not in place, Training not managed, | D | 4 |  | 4 | D4 | I | Training needs analysed and outlined in the specifications, Training matrix required, certificate of competence required from contractors. | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | OHSA, Construction regulation, Eskom Life Saving Rules(32-421)
ET058 | [5 empty] | Conditions leading to Fire | Possible fire | injury, fatality, environmental damage, damage to property, | Equipment failure, not following SOP's, electric short | D | 3 |  | 3 | D3 | II | Planned and breakdown maintenance in place, equipment upgrade, alarm systems detecting defects, emergency preparedness procedure in place and implemented | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.8, Line 40.6 | ETPR1149, Equipment maintenance procedure
ET059 | Radio and substation yard |  |  | External | Lifting and rigging | Incompetence in Rigging | Possible collapse of the structure | injury, fatality, | Training needs not analysed, Training matrix not in place, Training not managed, | D | 4 |  | 4 | D4 | I | Training needs analysed and outlined in the specifications, Training matrix required, certificate of competence required from contractors on Rigging, Fall protection plan pre- approved before work commences on site | B | 3 |  | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4 | ETPL1233, SHEQ Specification (ETSP1277)
ET060 | [5 empty] | Falling objects | Flying objects | injury, fatality, | incorrect use of PPE (Hard hat), ignorance, lack of training, lack of supervision, improper demarcation, Poor communication, lack of warning signs, Incompetence | C | 4 |  | 4 | C4 | II | contractor management in relation to SHEQ specification and plan evaluation in relation to competence through education in electrical connections, training on charger installations and other electrical connections, spefication availability, Eskom Life Saving Rules in place and monitored Risk assessment, PPE, Rigging & hauling training, awareness | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4 | Tower construction Specification ETSP0386, SHEQ Specification (ETSP1277)
ET061 | [5 empty] | Improper use of PPE | Possible falling | injury, fatality, | PPE not comfortable, ignorance, lack of awareness | C | 4 |  | 4 | C4 | II | Contractor Management, Awareness, specific Task Risk Assessment, Behavioural Safety Observation procedures in place and implemented | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.7, Line 34.2, Line 46.3, Line 46.4 | SHEQ Specification (ETSP1277)
ET062 | [5 empty] | Adverse weather | Poor visibility, slippery conditions, Possible trip and fall, possible collapse of the structure | Injury, fatality, damage to property | Rigging in bad weather conditions, Taking chances due to poor planning | C | 4 |  | 4 | C4 | II | Contractor Management, Awareness, specific Task Risk Assessment, Behavioural Safety Observation procedures in place and implemented | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, Line 46.6 | SHEQ Specification (ETSP1277)
ET063 | PowerStation manholes and tunnels |  |  | External | Confined spaces | Possible Exposure to low oxygen levels | Asphyxiation | Oxygen Deficiency | No sufficient oxygen for breathing within the tunnel | C | 4 |  | 4 | C4 | II | Presentation on working on confined spaces available and communicated, contractor Management, SHEQ specification issued to contractors, Permit to work implemented, Medical Surveillance | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.8 | SHEQ Specification (ETSP1277), Eskom Life Saving Rules
ET064 | [5 empty] | Possible Hydrogen Gas poisoning and self explosion | Shortness of breath | Occupational diseases, Injury, Fatality | Hydrogen gas emanating from stagnant water accumulating in the tunnel. Not following safe working procedures such as gas testing/ Not having correct PPE, | C | 4 |  | 4 | C4 | II | Presentation on working on confined spaces available and communicated, contractor Management, SHEQ specification issued to contractors, Medical Surveillance | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.9 | SHEQ Specification (ETSP1277), Man Job Specification
ET065 | [5 empty] | Claustrophobic condition | Fear of enclosed areas which leads to trauma and struggle in breathing | Injury, Fatality | Selection and placement not done correctly Wrong person for the job | D | 4 |  | 4 | D4 | I | Man-job-specs available which directs what tests to be done, risk assessment done on confined spaces which determines what controls to employ, Contractor Management. | B | 2 |  | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10 | SHEQ Specification (ETSP1277), Man Job Specification
ET066 | [5 empty] | Possible Exposure to Methane gas | Inhalation of obnoxious gases | Occupational Disease, Methane gas poisoning and self explosion | Methane Gas from stagnant water accumulating in the tunnel or coming from underground. Not following safe working procedures such as gas testing/ Not having correct PPE, | D | 3 |  | 3 | D3 | II | Man-job-specs available which directs what tests to be done, risk assessment done on confined spaces which determines what controls to employ, Contractor Management. | B | 4 | 4 | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.11 | SHEQ Specification (ETSP1277), Man Job Specification
ET067 | [5 empty] | Trip and fall hazard | Possible Bone Fractures | Tripping and falling, bodily injuries and fatalities | Not hooking when Ascending and descending the tunnel/ Manhole | C | 3 |  | 3 | C3 | II | A working at heights procedure (ETPR647) is in place and has been communicated. A fall protection plan is in place. Pre and post inspection of safety harnesses in place, Contractor Management. | A | 4 | 4 | 4 | A4 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.12 | SHEQ Specification (ETSP1277), Man Job Specification
ET068 | [5 empty] | Exposure to HV frequencies | Possible Electrocution | injury, fatality, Electrocution and Shock | Coming into contact with bare HV cables | D | 3 |  | 3 | D3 | II | ORHVS training and Authorization given to relevant personnel and renewed 3 yearly. Monitoring of adherence to cardinal rules, Contractor Management | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Eskom Life Saving Rules
ET069 | [5 empty] | Exposure to venomous bites and stings | Possible venomous bites and stings | Poisoning, Fatality | Working in an area which is prone to venomous reptiles | D | 2 |  | 2 | D2 | II | Awareness presentation on working on confined spaces in place and communicated. First aid training given to all person working on site, Contractor Management | C | 2 | 2 | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Practice note in case of bees, wasps and tick stings (ETPN1730)
ET070 | Equipment Room | Installation |  | Internal/ External | Equipment installation | Incompetence in the installation of equipment | Possible equipment damage | injury, property damage | Training needs not analysed, Training matrix not in place, Training not managed, | B | 3 |  | 3 | B3 | III | Training needs analysed and outlined in the specifications, Training matrix required, certificate of competence required from contractors on equipment installation, Training contract in place for equipment to be installed | B | 2 |  | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Technical Training procedure (39-86, ETPR0878), Equipment Installation procedure and guideline
ET071 | [5 empty] | Incorrect Hand Tools | Possible Pricks, Stabbing, and punctures | injury, property damage | use of incorrect hand tools, improvising | B | 3 |  | 3 | B3 | III | Toolbox issued to all technicians, Regular inspection of tools, Contractor Management | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Hand tools Procedure (ETPR0737) Tools inspection checklist (ETFM1556)
ET072 | [5 empty] | Improper planning | Improvising due to absence of proper tools | injury, property damage | Work pressure, time management, lack of experience | B | 3 |  | 3 | B3 | III | Existing processes allows for proper planning such as implemented Safety Management Systems including conducting Specific Task Risk Assessment before commencing with any activity, | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | OHSAS 18001, Risk Assessment Procedure and Form (ETPR0364 and ETFM1038)
ET073 | PowerStation, Radio and substation site | Cable handling |  | External | Trenching/ducting | Ergonomics | Body strain and muscle pull | minor and major injury | Bad Posture, Bending for Prolonged periods | C | 3 | 3 | 3 | C3 | II | Contractor Management, Availability of Manual Handling Guideline, SHEQ Specification issued, Hazard list issued to contractors to assist with the development of HIRA | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, 46,9 | ETGL0611
ET074 | [5 empty] | Exposure to Dust | Inhalation of particulate matter | Possible damage to the lungs | Exposure to dust for prolonged periods, Not wearing correct PPE(Dust Mask) | C | 2 | 2 | 2 | C2 | III | Contractor Management in ensuring that Correct PPE is issued for a specific activity, with regular monitoring to ensure that disposable masks are not reused | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Eskom Environmental management procedure
ET075 | [5 empty] | Defective Tools | Possible Pricks, Stabbing, and punctures | Injury, Fatality | Proper tools not issued, Improvising | B | 3 | 3 | 3 | B3 | III | Contractor Management to ensure that correct tools and equipment are issued and used | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Working with Power and Hand tools (ETPR0737)
ET076 | Fibre lines/ routes |  |  | Internal/ External | Splicing of Fibre | Incorrect Splicing | Possible pricking by fibre glass which may find its way into the blood stream | minor and major injury, fatality | Incompetence, Not following Safe working procedure on splicing | B | 4 |  | 4 | B4 | III | Contractor Management, Availability and implementation of Splicing procedure | B | 3 | 3 | 3 | B3 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR1029, SHEQ Specification
ET077 |  |  |  | Internal/External | Material handling | Incorrect Storage and Stacking | Equipment falling | injury, fatality, property damage | Incorrect stacking, No following SOP's, No supervision, no labelling of items | C | 4 |  | 4 | C4 | II | Contractor Management, to ensure that necessary competence is available | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 34.10 | ETFM 1042, ETFM 1132
ET078 | [5 empty] | Poor Housekeeping | Risk of fire | injury, fatality, property damage | Poor housekeeping, poor waste management, not following SOP's, No proper storage area | C | 5 | 5 | 5 | C5 | II | Proper Storage areas Available, SHE Inspections conducted, , restrict access, emergency preparedness procedure, contingency plan, awareness | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.6 | ETFM1042. ETFM1132
ET079 | [5 empty] | Unhygienic Conditions | Possible infections from bacterial infestation and Rodent infestation | Occupational diseases | Inadequate cleaning, Poor waste management | C | 5 | 5 | 5 | C5 | II | Monthly Health and Safety Inspections done on work areas including hygiene facilities by SHE Representatives, Deviations reported to facilities, Deviations escalated to SHE Committee for tracking and closure | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 42.5 | SHE rep Inspection form ETFM 1089, ETFM 1030, ETPR0364
ET080 | [5 empty] | Conditions leading to trips and falls | Trips and falls | Injury, fatality, property damage | Boxes placed on the walkways | C | 4 |  | 4 | C4 | II | Monthly Health and Safety Inspections done on work areas including hygiene facilities by SHE Representatives, Deviations reported to facilities, Deviations escalated to SHE Committee for tracking and closure | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 42.5 | SHE rep Inspection form ETFM 1089, ETFM 1030, ETPR0364
ET081 | [5 empty] | Poor Lighting | Possible falling from not seeing properly | Injury, fatality, property damage | Storage not well lit | C | 4 |  | 4 | C4 | II | Hygiene surveys conducted periodically, Breakdown maintenance conducted by facilities on fused lights as per reporting of defects, SHE inspection conducted and request made to facilities | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.3, Line 54.10 | OHSAS 18001, ISO 9001
ET082 | [5 empty] | Poor Ventilation | Poor indoor air quality | Occupational diseases (possible Legionella) | No free circulation of clean air, No regular maintenance done on the aircon system, Aircon System not working properly, No monitoring done on the system, no regular checks done | C | 4 |  | 4 | C4 | II | Hygiene surveys conducted periodically, Breakdown maintenance conducted by facilities on the Aircon system | B | 3 |  | 3 | B3 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.5, Line 54.10 | Occupational Hygiene Programme, OHSAS 18001
ET083 | [5 empty] | Incorrect Loading and Offloading (Lifting) | Body strain and muscle pull | Injury, Damage to property | Improper position, incorrect manual handling, Incorrect lifting techniques, lack awareness, ergonomics, lack of SOP's, Lack of proper lifting equipment | C | 4 |  | 4 | C4 | II | Availability of a Manual Handling guideline Awareness, Training and awareness, equipment casing allocated in pool vehicles | B | 3 |  | 3 | B3 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Manual Handling Procedure ETGL0611
ET084 | PowerStation, Radio and substation site | Construction Work |  | External | Structure Construction | Exposure to Dust ( Particulate Matter, Cement Dust) | Inhalation of particulate matter or coal dust | Possible lung infection | Not wearing correct PPE(Dust mask), prolonged exposure, poor ventilation, not following correct safe working procedure | C | 4 | 4 | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed, (PPE issue list and maintenance as a last resort) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET085 | [6 empty] | Possible Skin contact | Skin irritation | Contact with cement due to not wearing correct PPE(Overall, Gloves etc.), Not following safe working procedure | C | 4 | 4 | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed, (PPE issue list and maintenance as last resort) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET086 | [5 empty] | Exposure to Noise | Excessive noise | Damage to the ears | Not wearing correct PPE (Ear Plugs), Not following safe working procedure | C | 4 | 4 | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed, (PPE issue list and maintenance as last resort) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET087 | [5 empty] | Incorrect Use of Cranes | Possible disintegration of the crane | injury, fatality, property damage | Incompetence in operating the crane, lack of maintenance of the crane, Crane not in good working order | C | 4 |  | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed, (Crane relevant documentation for operation, competence of operator etc.) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6, Line 46.14 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET088 | [5 empty] | Conditions leading to Slips, trips and falls | Tripping and Falling | Injury, fatality, property damage | Poor housekeeping, Not wearing correct PPE, | C | 4 |  | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6, 46.17 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET089 | [5 empty] | Incorrect Use of scaffolding | Possible falling | Injury, Fatality, Property Damage | No Fall protection plan in place, Plan not implemented Incompetence in the erection of scaffolding, scaffolding not properly inspected and approved before use | C | 5 |  | 5 | C5 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed(Competence in constructing scaffolding, Inspection by a competent person etc.) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6, 46.11 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1534
ET090 | [5 empty] | working at elevated position | Possible falling | injury, fatality, property damage | No approved Fall protection plan in place, Not following Safe Working Procedure, Fall protection plan not implemented Not wearing correct PPE | C | 4 |  | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed( Fall protection plan availability and approval, Correct PPE to be issued, inspected and Maintained) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET091 | [5 empty] | Falling objects | Being struck by falling objects | injury, fatality, property damage | Not using correct PPE, Lack of awareness, not following safe working procedure when lifting, Not barricading the construction site, Not putting up prohibition signs | C | 4 |  | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed( Barricading, putting correct prohibition signage's, Correct PPE- Chin Strap Hard Hats etc. ) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6, 46.7 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET092 | [5 empty] | Incompetency | Possible falling | injury, fatality, property damage | Lack of skill, lack of training, poor supervision | C | 4 |  | 4 | C4 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed(Competency in the work being done ) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET093 | [5 empty] | Ergonomics | Possible body strain and twisting | Injury | Bad Posture, Bending for Prolonged periods | C | 5 |  | 5 | C5 | II | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed(Adherence to ET manual handling guideline ) | B | 4 |  | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1530
ET094 | [5 empty] | Improper usage of moving machinery | unnecessary injuries | injury, fatality, property damage, damage to moving machinery | No SOP's, Lack of training/experience, lack of maintenance of equipment , | B | 4 |  | 4 | B4 | III | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed(Driven Machinery requirements ) | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 36.2, 36.3 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1531
ET095 | [5 empty] | No Baseline risk assessment done | Not identifying possible hazards and risks in order to take preventative and corrective action | Injury, Fatality | Possible risks not identified and managed | B | 4 |  | 4 | B4 | III | Contractor Management, Availability of SHEQ Specifications and evaluation and approval of contractor SHEQ Plan, Contractor audits conducted and action plans developed and managed(Baseline and Specific Task Risk Assessment, List of hazards issued to assist with the development of HIRA ) | B | 4 |  | 4 | B4 | III | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 46.3, Line 46.4, 34.10, 46.5, 46.6 | SHEQ Specification (ETGL1277), Contractor Management Procedure (ETPR0822) ETFM1293, ETFM1532
ET096 | Office | Admin work |  | Internal | facilities (kitchen, ablutions, parking areas) | Poor hygiene | Possible infections from bacterial infestation | Occupational diseases | Inadequate cleaning of ablutions, poor waste management | B | 3 | 3 | 3 | B3 | III | Monthly Health and Safety Inspections done on work areas including hygiene facilities by SHE Representatives, Deviations reported to facilities, Deviations escalated to SHE Committee for tracking and closure | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 42.5 | SHE rep Inspection form ETFM 1089, ETFM 1030, ETPR0364
ET097 | [5 empty] | Ergonomics | Musculoskeletal disorders | Minor, Major Injury | Sitting for long periods, awkward postures, repetitive tasks | B | 3 | 3 | 3 | B3 | III | · Office occupants are provided with ergonomically designed chairs. Adequate work surfaces | B | 2 | 2 | 2 | B2 | IV | E | SHEQ Personnel, Senior supervisor, Employees | Line 32.3 | ETPR0364
ET098 | [5 empty] | Use of Urns in the kitchens | Possible burns | Possible Minor Burns | No Precautionary signs placed next to the urns on safe use, Awareness not raised on safe use | B | 3 | 3 | 3 | B3 | III | Warning signs placed next to each Urn to sensitise the user's to take precautions when using them | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | 32-93, ETPR0364
ET099 | Office surroundings |  |  | Internal/ External | Traffic in the complex | non adherence to traffic rules | being runned over or possible MVA | injury, fatality, | No Warning signs (Speed limit, road markings, Traffic Circle etc.), violation of traffic rules, inexperienced drivers, Speeding | C | 2 |  | 2 | C2 | III | Safe Driver Awareness raised continuously, Induction conducted to employees and contractors, Random observations done during vehicle safety awareness | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | SHE rep Inspection form ETFM 1089,
ET100 | [5 empty] | incorrect use of Staircases | possible falling | injury, fatality, | Absence or non-use of handrails, | D | 2 |  | 2 | D2 | II | Awareness raised on the use of handrails when ascending or descending stairs, Signage's places placed next to staircases | B | 2 |  | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.8. Line 46.19 | Risk Assessment Procedure (ETPR0364)
ET101 | [5 empty] | Conditions leading to slips and falls | Possible falling | Disabling Injury | Lack of warning signs, improper shoes, wet or slippery floors , uneven floors, housekeeping | D | 2 |  | 2 | D2 | II | Warning signs(Floor slippery when wet) available and used during floor cleaning, Awareness raised on wearing of correct shoes, holding on to hand rails. Reporting of unsafe conditions that may lead to slipping and falling, Regular inspection of workplaces done to identify conditions which have a potential to cause falling | B | 3 |  | 3 | B3 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.6 | Risk Assessment Procedure (ETPR0364)
ET102 | [5 empty] | Poor Housekeeping | Possible fire and trips and falls | injury, fatality, property damage | Poor housekeeping, poor waste management, not following SOP's, No proper storage area | D | 3 | 3 | 3 | D3 | II | Proper Storage areas Available, SHE Inspections conducted, , restrict access, emergency preparedness procedure, contingency plan, awareness | B | 2 | 2 | 2 | B2 | IV | I | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.6 | ETFM1042. ETFM1132
ET103 | [5 empty] | Poor Ventilation | No free circulation of clean air | Occupational diseases (possible Legionella) | No regular maintenance done on the aircon system, Aircon System not working properly, No monitoring done on the system, no regular checks done | C | 4 | 4 | 4 | C4 | II | Hygiene surveys conducted periodically, Breakdown maintenance conducted by facilities on the Aircon system | B | 4 | 4 | 4 | B4 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.5, Line 54.10 | Occupational Hygiene Programme, OHSAS 18001
ET104 | [5 empty] | Poor lighting | Poor visibility which may cause straining of the eyes | Occupational diseases(Damage to the eyes- long term) | No Maintenance on lights, No Monitoring done to pinpoint problem areas and correct deviations | C | 4 | 4 | 4 | C4 | II | Hygiene surveys conducted periodically, Breakdown maintenance conducted by facilities on fused lights as per reporting of defects, SHE inspection conducted and request made to facilities | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.3, Line 54.10 | OHSAS 18001, ISO 9001
ET105 | Office and other working Environments |  |  | Internal | Occupational expectations | Work overload | Fatigue, low morale | injury, fatality, Mental ill-health | poor planning, poor leadership, Not sufficient Human Resources | D | 3 | 3 | 3 | D3 | II | Management System Implementation assist with improvement on planning, | C | 2 | 2 | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Human resource policies
ET106 | [5 empty] | Staff shortage | Fatigue, low morale | injury, fatality, Mental ill-health | Non Availability of approved vacancies, work overload caused by shortage of staff, chasing of deadlines, taking shortcuts | C |  | 4 | 4 | C4 | II | Maximization of existing Human Resources, Retention of skills | C | 2 | 2 | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | OHSAS 18001, Business Plan, Integrated risk management document
ET107 | [5 empty] | Lack of resources | A lot of improvising which goes with errors | Injury, Fatality, Damage to property, Business risks | Improvising, Financial constraints, poor management | D | 3 |  | 3 | D3 | II | Financial Management/ resource management training | C | 2 | 2 | 2 | C2 | III | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPN1406, ETFM1389
ET108 | [5 empty] | Substance abuse | possible injuries | injury, fatality, | Personal Problems, Stress, irresponsibility, lack of awareness | D | 3 | 3 | 3 | D3 | II | Personnel trained and appointed in writing as testers, EAP, cardinal rules, awareness raised on Substance Abuse, Periodic Alcohol testing conducted, Disciplinary measures taken | B | 2 | 2 | 2 | B2 | IV | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 34.3 | Procedure 32-93, ETPR1067, ETFM0653
ET109 |  |  |  | Internal/ External | Applying First Aid | Exposure to Hazardous Biological Agents | possibility of contracting communicable diseases such as HIV, Hepatitis B etc. | Occupational Disease | Non adherence to First Aid precautionary measures ( not using a Mouth piece when performing CPR, not wearing Proper surgical gloves, not using mask) | C | 2 | 2 | 2 | C2 | III | First Aid training up to level 2 for all first aiders and for all those who travel to site. Portable First Aid Kits provided for all vehicles used for Eskom Business. Maintenance of FA kits | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, First Aiders and Employees | Line 32.3, 34.6, 44.2, 44.3 | Medical Surveillance programmes
ET110 |  |  |  |  | Working in close proximity to co-workers who may have infectious | Exposure to Hazardous Biological Agents | possibility of contracting communicable diseases such as resistant TB, | Occupational Disease | Employees not taking treatment, poor ventilation in an overcrowded environment | C | 2 | 2 | 2 | C2 | III | Medical clinic on site, pre, periodic and post medical surveillance programme in place and implemented, Health awareness raised | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, 34.6, 44.2, 44.3 | SHE rep Inspection form ETFM 1089, ETFM 1030, ETPR0364
ET111 |  |  |  |  | Working in close proximity to co-workers who may have communicable infections | Exposure to communicable diseases | Possibility of contracting diseases through contact, such as cholera, Hepatitis A | Occupational Disease | Poor personal hygiene (Not properly washing your hands after using a toilet) | C | 2 | 2 | 2 | C2 | III | Raising awareness in personal Hygiene, Availability of facilities for hand washing and for drying of hands | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 42.5 | Safe handling of hydrocarbon procedure (ETPR1280)
ET112 | Storage Areas |  |  | Internal | Handling of HCS/gases | Incompetence in Handling of HCS | Possible inhalation of HCS | Occupational Diseases, environmental damage, fatality, injury | Incompetence in Safe Handling of fuel for generators, and in handling of herbicides | B | 4 | 4 | 4 | B4 | III | Training on Handling of hazardous Chemical Substances conducted, Training analysis on relevant training to be conducted, Training and awareness procedure in place | B | 2 |  | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 41.2, 41.3, 41.4 | Safe handling of hydrocarbon procedure (ETPR1280)
ET113 | [5 empty] | Improper fuel storage | Possible Inhalation of HCS, Possible fire | Occupational Diseases, Environmental damage, fatality, injury | Incorrect containment, not having necessary permits, No following SOP's | B | 4 | 4 | 4 | B4 | III | Training provided on handling of Hazardous Substances, Proper storage provided where fuel is stored, Safe handling of hydrocarbon procedure in place | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 41.2, 41.12 | Safe handling of hydrocarbon procedure (ETPR1280)
ET114 | [5 empty] | Exposure to inhalation of fumes | Inhalation of fumes | Possible Lung infection, injury, Fatality | prolonged exposure to fumes, Not wearing correct PPE(Respirators) | B | 4 | 4 | 4 | B4 | III | Correct PPE issued to relevant employees, Awareness raised on the correct use when handling HCS, | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 41.10, 41.8 | ETFM1042, ETFM 1132
ET115 | [5 empty] | Improper stacking of equipment | Possibility of Equipment Falling | Possible falling of Equipment | uneven stacking, not correct PPE | B | 4 | 4 | 4 | B4 | III | Regular SHE rep Inspections done on storage areas, Correct PPE issued to employees having access to the storage area | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 34.10 | ETPR0364, ETPR 1029
ET116 | Fibre lines/ routes |  |  | Internal/ External | Conducting Walk down | Incorrect use of PPE | walking about in overgrown grass, falling in ditches | injury, | PPE not comfortable, ignorance, lack of awareness | C | 3 |  | 3 | C3 | II | Procedure on fibre handling in place and implemented, Awareness raised on the procedure, pre-task risk assessment, Behavioural Safety Observation, PPE Issued | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | ETPR0364, ETPR 1030
ET117 | [5 empty] | Incorrect Handling of fibre | Possible pricking by fibre glass which may find its way into the blood stream | injury, fatality | Ignorance, lack of training, Not following Safe working procedures, lack of supervision | B | 4 |  | 4 | B4 | III | Procedure on fibre handling in place and implemented, Awareness raised on the procedure, pre-task risk assessment, Behavioural Safety Observation, PPE Issued | B | 2 | 2 | 2 | B2 | IV | E | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency preparedness procedure ETPR1141
ET118 | Surrounding Areas | Hazards originating outside workplace | Non Routine | Internal | Working around the working area | Conditions leading to Explosion | Possible Explosion | Minor/Major injuries, Fatalities | Working in the vicinity of petrol stations | B | 6 | 6 | 6 | B6 | II | Implementation (Testing) and adherence to the Emergency Preparedness Plan | B | 6 | 6 | 6 | B6 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3, Line 40.8 | Emergency preparedness procedure ETPR1141
ET119 |  |  | Non Routine | Internal | Working in close proximity to the Lake and non maintenance of storm water drains | Conditions leading to Flooding | Possible flooding during heavy rains | Minor/Major injuries, Fatalities | Heavy rains, insufficient barriers around the lake, poor maintenance of storm water drains | B | 6 | 6 | 6 | B6 | II | Implementation (Testing) and adherence to the Emergency Preparedness Plan | B | 6 | 6 | 6 | B6 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | line 32.3, Line 40.7 | Emergency preparedness procedure ETPR1141
ET120 |  |  | Non Routine | Internal | Working in the vicinity of petrol stations | Conditions leading to Explosion | Possible explosion | Minor/Major injuries, Fatalities | No Proper emergency plans by the third party. Foul play, negligence | B | 6 | 6 | 6 | B6 | II | Implementation (Testing) and adherence to the Emergency Preparedness Plan | B | 6 | 6 | 6 | B6 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency preparedness procedure ETPR1141
ET121 |  |  | Non Routine | Internal | Situated in an area where there were mining activities | Conditions leading to Earth tremor | Possible occurrence of Earth tremors | Minor/Major injuries, Fatalities | No Proper rehabilitation of the mines, No Proper impact assessment done, blasting | B | 6 | 6 | 6 | B6 | II | Implementation (Testing) and adherence to the Emergency Preparedness Plan | B | 6 | 6 | 6 | B6 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency preparedness procedure (ETPR0373, ETPR1141)
ET122 |  |  |  |  | Helicopter landing not demarcated | Possibility of an aircraft accident | Helicopter or aircraft crashing | Minor, Major injuries, Fatality | Aviation authorities declared Simmerpan as a no fly zone, ignoring this declaration will cause the risk. | B | 6 | 6 | 6 | B6 | II | Implementation (Testing) and adherence to the Emergency Preparedness Plan | B | 6 | 6 | 6 | B6 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency preparedness procedure ( ETPR0373, ETPR1141, ETPR1692)
ET123 |  |  | Non Routine | Internal | Located at a close radius to Gas production companies | conditions leading to Explosion | Possible Explosion | Minor/Major injuries, Fatalities | No Proper emergency plans by the third party. Foul play, negligence | B | 6 | 6 | 6 | B6 | II | Implementation (Testing) and adherence to the Emergency Preparedness Plan | B | 6 | 6 | 6 | B6 | II | PE | Line Management, SHEQ Personnel, Head of sections/supervisors, Employees | Line 32.3 | Emergency preparedness procedure (ETPR0373, ETPR1141,
[20 empty] | 0 | 0 | #N/A
Note on K4: GanesaM: Raw Risk - without any controls
Note on P5: GanesaM: Automatic formulas
Note on W5: GanesaM: Automatic formulas
Note on X5: GanesaM: E = EFFECTVE PE = PARTIALLY EFFECTIVE I = INEFFECTIVE

## RISK ASSESSMENT MATRIX (hidden)
Risk Assessment Matrix | [6 empty] | A1 | IV | A1 | IV
Consequenses | 6 | III | II | I | I | I | B1 | IV | B1 | IV
| 5 | III | II | II | I | I | A2 | IV | A2 | IV
| 4 | IV | III | II | I | I | B2 | IV | B2 | IV
| 3 | IV | III | II | II | I | A3 | IV | A3 | IV
| 2 | IV | IV | III | II | II | A4 | IV | A4 | IV
| 1 | IV | IV | III | III | III | C1 | III | C1 | III
|  | A | B | C | D | E | D1 | III | D1 | III
|  | Likelihood |  |  |  |  | E1 | III | E1 | III
[7 empty] | C2 | III | C2 | III
[7 empty] | B3 | III | B3 | III
Priority | Suggested timing of treatment |  |  | Authority for continued toleration of residual risk |  |  | A5 | III | A5 | III
I | Short term. Normally within 1 month. |  |  | Managing Directors, Chief Executive and Board |  |  | A6 | III | A6 | III
II | Medium term. Normally within 3 months. |  |  | Managing Directors, Senior General Managers and General Managers |  |  | B4 | III | B4 | III
III | Normally within 1 year |  |  | Senior General Managers, General Managers and Managers |  |  | B6 | II | B6 | II
IV | Ongoing control as part of a management system. |  |  | All staff |  |  | B5 | II | B5 | II
[7 empty] | C5 | II | C5 | II
[7 empty] | C4 | II | C4 | II
[7 empty] | C3 | II | C3 | II
[7 empty] | D3 | II | D3 | II
[7 empty] | D2 | II | D2 | II
[7 empty] | E2 | II | E2 | II
[7 empty] | E3 | I | E3 | I
[7 empty] | D4 | I | D4 | I
[7 empty] | E4 | I | E4 | I
A1 | IV | A1 | IV |  |  |  | D5 | I | D5 | I
B1 | IV | B1 | IV |  |  |  | E5 | I | E5 | I
A2 | IV | A2 | IV |  |  |  | C6 | I | C6 | I
B2 | IV | B2 | IV |  |  |  | D6 | I | D6 | I
A3 | IV | A3 | IV |  |  |  | E6 | I | E6 | I
A4 | IV | A4 | IV
C1 | III | C1 | III
D1 | III | D1 | III
E1 | III | E1 | III
C2 | III | C2 | III
B3 | III | B3 | III
A5 | III | A5 | III
A6 | III | A6 | III
B4 | III | B4 | III
B6 | II | B6 | II
B5 | II | B5 | II
C5 | II | C5 | II
C4 | II | C4 | II
C3 | II | C3 | II
D3 | II | D3 | II
D2 | II | D2 | II
E2 | II | E2 | II
E3 | I | E3 | I
D4 | I | D4 | I
E4 | I | E4 | I
D5 | I | D5 | I
E5 | I | E5 | I
C6 | I | C6 | I
D6 | I | D6 | I
E6 | I | E6 | I