Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Purchaser’s Goods Information | 14 |
|  | (insert at award stage or delete if not applicable) |  |
|  | Total number of pages | 15 |

C3.1: Purchaser’s Goods Information

Contents

Part 3: Scope of Work	1

C3.1: Purchaser’s Goods Information	2

1	Overview and purpose of the goods and services	4

2	Specification and description of the goods	4

2.1	Purchaser’s design	5

2.2	Procedure for submission and acceptance of Supplier’s design	5

2.3	Other requirements of the Supplier’s design	5

2.4	Use of Supplier’s design	5

2.5	Manufacture & fabrication	6

2.6	Factory acceptance testing (FAT)	6

2.7	Other tests and inspections and commissioning in place of use	7

2.8	Operating manuals and maintenance schedules	7

3	Supply Requirements	8

4	Specification of the services to be provided	8

5	Constraints on how the Supplier Provides the Goods	8

5.1	Programming constraints	8

5.2	Work to be done by the Delivery Date	9

5.3	Marking the goods	10

5.4	Constraints at the delivery place and place of use	10

5.5	Cooperating with Others	11

5.6	Services & other things to be provided by the Purchaser or Supplier	11

5.7	Management meetings	11

5.8	Documentation control	11

5.9	Health and safety risk management	12

5.10	Environmental constraints and management	12

5.11	Quality	13

5.12	Invoicing and payment	13

5.13	Insurance provided by the Purchaser	13

5.14	Contract change management	14

5.15	Provision of bonds and guarantees	14

5.16	Records of Defined Cost, payments & assessments of compensation events to be kept by the Supplier	14

6	Procurement	14

6.1	Subcontracting	14

6.1.1	Preferred subcontractors	14

6.1.2	Limitations on subcontracting	14

6.1.3	Spares and consumables	14

6.1.4	Other requirements related to procurement	14

6.1.5	Cataloguing requirements by the Supplier	14

7	List of drawings	15

7.1	Drawings issued by the Purchaser	15

# Overview and purpose of the goods and services

The goods comprise the supply and delivery of:

- One (1) 13 ton carry deck mobile crane and

- One (1) 90 ton rough terrain mobile crane

complete with all associated accessories, operational manuals, statutory compliance documentation, and initial commissioning.

The purpose of procuring these cranes is to support lifting, materials handling and maintenance operations at the designated Kendal Power Station premises.

The supply requirements include:

- Delivery to site by the agreed Delivery Date.

- Full functional testing and commissioning on-site.

- Provision of operator training and competency certification for Eskom’s nominated personnel.

- Supply of statutory compliance documentation, including load test certificates, inspection reports, and maintenance schedules.

- Provision of after-sales support, minimum one (1) year warranty coverage and access to technical support for the agreed warranty period.

This procurement aims to ensure the availability of safe, reliable, and efficient lifting equipment that meets Eskom’s operational and statutory obligations.

# Specification and description of the goods

The Supplier shall supply, deliver, commission and provide training for the following cranes in accordance with the technical and operational requirements specified below. All cranes shall be new, unused, and fully compliant with applicable South African statutory requirements and OEM standards.

Key parameters for the 13 ton carry deck mobile crane include:

- Rearview mirrors

- All weather cab and wiper

- Strobe light

- Boom work lights

- Rated capacity limiter

- Pick and carry

- Capacity 13.6t on outriggers, 7.7t pick and carry

- Boom length 4.72m -15.24m

- 4-wheel steer and 4-wheel drive

- Diesel Engine

- Tyres high traction tread

- Electrical 12V

- RCL Light bar

Key parameters for the 90 ton rough terrain mobile crane include:

- Boom: 12.0 m – 47.0 m (5 sections)

- Jib: 10.1 m & 17.7 m, offset at 3.5°, 25°, and 45°

- Drive: 4 × 4 with 4 × 2 select

- Capacity: 90 ton

- Engine: Diesel Powered

- Steering: 4 modes (2-wheel front, 4-wheel coordinated, 4-wheel crab)

- Outriggers: H-type

- Tyres: 29.5-25 36PR

- Counterweight: Integrated 9,800 kg

- Hook Blocks: 90 t (8 sheave) and 35 t (3 sheave)

- Winches: Two

SAP Descriptions

- CRANE, TRUCK MOUNTED: TYPE: CARRY DESK MOBILE; LIFTING CAPACITY: 13 T; BOOM TYPE: TELESCOPIC; BOOM LENGTH AT LIFTING CAPACIT: 4.72 TO 15.24 M; WORKING RADIUS: 2.5 TO 12 M; OPERATING POWER TYPE: DIESEL; ENGINE TYPE: TURBO CHARGED DIESEL ENGINE 6-CYLINDER; DRUM QUANTITY: 2; BOOM OVERALL LENGTH: 18 M; HOOK BLOCKS 90 TO 8 SHEAVE 35T 3 SHEAVE JIB 10.1 M AND 17.7 M WITH OFFSTS 3.5 25 45 DEGREE STEERING 4 MODES 2W FRONT 4W COORDINATED 4W CRAB

- CRANE, TRUCK MOUNTED: TYPE: ROUGH TERRIAN; LIFTING CAPACITY: 90 T; BOOM TYPE: 5-SECTION TELESCOPIC; BOOM LENGTH AT LIFTING CAPACIT: 12 TO 47 M; WORKING RADIUS: 40 M; OPERATING POWER TYPE: DIESEL; ENGINE TYPE: DIESEL ENGINE; DRUM QUANTITY: 2 WINCHES; BOOM OVERALL LENGTH: 47 M; JIB 10.1 AND 17.7 M OFFSET 3.5 25 45 DEGREE STEERING 4 MODES 2W FRONT 4W COORD 4W CRAB HOOK BLOCK 90 TO 8 SHEAVE 35T 3 SHEAVE 4.7 MAIN BOOM

## Purchaser’s design

The Purchaser is not responsible for the design of any part of the goods.  All design work shall be undertaken by the Supplier in accordance with the Purchaser’s specifications.

## Procedure for submission and acceptance of Supplier’s design

The Supplier shall prepare and submit all design documentation, calculations and drawings necessary to demonstrate compliance with the Purchaser’s requirements.

## Other requirements of the Supplier’s design

None

## Use of Supplier’s design

Except as stated below, the Purchaser’s rights to use the Supplier’s design shall be limited to the purposes stated in core clause 22.1.

- Additional permitted uses:

- The Purchaser may reproduce, adapt, or modify the Supplier’s design documents for future maintenance, refurbishment, or replacement of the goods.

- The Purchaser may share the design documents with third parties engaged by the Purchaser for operation, maintenance, or integration of the goods into other systems, provided such parties are bound by confidentiality obligations equivalent to those in this contract.

- Exceptions:

- The Supplier’s design shall not be used for the manufacture or procurement of goods from another supplier without the Supplier’s prior written consent, except where the Supplier is unable or unwilling to provide such goods on reasonable commercial terms.

## Manufacture & fabrication

The Supplier is responsible for determining the manufacturing and fabrication methods necessary to meet the Purchaser’s requirements. In addition to the Supplier’s standard practices, the following specific requirements apply:

- Standards and Quality Control

- All manufacturing and fabrication shall be performed in accordance with recognised international and/or national standards (e.g., SANS, ISO, IEC, BS, ASME).

- The Supplier shall maintain a documented quality management system compliant with ISO 9001 or equivalent.

- Materials used shall be new, of first-class quality, and accompanied by material certificates where applicable.

- Inspection and Testing

- The Purchaser, or their appointed representative, shall have the right to inspect manufacturing and fabrication processes at the Supplier’s premises and/or subcontractor facilities with reasonable prior notice.

- The Supplier shall notify the Purchaser in writing at least 5 working days prior to any planned inspection and testing.

- All works shall be subject to factory acceptance tests (FAT) in accordance with the agreed inspection and test plan.

- Fabrication Requirements

- Welding, machining and finishing operations shall be performed by qualified personnel in compliance with applicable codes and standards.

- Protective coatings, painting, and surface treatments shall meet the requirements stated in Section 2 of the Goods Information.

- Components shall be fabricated to ensure ease of assembly, maintenance and transport.

- Traceability

- The Supplier shall maintain full traceability of all materials and critical components from receipt through manufacturing to final delivery.

## Factory acceptance testing (FAT)

The Supplier shall carry out factory acceptance testing (FAT) at the place of manufacture prior to delivery to demonstrate compliance with the Purchaser’s requirements.

- Testing Requirements

- FAT shall be conducted in accordance with the agreed Inspection and Test Plan (ITP) and applicable standards.

- FAT procedures shall cover all functional, performance, safety and compliance requirements specified in the Goods Information.

- All measuring and test equipment used shall be calibrated and traceable to recognised standards.

- Witnessing of Tests

- FAT shall be witnessed by the Supply Manager and/or a person nominated by the Purchaser.

- The Supplier shall provide reasonable access to all areas, facilities, and documentation required for witnessing and verification.

- In accordance with clause 25.2, the Supplier shall not restrict the Supply Manager’s right to witness any test.

- Test Results and documentation

- The Supplier shall compile complete FAT records, including test procedures, results, certificates and any non-conformance reports with corrective actions.

- A signed FAT acceptance certificate shall be issued by the Supply Manager (or nominated representative) before the goods are released for shipment.

- Failure and Retesting

- If any item fails to meet the acceptance criteria, the Supplier shall rectify the defect at their own cost and re-submit the goods for FAT until compliance is achieved.

- Retesting shall follow the same witnessing and documentation requirements as the original FAT.

## Other tests and inspections and commissioning in place of use

- Site Acceptance Testing (SAT)

- Upon delivery of the goods at the place of use, the Supplier shall conduct Site Acceptance Testing (SAT) to verify correct installation, integration, and performance under site conditions.

- SAT shall be performed in accordance with the agreed Inspection and Test Plan (ITP).

- The Supply Manager and/or a person nominated by the Purchaser shall witness the SAT.

- The Supplier shall give the Purchaser at least 5 working days prior written notice of the SAT schedule.

- Additional Tests and Inspections

- The Supplier shall carry out any additional functional, safety and performance tests required by statutory regulations, industry codes, or the Purchaser’s standards before handover.

- All measuring and testing equipment used shall be calibrated and traceable to recognised standards.

- Commissioning by the Supplier

- The Supplier shall undertake commissioning of the goods at the place of use after delivery, which shall include:
Verification of correct assembly, alignment and calibration of equipment.
Functional testing of all systems under normal and simulated operating conditions.
Adjustment and optimisation to achieve the performance specifications.
Training of the Purchaser’s operating and maintenance personnel.

- Commissioning shall only commence after successful completion of SAT and resolution of any defects identified.

## Operating manuals and maintenance schedules

- General Requirements

- The Supplier shall prepare and submit complete operating manuals and maintenance schedules covering all aspects of the goods, in accordance with the Purchaser’s requirements and applicable standards.

- Manuals and schedules shall be in English and use SI units.

- Content shall be clear, logically structured and supported with diagrams, photographs and exploded views where appropriate.

- Content of Operating Manuals

The operating manuals shall include, as a minimum:

- Overview of the goods and their intended use.

- Technical specifications and performance data.

- Detailed instructions for installation, commissioning, operation and shutdown.

- Safety precautions, hazard warnings and emergency procedures.

- Troubleshooting guide and fault-finding procedures.

- Parts identification list with exploded diagrams.

- Content of Maintenance Schedules

The maintenance schedules shall include, as a minimum:

- Recommended preventative maintenance activities and intervals.

- Detailed instructions for inspection, servicing, lubrication, calibration and adjustments.

- Replacement parts list with manufacturer part numbers.

- Special tools or equipment required for maintenance.

- End-of-life disposal guidelines, if applicable.

- As-Built Updates

- The Supplier shall update manuals and maintenance schedules to reflect any changes made during manufacturing, FAT, installation, or commissioning.

- Final “as-built” versions shall be submitted within 5 days after commissioning and acceptance of the

# Supply Requirements

In accordance with clause 11.2(16), the Supply Requirements form part of the Goods Information, and in accordance with clause 11.2(8), they are contractually binding.

For this contract, the Supply Requirements are contained in an Annexure to the Contract Data provided by the Purchaser and shall be read in conjunction with this Goods Information.

# Specification of the services to be provided

The Supplier shall provide the following services in relation to the supply and delivery of the 13 ton carry deck mobile crane and 90 ton rough terrain mobile crane:

- Training of Purchaser’s Staff

- Provide on-site operator training for the Purchaser’s personnel covering:

- Safe operation of the cranes in accordance with OEM guidelines and statutory requirements.

- Pre-start inspections and daily maintenance procedures.

- Emergency procedures and fault diagnosis.

- Provide maintenance training for the Purchaser’s technical staff, covering:

- Scheduled and preventative maintenance tasks.

- Basic fault-finding and repairs.

- Use of diagnostic tools and software, if applicable.

- Supply training manuals and certificates for all participants.

- Supervision the offloading of cranes

- Supervise the offloading of the cranes on the Purchaser’s property.

- Verify correct setup, calibration and functional readiness in accordance with OEM instructions.

- Commissioning

- Perform post-Delivery commissioning, including functional and safety checks under actual site conditions.

- Conduct Site Acceptance Testing (SAT) in accordance with the agreed Inspection and Test Plan (ITP) and obtain signed acceptance from the Supply Manager.

# Constraints on how the Supplier Provides the Goods

## Programming constraints

In addition to the requirements of clause 31.2, the Supplier’s programme shall include the following particulars:

- Key Milestones

- Submission dates for design documentation, drawings, and calculations.

- Inspection and Test Plan (ITP) submission and approval dates.

- Factory Acceptance Testing (FAT) dates and notice periods.

- Packing, shipping and delivery dates to Kendal Power Station.

- Site Acceptance Testing (SAT) and commissioning dates.

- Training delivery dates.

- Order and Timing of Work

- Manufacturing and testing shall be planned to avoid delivery before the Purchaser confirms readiness to receive the goods on site.

- FAT must be completed and accepted prior to shipment of the goods.

- SAT and commissioning must be scheduled in coordination with site access availability and operational requirements of Kendal Power Station.

- Training shall be completed no later than ten (10) days after commissioning.

- Programme Format

- The programme shall be prepared in a recognised project management format (e.g., MS Project) showing logical links, durations, float and critical path.

- The programme shall be updated at intervals not exceeding one week or as otherwise instructed by the Supply Manager.

## Work to be done by the Delivery Date

For the purposes of clause 11.2(5), Delivery shall mean that the Supplier has completed all of the following activities and requirements by the Delivery Date:

- Manufacture and Testing

- Completion of manufacture of the 13-ton carry deck mobile crane and the 90-ton rough terrain mobile crane in accordance with the approved design and specifications.

- Successful completion of all Factory Acceptance Tests (FAT) in accordance with the approved Inspection and Test Plan (ITP) and acceptance by the Supply Manager.

- Documentation

Submission and acceptance by the Purchaser of:

- As-built design drawings and data sheets.

- Operating manuals and maintenance schedules (final approved versions).

- OEM warranty certificates.

- FAT reports and quality control records.

- Packing lists and shipping documentation.

- Packing and Preparation for Transport

- Completion of packing, preservation, and marking of goods for safe transport to the Purchaser’s nominated Delivery Place as stated in the Supply Requirements.

- Compliance with all applicable transport, lifting and safety regulations for the mode of shipment.

- Readiness for Shipment

- Placement of goods into a condition ready for dispatch, including securing for transport and inspection by the Purchaser (if required).

- Notification to the Purchaser that the goods are ready for shipment.

## Marking the goods

If payment for the goods is made before they are brought within the Delivery Place, the Supplier shall clearly and permanently mark the goods in accordance with clause 71.1 to identify them as the property of the Purchaser.

The marking shall comply with the following requirements:

- Method of Marking

- Durable, corrosion-resistant identification plates or tags securely affixed to each major component of the goods.

- Markings to include the words “Property of Eskom Holdings SOC Ltd – Contract No. [insert contract number]” in English and in a legible, permanent format.

- For smaller components, tamper-evident adhesive labels with the same wording may be used.

- Location of Marking

- Markings shall be placed in a clearly visible and accessible location on each item without obstructing safety information or operational markings.

- For the cranes, markings shall be applied to:

- Main chassis/frame.

- Operator’s cab.

- Boom assembly.

- Verification

- The Supplier shall provide photographic evidence of markings prior to shipment.

- The Supply Manager reserves the right to inspect and verify markings at the Supplier’s premises prior to dispatch.

- Maintenance of Markings

- Markings shall remain legible and intact until the goods are delivered to the Delivery Place and formally accepted by the Purchaser.

## Constraints at the delivery place and place of use

The Supplier shall comply with all access, safety and operational requirements at both the Delivery Place and Kendal Power Station (place of use). The following specific constraints apply:

- Site Access and Security

- All Supplier and subcontractor personnel shall undergo site induction and security clearance in accordance with Eskom procedures prior to gaining access.

- The Supplier shall provide a list of all personnel, including full names, ID/passport numbers, and vehicle details, at least 3 working days before the planned site visit.

- Access to certain areas may be restricted and will require an escort provided by the Purchaser.

- Working Hours

- Normal working hours are Monday to Thursday, 07:15 to 16:30 and Friday 07:15 to 12:15   excluding public holidays, unless otherwise approved in writing by the Supply Manager.

- Any work outside these hours must be approved in advance and may be subject to additional site supervision or security charges.

- Health, Safety, and Environmental Requirements

- Compliance with all Kendal Power Station safety rules, Life Saving Rules, and environmental management requirements is mandatory.

- PPE must be worn at all times in designated areas, including hard hats, safety shoes, high-visibility vests, and any additional PPE specified in the safety file.

- The Supplier shall submit and have approved a safety file prior to commencement of any site work.

- Delivery Logistics

- The Supplier shall coordinate delivery with the Supply Manager to avoid congestion and to ensure availability of offloading equipment and personnel.

- Heavy or oversized loads must comply with Eskom and road transport regulations, including obtaining all necessary permits.

- Deliveries may be restricted during peak site traffic hours (typically shift change times).

- Special requirements

- Photography, videography, and use of recording devices are prohibited unless authorised in writing by the Purchaser.

- The Supplier shall allow for possible delays due to operational constraints.

## Cooperating with Others

The Supplier shall cooperate fully with the Purchaser’s personnel, contractors, consultants and any other parties (“Others”) engaged on related works or services at Kendal Power Station to ensure safe, efficient, and coordinated execution of all activities.

## Services & other things to be provided by the Purchaser or Supplier

In accordance with clause 23.2, the following services and other things shall be provided by each Party to facilitate the supply of the goods:

- Purchaser to Provide to the Supplier

- Site Access and Security Clearances: Facilitation of site induction for Supplier personnel.

- Site Escort/Permit Support: Escort services for access to restricted areas, and assistance in obtaining required permits for site work.

- Supplier to Provide to the Purchaser

- Offloading Equipment: Provision of site-based cranes, forklifts, or other lifting equipment (where available) for the offloading of goods at the Delivery Place.

- Labour and Supervision: All personnel necessary for the offloading, assembly, installation, commissioning and training as specified in this Goods Information.

- Specialist Tools and Equipment: Any specialised tools, jigs, or lifting equipment required for the installation, commissioning or maintenance of the goods.

- Documentation and Certifications: All required design data, manuals, test certificates, and quality documentation prior to Delivery and commissioning.

## Management meetings

Meetings of a specialist nature may be convened as specified elsewhere in this Goods Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the manufacture of the goods.  Records of these meetings shall be submitted to the Supply Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Documentation control

The Supplier shall implement and maintain a documentation control system to ensure that all contractual and technical communications are correctly identified, traceable, and in the format required by the Purchaser.

## Health and safety risk management

In addition to compliance with all applicable laws, regulations, and standards governing occupational health and safety, the Supplier shall meet the Purchaser’s specific health and safety requirements for the supply, delivery, and commissioning of the goods at Kendal Power Station.

- General Compliance

- The Supplier shall comply with the Occupational Health and Safety Act (Act No. 85 of 1993), the Mine Health and Safety Act (Act No. 29 of 1996) where applicable and all associated regulations.

- The Supplier shall comply with Eskom’s Personal Safety Regulations (PSR), environmental management standards, and any other station-specific safety rules.

- Safety File

- The Supplier shall compile and submit a complete safety file for acceptance by the Purchaser before commencing any work at site.

- The safety file shall include, as a minimum:

- Baseline and task-specific risk assessments.

- Safe work procedures and method statements.

- Copies of relevant training and competency certificates.

- Medical fitness certificates for all personnel entering site.

- PPE requirements and evidence of PPE issue.

- Emergency preparedness and response plan.

- The safety file shall be kept on site at all times during the execution of work.

- Site Safety Induction and Training

- All Supplier personnel and subcontractors shall attend Kendal Power Station’s site safety induction before starting work.

- Incident Reporting

- All safety incidents, near misses, and hazardous conditions shall be reported immediately to the Purchaser’s representative and recorded in accordance with Eskom’s incident reporting procedures.

- The Supplier shall assist in any incident investigation as required.

- Monitoring and Auditing

- The Purchaser reserves the right to carry out safety inspections and audits at any time during the contract.

- Non-conformances shall be rectified immediately or within an agreed time frame at the Supplier’s cost.

## Environmental constraints and management

The Supplier shall comply with all applicable environmental laws, regulations, and standards, as well as the Purchaser’s specific environmental management requirements, during the design, manufacture, delivery, installation and commissioning of the goods.

- General Compliance

- Compliance with the National Environmental Management Act (Act No. 107 of 1998) and all other applicable environmental legislation and municipal by-laws.

- Adherence to Eskom’s Environmental Management System and station-specific environmental rules for Kendal Power Station.

- Design Considerations

- The design of the goods shall minimise environmental impact, including:

- Energy efficiency.

- Reduced emissions (noise, exhaust gases, particulates).

- Use of environmentally sustainable materials where feasible.

- Provision for safe end-of-life disposal of components and materials.

- The Supplier shall, where possible, use recyclable, reusable, or biodegradable packaging materials.

- Noise and Dust Control

- The Supplier shall implement measures to control noise, vibration, and dust emissions during site activities, ensuring compliance with statutory and station limits.

- Monitoring and Reporting

- Any environmental incidents (e.g., spills, leaks, emissions exceedances) shall be reported immediately to the Purchaser’s environmental representative.

- The Supplier shall cooperate fully with the Purchaser’s environmental monitoring and auditing processes.

## Quality

The Supplier shall implement and maintain a quality management system to ensure that all goods and services supplied under this contract meet the requirements of the Goods Information and applicable standards.

- Inspection and Testing

- The Supplier shall carry out inspections and tests in accordance with the approved ITP and provide the Purchaser with reasonable notice to witness these activities.

- Test records, material certificates, and inspection reports shall be submitted as part of the manufacturing record book.

- Control of Non-Conformance

- Any non-conforming goods or services shall be reported immediately to the Purchaser.

- The Supplier shall implement corrective actions to prevent recurrence and shall not proceed with work until the non-conformance has been resolved to the Purchaser’s satisfaction.

- Final Documentation

- The Supplier shall provide a manufacturing record book containing all quality-related documents, certificates, and test results before or at delivery.

## Invoicing and payment

Within one week of receiving a payment certificate from the Supply Manager in terms of core clause 51.1, the Supplier provides the Purchaser with a tax invoice showing the amount due for payment equal to that stated in the Supply Manager’s certificate.

The Supplier shall address the tax invoice to Purchaser and include on each invoice the following information:

- Name and address of the Supplier and the Supply Manager;

- The contract number and title;

- Supplier’s VAT registration number;

- The Purchaser’s VAT registration number.

- Description of goods and services provided for each item invoiced based on the Price Schedule;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

- Supplier’s Banking Details

## Insurance provided by the Purchaser

In accordance with SC3 Core Clause 84.1, the Purchaser provides the insurances stated in the Contract Data.

## Contract change management

None

## Provision of bonds and guarantees

None

## Records of Defined Cost, payments & assessments of compensation events to be kept by the Supplier

In accordance with clauses 63.2 and 11.2(4), where compensation events are to be assessed based on Defined Cost, the Supplier shall maintain accurate and complete records to substantiate such costs.

# Procurement

## Subcontracting

### Preferred subcontractors

None

### Limitations on subcontracting

None

### Spares and consumables

None

### Other requirements related to procurement

None

### Cataloguing requirements by the Supplier

None

# List of drawings

## Drawings issued by the Purchaser

This is the list of drawings issued by the Purchaser at or before the Contract Date and which apply to this contract.

| Drawing number | Revision | Title |
| --- | --- | --- |