## Main & BFPT Condenser HPC
Occupational Health and Safety Baseline risk assessment template
Business/Operating unit: | Lethabo Power Station | [9 empty] | Next Review Date (every 2 years):
Date: | 22/11/2024 | [5 empty] | Authorised by: |  | Name: Jan Ngoepe
Designation: Outage Execution Manager
Signed:
Date:22/11/2024
Refer to Occupational Health and Safety Risk assessment procedure 32-520
List activity | Activity type (Routine/Non-routine) | Hazard Identification | Associated risk | Risk type | Cause(s) of the risk | What are the possible consequences? | Existing Controls |  |  | Risk Priority Rating | Legal and Other Requirements
List specific activities to be performed taking into consideration the equipment to be used, the personnel involved in the task. | Indicate R or N 1. Routine activities and situations create hazards through day-to-day operations and normal work activities; 2. Non-routine activities and situations are occasional or unplanned; | Anything with potential to cause of harm. Note: A hazard can pose more than one risk. | A chance that injury , ill health or damage could occur as a result of uncontrolled hazard. | Safety or health | What causes the risk to come into effect? | Consider the worse case scenario without controls? | Include: - Preventative Controls (controls implemented to eliminate hazards or reduce the likelihood of the risk occurring), and - Reactive Controls (controls implemented to reduce the immediate impact of the risk occurring) Elimination Substitution Engineering controls Administrative controls Personal protective equipment (PPE) | Consequence | Likelihood | Risk Priority Rating | Where relevant, list the relevant legislative and or Eskom requirements that prescribe the control.
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Noise generated from operating of machinery (grinders) | NIHL | Health | Noise generated from operating of machinery (grinders) | NIHL | Administrative: Medical surveillance, person job specifications, education and training. Task Risk Assessment,PPE: Hearing protection. | 4 | B | III | Noise-Induced Hearing Loss, reg 3,9 &10
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Manual Lifting of materials | Falling materials - contusion, finger pinching, back injury | Safety | Manual Lifting of materials for fabrication in workshop | Falling materials - contusion, finger pinching, back injury | Engineering: Use overhead crane, forklift, Administrative: Training in work procedures, qualified operators,Task Risk Assessment,apply manual lifting technique. PPE: Gloves | 4 | B | III | Compliance to Plant Safety Regulation; Occupational Health & Safety Act, sec 14;
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Heat generated inside the condenser | Exposure to heat - fatigue/dehydration | Health | Heat generated from outside and inside the boiler | Exposure to heat - fatigue/dehydration | Engineering: ventilation/ natural air. Administrative: Medical surveillance, person job specifications, education and training, safe work procedures, drinking of water, heat stress monitoring.Task Risk Assessment | 4 | B | III | Environmental Regulations For Workspalces 2 & 5;Compliance to Plant Safety Regulation
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Working in and around the Condenser | Irritation/bronchitis due to airborne contaminants or seroius respiratory problems | Health | Working in and around the precipitators | Irritation/bronchitis due to airborne contaminants or seroius respiratory problems | Administration: Medical surveillance, person job specifications, gas testing, education and training. Task Risk Assessment.PPE: Dust mask. | 4 | B | III | General Mechinary Regulations2&3; Compliance to Plant Safety Regulation:Environmental Regulations For Workplace 2&5
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Noise from plant | NIHL | Health | Noise from plant | NIHL | Administration: Medical surveillance, person job specifications, education and training. PPE: Hearing protection. | 4 | B | III | Noise-Induced Hearing Loss, reg 3,9 &10
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Working at height when working inside/climbing up the cat ladder | Falling from heights - fatality | Safety | Working at height when working inside precipitators. | Falling from heights - fatality | Engineering: Guarding/barriers/rails. Administrative: Medical surveillance, person job specifications, education and training, Task Risk Assessment,permit to work. PPE: Fall protection. | 4 | B | III | Construction Regulations 2014 reg 10;Driven Machinery Regulations 18.,Compliance to Plant Safety Regulation
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Exposure to noise | NIHL | Health | Noise from plant | NIHL | Administration: Medical surveillance, person job specifications, education and training. PPE: Hearing protection. | 4 | B | III | Noise-Induced Hearing Loss Regulations 3,9 &10
Unit 1-6 Main & BFPT Condenser High Pressure Jet Washing during various outages, running and opportunity maintenance for period of five (5) years on the basis of as and when required at Lethabo Power Station | Yes | Toxic gas inside confined space | Exposure to toxic gas - asphyxiation | Health | Toxic gas inside confined space | Exposure to toxic gas - asphyxiation | Administrative: Plant safety regulations, medical surveillance, person job specifications, education and training,gas test monitoring. PPE: Respiratory equipment. | 4 | B | III | Regulation For Hazardous Chemical Agents 6,7, 8 ;Compliance to Eskom Plant Safety Regulation
Night time travelling | No | Lack of rest | Motor Vehicle Accident-Injuries | Safety | Lack of rest | Motor Vehicle Accident-Injuries | Administrative: Strict adherence to rest period, if can't drive make use of Transport Service Provider( Batloung) | 4 | B | III | Basic Conditions of Employment Act, Section 7,9,10,11,14,15&17
Night time travelling | No | Animals on the road | Motor Vehicle Accident-Injuries | Safety | Animals on the road | Motor Vehicle Accident-Injuries | Engineering: Road worthiness vehicleAdministrative: Inpections on the car,. (Lights working) Training. Risk Assessment, Being vigilant, adherence to speed limit. | 4 | B | III | National Roads Traffic Act 93 of 1996, sections 58,59,60,63,64,65
Travelling | Yes | Bad road conditions | Motor Vehicle Accident-Injuries | Safety | Bad road conditions | Motor Vehicle Accident-Injuries | Engineering: Vehicle roadworthiness,(Lights working); Administrative: Safety awareness, vehicle inspection, adherence to road signs. Travelling risk assessment | 4 | B | III | National Roads Traffic Act 93 of 1996, sections 58,59,60,63,64,65
Travelling | Yes | Speeding | MVA-fatality | Safety | Speeding | MVA-fatality | Engineering: Vehicle roadworthiness,(Lights working), on-board computer speed control; Administrative: Safety awareness, vehicle inspection, adherence to road signs. Travelling risk assessment | 4 | B | III | National Roads Traffic Act 93 of 1996, sections 58,59,60,63,64,66
Travelling | Yes | Rural/dangerous roads | High jacking-Injuries | Safety | Rural/dangerous roads | High jacking-Injuries | Engineering: Emergency panic button,Administrative: safety awareness, travelling risk assessment, Always being cautious on the road. | 4 | B | III | National Roads Traffic Act 93 of 1996, sections 58,59,60,63,64,67
Walking to and from site | Yes | Uneven road/floor surfaces | Trip and fall - injury | Safety | Uneven road/floor surfaces | Trip and fall - injury | Administrative: Safety awareness, 3 point contact, Task risk assessmnet | 4 | B | III | Occupational Health & Safety Act, sec 8
Walking to and from site | Yes | Slippery road/floor surfaces | Slip and fall - injury | Safety | Slippery road/floor surfaces | Slip and fall - injury | Administrative: Safety awareness, 3 point contact in case of using stairs, task risk assessmnet, Being careful of your surrounding | 4 | B | III | Occupational Health & Safety Act, sec 8
Walking to and from site | Yes | Exposure to Open manholes | Falling - Body Injuries,Fractures | Safety | Exposure to Open manholes | Falling - Body Injuries,Fractures | Engineering: Solid barricading if opened.,Administrative: Safety Awareness, Task risk assessmnet, Being carefulof your surrounding | 4 | B | III | Occupational Health & Safety Act, sec 8
Driving | Yes | Use of cell phone while driving | Distraction leading to Accident | Safety | Use of cell phone while driving | MVA-Injuries | Engineering: Bleutooth device installed,Installation of vehicle cameras systems. Administrative: training/awareness.Task risk assessment.. | 4 | B | III | Eskom's Vehicle & Drivers Safety Manegement Procedure 240-62946386, clause 3.4.20

## Risk matrix
RISK MATRIX
Consequences | 6 | I | I | I | I | I
| 5 | II | II | II | I | I
| 4 | III | III | II | I | I
| 3 | IV | III | II | II | I
| 2 | IV | IV | III | II | II
| 1 | IV | IV | III | III | III
|  | A | B | C | D | E
Likelihood
| Priority | Risk ranking | Action required
| I | Very high
| II | High
| III | Medium | Action required, possibly at administrative level.
| IV | Low | Minor or no action required.

## Likelihood rating
Likelihood criteria
| Score | Descriptor | Safety | Occupational hygiene
|  |  |  | Exposure | Probability of exceeding OEL
| A | Highly unlikely | § More than a “100 year event” | Rare (once a year) | No exposure (or exposure < 10% of OEL)
§ Exceptionally unlikely, even in the long-term future
§ < 5% probability.
| B | Unlikely | § Could occur in “years to decades” | Short periods of time, a few times per day/ intermittent (once in six months, three months, or a month) | Low exposure (< 50% of OEL)
§ May occur but not anticipated
§ ≥ 5% and < 20% probability.
| C | Possible | § Could occur within “months to years” | Continuous for between one and two hours (often/ weekly) | Moderate exposure (chronic exposure > 50% of OEL or acute exposure ≥ OEL)
§ May occur shortly but a distinct probability it will not, or ≥ 20% and < 70% probability.
| D | Likely | § Could occur within “weeks to months” | Continuous for between two and four hours (frequent/daily) | High exposure (chronic exposure > OEL, or exposure exceeding OEL-STEL)
§ Balance of probability will occur
§ ≥ 70% and < 90% probability.
| E | Unavoidable | § Could occur within “days to weeks” | Continuous for eight-hour shift | Very high exposure (chronic exposure > 2 x OEL or exposure exceeding OEL-C)
§ Impact is imminent
§ ≥ 90% probability.

## Consequence rating
Consequence criteria
Consequence rating | Description | [7 empty] | R | Safety | 1 | A | Fully effective | I
| Health and Safety | [7 empty] | N | Health | 2 | B | Mostly effective | II
1 | No injuries or health effects(near misses) | [9 empty] | 3 | C | Mostly ineffective | III
2 | First-aid treatment case, and temporary discomfort case | [9 empty] | 4 | D | None | IV
3 | Medical treatment case; occupational disease with reversible/non-permanent effect | [9 empty] | 5 | E
4 | Lost Time Injury. Irreversible health effects/occupational disease with permanent consequence | [9 empty] | 6
5 | Fatality or life threatening health effects | Consequences | 6 | III | II | I | I | I
6 | Multiple fatalities |  | 5 | III | II | II | I | I
|  |  | 4 | IV | III | II | I | I
|  |  | 3 | IV | III | II | II | I
|  |  | 2 | IV | IV | III | II | II
|  |  | 1 | IV | IV | III | III | III
|  |  |  | A | B | C | D | E
Likelihood