## Risk Assessment
| Project Risk Assessment |  |  |  | Unique Identifier | 240-51017565
[5 empty] | Revision | Rev.0
[5 empty] | Revision Date | 2025-08-01
Distribution Division
Risk # | Hazard | Risk | Consequences | Existing Control Measures | Control Owners | Consequence Rating | Likelihood Rating | Risk Rating
1 | Ineffective incident management | Incidents root causes not identified and mitigated | Reoccurence of incidents | Induction, Contractor SHE Plan | Induction, Contrctor SHE Plan | 4 | 3 | II
2 | Uneven surfaces | Slips, trips and falls | Injury | Induction, Contractor SHE Plan | Induction, Contrctor SHE Plan | 5 | 2 | II
3 | Manual handling of heavy objects / material | Back, and finger injuries | Serious Injury | Induction, Contractor SHE Plan | Eskom and Contractors | 5 | 3 | II
4 |  |  |  | Induction, Contractor SHE Plan | Eskom and Contractors | 5 | 3 | II
5 | Motor Vehicle Accidents | Damage to property, injuries, liability | Injuries, fatalities | Vehicle Mangen Procedure,Induction,Contractor SHE Plan | Eskom and Contractors | 5 | 3 | II
6 | Failure to manage emergencies | Inability to respond promptely and effectively to emergencies; Industrial actions | Fire, burns,legal contravention;delivery failure resulting in lack of electricity supply | Induction, Contractor SHE Plan | Eskom and Contractors | 5 | 3 | II
7 | Failure to appoint as per the OHSAct and legal requirements | Management and employees responsibilities, acountability not clearly defined and understood | Legal contravention | Induction, Contractor SHE Plan | Eskom and Contractors | 4 | 2 | II
8 | Lack of HSE training and awareness of employees | Employees not aware of hazards related to the scope of work | Fatalities and serious injuries | Induction, Contractor SHE Plan | Eskom and Contractors | 4 | 2 | II
9 | Poor communication of Eskom requirements between the main contractor and subcontractor | Subcontractor not complying to Eskom requirements | Fatalities, serious injuries, damage to equipment and plant | SHE specification | Contractor | 5 | 2 | II
Compiled by:
Name: | Signatures:
Brenda Matsie