NEC3 Engineering & Construction Contract

| Between | ESKOM HOLDINGS SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | (Reg No. ___________ ) |  |
| for | Design, supply, installation, and commissioning capability of the total rooftop PV solution for Single phase customers from 20 – 60 Amps for the Distribution Division for the period of 3 years. |  |
| Contents: |  |  |
| Part C1 | Agreements & Contract Data |  |
| Part C2 | Pricing Data |  |
| Part C3 | Scope of Work |  |
| Part C4 | Site Information |  |
| TENDER NO. | E2392DXGOU |  |

Part C1: Agreements & Contract Data

| Contents: |  |  |
| --- | --- | --- |
| C1.1 | Form of Offer and Acceptance [to be inserted from Returnable Documents at award stage] |  |
| C1.2a | Contract Data provided by the Employer |  |
| C1.2b | Contract Data provided by the Contractor [to be inserted from Returnable Documents at award stage] |  |
| C1.3 | Proforma Guarantees |  |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

Design, supply, installation, and commissioning capability of the total rooftop PV solution for Single phase customers from 20 – 60 Amps for the Distribution Division for the period of 3 years.

The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender.

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

Delete the Options which do not apply

| Options B | The offered total of the Prices exclusive of VAT is | Rates Based Contract |
| --- | --- | --- |
|  | Sub total | Rates Based Contract |
|  | Value Added Tax @ 15% is | Rates Based Contract |
|  | The offered total of the amount due inclusive of VAT is | Rates Based Contract |
|  | (in words) |  |

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |
| Tenderer’s CIDB registration number (if applicable) |  |  |  |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: Works Information

Part C4		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy signed between them of this document, including the Schedule of Deviations (if any).

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Employer in writing of any reason why he cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.

## Schedule of Deviations to be completed by the Employer prior to contract award

Note:

- This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 ECC3 Contract Data

# Part one - Data provided by the Employer.

Completion of the data in full, according to the Options chosen, is essential to create a complete contract.

| ## Clause |  | ## Statement | ## Data |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | ## General |  |  |  |  |  |  |  |  |  |  |
|  |  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A: Priced contract with activity schedule |  |  |  |  |  |  |  |  |  |
|  |  | dispute resolution Option | W1: Dispute resolution procedure |  |  |  |  |  |  |  |  |  |
|  |  | and secondary Options |  |  |  |  |  |  |  |  |  |  |
|  |  |  | X1: Price adjustment for inflation |  |  |  |  |  |  |  |  |  |
|  |  |  | X2 Changes in the law |  |  |  |  |  |  |  |  |  |
|  |  |  | X3: Multiple currencies (If applicable) |  |  |  |  |  |  |  |  |  |
|  |  |  | X4: Parent company guarantee (If applicable) |  |  |  |  |  |  |  |  |  |
|  |  |  | X5: Sectional Completion |  |  |  |  |  |  |  |  |  |
|  |  |  | X7: Delay damages |  |  |  |  |  |  |  |  |  |
|  |  |  | X13: Performance Bond (If applicable) |  |  |  |  |  |  |  |  |  |
|  |  |  | X15: Limitation of Contractor’s liability for design to reasonable skill and care |  |  |  |  |  |  |  |  |  |
|  |  |  | X16: Retention |  |  |  |  |  |  |  |  |  |
|  |  |  | X17: Low performance damages |  |  |  |  |  |  |  |  |  |
|  |  |  | X18: Limitation of liability |  |  |  |  |  |  |  |  |  |
|  |  |  | Z: Additional conditions of contract |  |  |  |  |  |  |  |  |  |
|  |  | of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |  |  |  |  |  |  |
| 10.1 |  | The Employer is (Name): | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state-owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |  |  |  |  |  |  |
|  |  | Address | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |  |  |  |  |
| 10.1 |  | The Project Manager is: (Name) | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | Address | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | Tel | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | Fax | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | e-mail | To be advised |  |  |  |  |  |  |  |  |  |
| 10.1 |  | The Supervisor is: (Name) | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | Address | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | Tel No. | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | Fax No. | To be advised |  |  |  |  |  |  |  |  |  |
|  |  | e-mail | To be advised |  |  |  |  |  |  |  |  |  |
| 11.2(13) |  | The works are | Design, supply, installation, and commissioning capability of the total rooftop PV solution for Single phase customers from 20 – 60 Amps. |  |  |  |  |  |  |  |  |  |
| 11.2(14) |  | The following matters will be included in the Risk Register | 1. Resistance from Consumers 2. External Security Threats 3. Theft and vandalism 4. Technological Failures |  |  |  |  |  |  |  |  |  |
| 11.2(15) |  | The boundaries of the site are | All projects to be executed in terms of this contract will be executed at various sites across the Eskom Distribution Division. |  |  |  |  |  |  |  |  |  |
| 11.2(16) |  | The Site Information is in | Part 4: Site Information |  |  |  |  |  |  |  |  |  |
| 11.2(19) |  | The Works Information is in | Part 3: Scope of Work and all documents and drawings to which it makes reference. |  |  |  |  |  |  |  |  |  |
| 12.2 |  | The law of the contract is the law of | the Republic of South Africa |  |  |  |  |  |  |  |  |  |
| 13.1 |  | The language of this contract is | English |  |  |  |  |  |  |  |  |  |
| 13.3 |  | The period for reply is | One [1] week |  |  |  |  |  |  |  |  |  |
| ## 2 |  | ## The Contractor's main responsibilities | Data required by this section of the core clauses is provided by the Contractor in Part 2 and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |  |  |
| ## 3 |  | ## Time |  |  |  |  |  |  |  |  |  |  |
| 11.2(3) |  | The completion date for the whole of the works is | 3 Year period |  |  |  |  |  |  |  |  |  |
| 11.2(9) |  | The key dates and the conditions to be met are: | Condition to be met |  |  |  |  |  |  | key date |  |  |
|  |  |  | 1 | Any key date and conditions will be specified in the Project Specific Agreement for any project executed in terms of this contract |  |  |  |  |  |  |  |  |
| 30.1 |  | The access dates are: | Part of the Site |  |  |  |  |  | Date |  |  |  |
|  |  |  | 1 | Access dates will be specified in the Project Specific Agreement for any project executed in terms of this contract |  |  |  |  |  |  |  |  |
| 31.1 |  | The Contractor is to submit a first programme for acceptance within | One [1] week of the Contract Date. |  |  |  |  |  |  |  |  |  |
| 31.2 |  | The starting date is | To be advised |  |  |  |  |  |  |  |  |  |
| 32.2 |  | The Contractor submits revised programmes at intervals no longer than | [4] weeks. |  |  |  |  |  |  |  |  |  |
| 35.1 |  | The Employer is not willing to take over the works before the Completion Date. |  |  |  |  |  |  |  |  |  |  |
| ## 4 |  | ## Testing and Defects |  |  |  |  |  |  |  |  |  |  |
| 42.2 |  | The defects date is | 52 weeks after Completion of the whole of the works. |  |  |  |  |  |  |  |  |  |
| 43.2 |  | The defect correction period is | Within one week upon notification of defect |  |  |  |  |  |  |  |  |  |
| ## 5 |  | ## Payment |  |  |  |  |  |  |  |  |  |  |
| 50.1 |  | The assessment interval is | between the 15th and 20th day of each successive month. |  |  |  |  |  |  |  |  |  |
| 51.1 |  | The currency of this contract is the | South African Rand. |  |  |  |  |  |  |  |  |  |
| 51.2 |  | The period within which payments are made is | For contracts valued below R50 000 000 (Fifty Million Rand) including VAT, Eskom is committed to paying Suppliers within 30 days of submission of a tax compliant invoice with a GR number to Eskom Financial Shared Services. For contracts valued above R50 000 000 (Fifty Million Rand) including VAT, Eskom is committed to paying suppliers within 60 days of submission of a tax compliant invoice with a GR number to Eskom Financial Shared Services. |  |  |  |  |  |  |  |  |  |
| 51.4 |  | The interest rate is | the publicly quoted prime rate of interest (calculated on a 365-day year) charged from time to time by the Standard Bank of South Africa Limited (as certified, in the event of any dispute, by any manager of such bank, whose appointment it shall not be necessary to prove) for amounts due in Rands and |  |  |  |  |  |  |  |  |  |
| ## 6 |  | ## Compensation events |  |  |  |  |  |  |  |  |  |  |
| 60.1(13) |  | The place where weather is to be recorded is: | The established site |  |  |  |  |  |  |  |  |  |
|  |  | The weather measurements to be recorded for each calendar month are, | the cumulative rainfall (mm) |  |  |  |  |  |  |  |  |  |
|  |  |  | the number of days with rainfall more than 10 mm |  |  |  |  |  |  |  |  |  |
|  |  |  | the number of days with minimum air temperature less than 0 degrees Celsius |  |  |  |  |  |  |  |  |  |
|  |  |  | the number of days with snow lying at 09:00 hours South African Time |  |  |  |  |  |  |  |  |  |
|  |  |  | and these measurements: |  |  |  |  |  |  |  |  |  |
|  |  | The weather measurements are supplied by | The nearest weather station of the South African Weather Service to the site |  |  |  |  |  |  |  |  |  |
|  |  | The weather data are the records of past weather measurements for each calendar month which were recorded at: | The nearest weather station of the South African Weather Service to the site |  |  |  |  |  |  |  |  |  |
|  |  | and which are available from: | the South African Weather Bureau and included in Annexure A to this Contract Data provided by the Employer |  |  |  |  |  |  |  |  |  |
| ## 7 |  | ## Title | As per the terms and conditions of the NEC3 Engineering and Construction Contract, April 2013 (ECC3) |  |  |  |  |  |  |  |  |  |
| ## 8 |  | ## Risks and insurance |  |  |  |  |  |  |  |  |  |  |
| 80.1 |  | These are additional Employer's risks | None |  |  |  |  |  |  |  |  |  |
| ## 9 |  | ## Termination | As per the terms and conditions of the NEC3 Engineering and Construction Contract, April 2013 (ECC3). |  |  |  |  |  |  |  |  |  |
| ## 10 |  | ## Data for main Option clause |  |  |  |  |  |  |  |  |  |  |
| B |  | Priced contract with bill of quantities |  |  |  |  |  |  |  |  |  |  |
| 60.6 |  | The method of measurement is | as stated in Part C2.1, Pricing Assumptions. |  |  |  |  |  |  |  |  |  |
| ## 11 |  | ## Data for Option W1 |  |  |  |  |  |  |  |  |  |  |
| W1.1 |  | The Adjudicator is | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |  |  |  |  |  |  |
| W1.2(3) |  | The Adjudicator nominating body is: | the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body. |  |  |  |  |  |  |  |  |  |
| W1.4(2) |  | The tribunal is: | arbitration. |  |  |  |  |  |  |  |  |  |
| W1.4(5) |  | The arbitration procedure is | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |  |  |
|  |  | The place where arbitration is to be held is | [Sandton] South Africa |  |  |  |  |  |  |  |  |  |
|  |  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |  |  |
| ## 12 |  | ## Data for secondary Option clauses |  |  |  |  |  |  |  |  |  |  |
| X1 |  | Price adjustment for inflation |  |  |  |  |  |  |  |  |  |  |
| X1.1(a) |  | The base date for indices is | One month prior to tender closing date. |  |  |  |  |  |  |  |  |  |
| X1.1(c) |  | The proportions used to calculate the Price Adjustment Factor are: | proportion |  | linked to index for |  |  | Index prepared by |  |  |  |  |
|  |  |  | 0. [●] |  | [●] |  |  | [●] |  |  |  |  |
|  |  |  | 0. [●] |  | [●] |  |  | [●] |  |  |  |  |
|  |  |  | 0. [●] |  | [●] |  |  | [●] |  |  |  |  |
|  |  |  | 0. [●] |  | [●] |  |  | [●] |  |  |  |  |
|  |  |  | 0. [●] |  | [●] |  |  | [●] |  |  |  |  |
|  |  |  | [●] |  | non-adjustable |  |  |  |  |  |  |  |
|  |  | Total CPA will be negotiated with the supplier’s prior contract award, to ensure alignment to Eskom CPA guideline. | 1.00 |  |  |  |  |  |  |  |  |  |
| X2 |  | Changes in the law | As per the terms and conditions of the NEC3 Engineering and Construction Contract, April 2013 (ECC3). |  |  |  |  |  |  |  |  |  |
| X3 |  | Multiple currencies |  |  |  |  |  |  |  |  |  |  |
| X3.1 |  | The Employer will pay for these items or activities in the currencies stated | Items & activities |  |  |  | Other currency |  |  |  |  | Maximum payment in other currency |
|  |  | To be provided by the Tenderer, if any. | [●] |  |  |  | [●] |  |  |  |  | [●] |
|  |  |  | [●] |  |  |  | [●] |  |  |  |  | [●] |
|  |  |  | [●] |  |  |  | [●] |  |  |  |  | [●] |
|  |  |  | [●] |  |  |  | [●] |  |  |  |  | [●] |
| X3.1 |  | The exchange rates are those published in | [●] on [●] (date) |  |  |  |  |  |  |  |  |  |
|  |  | Note: | The items & activities will be paid in the other currency - to a foreign Bank account nominated by the Contractor - to a valid SARB approved CFC account in South Africa - in accordance with an alternative payment method agreed with the Employer before the Contract Date. It should be noted that all commodities and foreign currencies exposure in this contract will be hedged in line with the Eskom Foreign exchange Policy and procedure via Eskom Treasury. |  |  |  |  |  |  |  |  |  |
| X4 |  | Parent company guarantee | This will only be applicable should the Financial Analysis report recommend that the parent company guarantee be obtained. If a parent company owns the Contractor, the Contractor gives to the Employer a guarantee by the parent company of the Contractor’s performance in the form set out in the Works Information. If the guarantee was not given by the Contract Date, it is given to the Employer within four weeks of the Contract Date. |  |  |  |  |  |  |  |  |  |
| X5 |  | Sectional Completion |  |  |  |  |  |  |  |  |  |  |
| X5.1 |  | The completion date for each section of the works is: | Section |  | Description |  |  |  |  |  | Completion date |  |
|  |  |  |  |  | The completion date for each section of the work will be specified in the Project Specific Agreement for any project executed in terms of this contract. |  |  |  |  |  |  |  |
| X5 & X7 |  | Sectional Completion and delay damages used together |  |  |  |  |  |  |  |  |  |  |
| X7.1 X5.1 |  | Delay damages for late Completion of the sections of the works are: | The delay damage for each section of the work will be specified in the Project Specific Agreement for any project executed in terms of this contract and will be relevant to the specific project being executed. |  |  |  |  |  |  |  |  |  |
| X13 |  | Performance bond |  |  |  |  |  |  |  |  |  |  |
| X13.1 |  | The amount of the performance bond is | To be advised at contract award stage. This will only be applicable should the Financial Analysis report recommend that the Performance bond be obtained. |  |  |  |  |  |  |  |  |  |
| X15 |  | Limitation of the Contractor’s liability for his design to reasonable skill & care | The Contractor is not liable for Defects in the works due to his design so far as he proves that he used reasonable skill and care to ensure that his design complied with the Works Information. If the Contractor corrects a Defect for which he is not liable under this contract it is a compensation event. |  |  |  |  |  |  |  |  |  |
| X16 |  | Retention (not used with Option F) |  |  |  |  |  |  |  |  |  |  |
| X16.1 |  | The retention free amount is | Items where no retention will be held includes material purchases by Contractors, transport costs, and preliminaries and generals. |  |  |  |  |  |  |  |  |  |
|  |  | The retention percentage is | 5% (Only applicable for Labour Purchase Order) |  |  |  |  |  |  |  |  |  |
| X17 |  | Low performance damages |  |  |  |  |  |  |  |  |  |  |
| X17.1 |  | The amounts for low performance damages are: | Amount |  |  | Performance level |  |  |  |  |  |  |
|  |  |  | Refer to Annexure A |  |  | Refer To Annexure A |  |  |  |  |  |  |
| X18 |  | Limitation of liability |  |  |  |  |  |  |  |  |  |  |
| X18.1 |  | The Contractor’s liability to the Employer for indirect or consequential loss is limited to: | R0.0 (zero Rand) |  |  |  |  |  |  |  |  |  |
| X18.2 |  | For any one event, the Contractor’s liability to the Employer for loss of or damage to the Employer’s property is limited to: | the amount of the deductibles relevant to the event |  |  |  |  |  |  |  |  |  |
| X18.3 |  | The Contractor’s liability for Defects due to his design which are not listed on the Defects Certificate is limited to | The greater of - the total of the Prices at the Contract Date and - the amounts excluded and unrecoverable from the Employer’s assets policy for correcting the Defect (other than the resulting physical damage which is not excluded) plus the applicable deductible as at contract date. |  |  |  |  |  |  |  |  |  |
| X18.4 |  | The Contractor’s total liability to the Employer for all matters arising under or in connection with this contract, other than excluded matters, is limited to: | the total of the Prices other than for the additional excluded matters. The Contractor’s total liability for the additional excluded matters is not limited. The additional excluded matters are amounts for which the Contractor is liable under this contract for - Defects due to his design which arise before the Defects Certificate is issued, - Defects due to manufacture and fabrication outside the Site, - loss of or damage to property (other than the works, Plant and Materials), - death of or injury to a person and - infringement of an intellectual property right. |  |  |  |  |  |  |  |  |  |
| X18.5 |  | The end of liability date is | (i) Seven years after the defects date for latent Defects and (ii) the date on which the liability in question prescribes in accordance with the Prescription Act No. 68 of 1969 (as amended or in terms of any replacement legislation) for any other matter. A latent Defect is a Defect which would not have been discovered on reasonable inspection by the Employer or the Supervisor before the defects date, without requiring any inspection not ordinarily carried out by the Employer or the Supervisor during that period. If the Employer or the Supervisor do undertake any inspection over and above the reasonable inspection, this does not place a greater responsibility on the Employer or the Supervisor to have discovered the Defect. |  |  |  |  |  |  |  |  |  |
| Z |  | The Additional conditions of contract are | Z1 to Z15 always apply. Z16 Intellectual Property – OEM owning Intellectual Property. |  |  |  |  |  |  |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |  |  |  |  |  |  |
| Z1.1 | The Contractor does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Contractor cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |  |  |  |  |  |  |
| Z2.1 | If the Contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Project Manager within two weeks of the Contract Date of the key person who has the authority to bind the Contractor on their behalf. |  |  |  |  |  |  |  |  |  |  |  |
| Z2.3 | The Contractor does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Contractor in writing. |  |  |  |  |  |  |  |  |  |  |  |
| Z3 |  | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |  |  |  |  |
| Z3.1 |  | Where a change in the Contractor’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Contractor’s B-BBEE status, the Contractor notifies the Employer within seven days of the change. |  |  |  |  |  |  |  |  |  |  |
| Z3.2 |  | The Contractor is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Project Manager within thirty days of the notification or as otherwise instructed by the Project Manager. |  |  |  |  |  |  |  |  |  |  |
| Z3.3 |  | Where, as a result, the Contractor’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Contractor’s obligation to Provide the Works. |  |  |  |  |  |  |  |  |  |  |
| Z3.4 |  | Failure by the Contractor to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are P1, P2 and P3 as stated in clause 92, and the amount due is A1 and A3 as stated in clause 93. |  |  |  |  |  |  |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |  |  |  |  |  |  |
| Z4.1 | The Contractor does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Contractor, enters the public domain or to information which was already in the possession of the Contractor at the time of disclosure (evidenced by written records in existence at that time). Should the Contractor disclose information to Others in terms of clause 25.1, the Contractor ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.2 | If the Contractor is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Project Manager. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.3 | In the event that the Contractor is, at any time, required by law to disclose any such information which is required to be kept confidential, the Contractor, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Contractor may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the works or any portion thereof, in the course of Providing the Works and after Completion, requires the prior written consent of the Project Manager. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.5 | The Contractor ensures that all his subcontractors abide by the undertakings in this clause. |  |  |  |  |  |  |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, the Project Manager, the Supervisor, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |  |  |  |  |
| Z6 |  | Health, safety and the environment: Add to core clause 27.4 |  |  |  |  |  |  |  |  |  |  |
| Z6.1 |  | The Contractor undertakes to take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the Contractor: - accepts that the Employer may appoint him as the “Principal Contractor” (as defined and provided for under the Construction Regulations 2014 (promulgated under the Occupational Health & Safety Act 85 of 1993) (“the Construction Regulations”) for the Site; - warrants that the total of the Prices as at the Contract Date includes a sufficient amount for proper compliance with the Construction Regulations, all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for in this contract and generally for the proper maintenance of health & safety in and about the execution of works; and - undertakes, in and about the execution of the works, to comply with the Construction Regulations and with all applicable health & safety laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |  |  |  |
| Z6.2 |  | The Contractor, in and about the execution of the works, complies with all applicable environmental laws and regulations and rules, guidelines and procedures otherwise provided for under this contract and ensures that his Subcontractors, employees and others under the Contractor’s direction and control, likewise observe and comply with the foregoing. |  |  |  |  |  |  |  |  |  |  |
| Z7 | Provision of a Tax Invoice and interest. Add to core clause 51 |  |  |  |  |  |  |  |  |  |  |  |
| Z7.1 | Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice in accordance with the Employer's procedures stated in the Works Information, showing the amount due for payment equal to that stated in the payment certificate. |  |  |  |  |  |  |  |  |  |  |  |
| Z7.2 | If the Contractor does not provide a tax invoice in the form and by the time required by this contract, the time by when the Employer is to make a payment is extended by a period equal in time to the delayed submission of the correct tax invoice. Interest due by the Employer in terms of core clause 51.2 is then calculated from the delayed date by when payment is to be made. |  |  |  |  |  |  |  |  |  |  |  |
| Z7.3 | The Contractor (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |  |  |  |  |
| Z8 | Notifying compensation events |  |  |  |  |  |  |  |  |  |  |  |
| Z8.1 | Delete from the last sentence in core clause 61.3, “unless the Project Manager should have notified the event to the Contractor but did not”. |  |  |  |  |  |  |  |  |  |  |  |
| Z9 | Employer’s limitation of liability |  |  |  |  |  |  |  |  |  |  |  |
| Z9.1 | The Employer’s liability to the Contractor for the Contractor’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |  |  |  |  |
| Z9.2 | The Contractor’s entitlement under the indemnity in 83.1 is provided for in 60.1(14) and the Employer’s liability under the indemnity is limited. |  |  |  |  |  |  |  |  |  |  |  |
| Z10 | Termination: Add to core clause 91.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |  |  |  |  |
| Z10.1 | or had a business rescue order granted against it. |  |  |  |  |  |  |  |  |  |  |  |
| Z11 | Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |  |  |  |  |  |
| Z11.1 | If the amount due for the Contractor’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Contractor’s obligation to Provide the Works using the same procedures and payment on termination as those applied for reasons R1 to R15 or R18 stated in the Termination Table. |  |  |  |  |  |  |  |  |  |  |  |

| Z12 | Ethics |  |
| --- | --- | --- |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| Affected Party |  | means, as the context requires, any party, irrespective of whether it is the Contractor or a third party, such party’s employees, agents, or Subcontractors or Subcontractor’s employees, or any one or more of all of these parties’ relatives or friends, |
| Coercive Action |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |
| Collusive Action |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |
| Committing Party |  | means, as the context requires, the Contractor, or any member thereof in the case of a joint venture, or its employees, agents, or Subcontractor or the Subcontractor’s employees, |
| Corrupt Action |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |
| Fraudulent Action |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |
| Obstructive Action |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |
| Prohibited Action |  | means any one or more of a Coercive Action, Collusive Action Corrupt Action, Fraudulent Action or Obstructive Action. |
| Z12.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |
| Z12.2 | The Employer may terminate the Contractor’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Contractor did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Contractor’s obligation to Provide the Services for this reason. |  |
| Z12.3 | If the Employer terminates the Contractor’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |
| Z12.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Contractor ensures that the Committing Party co-operates fully with an investigation. |  |
| Z13 | Insurance |  |
| Z 13.1 | Replace core clause 84 with the following: |  |

| Insurance cover | 84 |  |
| --- | --- | --- |
|  | 84.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |
|  | 84.2 | The Contractor provides the insurances stated in the Insurance Table A. |
|  | 84.3 | The insurances provide cover for events which are at the Contractor’s risk from the starting date until the earlier of Completion and the date of the termination certificate. |
|  |  | ### INSURANCE TABLE A Insurance against; Minimum amount of cover or minimum limit of indemnity. Loss of or damage to the works, Plant and Materials; The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance. Loss of or damage to Equipment; The replacement cost. Liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract; Loss of or damage to property Employer’s property The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance Other property The replacement cost Bodily injury to or death of a person The amount required by applicable law. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law. |
| Z 13.2 |  | Replace core clause 87 with the following: The Employer provides the insurances stated in the Insurance Table B. |
|  |  | - INSURANCE TABLE B Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |

| Z14 | Nuclear Liability |  |
| --- | --- | --- |
| Z14.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa and is the holder of a nuclear licence in respect of the KNPS. |  |
| Z14.2 | The Employer is solely responsible for and indemnifies the Contractor or any other person against any and all liabilities which the Contractor or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Contractor or any other person or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.3 | Subject to clause Z14.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Contractor or any other person, or the presence of the Contractor or that person or any property of the Contractor or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |
| Z14.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |
| Z14.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |
| Z15 | Asbestos |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |
| AAIA |  | means approved asbestos inspection authority. |
| ACM |  | means asbestos containing materials. |
| AL |  | means action level, i.e., a level of 50% of the OEL, i.e., 0.1 regulated asbestos fibres per ml of air measured over a 4-hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |
| Ambient Air |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |
| Compliance Monitoring |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| OEL |  | means occupational exposure limit. |
| Parallel Measurements |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |
| Safe Levels |  | Means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |
| Standard |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |
| SANAS |  | means the South African National Accreditation System. |
| TWA |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalized to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |
| Z15.1 | The Employer ensures that the Ambient Air in the area where the Contractor will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short-term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |
| Z15.2 | Upon written request by the Contractor, the Employer certifies that these conditions prevail. All measurements and reporting are affected by an independent, competent, and certified occupational hygiene inspection body, i.e., a SANAS accredited, and Department of Employment and Labour approved AAIA. The Contractor may perform Parallel Measurements and related control measures at the Contractor’s expense. For the purposes of compliance, the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z15.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |
| Z15.3 | The Employer manages asbestos and ACM according to the Standard. |  |
| Z15.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented, and relevant air monitoring conducted in order to declare the area safe. |  |
| Z15.5 | The Contractor’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |
| Z15.6 | The Contractor continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |
| Z15.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |

| - Z15 | Intellectual Property – OEM owning Intellectual Property |
| --- | --- |
| “Intellectual Property” | means (a) patents, trade marks, service marks, rights in designs, trade names, trade secrets, know how, copyrights and topography rights, in each case whether registered or not; (b) applications for registration of any of them; (c) rights under licences and consents in relation to any of them; (d) all forms of protection of a similar nature or having equivalent or similar effect to any of them which may subsist anywhere in the world. |
| Z15.1 | All Intellectual Property rights, contained in any developed materials which are created by the [Contractor / Consultant / Supplier] or on behalf of the [Contractor / Consultant / Supplier], for the purposes of and in support of the provision of the [works / services / goods] vests with the [Contractor / Consultant / Supplier]. The [Contractor / Consultant / Supplier] retains the Intellectual Property rights in and to the [Contractor / Consultant / Supplier]’s Intellectual Property made by or on behalf of the [Contractor / Consultant / Supplier] as part of the [works / services / goods]. |
| Z15.2 | Any data or any other information relating to [Employer / Client / Purchaser]’s proprietary information generated from the use of the [Contractor / Consultant / Supplier]’s Background Intellectual Property, the copyright therein shall be owned by the [Employer / Client / Purchaser] (“[Employer / Client / Purchaser] IP”). |
| Z15.3 | The [Contractor / Consultant / Supplier] ensures that a copyright notice is incorporated or embossed or labelled on the [Employer / Client / Purchaser] IP, where the [Employer / Client / Purchaser] is reflected as the owner of the [Employer / Client / Purchaser] IP. |
| Z15.4 | The [Contractor / Consultant / Supplier] is obliged to provide [Employer / Client / Purchaser] IP manufacturing documents, designs, processes and/or specifications to the [Employer / Client / Purchaser] before/on the [completion date / defect state]. |
| Z15.5 | The [Contractor / Consultant / Supplier] grants to the [Employer / Client / Purchaser] and its subsidiaries, with effect from the starting date or, in the case of documents or other matters not yet in existence, with effect from the creation thereof (and notwithstanding the Completion or termination of this contract), an irrevocable, perpetual, royalty-free non-exclusive licence to use all of the IP documents provided (including, but not limited to calculations, computer programmes and other software, drawings, manuals, models and other documents of a technical nature), for any purpose whatsoever in connection with the [works / services / goods], including for the purpose of operating, repairing, maintaining, dismantling, re-assembling, refurbishing and making adjustments to all parts of the [works / services / goods] (the “Purposes”). |
| Z15.6 | The [Contractor / Consultant / Supplier] procures that each sub-[Contractor / Consultant / Supplier] executes all and any further documents and takes all and any other actions as may be required in order to give effect to this licence. |
| Z15.7 | The [Employer / Client / Purchaser] keeps confidential and does not disclose to any third party any information relating to the IP documents or use copy, or communicate to a third party, save as for the Purposes, or required by law or with the prior written consent of the [Contractor / Consultant / Supplier] which consent will not be unreasonably withheld. |
| Z15.8 | The [Employer / Client / Purchaser] agrees to keep all such information confidential and to disclose it only to its officers, directors, employees, sub-contractors, consultants, suppliers, tenderers and professional advisors who are employed in the maintenance or operation of the [works / services / goods] or for the Purposes and who: - Have a need to know (an then only to the extent that such person has a need to know); - Are aware that the confidential information should be kept confidential; - Are aware of the [Employer / Client / Purchaser]’s undertaking in relation to such information in terms of this contract; and - Have been directed by the [Employer / Client / Purchaser] to keep the information confidential and have undertaken to keep the information confidential. |
| Z15.9 | The [Employer / Client / Purchaser] retains all Intellectual Property rights in all documents made by or on behalf of the [Employer / Client / Purchaser] including all documents and requirements provided prior to or during the execution of the [works / services / goods] by the [Employer / Client / Purchaser] to the [Contractor / Consultant / Supplier]. The [Contractor / Consultant / Supplier] does not, without the written consent, of the [Employer / Client / Purchaser], copy, use or issue to a third party any of these document and requirements except for the purposes of executing the [works / services / goods]. |
| Z15.10 | Either party procures that a third party executes confidentiality undertakings not to disclose to any other third parties, any of the [Employer / Client / Purchaser]’s documents and requirements at all, in respect of the [Employer / Client / Purchaser], or the IP Documents, in respect of the [Contractor / Consultant / Supplier] and undertake to only use the IP Documents for the Purposes. |
| Z15.11 | Third Party Claims |
| Z15.11.1 | In the event of any claims being made or actions brought against the [Employer / Client / Purchaser], on the ground that the [Contractor / Consultant / Supplier] infringed any patent, trade mark, designs or copyright, the [Contractor / Consultant / Supplier] is notified thereof and at its own expense, conducts all negotiations in consultation with the [Employer / Client / Purchaser] for the settlement of the claim and litigation that may arise from such alleged infringement provided the [Employer / Client / Purchaser] does not bear any financial burden or losses. |
| Z15.11.2 | Save where the [Contractor / Consultant / Supplier] fails to take over the conduct of the negotiation or litigation within a reasonable time of the notification of the alleged infringement, the [Employer / Client / Purchaser] does not make any admission which might be prejudicial to the [Contractor / Consultant / Supplier]’s position. The [Employer / Client / Purchaser], at the request and the cost of the [Contractor / Consultant / Supplier] affords it all reasonable technical assistance that the [Employer / Client / Purchaser] is able to provide for the purpose of contesting any such claim or action. |
| Z15.11.3 | Should it be held in any such action that any such protected rights have been infringed, as definitely stated by a judgment of the court before which the action is brought, the [Contractor / Consultant / Supplier], at its own expense and in consultation with the [Employer / Client / Purchaser], either: - procures for [Employer / Client / Purchaser] the right to continue to use the affected item or design, or - replaces the said affected item or design with a non-infringing item, or - provides a design of equivalent quality or modify such affected item or design so as to make it non-infringing without affecting the quality. |
| Z15.11.4 | Notwithstanding anything contained in this contract, the foregoing sets forth the entire responsibility of [Contractor / Consultant / Supplier] with respect to claims relating to infringement. |
| Z15.11.5 | Where it is alleged that the [Employer / Client / Purchaser] has committed an infringement as intended vis-à-vis the [Contractor / Consultant / Supplier] as set out in the third party intellectual property infringement clause, the [Employer / Client / Purchaser] has the same rights and obligations as the [Contractor / Consultant / Supplier], mutatis mutandis, as regards such alleged infringement. |
| Z15.11.6 | The [Contractor / Consultant / Supplier] herewith indemnifies the [Employer / Client / Purchaser] and undertakes to keep the [Employer / Client / Purchaser] indemnified against all claims of whatsoever nature, real or imagined, which may be made against the [Employer / Client / Purchaser] arising from the infringement of any third party intellectual property rights. |

# Annexure A:	 One-in-ten-year-return weather data obtained from SA Weather Bureau for [weather station]

If weather measurements recorded within a calendar month, before the Completion Date for the Task Order and at the place stated in this Contract Data is shown to be more adverse than the normal weather amounts recorded by the South African weather services then the Contractor may notify a compensation event.

|  | Weather measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Cumulative rainfall (mm) | Number of days with rain more than 10mm | Number of days with min air temp < 0 deg.C | Number of days with snow lying at 08:00 CAT | [Other measurements if applicable] |
| January | [●] | [●] | [●] | [●] |  |
| February | [●] | [●] | [●] | [●] |  |
| March | [●] | [●] | [●] | [●] |  |
| April | [●] | [●] | [●] | [●] |  |
| May | [●] | [●] | [●] | [●] |  |
| June | [●] | [●] | [●] | [●] |  |
| July | [●] | [●] | [●] | [●] |  |
| August | [●] | [●] | [●] | [●] |  |
| September | [●] | [●] | [●] | [●] |  |
| October | [●] | [●] | [●] | [●] |  |
| November | [●] | [●] | [●] | [●] |  |
| December | [●] | [●] | [●] | [●] |  |

Only the difference between the more adverse recorded weather and the equivalent measurement given by the South African weather services will be taken into account in assessing a compensation event.

C1.2 Contract Data

# Part two - Data provided by the Contractor.

Notes to a tendering contractor:

- Please read both the NEC3 Engineering and Construction Contract (April 2013) and the relevant parts of its Guidance Notes (ECC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 156 to 158 of the ECC3 (April 2013) Guidance Notes.

- The number of the clause which requires the data is shown in the left-hand column for each statement however other clauses may also use the same data

- Where a form field like this [     ] appears, data is required to be inserted relevant to the option selected. Click on the form field once and type in the data.  Otherwise, complete by hand and in ink.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 10.1 | The Contractor is (Name): |  |  |  |  |
|  | Address |  |  |  |  |
|  | Tel No. |  |  |  |  |
|  | Fax No. |  |  |  |  |
| 11.2(8) | The direct fee percentage is | % |  |  |  |
|  | The subcontracted fee percentage is | % |  |  |  |
| 11.2(18) | The working areas are the Site and |  |  |  |  |
| 24.1 | The Contractor's key persons are: |  |  |  |  |
|  | 1 Name: |  |  |  |  |
|  | Job: |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  | 2 Name: |  |  |  |  |
|  | Job |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |  |  |  |
| 11.2(3) | The completion date for the whole of the works is |  |  |  |  |
| 11.2(14) | The following matters will be included in the Risk Register |  |  |  |  |
| 11.2(19) | The Works Information for the Contractor’s design is in: |  |  |  |  |
| 31.1 | The programme identified in the Contract Data is |  |  |  |  |
| A | Priced contract with Activity Schedule |  |  |  |  |
| 11.2(21) | The Activity Schedule is in | Part of this contract |  |  |  |
| 11.2(31) | The tendered total of the Prices is | Rates Based Contract Rates Based Contract |  |  |  |
|  | ## Data for Schedules of Cost Components | Note “SCC” means Schedule of Cost Components starting on page 60, and “SSCC” means Shorter Schedule of Cost Components starting on page 63 of ECC3 (April 2013). |  |  |  |
| A | Priced contract with Activity Schedule | Data for the Shorter Schedule of Cost Components |  |  |  |
| 41 in SSCC | The percentage for people overheads is: | % |  |  |  |
| 21 in SSCC | The published list of Equipment is the last edition of the list published by |  |  |  |  |
|  | The percentage for adjustment for Equipment in the published list is | Minus % |  |  |  |
| 22 in SSCC | The rates of other Equipment are: | Equipment | Size or capacity |  | Rate |
| 61 in SSCC | The hourly rates for Defined Cost of design outside the Working Areas are | Category of employee |  | Hourly rate |  |
|  | Note: Hourly rates are estimated ‘cost to company of the employee’ and not selling rates. |  |  |  |  |
|  | Please insert another schedule if foreign resources may also be used |  |  |  |  |
| 62 in SSCC | The percentage for design overheads is | % |  |  |  |
| 63 in SSCC | The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are: |  |  |  |  |

C1.3 Forms of Securities

- Pro formas for Bonds & Guarantees

- For use with the NEC3 Engineering & Construction Contract

The conditions of contract stated in the Contract Data Part 1 include the following Secondary Options:

Option X4:	Parent company guarantee

Option X13:	Performance Bond

Each of these secondary Options requires a bond or guarantee “in the form set out in the Works Information”.    Pro forma documents for these bonds and guarantees are provided here for convenience but are to be treated as part of the Works Information.

The organisation providing the bond / guarantee does so by copying the pro forma document onto his letterhead without any change to the text or format and completing the required details.  The completed document is then given to the Employer within the time stated in the contract.

# Pro forma Parent Company Guarantee (for use with Option X4)

(to be reproduced exactly as shown below on the letterhead of the Contractor’s Parent Company)

| Eskom Holdings SOC Ltd Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs,

## Parent Company Guarantee for Contract No

With reference to the above numbered contract made or to be made between

| Eskom Holdings SOC Ltd | (the Employer) and |
| --- | --- |
| {Insert registered name and address of the Contractor} | (the Contractor), for |
| {Insert details of the works from the Contract Data} | (the works). |

| I/We the undersigned |  |
| --- | --- |
| on behalf of the Contractor’s parent company |  |
| of physical address |  |

and duly authorised thereto do hereby unconditionally guarantee to the Employer that the Contractor shall Provide the Works in accordance with the above numbered Contract.

- If for any reason the Contractor fails to Provide the Works, we hereby agree to cause to Provide the Works at no additional cost to the Employer.

- If we fail to comply with the terms of this Deed of Guarantee, the Employer may itself procure such performance (whether or not the Agreement be formally determined).  The Employer is to notify us and we shall indemnify the Employer for any additional cost or expense it incurs.

- Our liability shall be as primary obligor and not merely as surety and shall not be impaired or discharged by reason of any arrangement or change in relationship made between the Contractor and the Employer and/or between us and Contractor; nor any alteration in the obligations undertaken by the Contractor or in the terms of the Agreement; nor any indulgence, failure, delay by you as to any matter; nor any dissolution or liquidation or such other analogous event of the Contractor.

- The Employer shall not be obliged before taking steps to enforce the terms of this Deed of Guarantee to obtain judgement against the Contractor in any court or other tribunal, to make or file any claim in liquidation (or analogous proceedings) or to seek any remedy or proceed first against the Contractor.

- This Deed of Guarantee shall be governed by and construed in accordance with the laws of the Republic of South Africa and we hereby submit to the non-exclusive jurisdiction of the High Court of South Africa.

| Signed at |  | on this |  | day of |  | 200_ |
| --- | --- | --- | --- | --- | --- | --- |

| Signature(s) |  |  |
| --- | --- | --- |
| Name(s) (printed) |  |  |
| Position in parent company |  |  |
| Signature of Witness(s) |  |  |
| Name(s) (printed) |  |  |

# Pro forma Performance Bond – Demand Guarantee (for use with Option X13)

(to be reproduced exactly as shown below on the letterhead of the Contractor’s Parent Company)

| Eskom Holdings SOC Ltd Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Performance Bond – Demand Guarantee: [Drafting Note: Name of Contractor to be inserted]

Project [  ] Contract Reference: …… [Drafting Note: Contractor contract reference number to be inserted]

- In this Guarantee the following words and expressions shall have the following meanings:-

  - “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

  - “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

  - “Contract” – means the written agreement relating to the Project, entered into between Eskom and the Contractor, on or about the [●] day of [●] 200[●] (Contract Reference No. [.]as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

  - “Contractor” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Contractor to be inserted]

  - “Eskom” - means Eskom Holdings SOC Ltd, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30].

  - “Expiry Date” - means the date on which the Defects Certificate is issued in terms of the Contract.

  - “Guaranteed Sum” - means the sum of R [●] ([●] Rand);

  - “Project” - means [insert if applicable.].

- At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

- A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

  - be signed on behalf of Eskom by a Group Executive, Divisional Executive, Senior General Manager, General Manager  or its delegate;

  - state the amount claimed (“the Demand Amount’);

  - state that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

- Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

  - is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

  - is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

- The Bank’s obligations in terms of this Guarantee:

  - shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

  - shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed, by the fact that a dispute may exist between Eskom and the Contractor.

- Eskom shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract.

- Should Eskom cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

- This Guarantee:

  - shall expire on the Expiry Date until which time it is irrevocable;

  - is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

  - shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

  - shall be regarded as a liquid document for the purpose of obtaining a court order; and

  - shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

  - Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

- The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________________________

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

Bank’s seal or stamp

Part 2: Pricing Data

ECC3 Option B

| Document reference | Title |  |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option A |  |
| C2.2 | The Activity Schedule |  |

C2.1 Pricing assumptions: Option A

- How work is priced and assessed for payment

Clause 11 in NEC3 Engineering and Construction Contract, (ECC3) Option A states:

| Identified and defined terms | 11 11.2 | (20) The Activity Schedule is the activity schedule unless later changed in accordance with this contract. |
| --- | --- | --- |
|  |  | (27) The Price for Work Done to Date is the total of the Prices for - each group of completed activities and - each completed activity which is not in a group. A completed activity is one which is without Defects which would either delay or be covered by immediately following work. |
|  |  | (30) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with this contract. |

This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date.

- Function of the Activity Schedule

Clause 54.1 in Option A states: “Information in the Activity Schedule is not Works Information or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Works Information.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Works Information”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.

- Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme which he submits for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.

- Preparing the activity schedule

Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Works Information into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Employer, in his Instructions to Tenderers or in a Tender Schedule, may have listed some items that he requires the Contractor to include in his activity schedule and be priced accordingly.

It is assumed that in preparing his activity schedule the Contractor:

- Has taken account of the guidance given in the ECC3 Guidance Notes pages 19 and 20;

- Understands the function of the Activity Schedule and how work is priced and paid for;

- Is aware of the need to link the Activity Schedule to activities shown on his programme;

- Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Works Information, as it was at the time of tender, as well as correct any Defects not caused by an Employer’s risk;

- Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices.

- Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event.

C2.2 The activity schedule

REFER TO ATTACHED ACTIVITY SCHEDULE.

Part 3: Scope of Work

| Document reference | Title |  |
| --- | --- | --- |
|  | This cover page |  |
| C3.1 | Employer’s Works Information |  |
| C3.2 | Contractor’s Works Information (insert at award stage or delete if not applicable) |  |

C3.1: Employer’s works Information

# Description of the works

## Executive overview

Eskom, in alignment with South Africa’s national energy policies and sustainability goals, is accelerating the integration of renewable energy technologies to promote cleaner, more efficient, and resilient power solutions. This initiative includes the rollout of residential solar photovoltaic (PV) systems, with or without Battery Energy Storage Systems (BESS), designed to reduce grid dependency, enhance energy reliability, and contribute to Eskom’s carbon reduction and cost-optimisation strategies.

The invitation to tender is intended to assess the potential for Eskom Distribution to develop partnerships with PV suppliers and installers as part of its initiative to provide PV solutions to consumers.

## Employer’s objectives and purpose of the works

Scope of Work

This specification applies to all residential-scale solar PV and BESS installations undertaken within Eskom’s distribution network.

The scope encompasses:

Customer feasibility study/analysis: The Contractor shall facilitate and demonstrate the ability to conduct a feasibility study which will show the potential benefits to customer. This includes the provision of a quote and high-level design.

Site Assessment: Perform a thorough site evaluation, including an assessment of the equipment arrangement.

The solutions that shall be offered include a 5kW, 8kW, 10kW and 12kW single-phase solutions.

System Design and Engineering: Development of detailed designs for 20A to 60A single-phase residential solar PV systems, including hybrid configurations with battery storage.

Structural Assessment: Contractor shall choose the mounting structure and perform a structural analysis (or request the services of a structural engineer) to verify the load bearing capacity of the roof, prepare a module allocation plan including hook positions, cable routing and laying and determine inlets and cable length.

Procurement and Supply: Provision of all materials, equipment, and components necessary for complete system functionality in accordance with approved standards and specifications.

Installation and Construction: Mechanical and electrical installation of PV modules, inverters, battery systems, wiring, and balance of plant components.

Testing and Commissioning: Verification of system performance, compliance testing, and functional commissioning in line with Eskom and regulatory requirements.

Training: Development and delivery of user and maintenance training, and submission of all associated technical documentation, drawings, and manuals.

Operation and Maintenance: Provision of post-installation support, including preventative and corrective maintenance for a defined period after commissioning.

Only customers that have internet access shall be considered for these solutions. In cases where the customer does not have internet access, the Contractor shall offer a solution to provide such services.

Customer After Sales Installation Support: To ensure optimal performance and customer satisfaction, the Contractor shall provide comprehensive installation support and after-sales service for a period as specified in the Technical Schedules following the commissioning of the rooftop PV system.

Detailed specification and user requirements are on the attached document with unique Identifier: 240-171000566 - User Requirement Specification For

Residential Solar Photovoltaic (PV) And

Battery Energy Storage Systems (BESS)

The scope of work also includes Major Equipment for Distribution Solar PV and BESS as follows:

a) Hybrid Inverters

b) Battery banks (Energy Storage System)

c) Solar Panels

d) SCADA System

e) AC Distribution Board

f) DC Distribution Board

g) HVAC system

h) Physical Security System

i) Fire Detection and Suppression System

j) Telecommunications system

Detailed specification is attached from the document with Unique Identifier: 240-171000418 - Major Equipment Requirements for Distribution Solar PV AND BESS: SSEG And Microgrids.

# Management and start up.

## Management meetings

Regular meetings of a general nature may be convened and chaired by the Project Manager as follows:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | As required | To be advised | Both parties |
| Overall Contract progress and feedback | As required | To be advised | Both parties |

Meetings of a specialist nature may be convened as specified elsewhere in this Works Information or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the works.  Records of these meetings shall be submitted to the Project Manager by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

## Documentation control

All correspondence is to be addressed to the Project Manager with a chronological numbering system.

## Health and safety risk management

The Contractor shall comply with the health and safety requirements in accordance with the Occupational Health & Safety Act, No. 85 of 1993.

## Environmental constraints and management

The Contractor shall comply with the environmental criteria and constraints in line with the Environmental Legislation and by-laws.

## Quality assurance requirements

Quality Assessment Criteria, Forms A and Form B of the QM-58 specification will be selected and completed by Eskom Representative who will identify the applicable Contractor quality requirements to be met. Form A and Form B of the QM-58 specification shall be signed by the Contractor responding to an Eskom Enquiry.

## Programming constraints

A comprehensive and fully detailed programme is to be submitted within the seven (7) days after the introductory meeting and should indicate all milestones and critical dates. This programme must first be approved by the Project Manager and must be updated on an as and when required basis by the Project Manager.

The following dates shall be clearly reflected on the programme:

- Starting and completion dates for all activities as well as relevant key dates for hold or witness points. All relevant significant activities shall be shown in order to monitor the progress in the factory/workshop.

- The programme shall also reflect a 2-week period for inspection and correcting of Defects before the completion date.

Updated programmes must be available at all meetings reflecting progress to date and the date when delivery will take place through the use of task orders.

FORMAT OF THE PROGRAM

- The Contractor shall submit his construction program in terms of the conditions of contract.

- The Contractor is to submit a revised programme for acceptance at each site meeting.

- This program shall be in the form of an approved Gantt Chart containing the following information:

- All construction activities, including milestones, initial tasks, critical path, required Outages, and target Dates. All potential risk activities should be clearly indicated on the critical path.

- Every activity on the programme will be clearly linked to labour resources and equipment required to perform the specific activity.

- Projected weekly progress on site for the entire duration of the contract.

- Completion and hand-over Dates for formal inspection by the site supervisor must be indicated.

- A column showing the daily tempo of all the construction activities must be indicated next to the activity on the programme.

- Project expenditure on a monthly basis for the entire duration of the contract.

- The following project phases and activities are minimum requirements for the programme:

- Site Establishment and Material Delivery – Lead times to be specified.

- Preparation work – Work that can be completed without the necessity of power outages.

- Outage work – Work that must be completed under outage conditions.

- Planned outages to be included in the programme.

- Contractors float to be included in the programme.

- The Contract Program will be on display in the Contractors Site Offices and will be updated weekly. In addition to the maintaining of this programme, the Contractor will report progress to the Project Manager at each site meeting or at request of the Project Manager.

- The Contractor shall also provide an organisation chart showing the personnel to be employed for the works, along with a detailed CV of all key personnel.

- Should any deviations to the program be found the Contractor shall submit a revised program to the

- Project Manager within one week of such deviations being brought to the Contractor's attention.

- The Outages must be arranged with Employer via the Outage arrangement procedures, as a pre- requisite for the acceptance of the programme by the Project Manager.

- Acceptance of any program by the Project Manager shall have no contractual status other than an indication that the Project Manager is satisfied as to the order in which the work is to be carried out, and that the Contractor undertakes to perform all work in accordance with the accepted program.

- The Project Manager retains the right to alter the accepted program should circumstances on site

- necessitate such a change.

OTHER INFORMATION TO BE SHOWN ON THE PROGRAM.

The following Statutory non-working days are included within the contract period:

- All Public Holidays for the duration of the contract.

- The programme must clearly indicate the non-working days for the entire construction period.

## Contractor’s management, supervision and key people

The Contractor is to submit an organogram showing all key people involved in the contract 7 days after contract award. All Key Personnel must be appointed in writing, must be current for the specific site and area of work and must be kept on file. This would be essential if the Contractor is a Joint Venture.

## Invoicing and payment

Within one week of receiving a payment certificate from the Project Manager in terms of core clause 51.1, the Contractor provides the Employer with a tax invoice showing the amount due for payment equal to that stated in the Project Manager’s payment certificate.

The Contractor shall address the tax invoice to Eskom Holdings SOC Ltd and include on each invoice the following information:

- Name and address of the Contractor and the Project Manager.

- The contract number and title.

- Contractor’s VAT registration number.

- The Employer’s VAT registration number 4740101508.

- Description of service provided for each item invoiced based on the Price List.

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT.

Add procedures for invoice submission and payment (e. g. electronic payment instructions)

| General Information | X |
| --- | --- |
| - No Pro-forma Invoice |  |
| - Check Vendor number against the Address and name on Tax invoice |  |
| - Insert the Vendor number on Tax invoice (Top right-hand corner) |  |
| - Bank details must be on the invoice or on an attach sheet, but it does not require a bank stamp just a letter) |  |
| - Check banking details on invoice against SAP system. If more than one banking account check bank account against banking details on invoice. If banking details not on invoice, write the bank code next to the vendor account (bank code 0002) |  |
| - Check Vendor VAT number against the vendor master. (FK03) If VAT number not on master records, prepare a list and forward to Vendor Management to check and update the vendor master records |  |
| - No fax copies of Tax invoices allowed |  |
| - No copies of Tax invoices allowed unless originally printed by the Vendor if a photocopy tax invoice, it must be an original “certified copy” (i.e., not a copy of a “certified copy” invoice) from the vendor and check in system if not previously be paid. Put stamp “not previously paid” on invoice and sign. |  |
| - Ensure that date received stamp is clear on invoice |  |
| - Stamp all Invoices with the Vat stamp, complete and sign (only when VAT is applicable) |  |
| - The stamp should not be stamped over any written information |  |
| - When scanning invoice, check the quality before linking in SAP (inboxes) |  |
| With Reference Invoices | X |
| - Goods receipt must be done (payment with reference) |  |

| - Ensure that the SAP purchase order number is clear and correct on the invoice |  |
| --- | --- |
| - GR number to be written on the Invoices |  |
| - If multiple lines on invoice write the line number of the order against the line to ensure that the processors match the correct lines (to ensure that 191100 is matched correctly) |  |

## Insurance provided by the Employer.

Refer to the embedded document below for details.

## Contract change management

The NEC contractual mechanism will be applied for changes to the Contract and supporting documents must be provided by the Contractor when required by the Employer.

## Provision of bonds and guarantees

The Employer may withhold payment of amounts due to the Contractor until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Contractor by the Project Manager to receive and accept such bond or guarantee.  Such withholding of payment due to the Contractor does not affect the Employer’s right to termination stated in this contract.

## Records of Defined Cost, payments & assessments of compensation events to be kept by the Contractor

For other compensation events, the changes to the Prices are assessed as the effect of the compensation event upon

- the actual Defined Cost of the work already done,

- the forecast Defined Cost of the work not yet done and

- the resulting amount calculated by applying the percentage for overheads and profit to the Defined Cost of the work.

Effects on Defined Cost are assessed separately for

- people,

- equipment,

- plant and materials included in the goods,

- work subcontracted by the Supplier and

- transport.

The Contractor shows how each of these effects is built up in each quotation for a compensation event.

If the compensation event arose from the Supply Manager giving an instruction, changing an earlier decision or correcting an assumption, the date which divides the work already done from the work not yet done is the

date of that communication. In all other cases, the date is the date of the notification of the compensation event.

The percentage for overheads and profit is applied to the assessed effect of the event on Defined Cost

except that it is not applied to any tax charges for

- customs clearance and

- export and import.

The date when the Project Manager instructed or should have instructed the Contractor to submit quotations

divides the work already done from the work not yet done.

## Training workshops and technology transfer

The obligation for technology transfer being included as part of this contract on both during Project execution, and for future training (Support and Maintenance). The Contractor shall provide a proposal that addresses this requirement, without the need for dedicated training infrastructure.

# Engineering and the Contractor’s design

## Employer’s design

Detailed specification and user requirements are on the attached document with unique Identifier: 240-171000566 - User Requirement Specification for Residential Solar Photovoltaic (PV) And

Battery Energy Storage Systems (BESS).

Unique Identifier: 240-171000418 - Major Equipment Requirements for Distribution Solar PV AND BESS: SSEG And Microgrids.

## Parts of the works which the Contractor is to design

Refer to the specifications stipulated under section 3.1 of the scope of work.

## Procedure for submission and acceptance of Contractor’s design

- The Contractor designs the parts of the works which the Works Information states he is to design.

- The Contractor submits the particulars of his design as the Works Information requires to the Project Manager for acceptance. A reason for not accepting the Contractor’s design is that it does not comply with either the Works Information or the applicable law.

- The Contractor does not proceed with the relevant work until the Project Manager has accepted his design.

- The Contractor may submit his design for acceptance in parts if the design of each part can be assessed fully.

## Other requirements of the Contractor’s design

Refer to the specifications stipulated under section 3.1 of the scope of work.

## Use of Contractor’s design

The Employer may use and copy the Contractor’s design for any purpose connected with construction, use, alteration or demolition of the works unless otherwise stated in the Works Information and for other purposes as stated in the Works Information.

## Design of Equipment

Refer to the specifications stipulated under section 3.1 of the scope of work.

## Equipment required to be included in the works

Refer to the specifications stipulated under section 3.1 of the scope of work.

## As-built drawings, operating manuals and maintenance schedules

As-built drawings required, must be marked up by The Contractor in conjunction with the Engineer. The final completion certificate for the works will not be issued by The Project Manager unless all as-built drawings have been received if required. The Contractor should take note that the 50% retention release is subject to the Employer having received the As-built drawings if applicable. The Contractor is required to comply with the Eskom 240-105658000 Supplier Quality Management Specification Should there be a requirement for The Contractor to provide any operating and maintenance manuals, two full sets must be provided to the Employer within one working day of the handover.

Handover: Contractor shall handover the works after commissioning procedure standards has been confirmed and issuing of Certificate of Compliance has been made available and signed and approved by accredited Lab Master Installation Electrician. Configuration Management: All name coding shall be guided by the Employer. • Labels shall be manufactured as per configured data by The Contractor and affixed. • Employer shall provide The Contractor with a Labelling Standard which provides a guideline on the manufacture of the labels.

# Procurement

4.1 Mandatory Subcontracting as condition of contract award Where feasible, up to 30% subcontracting will be considered for purchase orders that are R30M and above at task order stage. The beneficiaries will be EMEs and or QSEs that are 51% Black owned or more. A progress report on this requirement will be required on a monthly basis by contract management which will include invoices paid to the subcontracting company. Tenderers shall subcontract with the following designated groups: - an EME or QSE which is at least 51% owned by black people. - an EME or QSE which is at least 51% owned by black people who are youth. - an EME or QSE which is at least 51% owned by black people who are women. - an EME or QSE which is at least 51% owned by black people with disabilities. - an EME or QSE which is 51% owned by black people living in rural or underdeveloped area or townships. - a cooperative which is at least 51% owned by black people. - a EME or QSE which is at least 51% owned by black people who are military veterans. The following documents must be submitted before contract award: - Proof of a sub-contract agreement/s - CSD report of subcontractor/s - Sub-contractor/s B-BBEE certificate / sworn affidavit. Participating tenderer/s are required to populate the sub-contracting information on the table below: Sub – contractor details: Name of contractor / Contractors. Proposed Scope of work to be performed by sub-contractor. % Subcontracting. Subcontractor B-BBEE Status Level. Contact person. Telephone number. E-mail address. Name of contractor / Contractors. Proposed Scope of work to be performed by sub-contractor. % Subcontracting. Subcontractor B-BBEE Status Level. Contact person. Telephone number. E-mail address. Name of contractor / Contractors. Proposed Scope of work to be performed by sub-contractor. % Subcontracting. Subcontractor B-BBEE Status Level. Contact person. Telephone number. E-mail address. Note: A supplier awarded a contract/purchase order may not subcontract more than 25% of the value of the purchase order to any other entity that does not have an equal or higher B-BBEE status level of a contributor than the supplier concerned unless the contract is subcontracted to an EME that has the capability and ability to execute the subcontract. SDL&I Objectives in line with Reconstruction and Development Programme (RDP) Goals Tenderers who complete and submit the objectives as required, but who do not meet Eskom’s targets, will not be disqualified. SDL&I objectives do not form part of scoring but commitments will form part of contractual obligations. Transformation – B-BBEE Improvement or Retention Plan Transformation remains an area of focus, where Eskom continuously strives to align itself with national transformation imperatives to unlock growth, drive industrialization, create employment and contribute to skills development. Eskom encourages its suppliers to constantly strive to improve their B-BBEE rating. Whereas Tenderer/s will be allocated points in terms of a preference point system based on specific goals. Tenderer/s are therefore requested to indicate the extent to which they will maintain (only if the respondent is a Level 1-3). Tenderer/s with a B-BBEE status level 4 at the time of contract award, shall migrate and achieve a milestone of B-BBEE Level 3 by the end of the first year of the contract and thereafter maintain their B-BBEE status level. Tenderer/s with a B-BBEE recognition status of Level 5 to Level 8 or non-compliant at the time of contract award, shall migrate and achieve as a non-negotiable a milestone of Level 4 by the end of the first year of the contract and thereafter improve at least one B-BBEE Level higher (level 3) on the second year anniversary of the contract thereafter maintain a level 3 throughout the duration of the contract. Tenderer/s are requested to submit their B-BBEE Improvement Plan as an essential document within 30 days of signing the contract. NB: A valid B-BBEE certificate or Sworn Affidavit is a condition for contract award, if your company’s annual Total Revenue is R10 Million or less you qualify as an Exempted Micro Enterprise therefore you can submit Sworn Affidavit. If your annual Total Revenue is R50 Million or less, you qualify as Qualifying Small Enterprise and must comply with all of the elements of QSE score card relevant to your sector unless an entity is at least 51% Black owned you are required to obtain a Sworn affidavit. If your Annual Total Revenue is above R50m you need to submit a Valid B-BBEE certificate. Local Procurement Content “Local Procurement Content” refers to value added in South Africa by South African resources. Where a single contract involves a combination of local and imported goods and/or services, the tender response must be separated into its components as per the Price Schedule included with the tender documents. Local procurement content is total spending minus the imported component. Tenderers are required to submit their proposals in the table below: Local Procurement Content; Eskom target; Tenderer Proposal. 70%. Procurement spends on entities with a minimum 51% black ownership The winning tenderer/s is/are encouraged to procure/spend on designated groups on the following paid invoices for both: • the indirect expenses (e.g. overheads) on goods and services supplied to the contractor/supplier by designated groups; and • direct spend on goods and services supplied by the subcontractors for the execution of the scope of work. Activities, as a proportion of the local procurement content, which may be subcontracted to designated black owned enterprises must be submitted in a table below. Procurement from Designated Group; Eskom Target; Tenderer Proposal. Black Owned; 4%. Black Women Owned; 3%. Black Youth Owned; 2%. Black Persons with Disability; 1%. Job Creation and Retention Tenderers are required to submit proposals for the type and number of jobs that will be created and retained in South Africa as a direct result of being awarded a contract. Type of Jobs to be created; Number of Jobs to be created. Type of Jobs to be retained; Number of Jobs to be retained. Skills Development Tenderers are required to submit proposals of the skill types / occupations to be upskilled for this transaction. The candidates selected for skills development shall be currently unemployed graduates from university schools and technical, vocational, education and training (TVET) campuses of South Africa. The threshold will be as follows to ensure successful implementation of this initiative: - The successful tenderer will be obligated to skill one candidate for every R3 Million spend cumulatively through purchase orders/instructions awarded to the supplier. - The tenderer will be expected to submit a letter of competence/proof of attendance/service contract/certificate of compliance as proof that a candidate has been appointed for work experience. The supplier will be required to implement this requirement a month after the threshold is reached. Candidates shall be from all provinces in the country, and their composition shall be a representative of the population demographics of South Africa. Skill type / Occupation Scope of work-related skill types/Occupation; Tenderer Proposal. No; Skill Type; Quantity. 1.. 2.. 3.. 4.. 5.. The process of developing these skills shall involve the participation by tenderers directly and through their supply network. In certain cases, the SETA’s accredited training providers can be approached to participate in developing critical and scarce skills. Note: Tenderers are required to take full responsibility for the total cost of developing the requisite skills, and Eskom shall not make any financial contribution towards the fulfilment of this obligation. Tenderers also are advised to approach their relevant SETAs to access grants, subsidies and incentives as well as South African Revenue Services for tax rebates that are earmarked for skills development initiatives.. SDL&I Retention and Performance Security Eskom will apply a retention of 2.5% of the invoice amount for failure to meet SDL&I obligations.. As security for the fulfilment of SDL&I obligations, Eskom will apply a retention of 2.5% on every invoice amount (excluding VAT) for failure to submit SDL&I performance reports every quarter; or failure to meet the SDL&I obligations in this contract. The 2.5% retention clause will be applied as follows: - Submission of the tenderer’s performance reports on a quarterly basis towards SDL&I obligations. - SDL&I will assess the submitted performance report then issue a compliance report. - Should the report yield a non-compliance outcome, Eskom will retain the 2.5%. - Should the compliance results be positive, Eskom will release the retained funds to the tenderer.

## Plant and Materials

### Quality

The Contractor shall control his activities and processes in accordance with Eskom’s Quality Requirements for Procurement of Assets, Goods & Services, QM-58 and ISO-9001.

### Plant & Materials provided “free issue” by the Employer

The Employer requires warranties from the Contractor to be in favour of the Employer and not just to the favour of the Contractor during the life of the contract.

### Contractor’s procurement of Plant and Materials

The Contractors must adhere to all relevant safety regulations during procurement and installation of materials and plant as well as environmental laws and regulations regarding material sourcing, disposal of waste, and energy consumption.

Contractors need to ensure that all procured components are compatible with each other and with the existing infrastructure and that they meet the required quality standards.

### Spares and consumables

Not applicable

## Tests and inspections before delivery

All materials shall be regularly tested at the manufacturers' factories within the country. The Contractor shall make sure that regular quality control tests are carried out to ensure that good quality of the materials is maintained.

## Marking Plant and Materials outside the Working Areas

Whatever title the Contractor has to Plant and Materials which is outside the Working Areas passes to the Employer if the Supervisor has marked it as for this contract.

The Supervisor marks Equipment, Plant and Materials which are outside the Working Areas if

- this contract identifies them for payment and

- the Contractor has prepared them for marking as the Works Information requires.

## Contractor’s Equipment (including temporary works).

The Contractor provides equipment that is rated for the environment that is suitable for the equipment. The Contractor incorporates factors such as ambient temperature, relative humidity, dust ingress, water ingress, wind, oil, access for maintenance and theft when selecting the equipment and its siting. The operating conditions where equipment will be installed must not reduce the life expectancy of the equipment.

## Cataloguing requirements by the Contractor

## The required goods already have SAP numbers which the Supplier have to indicate at all times.

# Construction

## Temporary works, Site services & construction constraints

### Employer’s Site entry and security control, permits, and Site regulations

- The Contractor is responsible to comply with all site regulations during construction phase of the project until completion date.

- The Contractor is responsible for the safety of all personnel involved in the works as well as the safety of all personnel and other members of the public affected by the construction of the works.

- The Contractor is responsible for the design, erection, maintenance and removal of all temporary bracing or propping or falsework required for the execution of the works.

- All construction works complies with SANS 1200 standardised specification for civil engineering construction.

### Restrictions to access on Site, roads, walkways and barricades

In addition to the above, there may be restrictions on access to sites, roads, walkways, and the use of barricades which are crucial for safety and traffic management. These measures, often involving signage and physical barriers, are implemented to control the flow of people and vehicles, protect infrastructure, and minimize hazards. The Contractor shall comply to site specific rules.

### People restrictions on Site; hours of work, conduct and records

Restrictions and hours of work may apply on some Sites.  It is very important that the Contractor keeps records of his people on Site, including those of his Subcontractors which the Project Manager or Supervisor have access to at any time.  These records may be needed when assessing compensation events.

### Health and safety facilities on Site

The Employer prioritize health and safety in all construction sites, adhering to national standards, legislative requirements, and industry best practices. Contractors are responsible for managing their own health and safety programs, ensuring compliance with Eskom's policies and procedures, as well as relevant legislation.

### Environmental controls, fauna & flora, dealing with objects of historical interest

This has been addressed under section 2.4 of the works information.

### Title to materials from demolition and excavation

- The Contractor removes Equipment from the Site when it is no longer needed unless the Project Manager allows it to be left in the works.

- The Contractor has no title to an object of value or of historical or other interest within the Site. The Contractor notifies the Project Manager when such an object is found, and the Project Manager instructs the Contractor how to deal with it. The Contractor does not move the object without instructions.

### Cooperating with and obtaining acceptance of Others

The Contractor shall co-operate with Others in obtaining and providing information which they need in connection with the works. Furthermore, He shall co-operate with Others and share the Working Areas with them.

### Publicity and progress photographs

All pictures taken must be used for Contract purpose/ requirement. The Contractor must get an approval from the Employer to use site pictures for reasons outside the Contract.

### Contractor’s Equipment

The Contractor must provide all equipment and tools required to execute the works and complete the project.

The Contractor is responsibility for safeguard of his equipment on site.

### Equipment provided by the Employer

The Employer provides no equipment to the Contractor for execution of this scope of work.

### Site services and facilities

Ablution Facilities:

Contractors are required to provide adequate and clean ablution facilities, often chemical toilets, or connect to existing Eskom facilities if available.

Wastewater Management:

A system for managing wastewater, such as a septic tank or a portable toilet system, is crucial for environmental compliance.

Potable Water:

Access to clean, potable water is essential for drinking and other site activities.

Contractor's Yard:

A designated area for the contractor's use, including space for storing materials and equipment.

### Facilities provided by the Contractor

The Contractors must provide and manage their facilities that supports their work and personnel. These include site offices, storage areas, waste management solutions, and health and safety provisions like toilets. They are also responsible for ensuring access roads are maintained and restored to their original condition after construction.

### Existing premises, inspection of adjoining properties and checking work of Others

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

### Survey control and setting out of the works

Not applicable.

### Excavations and associated water control

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

### Underground services, other existing services, cable and pipe trenches and covers

The Contractor must conduct underground survey/ detection to check and confirm existing services/ cables/ infrastructure in the specific area before excavating or trenching the ground.

### Control of noise, dust, water and waste

The Contractor must comply with SHE specification requirements.

### Sequences of construction or installation

Not applicable.

### Giving notice of work to be covered up

The Contractor must give the Supervisor early notice before covering up work. This allows the Supervisor to inspect the work before it's covered. The specific notice period should be sufficient to allow for inspection. The Contractor is obligated to provide all necessary information and assistance for the inspection. Failing to provide proper notice could lead to delays or issues if the Supervisor needs to inspect the work after it's been covered.

### Hook ups to existing works

The Contractor must comply with SHE specification requirements.

## Completion, testing, commissioning and correction of Defects

### Work to be done by the Completion Date

On or before the Completion Date the Contractor shall have done everything required to Provide the Works except for the work listed below which may be done after the Completion Date but in any case before the dates stated.  The Project Manager cannot certify Completion until all the work except that listed below has been done and is also free of Defects which would have, in his opinion, prevented the Employer from using the works and Others from doing their work.

|  | Item of work | To be completed by |
| --- | --- | --- |
|  | As built drawings of | Within days after Completion |
|  | Performance testing of the works in use as specified in paragraph of this Works Information. | See performance testing requirements. |

### Use of the works before Completion has been certified

The Contractor will have to carry out the supervision of the installations, as per the instruction of the Project Manager

### Materials facilities and samples for tests and inspections

From time-to-time random sample test and inspections may be requested, to ensure good quality of the goods being supplied.

The Contractor and the Employer must provide materials, facilities and samples for tests and inspections. These include but not limited to smart meter itself, along with communication modules, testing equipment, and potentially specialized facilities for handling and storing the meters, as well as samples for quality assurance.

### Commissioning

Commissioning is to be done before or after Completion depending on the Programme from the Project Manager.

### Start-up procedures required to put the works into operation

In order to put the works into operation the Project Manager may require the Contractor to either do this for him or be in attendance whilst he does it, depending on who is the responsible person.

### Take over procedures

Take-over is after or at the same time as Completion. The Contractor is to arrange an inspection before completion of the installation to inspect and identify any outstanding or any defects. The Project Manager may require the Contractor to provide assistance, on an as and when required basis.

### Access given by the Employer for correction of Defects

The Project Manager arranges for the Employer to allow the Contractor access to and use of a part of the works which he has taken over if they are needed for correcting a Defect. In this case the defect correction period begins when the necessary access and use have been provided.

### Performance tests after Completion

The Contractor to demonstrate that the works can operate as guaranteed by the Contractor (in Contractor’s Works Information) or specified by the Employer either here or elsewhere in this Works Information.

### Training and technology transfer

The Employer requires the Contractor to provide training in the use and maintenance of the works or any associated transfer of technology from him to the Employer.

### Operational maintenance after Completion

The Employer may require the Contractor before the defects date to perform certain duties after Completion and take over which relate to maintenance of the works.

# Plant and Materials standards and workmanship

Detailed specification and user requirements are on the attached document with unique Identifier: 240-171000566 - User Requirement Specification for Residential Solar Photovoltaic (PV) And

Battery Energy Storage Systems (BESS).

Unique Identifier: 240-171000418 - Major Equipment Requirements for Distribution Solar PV AND BESS: SSEG And Microgrids.

## Investigation, survey and Site clearance

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

## Building works

Refer to Standards and Codes below:

Detailed specification and user requirements are on the attached document with unique Identifier: 240-171000566 - User Requirement Specification for Residential Solar Photovoltaic (PV) And

Battery Energy Storage Systems (BESS).

Unique Identifier: 240-171000418 - Major Equipment Requirements for Distribution Solar PV AND BESS: SSEG And Microgrids.

## Civil engineering and structural works

Refer to section 6.2 of the works information.

## Electrical & mechanical engineering works

Refer to section 6.2 of the works information.

## Process control and IT works

Refer to section 6.2 of the works information.

# List of drawings

## Drawings issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

Note:  Some drawings may contain both Works Information and Site Information.

| Drawing number | Revision | Title |
| --- | --- | --- |
| See on Technical Specification |  |  |

C3.2	Contractor’s Works Information

This section of the Works Information will always be contract specific depending on the nature of the works. It is most likely to be required for design and construct contracts where the tendering contractor will have proposed specifications and schedules for items of Plant and Materials and workmanship, which once accepted by the Employer prior to award of contract now become obligations of the Contractor per core clause 20.1. Typical sub headings could be a) Contractor’s design b) Plant and Materials specifications and schedules c) Other

This section could also be compiled as a separate file.

ANNEXURE A: LOW SERVICES DAMAGES

| No. | Service Affected | Description of Loss / Delay | Measurement Basis | Rate (ZAR) |
| --- | --- | --- | --- | --- |
| 1 | System Installation Delay | Delay in completing PV, inverter, or battery installation beyond agreed completion date. | Per calendar day | R3,500 / day |
| 2 | Commissioning Delay | Failure to commission system (including testing & CoC) within agreed timeline | Per calendar day | R4,000 / day |
| 3 | System Downtime (Post-Commissioning) | Installed system unavailable due to contractor fault (excluding grid outages or force majeure). | Per calendar day | R2,500 / day |
| 4 | Remote Monitoring Unavailability | Failure to provide or restore monitoring connectivity where included in scope | Per calendar day | R1,500 / day |
| 5 | Training Delay | Delay in scheduled training beyond agreed dates. | Per training day | R2,000 / day |
| 6 | Maintenance Service Failure | Missed or incomplete scheduled maintenance during O&M period. (Months 13–36) | Per occurrence / day | R2,500 / day |
| 7 | Documentation Non-Compliance | Delay in submission of mandatory documents (SLD, CoC, SSEG approval pack, manuals). | Per calendar day | R1,000 / day |

Part 4: Site Information

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C4 | Site Information | 1 |
|  | Total number of pages | 2 |

Part 4: Site Information

Core clause 11.2(16) states

“Site Information is information which

- describes the Site and its surroundings and

- is in the documents which the Contract Data states it is in.”

In Contract Data, reference has been made to this Part 4 of the contract for the location of Site Information.

# General description

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

# Existing buildings, structures, and plant & machinery on the Site

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

# Subsoil information

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

# Hidden services

Before any work commences, it will be the responsibility of The Contractor to verify and ascertain the position of any other existing services on site. Once these are indicated to The Contractor they shall be deemed “known”. Any costs incurred for repairs to any “known” services due to Contractor’s fault/damage shall be for The Contractor’s account

# Other reports and publicly available information

All relevant descriptions will be specified in the Project Specific Agreement for any project executed in terms of this contract.

This total is required by the Employer for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.

Available from Engineering Contract Strategies Tel 011 803 3008, Fax 011 803 3009 or see www.ecs.co.za