NEC3 Professional Services Contract (PSC3)

| Contract between | Eskom Holdings SOC Ltd (Reg No. 2002/015527/30) |  |
| --- | --- | --- |
| and | [Insert at award stage] (Reg No. ___________ ) |  |
| for | GCD Governance, Compliance and Assurance Services Provider Insert title of the services |  |
| Contents: |  | No of pages |
| Part C1 | Agreements & Contract Data | 24 |
| Part C2 | Pricing Data | 7 |
| Part C3 | Scope of Work: The Scope | 33 |
| CONTRACT No. | [Insert at award stage] |  |

PART C1:	AGREEMENTS & CONTRACT DATA

| ## Document reference | ## Title | ## No of pages |
| --- | --- | --- |
| C1.1 | Form of Offer & Acceptance | 3 |
| C1.2a | Contract Data provided by the Employer | 14 |
| C1.2b | Contract Data provided by the Consultant | 2 |
| C1.3 | Securities proforma | 4 |

C1.1 Form of Offer & Acceptance

## Offer

The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

# GCD Governance, Compliance and Assurance Services Provider

The tenderer, identified in the Offer signature block, has

| either | examined the documents listed in the Tender Data and addenda thereto as listed in the Returnable Schedules, and by submitting this Offer has accepted the Conditions of Tender. |
| --- | --- |
| or | examined the draft contract as listed in the Acceptance section and agreed to provide this Offer. |

By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Consultant under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data.

| The offered total of the Prices exclusive of VAT is | (Not Applicable – Cost reimbursable) |
| --- | --- |
| Value Added Tax @ 15% is |  |
| The offered total of the Prices inclusive of VAT is |  |
| (in words) |  |

If Option E or G apply, for each offered total insert in brackets, “(Not Applicable – Cost reimbursable)”

This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Consultant in the conditions of contract identified in the Contract Data.

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| For the tenderer: |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

## Acceptance

By signing this part of this Form of Offer and Acceptance, the Employer identified below accepts the tenderer’s Offer.  In consideration thereof, the Employer shall pay the Consultant the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Employer and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in:

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work: The Scope

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Employer during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Employer’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed and signed original copy of this document, including the Schedule of Deviations (if any).

| Signature(s) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name(s) |  |  |  |  |
| Capacity |  |  |  |  |
| for the Employer |  |  |  |  |
| Name & signature of witness | (Insert name and address of organisation) |  | Date |  |

## Schedule of Deviations

Note:

- To be completed by the Employer prior to award of contract.  This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.

- The extent of deviations from the tender documents issued by the Employer prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.

- A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.

| No. | Subject | Details |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |

By the duly authorised representatives signing this Schedule of Deviations below, the Employer and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Employer during this process of Offer and Acceptance.

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement.

|  | #### For the tenderer: |  | #### For the Employer |
| --- | --- | --- | --- |
| Signature |  |  |  |
| Name |  |  |  |
| Capacity |  |  |  |
| On behalf of | (Insert name and address of organisation) |  | (Insert name and address of organisation) |
| Name & signature of witness |  |  |  |
| Date |  |  |  |

C1.2 PSC3 Contract Data

# Part one - Data provided by the Employer

| ## Clause | ## Statement |  |  | ## Data |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ## General |  |  |  |  |  |  |  |  |  |  |  |
|  | The conditions of contract are the core clauses and the clauses for main Option |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | G: Term contract |  |  |  |  |  |  |  |  |
|  | dispute resolution Option |  |  | W1: Dispute resolution procedure |  |  |  |  |  |  |  |  |
|  | and secondary Options |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | X1: Price adjustment for inflation |  |  |  |  |  |  |  |  |
|  |  |  |  | X2 Changes in the law |  |  |  |  |  |  |  |  |
|  |  |  |  | X7: Delay damages |  |  |  |  |  |  |  |  |
|  |  |  |  | X9: Transfer of rights |  |  |  |  |  |  |  |  |
|  |  |  |  | X10 Employer’s Agent |  |  |  |  |  |  |  |  |
|  |  |  |  | X11: Termination by the Employer |  |  |  |  |  |  |  |  |
|  |  |  |  | X13: Performance bond |  |  |  |  |  |  |  |  |
|  |  |  |  | X18: Limitation of liability |  |  |  |  |  |  |  |  |
|  |  |  |  | Z: Additional conditions of contract |  |  |  |  |  |  |  |  |
|  | of the NEC3 Professional Services Contract (April 2013) |  |  | If 2005 Edition is to be used delete “April 2013” and replace with “June 2005 with amendments June 2006”. Always delete this note before finalising this Data |  |  |  |  |  |  |  |  |
| 10.1 | The Employer is (Name): |  |  | Eskom Holdings SOC Ltd (reg no: 2002/015527/30), a state owned company incorporated in terms of the company laws of the Republic of South Africa |  |  |  |  |  |  |  |  |
|  | Address |  |  | Registered office at Megawatt Park, Maxwell Drive, Sandton, Johannesburg |  |  |  |  |  |  |  |  |
|  | Tel No. |  |  | [●] |  |  |  |  |  |  |  |  |
|  | Fax No. |  |  | [●] |  |  |  |  |  |  |  |  |
| 11.2(9) | The services are |  |  | Provision of governance, compliance and assurance services for infrastructure construction projects across Eskom on behalf of Group Capital Division (GCD) |  |  |  |  |  |  |  |  |
| 11.2(10) | The following matters will be included in the Risk Register |  |  | - Unavailability of Key People - Skill or qualification gaps - High turnover or staffing shortages - Delays in mobilising staff - Consultant initiated personnel changes - Industrial action or labour disputes - Health & safety incidents involving personnel - Personnel non-compliance or misconduct - A Risk Register will be compiled prior to the commencement of each task order. |  |  |  |  |  |  |  |  |
| 11.2(11) | The Scope is in |  |  | Part 3: Scope of Work |  |  |  |  |  |  |  |  |
| 12.2 | The law of the contract is the law of |  |  | the Republic of South Africa |  |  |  |  |  |  |  |  |
| 13.1 | The language of this contract is |  |  | English |  |  |  |  |  |  |  |  |
| 13.3 | The period for reply is |  |  | 48 Hours |  |  |  |  |  |  |  |  |
| 13.6 | The period for retention is |  |  | 5 (five) years following Completion or earlier termination. |  |  |  |  |  |  |  |  |
| ## 2 | ## The Parties’ main responsibilities |  |  |  |  |  |  |  |  |  |  |  |
| 25.2 | The Employer provides access to the following persons, places and things |  |  | Not applicable |  |  |  |  |  |  |  |  |
| ## 3 | ## Time |  |  |  |  |  |  |  |  |  |  |  |
| 31.2 | The starting date is. |  |  | Upon signing of the contract |  |  |  |  |  |  |  |  |
| 11.2(3) | The completion date for the whole of the services is. |  |  | 60 (sixty) Months from the starting date |  |  |  |  |  |  |  |  |
| 11.2(6) | The key dates and the conditions to be met are: |  |  | Condition to be met |  |  |  | key date |  |  |  |  |
|  |  |  |  | 1 | Acceptance of Contract |  |  | TBA |  |  |  |  |
|  |  |  |  | 2 | Submission of Mandatory and Supplementary information and documentation |  |  | TBA |  |  |  |  |
|  |  |  |  | 3 | Issuing of Task Order |  |  | TBA (on an ongoing basis_ |  |  |  |  |
| 31.1 | The Consultant is to submit a first programme for acceptance within |  |  | 2 (Two) weeks of receipt of task order |  |  |  |  |  |  |  |  |
| 32.2 | The Consultant submits revised programmes at intervals no longer than |  |  | 4 (four) weeks. |  |  |  |  |  |  |  |  |
| ## 4 | ## Quality |  |  |  |  |  |  |  |  |  |  |  |
| 40.2 | The quality policy statement and quality plan are provided within |  |  | 1 (one) week of the Contract Date. |  |  |  |  |  |  |  |  |
| 42.2 | The defects date is |  |  | 52 weeks after Completion of the whole of the services. |  |  |  |  |  |  |  |  |
| ## 5 | ## Payment |  |  |  |  |  |  |  |  |  |  |  |
| 50.1 | The assessment interval is |  |  | between the 24th and 25th day of each successive month. |  |  |  |  |  |  |  |  |
| 50.3 | The expenses stated by the Employer are |  |  | Item |  |  | Amount |  |  |  |  |  |
|  | Accommodation Expenses |  |  | Sum |  |  | As per Eskom Travel Procedure 32-1042 |  |  |  |  |  |
|  | Travel Reimbursements |  |  | Per km |  |  | As per Eskom Travel Procedure 32-1042 |  |  |  |  |  |
| 51.1 | The period within which payments are made is |  |  | 8 (Eight) weeks. |  |  |  |  |  |  |  |  |
| 51.2 | The currency of this contract is the |  |  | South African Rand |  |  |  |  |  |  |  |  |
| 51.5 | The interest rate is |  |  | - For South African Rand (ZAR), it is the publicly quoted South African Rand Overnight Index Average (ZARONIA) rate published by the South African Reserve Bank. - For United States Dollar (USD), it is the Secured Overnight Financing Rate (SOFR) administered by the Federal Reserve Bank of New York (or any other person which takes over the administration of that rate) published by the Federal Reserve Bank of New York (or any other person which takes over the publication of that rate), and depending on the period that interest is incurred, the 30-day, 90-day or 180-day average SOFR (using the simple compounding convention) will apply and, for periods longer than 180 days, interest will be based on the extended period. - For other currencies, it is the publicly quoted risk-free reference rate as published by the applicable Central Bank of the applicable currency, or, if this is not available, the policy rate as published by the applicable Central Bank at the time for amounts due in other currencies or if no rate is quoted for the currency in question then the rate for United States Dollars, and if no such rate appears in The Wall Street Journal then the rate as quoted by the Reuters Monitor Money Rates Service (or such service as may replace the Reuters Monitor Money Rates Service) on the due date for the payment in question, adjusted mutatis mutandis every 6 months thereafter and as certified, in the event of any dispute, by any manager employed in the foreign exchange department of South African Reserve Bank, whose appointment it shall not be necessary to prove. |  |  |  |  |  |  |  |  |
| ## 6 | ## Compensation events |  |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |  |
| ## 7 | ## Rights to material |  |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |  |
| ## 8 | ## Indemnity, insurance and liability |  |  | ## There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |  |
| ## 82.1 | ## The Consultant’s total liability to the Employer for all matters arising under or in connection with this contract, other than the excluded matters, is limited to |  |  | ## The total of the Prices |  |  |  |  |  |  |  |  |
| ## 9 | ## Termination |  |  | There is no reference to Contract Data in this section of the core clauses and terms in italics used in this section are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |  |
| ## 10 | ## Data for main Option clause |  |  |  |  |  |  |  |  |  |  |  |
| G | Term contract |  |  |  |  |  |  |  |  |  |  |  |
| 21.4 | The Consultant prepares forecasts of the total Time Charge and expenses at intervals no longer than |  |  | Four (4) weeks. |  |  |  |  |  |  |  |  |
| 50.4 | The exchange rates are those published in |  |  | N/A. |  |  |  |  |  |  |  |  |
| ## 11 | ## Data for Option W1 |  |  |  |  |  |  |  |  |  |  |  |
| W1.1 | The Adjudicator is |  |  | the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him. (see www.ice-sa.org.za). If the Parties do not agree on an Adjudicator the Adjudicator will be appointed by the Arbitration Foundation of Southern Africa (AFSA). |  |  |  |  |  |  |  |  |
|  | Address |  |  | TBA |  |  |  |  |  |  |  |  |
|  | Tel No. |  |  | TBA |  |  |  |  |  |  |  |  |
|  | Fax No. |  |  | TBA |  |  |  |  |  |  |  |  |
|  | e-mail |  |  | TBA |  |  |  |  |  |  |  |  |
| W1.2(3) | The adjudicator nominating body is: |  |  | the Chairman of the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering. (See www.ice-sa.org.za). |  |  |  |  |  |  |  |  |
| W1.4(2) | The tribunal is: |  |  | arbitration |  |  |  |  |  |  |  |  |
| W1.4(5) | The arbitration procedure is |  |  | the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |  |
|  | The place where arbitration is to be held is |  |  | Johannesburg South Africa |  |  |  |  |  |  |  |  |
|  | The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator, is |  |  | the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body. |  |  |  |  |  |  |  |  |
| ## 12 | ## Data for secondary Option clauses |  |  |  |  |  |  |  |  |  |  |  |
| X1 | Price adjustment for inflation |  |  |  |  |  |  |  |  |  |  |  |
| X1.1 | The index is |  |  | ## Indices to be updated as per accepted offer. ## 15% Non-Adjustable Constant |  |  |  |  |  |  |  |  |
|  | The staff rates are |  |  | ## Fixed at the Contract Date for the first 12 months, and are not variable with changes in salary paid to individuals. After the first 12 months CPA will be calculated as per above indices. |  |  |  |  |  |  |  |  |
| X2 | Changes in the law |  |  |  |  |  |  |  |  |  |  |  |
| X2.1 | The law of the project is |  |  | ## The current and applicable law in South Africa shall apply in this contract. |  |  |  |  |  |  |  |  |
| X3 | Multiple currencies |  |  |  |  |  |  |  |  |  |  |  |
| X3.1 | The Employer will pay for these items or activities in the currencies stated |  |  | Items & activities |  | Other currency |  |  |  | Maximum payment in other currency |  |  |
|  |  |  |  | N/A |  |  |  |  |  |  |  |  |
|  |  |  |  | N/A |  |  |  |  |  |  |  |  |
|  |  |  |  | N/A |  |  |  |  |  |  |  |  |
| X3.1 | The exchange rates are those published in |  |  | There will be no payments made in other currencies under this contract. |  |  |  |  |  |  |  |  |
| X7 | Delay damages |  |  |  |  |  |  |  |  |  |  |  |
| X7.1 | Delay damages for late Completion of the whole of the services are |  |  | R5 000 per day per task order |  |  |  |  |  |  |  |  |
| X9 | Transfer of rights |  |  | There is no reference to Contract Data in this Option and terms in italics used in this Option are identified elsewhere in this Contract Data. |  |  |  |  |  |  |  |  |
| X10 | The Employer’s Agent |  |  |  |  |  |  |  |  |  |  |  |
| X10.1 | The Employer’s Agent is |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  | TBA |  |  |  |  |  |  |  |  |
|  | Address |  |  | TBA |  |  |  |  |  |  |  |  |
|  | The authority of the Employer’s Agent is |  |  | TBA |  |  |  |  |  |  |  |  |
| X11 | Termination by the Employer |  |  | Delete X11.2 and replace with the following “The amount due on termination includes an amount due assessed as for normal payments” |  |  |  |  |  |  |  |  |
| X13 | Performance bond |  |  |  |  |  |  |  |  |  |  |  |
| X13.1 | The amount of the performance bond is |  |  | 10% of the contract price |  |  |  |  |  |  |  |  |
| X18 | Limitation of liability |  |  |  |  |  |  |  |  |  |  |  |
| X18.1 | The Consultant’s liability to the Employer for indirect or consequential loss is limited to: |  |  | R0.00 (Zero Rand) |  |  |  |  |  |  |  |  |
| X18.2 | The Consultant’s liability to the Employer for Defects that are not found until after the defects date is limited to: |  |  | The total of the Prices |  |  |  |  |  |  |  |  |
| X18.3 | The end of liability date is |  |  | five years after Completion of the whole of the services/task order. |  |  |  |  |  |  |  |  |
| Z | The Additional conditions of contract are |  |  | Z1 to Z22 always apply. |  |  |  |  |  |  |  |  |
| Z1 | Cession delegation and assignment |  |  |  |  |  |  |  |  |  |  |  |
| Z1.1 | The Consultant does not cede, delegate or assign any of its rights or obligations to any person without the written consent of the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z1.2 | Notwithstanding the above, the Employer may on written notice to the Consultant cede and delegate its rights and obligations under this contract to any of its subsidiaries or any of its present divisions or operations which may be converted into separate legal entities as a result of the restructuring of the Electricity Supply Industry. |  |  |  |  |  |  |  |  |  |  |  |
| Z2 | Joint ventures |  |  |  |  |  |  |  |  |  |  |  |
| Z2.1 | If the Consultant constitutes a joint venture, consortium or other unincorporated grouping of two or more persons or organisations then these persons or organisations are deemed to be jointly and severally liable to the Employer for the performance of this contract. |  |  |  |  |  |  |  |  |  |  |  |
| Z2.2 | Unless already notified to the Employer, the persons or organisations notify the Employer within two weeks of the Contract Date of the key person who has the authority to bind the Consultant on their behalf. |  |  |  |  |  |  |  |  |  |  |  |
| Z2.3 | The Consultant does not alter the composition of the joint venture, consortium or other unincorporated grouping of two or more persons without the consent of the Employer having been given to the Consultant in writing. |  |  |  |  |  |  |  |  |  |  |  |
| Z3 | Change of Broad Based Black Economic Empowerment (B-BBEE) status |  |  |  |  |  |  |  |  |  |  |  |
| Z3.1 | Where a change in the Consultant’s legal status, ownership or any other change to his business composition or business dealings results in a change to the Consultant’s B-BBEE status, the Consultant notifies the Employer within seven days of the change. |  |  |  |  |  |  |  |  |  |  |  |
| Z3.2 | The Consultant is required to submit an updated verification certificate and necessary supporting documentation confirming the change in his B-BBEE status to the Employer within thirty days of the notification or as otherwise instructed by the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z3.3 | Where, as a result, the Consultant’s B-BBEE status has decreased since the Contract Date the Employer may either re-negotiate this contract or alternatively, terminate the Consultant’s obligation to Provide the Services. |  |  |  |  |  |  |  |  |  |  |  |
| Z3.4 | Failure by the Consultant to notify the Employer of a change in its B-BBEE status may constitute a reason for termination. If the Employer terminates in terms of this clause, the procedures on termination are those stated in core clause 91. The payment on termination includes a deduction of the forecast of the additional cost to the Employer of completing the whole of the services in addition to the amounts due in terms of core clause 92.1. |  |  |  |  |  |  |  |  |  |  |  |
| Z4 | Confidentiality |  |  |  |  |  |  |  |  |  |  |  |
| Z4.1 | The Consultant does not disclose or make any information arising from or in connection with this contract available to Others. This undertaking does not, however, apply to information which at the time of disclosure or thereafter, without default on the part of the Consultant, enters the public domain or to information which was already in the possession of the Consultant at the time of disclosure (evidenced by written records in existence at that time). Should the Consultant disclose information to Others in terms of clause 23.1, the Consultant ensures that the provisions of this clause are complied with by the recipient. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.2 | If the Consultant is uncertain about whether any such information is confidential, it is to be regarded as such until notified otherwise by the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.3 | In the event that the Consultant is, at any time, required by law to disclose any such information which is required to be kept confidential, the Consultant, to the extent permitted by law prior to disclosure, notifies the Employer so that an appropriate protection order and/or any other action can be taken if possible, prior to any disclosure. In the event that such protective order is not, or cannot, be obtained, then the Consultant may disclose that portion of the information which it is required to be disclosed by law and uses reasonable efforts to obtain assurances that confidential treatment will be afforded to the information so disclosed. |  |  |  |  |  |  |  |  |  |  |  |
| Z4.4 | The taking of images (whether photographs, video footage or otherwise) of the Employer’s project works or any portion thereof, in the course of Providing the Services and after Completion, requires the prior written consent of the Employer. All rights in and to all such images vests exclusively in the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z5 | Waiver and estoppel: Add to core clause 12.3: |  |  |  |  |  |  |  |  |  |  |  |
| Z5.1 | Any extension, concession, waiver or relaxation of any action stated in this contract by the Parties, or the Adjudicator does not constitute a waiver of rights, and does not give rise to an estoppel unless the Parties agree otherwise and confirm such agreement in writing. |  |  |  |  |  |  |  |  |  |  |  |
| Z6 | Provision of a Tax Invoice. Add to core clause 51 |  |  |  |  |  |  |  |  |  |  |  |
| Z6.1 | The Consultant (if registered in South Africa in terms of the companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) and to include the Employer’s VAT number 4740101508 on each invoice he submits for payment. |  |  |  |  |  |  |  |  |  |  |  |
| Z7 | Notifying compensation events |  |  |  |  |  |  |  |  |  |  |  |
| Z7.1 | Delete from the last sentence in core clause 61.3, “unless the Employer should have notified the event to the Consultant but did not”. |  |  |  |  |  |  |  |  |  |  |  |
| Z8 | Employer’s limitation of liability |  |  |  |  |  |  |  |  |  |  |  |
| Z8.1 | The Employer’s liability to the Consultant for the Consultant’s indirect or consequential loss is limited to R0.00 (zero Rand) |  |  |  |  |  |  |  |  |  |  |  |
| Z9 | Termination: Add to core clause 90.1, at the second main bullet point, fourth sub-bullet point, after the words "against it": |  |  |  |  |  |  |  |  |  |  |  |
| Z9.1 | or had a business rescue order granted against it. |  |  |  |  |  |  |  |  |  |  |  |
| Z10 | Delay damages: Addition to secondary Option X7 Delay damages (if applicable in this contract) |  |  |  |  |  |  |  |  |  |  |  |
| Z10.1 | If the Consultant’s payment of delay damages reaches the limits stated in this Contract Data for Option X7 or Options X5 and X7 used together, the Employer may terminate the Consultant’s obligation to Provide the Services. |  |  |  |  |  |  |  |  |  |  |  |
| Z10.2 | If the Employer terminates in terms of this clause, the procedures on termination are those stated in core clause 91. The payment on termination includes a deduction of the forecast of the additional cost to the Employer of completing the whole of the services in addition to the amounts due in terms of core clause 92.1. |  |  |  |  |  |  |  |  |  |  |  |
| Z11 | Ethics |  |  |  |  |  |  |  |  |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |  |  |  |  |  |  |  |  |
| Affected Party |  | means, as the context requires, any party, irrespective of whether it is the Consultant or a third party, such party’s employees, agents, or Subconsultants or Subconsultant’s employees, or any one or more of all of these parties’ relatives or friends, |  |  |  |  |  |  |  |  |  |  |
| Coercive Action |  | means to harm or threaten to harm, directly or indirectly, an Affected Party or the property of an Affected Party, or to otherwise influence or attempt to influence an Affected Party to act unlawfully or illegally, |  |  |  |  |  |  |  |  |  |  |
| Collusive Action |  | means where two or more parties co-operate to achieve an unlawful or illegal purpose, including to influence an Affected Party to act unlawfully or illegally, |  |  |  |  |  |  |  |  |  |  |
| Committing Party |  | means, as the context requires, the Consultant, or any member thereof in the case of a joint venture, or its employees, agents, or Subconsultants or the Subconsultant’s employees, |  |  |  |  |  |  |  |  |  |  |
| Corrupt Action |  | means the offering, giving, taking, or soliciting, directly or indirectly, of a good or service to unlawfully or illegally influence the actions of an Affected Party, |  |  |  |  |  |  |  |  |  |  |
| Fraudulent Action |  | means any unlawfully or illegally intentional act or omission that misleads, or attempts to mislead, an Affected Party, in order to obtain a financial or other benefit or to avoid an obligation or incurring an obligation, |  |  |  |  |  |  |  |  |  |  |
| Obstructive Action |  | means a Committing Party unlawfully or illegally destroying, falsifying, altering or concealing information or making false statements to materially impede an investigation into allegations of Prohibited Action, and |  |  |  |  |  |  |  |  |  |  |
| Prohibited Action |  | means any one or more of a Coercive Action, Collusive Action, Corrupt Action, Fraudulent Action or Obstructive Action. |  |  |  |  |  |  |  |  |  |  |
| Z11.1 | A Committing Party may not take any Prohibited Action during the course of the procurement of this contract or in execution thereof. |  |  |  |  |  |  |  |  |  |  |  |
| Z11.2 | The Employer may terminate the Consultant’s obligation to Provide the Services if a Committing Party has taken such Prohibited Action and the Consultant did not take timely and appropriate action to prevent or remedy the situation, without limiting any other rights or remedies the Employer has. It is not required that the Committing Party had to have been found guilty, in court or in any other similar process, of such Prohibited Action before the Employer can terminate the Consultant’s obligation to Provide the Services for this reason. |  |  |  |  |  |  |  |  |  |  |  |
| Z11.3 | If the Employer terminates the Consultant’s obligation to Provide the Services for this reason, the amounts due on termination are those intended in core clauses 92.1 and 92.2. |  |  |  |  |  |  |  |  |  |  |  |
| Z11.4 | A Committing Party co-operates fully with any investigation pursuant to alleged Prohibited Action. Where the Employer does not have a contractual bond with the Committing Party, the Consultant ensures that the Committing Party co-operates fully with an investigation. |  |  |  |  |  |  |  |  |  |  |  |
| Z12 | Insurance |  |  |  |  |  |  |  |  |  |  |  |
| Z12.1 | Replace core clause 81 with the following: |  |  |  |  |  |  |  |  |  |  |  |
| 81.1 | When requested by a Party, the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |  |  |  |  |  |  |  |  |  |  |  |
| 81.2 | The Consultant provides the insurances stated in the Insurance Table A from the starting date until the earlier of Completion and the date of the termination certificate. |  |  |  |  |  |  |  |  |  |  |  |
|  | INSURANCE TABLE A |  |  |  |  |  |  |  |  |  |  |  |
|  | - Insurance against; Minimum amount of cover; For the period following Completion of the whole of the services or earlier termination. Liability of the Consultant for claims made against him arising out of his failure to use the skill and care normally used by professionals providing services similar to the services; Whatever the Consultant deems necessary for any occurrence or series of occurrences arising out of one event without limit to the number of claims.; 12 months after contract completion or termination. Liability for death of or bodily injury to a person (not an employee of the Consultant) or loss of or damage to property resulting from an action or failure to take action by the Consultant; Loss of or damage to property: The replacement cost where not covered by the Employer’s insurance The Employer’s policy deductible, as at Contract Date, where covered by the Employer’s insurance Bodily injury to or death of a person: The amount required by the applicable law.; 12 months after contract completion or termination. Liability for death of or bodily injury to employees of the Consultant arising out of and in the course of their employment in connection with this contract; The amount required by the applicable law; 12 months after contract completion or termination. |  |
| 81.3 | - The Employer provides the insurances stated in the Insurance Table B. |  |  |  |  |  |  |  |  |  |  |  |
|  | - INSURANCE TABLE B |  |  |  |  |  |  |  |  |  |  |  |
|  | Insurance against or name of policy; Minimum amount of cover or minimum limit of indemnity. Assets All Risk; Per the insurance policy document. Contract Works insurance; Per the insurance policy document. Environmental Liability; Per the insurance policy document. General and Public Liability; Per the insurance policy document. Transportation (Marine); Per the insurance policy document. Motor Fleet and Mobile Plant; Per the insurance policy document. Terrorism; Per the insurance policy document. Cyber Liability; Per the insurance policy document. Nuclear Material Damage and Business Interruption; Per the insurance policy document. Nuclear Material Damage Terrorism; Per the insurance policy document. |  |
| Z13 | Nuclear Liability |  |  |  |  |  |  |  |  |  |  |  |
| Z13.1 | The Employer is the operator of the Koeberg Nuclear Power Station (KNPS), a nuclear installation, as designated by the National Nuclear Regulator of the Republic of South Africa, and is the holder of a nuclear licence in respect of the KNPS. |  |  |  |  |  |  |  |  |  |  |  |
| Z13.2 | The Employer is solely responsible for and indemnifies the Consultant or any other person against any and all liabilities which the Consultant or any person may incur arising out of or resulting from nuclear damage, as defined in Act 47 of 1999, save to the extent that any liabilities are incurred due to the unlawful intent of the Consultant or any other person or the presence of the Consultant or that person or any property of the Consultant or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z13.3 | Subject to clause Z13.4 below, the Employer waives all rights of recourse, arising from the aforesaid, save to the extent that any claims arise or liability is incurred due or attributable to the unlawful intent of the Consultant or any other person, or the presence of the Consultant or that person or any property of the Consultant or such person at or in the KNPS or on the KNPS site, without the permission of the Employer or of a person acting on behalf of the Employer. |  |  |  |  |  |  |  |  |  |  |  |
| Z13.4 | The Employer does not waive its rights provided for in section 30 (7) of Act 47 of 1999, or any replacement section dealing with the same subject matter. |  |  |  |  |  |  |  |  |  |  |  |
| Z13.5 | The protection afforded by the provisions hereof shall be in effect until the KNPS is decommissioned. |  |  |  |  |  |  |  |  |  |  |  |
| Z14 | Asbestos |  |  |  |  |  |  |  |  |  |  |  |
| For the purposes of this Z-clause, the following definitions apply: |  |  |  |  |  |  |  |  |  |  |  |  |
| AAIA |  |  | means approved asbestos inspection authority. |  |  |  |  |  |  |  |  |  |
| ACM |  |  | means asbestos containing materials. |  |  |  |  |  |  |  |  |  |
| AL |  |  | means action level, i.e. a level of 50% of the OEL, i.e. 0.1 regulated asbestos fibres per ml of air measured over a 4-hour period. The value at which proactive actions is required in order to control asbestos exposure to prevent exceeding the OEL. |  |  |  |  |  |  |  |  |  |
| Ambient Air |  |  | means breathable air in area of work with specific reference to breathing zone, which is defined to be a virtual area within a radius of approximately 30cm from the nose inlet. |  |  |  |  |  |  |  |  |  |
| Compliance Monitoring |  |  | means compliance sampling used to assess whether or not the personal exposure of workers to regulated asbestos fibres is in compliance with the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |  |  |  |  |  |  |  |  |  |
| OEL |  |  | means occupational exposure limit. |  |  |  |  |  |  |  |  |  |
| Parallel Measurements |  |  | means measurements performed in parallel, yet separately, to existing measurements to verify validity of results. |  |  |  |  |  |  |  |  |  |
| Safe Levels |  |  | means airborne asbestos exposure levels conforming to the Standard’s requirements for safe processing, handling, storing, disposal and phase-out of asbestos and asbestos containing material, equipment and articles. |  |  |  |  |  |  |  |  |  |
| Standard |  |  | means the Employer’s Asbestos Standard 32-303: Requirements for Safe Processing, Handling, Storing, Disposal and Phase-out of Asbestos and Asbestos Containing Material, Equipment and Articles. |  |  |  |  |  |  |  |  |  |
| SANAS |  |  | means the South African National Accreditation System. |  |  |  |  |  |  |  |  |  |
| TWA |  |  | means the average exposure, within a given workplace, to airborne asbestos fibres, normalised to the baseline of a 4 hour continuous period, also applicable to short term exposures, i.e. 10-minute TWA. |  |  |  |  |  |  |  |  |  |
| Z14.1 | The Employer ensures that the Ambient Air in the area where the Consultant will Provide the Services conforms to the acceptable prescribed South African standard for asbestos, as per the regulations published in GNR 155 of 10 February 2002, under the Occupational Health and Safety Act, 1993 (Act 85 of 1993) (“Asbestos Regulations”). The OEL for asbestos is 0.2 regulated asbestos fibres per millilitre of air as a 4-hour TWA, averaged over any continuous period of four hours, and the short term exposure limit of 0.6 regulated asbestos fibres per millilitre of air as a 10-minute TWA, averaged over any 10 minutes, measured in accordance with HSG248 and monitored according to HSG173 and OESSM. |  |  |  |  |  |  |  |  |  |  |  |
| Z14.2 | Upon written request by the Consultant, the Employer certifies that these conditions prevail. All measurements and reporting are effected by an independent, competent, and certified occupational hygiene inspection body, i.e. a SANAS accredited and Department of Employment and Labour approved AAIA. The Consultant may perform Parallel Measurements and related control measures at the Consultant’s expense. For the purposes of compliance the results generated from Parallel Measurements are evaluated only against South African statutory limits as detailed in clause Z14.1. Control measures conform to the requirements stipulated in the AAIA-approved asbestos work plan. |  |  |  |  |  |  |  |  |  |  |  |
| Z14.3 | The Employer manages asbestos and ACM according to the Standard. |  |  |  |  |  |  |  |  |  |  |  |
| Z14.4 | In the event that any asbestos is identified while Providing the Services, a risk assessment is conducted and if so required, with reference to possible exposure to an airborne concentration of above the AL for asbestos, immediate control measures are implemented and relevant air monitoring conducted in order to declare the area safe. |  |  |  |  |  |  |  |  |  |  |  |
| Z14.5 | The Consultant’s personnel are entitled to stop working and leave the contaminated area forthwith until such time that the area of concern is declared safe by either Compliance Monitoring or an AAIA approved control measure intervention, for example, per the emergency asbestos work plan, if applicable. |  |  |  |  |  |  |  |  |  |  |  |
| Z14.6 | The Consultant continues to Provide the Services, without additional control measures presented, on presentation of Safe Levels. The contractually agreed dates to Provide the Services, including the Completion Date, are adjusted accordingly. The contractually agreed dates are extended by the notification periods required by regulations 3 and 21 of the Asbestos Regulations, 2001. |  |  |  |  |  |  |  |  |  |  |  |
| Z14.7 | Any removal and disposal of asbestos, asbestos containing materials and waste, is done by a registered asbestos contractor, instructed by the Employer at the Employer’s expense, and conducted in line with South African legislation. |  |  |  |  |  |  |  |  |  |  |  |

Z18 Security Clearance/ Criminal Checks

Z18.1 	The Consultant and its subcontractors implement risk and security management processes and measures to mitigate any threats against any premises, installations or sites, systems, or information of the Employer with only persons with criminal verification record security clearance certificates being given access after verification of these and identifying documents by the Employer’s security system.

Z18.2 	The Consultant provides, at the Consultant’s cost, to the Employer, criminal verification record   security clearance certificates for each person the Consultant or its subcontractors requires to access any premises, installations or sites, systems, or information of the Employer, with copies of their identifying documents, such as passports, before allowed such access by the Employer. The Employer’s refusal to allow access to premises, installations or site/s, systems or information is at the Employer’s sole discretion and is not a compensation event.

Z18.3 	The criminal verification record security clearance certificates provided are to have been issued by a service provider which is to be a reputable screening company accredited by the South African Police Services, are to be no older than four weeks since issue and valid for as long as each person is required to access premises, installations or sites, systems or	information. The Employer may require updated certificates and identifying documents every 26 to 52 weeks, subject to safety and security concerns and the risk rating of the works or services undertaken and/or premises, installations or sites, systems or information.

Z18.4	If any such criminal verification record security clearance certificates is cancelled, withdrawn, invalidated, amended, or expires, or a criminal conviction is noted against any person requiring access, even if an appeal against the criminal conviction has been noted, the Employer may instruct the Consultant to ensure that such person leaves the premises, installations or site/s and is blocked from systems and information and the giving of this instruction is not a compensation event.

Z19 Health, safety, environmental, professional and other legal requirements

Add to main responsibilities in section 2 of conditions of contract:

Z19.1 	The Consultant acts in accordance with all applicable law and regulations and rules, guidelines, policies, standards, directives, occupational health and safety and environmental	specifications, requirements and procedures otherwise provided for under this contract and ensures that subcontractors, employees and others under the Consultant’s direction and control, likewise, observe these and comply.

Z19.2 	The Consultant undertakes all reasonable and proper precautions to ensure the health and safety of persons and to protect the environment in and about the Affected Property or affected by the provision or execution of the services.

Z19.3 	The Consultant warrants that the Prices, at the date when this contract came into existence, sufficiently provides for proper compliance with all applicable law and regulations	and rules, guidelines and procedures of the law of the contact, and otherwise provided for under this contract, including resourcing and appointment of professionally registered persons as required, and for properly ensuring the health and safety of persons and to protect the environment in and about or affected by the provision of the services.

Z19.4	Where applicable, the Consultant may not commence with the provision or execution of the services until the Consultant’s Health and Safety file has been approved by the professional construction health and safety agent notified by Employer, and accepts that the Employer may appoint the Consultant as the “Principal Contractor” (as defined and provided for under the Construction Regulations (promulgated under the Occupational Health & Safety Act 85 of 1993) for the Affected Property.

Z20 Provision of a tax invoice, payment, and interest

Add the following to section 5 of the conditions of contract:

Z20.1 	The Consultant (if registered in South Africa in terms of the Companies Act) complies with the requirements of the Value Added Tax Act, (Act 89 of 1991 (as amended)) and includes the Employer’s VAT number 4740101508 on each invoice submitted for payment.

Z20.2 	Within one week of receiving a payment certificate from the Employer’s acceptance or correction of the Consultant’s assessment or application for payment, the Consultant provides	the Employer with a tax invoice in the form required by the law of the contract, and this contract, including in accordance with any requirements and procedures stated in the Scope of Works Information, and showing the amount due for payment equal to that stated in the payment certificate, or the accepted or corrected assessment or application for payment.

Z20.3 	If the Consultant does not provide a tax invoice in accordance with this Z-clause, and by the time required by this contract, the time by when the Employer is to make a payment, and the date from which interest is assessed for the certified, accepted or corrected amount, is extended by a period equal in time to the delayed submission of such an invoice.

Z20.4 	The Consultant’s provision of a tax invoice reflecting the certified, accepted, or corrected amount does not affect the Parties’ rights in terms of this contract, including with respect to disputed amounts.

Z20.5 	The Consultant at all times complies with Employer’s Vendor Management System requirements to ensure invoices are processed and paid timeously. It is the Consultant’s responsibility to ensure that the Employer is informed of any changes in its organisation that would affect its vendor status, and to ensure that the necessary actions and due diligences are taken to ensure compliance with the Employer’s Vendor Management System. The Employer will not be liable for a delay in payment of invoices as a result of the Consultant’s non-compliant status on the Employer’s Vendor Management System and no interest will be claimable in this instance.

Z22 Aggregate Liability for Penalties and Termination

Z22.1 	If the limits for accumulated damages or other penalties are not otherwise stated in this contract, the total aggregate liability is limited to 10% of the offered total of the Prices when this contract came into existence.

Z22.2 	If the amount due for accumulated damages or other penalties reaches the limits stated in this contract, without further notification of default, the Employer may terminate the Consultant’s obligation to Provide the Services.

Z22.3 	If the Consultant’s obligation to Provide the Services is terminated for this reason, the procedure and amount due on termination are those intended as if the Employer has terminated for a reason due to the Consultant’s default.

C1.2 Contract Data

# Part two - Data provided by the Consultant

[Instructions to the tendering consultant:  (delete these notes in the final draft of a contract)

- The tendering consultant is advised to read both the NEC3 Professional Services Contract, April 2013 and the relevant parts of its Guidance Notes (PSC3-GN) in order to understand the implications of this Data which the tenderer is required to complete.  An example of the completed Data is provided on pages 158 & 159 of the PSC3 April 2013 Guidance Notes.

- The number of the clause in the PSC3 which requires the data is shown in the left hand column for each statement however other clauses may also use the same data.

- Whenever a cell is shaded in the left hand column it denotes this data is optional in PSC3 and would be required in relation to the option selected.  The Employer should already have made the selection and deleted the rows not required.

Completion of the data in full, according to Options chosen, is essential to create a complete contract.

| ## Clause | ## Statement | ## Data |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 10.1 | The Consultant is (Name): |  |  |  |  |
|  | Address |  |  |  |  |
|  | Tel No. |  |  |  |  |
|  | Fax No. |  |  |  |  |
| 22.1 | The key people are: |  |  |  |  |
|  | 1 Name: |  |  |  |  |
|  | Job: |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
|  | 2 Name: |  |  |  |  |
|  | Job |  |  |  |  |
|  | Responsibilities: |  |  |  |  |
|  | Qualifications: |  |  |  |  |
|  | Experience: |  |  |  |  |
| Only if required |  | CV's (and further key persons data including CVs) are appended to Tender Schedule entitled . |  |  |  |
| 11.2(3) | The completion date for the whole of the services is | 60 (sixty) months after Starting date |  |  |  |
| 11.2(10) | The following matters will be included in the Risk Register | A Risk Register will be compiled prior to the commencement of each task order. |  |  |  |
| 11.2(13) | The staff rates are: | name/designation |  | rate |  |
|  | Either complete here or cross refer to a schedule in Part C2.2 |  |  |  |  |
| 25.2 | The Employer provides access to the following persons, places and things | access to |  |  | access date |
|  |  | 1 |  |  |  |
|  |  | 2 |  |  |  |
|  |  | 3 |  |  |  |
| 31.1 | The programme identified in the Contract Data is | To be submitted after issuance of Task Order. |  |  |  |
| 50.3 | The expenses stated by the Consultant are | item |  | amount |  |
| G | Term contract |  |  |  |  |
| 11.2(25) | The task schedule is in |  |  |  |  |

C1.3 Forms of Securities

- Pro formas for Bonds & Guarantees

- For use with the NEC3 Professional Services Contract

The conditions of contract stated in the Contract Data Part 1 include the following Secondary Options:

Option X13:	Performance Bond

These secondary Options require a bond or guarantee “in the form set out in the Scope”.    Pro forma documents for these bonds and guarantees are provided here for convenience but are to be treated as part of the Scope.

The organisation providing the bond / guarantee does so by copying the pro forma document onto his letterhead without any change to the text or format and completing the required details.  The completed document is then given to the Employer within the time stated in the contract.

# Pro forma Performance Bond – Demand Guarantee (for use with Option X13)

(to be reproduced exactly as shown below on the letterhead of the Consultant’s Parent Company)

| Eskom Holdings SOC Ltd Megawatt Park Maxwell Drive Sandton Johannesburg | Date: |  |
| --- | --- | --- |

Dear Sirs

Reference No. [●] [Drafting Note: Bank reference number to be inserted]

Performance Bond – Demand Guarantee: [Drafting Note: Name of Consultant to be inserted]

Project [  ] Contract Reference: …… [Drafting Note: Consultant contract reference number to be inserted]

- In this Guarantee the following words and expressions shall have the following meanings:-

  - “Bank” - means [●], [●] Branch, (Registration No. [●]); [Drafting Note: Name of Bank to be inserted]

  - “Bank’s Address” - means [●]; [Drafting Note: Bank’s physical address to be inserted]

  - “Contract” – means the written agreement relating to the Services, entered into between Eskom and the Consultant, on or about the [●] day of [●] 200[●] (Contract Reference No. [.]as amended, varied, restated, novated or substituted from time to time; [Drafting Note: Signature Date and Contract reference number to be inserted]

  - ”Consultant” – means [●] a company registered in accordance with the laws of [●] under Registration Number [●]. [Drafting Note: Name and details of Consultant to be inserted]

  - “Eskom” - means Eskom Holdings SOC Ltd, a company registered in accordance with the laws of the Republic of South Africa under Registration Number 2002/015527/30].

  - “Expiry Date” - means the earlier of

- the date that the Bank receives a notice from Eskom stating that all amounts due from the Consultant as certified in terms of the contract have been received by Eskom and that the Consultant has fulfilled all his obligations under the Contract, or

- the date that the Bank issues a replacement Bond for such lesser or higher amount as may be required by Eskom

  - “Guaranteed Sum” - means the sum of R [●] ([●] Rand);

  - “Services” - means [insert if applicable.].

- At the instance of the Consultant, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of Eskom, as security for the proper performance by the Consultant of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to Eskom, on written demand from Eskom received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

- A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

  - be signed on behalf of Eskom by a Group Executive, Divisional Executive, Senior General Manager, General Manager  or its delegate;

  - state the amount claimed (“the Demand Amount’);

  - state that the Demand Amount is payable to Eskom in the circumstances contemplated in the Contract.

- Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

  - is and shall be absolute provided demand is made in terms of this bond in all circumstances; and

  - is not, and shall not be construed to be, accessory or collateral on any basis whatsoever.

- The Bank’s obligations in terms of this Guarantee:

  - shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and

  - shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed, by the fact that a dispute may exist between Eskom and the Consultant.

- Eskom shall be entitled to arrange its affairs with the Consultant in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Consultant or any variation under or to the Contract.

- Should Eskom cede its rights against the Consultant to a third party where such cession is permitted under the Contract, then Eskom shall be entitled to cede to such third party the rights of Eskom under this Guarantee on written notification to the Bank of such cession.

- This Guarantee:

  - shall expire on the Expiry Date until which time it is irrevocable;

  - is, save as provided for in 7 above, personal to Eskom and is neither negotiable nor transferable;

  - shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;

  - shall be regarded as a liquid document for the purpose of obtaining a court order; and

  - shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa.

  - Any claim which arises or demand for payment received after expiry date will be invalid and unenforceable.

- The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

Signed at _____________________		Date ____________________________

For and behalf of the Bank

Bank Signatory: ___________________		Bank Signatory: ___________________

Witness: ________________________		Witness: _________________________

Bank’s seal or stamp

Part 2: Pricing Data

PSC3 Option G

| Document reference | Title | No of pages |
| --- | --- | --- |
| C2.1 | Pricing assumptions: Option G | 2 |
| C2.2 | Staff rates, expenses and the task schedule. | 4 |

C2.1 Pricing assumptions: Option G

# How work is priced and assessed for payment

From Option G: Term contract

| Identified and defined terms | 11 11.2 | (17) The Price for Services Provided to Date is, for each Task, the total of - the Time Charge for work which has been completed on time-based items on the Task Schedule and - a proportion of the lump sum price for each other item on the Task Schedule which is the proportion of work completed on that item. |
| --- | --- | --- |
|  |  | (20) The Prices are - the Time Charge for items described as time based on the Task Schedule and - the lump sum price in the Task Schedule for each other item. |

From the Core Clauses:

| Identified and defined terms | 11.2 | (13) The Time Charge is the sum of the products of each of the staff rates multiplied by the total staff time appropriate to that rate properly spent on work in this contract. |
| --- | --- | --- |

and

| Assessing the amount due | 50.3 | The amount due is - the Price for Services Provided to Date, - the amount of the expenses properly spent by the Consultant in Providing the Services and - other amounts to be paid to the Consultant less amounts to be paid by or retained from the Consultant. Any tax which the law requires the Employer to pay to the Consultant is included in the amount due. |
| --- | --- | --- |

In effect Option G is a cost reimbursable form of contract with work ordered by the Employer on a Task by Task basis using the Task Schedule to compile the cost of carrying out a Task.

Expenses are calculated separately and added to the amount due for the services provided.

# Staff rates and expenses

Tendering consultants are advised to consult the NEC3 Professional Services Contract Guidance Notes before entering staff rates into Contract Data, or in section C2.2 which follows.

This is because staff rates can be established in one of three ways:

- rates for named staff,

- rates for categories of staff, or

- rates related to salaries paid to staff.

Rate adjustment for inflation, if necessary, will be based on using Option X1: Price adjustment for inflation.  See pages 13 and 14 of the PSC3 Guidance Notes.

Expenses associated with employing a staff member in Providing the Services can be listed separately either by the Employer in Contract Data provided by the Employer or by the Consultant in Contract Data provided by the Consultant.

As only the expenses listed may be claimed by the Consultant, all other cost to the Consultant associated with Providing the Services must be included within the staff rates.

Rate adjustment for inflation of expenses is explained on page 15 of the PSC3 Guidance Notes.

# The function of the Task Schedule

The Task Schedule may include items of work to be paid for on a rate (Time Charge) or on a lump sum price for the item.    Any work ordered during the term of the contract – i.e. before the Completion Date – for which there is no priced item in the Task Schedule is priced using the compensation event procedure and the resulting Price is added into the Price List.

The task schedule is prepared by the Employer for the Consultant to price, or may be prepared jointly with the Consultant.  It is typically priced in two parts as items of work to be carried out on a time basis and lump sum prices for other items of work.   The task schedule must be as complete as possible and fully representative of all the work and services which the Employer may require the Consultant to carry out.  The only unknown is when the work is to be carried out; the Task Order will be used to instruct when work to be done.

C2.2 Staff rates, expenses & the task schedule

This section can be used when the staff rates and expenses are considerable in number and more conveniently located here than in the Contract Data.  Entries in the Contract Data should refer to this section of Part 2.

State whether the staff rates and expenses exclude or include VAT.

# The staff rates are:

| No. | Designation (or category) or name of staff member | Rate per {hour, day, month} excluding VAT |
| --- | --- | --- |
|  | *Refer to Annexure___ (Pricing schedule) of the ITT |  |

- Resources are to be claimed at an hourly rate, where resources shall be allocated to the project on a full-time basis, time schedule shall be 8 hours per day, 5 days per week over 4 weeks per month totalling 160 working hours per month.

- Should there be a need for overtime, the applicable rate shall be 1.5 times standard rate for Employer approved after-hours work and 2 times standard rate for Employer approved weekend and South African public holidays worked.

- Description and explanation of rates to be provided.

- Definition of resource category levels (as a minimum):

- The resource category levels cover specialists from all the disciplines as indicated in Part 3: Scope of Work, under Section 3.5 - Resources and Skills Requirement.

- Resource Category: Senior level (Local)

- Staff Category: Information Technology Manager, Project Manager (Registered).

- Experience range: 15 to 20 years

- Key attributes:

- Relevant tertiary qualification

- Professional registration (where applicable)

- Advanced specialist skills and knowledge

- Industry knowledge

- Resource Category: Expert level (Local)

- Staff Category: Project Manager (Registered), Construction Manager, Contracts Manager, Project Planner Master, Project Cost Engineer, Industrial Engineer t, Civil Engineer, Mechanical Engineer, Electrical Engineer, Commissioning Engineer, Hydrologist, Chemical Engineer, Geotech Engineer, Instrumentation Engineer, Metallurgical Engineer, Nuclear Engineer, Petroleum Engineer, Design Engineer, Control Systems Engineer, Data Analyst, Process Engineer, Software Engineer, Risk Analyst.

- Experience range: 20 to 25 years

- Key attributes:

- Relevant tertiary qualification

- Professional registration (where applicable)

- Expert-level specialist skills and knowledge

- Extensive industry knowledge

- Resource Category: Senior level (International)

- Staff Category: Civil Engineer, Project Manager.

- Experience range: 15 to 20 years

- Key attributes:

- Relevant tertiary qualification in the engineering field

- Professional registration (with an international body)

- Advanced specialist skills and knowledge

- International industry knowledge

- International exposure and experience

- Resource Category: Expert level (International)

- Staff Category: Mechanical Engineer, Commissioning Expert, Project Planner, Cost Engineer, Project Manager, Claims Specialist, Industrial Engineer, Nuclear Engineer, Petroleum Engineer.

- Experience range: 20 to 25 years

- Key attributes:

- Relevant tertiary qualification

- Professional registration (where applicable)

- Expert-level specialist skills and knowledge

- Extensive and international industry knowledge

- Extensive international exposure and experience

- Proposals including CV’s must be provided before appointment and the relevant General Manager of the department will be required to sign off and approve the proposed resources for each Task Order.  Eskom reserves right of refusal should the proposed resource be found to be unsuitable. Eskom management may request interviews with selected individuals prior to task order contract award.

# The expenses are:

| Cost element | Unit of measure | Rate |
| --- | --- | --- |
| Fuel | per Kilometre | R 3.60 |
| Domestic hotel accommodation (inclusive of VAT and Tourism Levy) | per Night | 3 star – maximum of: R1 190.00 – room only R1 210.00 – room and breakfast R1 530.00 – room, breakfast and dinner |
| Car Rental Vehicle Category | Group B | Group B or an equivalent class. Where a different class of vehicle is required for a particular terrain or to cater for the special needs of travel, this must be signed off by the appointed contracts manager. |
| Meal allowance (only applicable for meals not provided by the accommodation) | Breakfast Lunch Dinner | R100.00 R158.50 R158.50 *Not applicable if included in room fee. |
| Air travel | Domestic and International | Economy class |

Travel requirements:

- Only Employer sanctioned travel will be paid for.

- Eskom Travel Procedure (32-1042) requirements shall apply as below but not limited to:

- For flights, three quotes must be supplied and the cheapest is to be booked.

- For Hired vehicles, only vehicles from category group B (compact or medium sized vehicle category) is to be booked.

- Accommodation requests shall be managed as per Eskom Travel Procedure (32-1042).

*Note: Travel that does not meet the requirements as stated in the Eskom Travel Procedure (32-1042) will not be re-imbursed.

# The task schedule

The following format could be used:

| No. | Items of work to be carried out on a time basis |
| --- | --- |

| No. | Items of work priced on a lump sum basis | Price (excluding VAT) |
| --- | --- | --- |

# Resources List and Skills Requirement

The service provider shall be able to mobilise following resources and skills, at a minimum, to provide services as and when required during the contract term:

- Project Manager (Senior) Registered

- Information Technology Manager (Senior)

- Industrial Engineer (Expert)

- Project Manager (Expert) Registered

- Mechanical Engineer (Expert)

- Electrical Engineer (Expert)

- Civil Engineer (Expert)

- Construction Manager (Expert)

- Commissioning Engineer (Expert)

- Contracts Manager (Expert)

- Hydrologist (Expert)

- Chemical Engineer (Expert)

- Geotech Engineer (Expert)

- Instrumentation Engineer (Expert)

- Metallurgical Engineer (Expert

- Nuclear Engineer (Expert)

- Petroleum Engineer (Expert)

- Design Engineer (Expert)

- Data Analyst (Expert)

- Process Engineer (Expert)

- Software Engineer (Expert)

- Risk Analyst (Expert)

- Control Systems Engineer (Expert)

- Project Planner Master (Expert)

- Project Cost Engineer (Expert)

- Mechanical Engineer (Expert) International

- Civil Engineer (Senior) International

- Commissioning (Expert) International

- Project Manager (Expert) International

- Project Planner (Expert) International

- Project Cost Engineer (Expert) International

- Claims Specialist (Expert) International

- Project Manager (Senior) International

- Industrial Engineer (Expert) International

- Nuclear Engineer (Expert) International

- Petroleum Engineer (Expert) International

*International is in reference to the personnel with proven international exposure and experience on the specified scope of work/ category as per task order.

The above provides the types of resources and skills that may be required for the services to be rendered under this contract. Resources will be deployed only as per each Task Order issued to the service provider.

For each Task Order, the service provider shall provide:

- Onboarding pack (for each proposed resource): Curriculum Vitae, qualifications/certification, skill matrix, workplan (within 10 working days of contract kick-off for a specific request under the Consultant agreement).

- Governance reports (as agreed to per task order): Consolidated report to be presented at relevant forum.

- Knowledge-transfer artifacts: Training materials, workshop recordings, “how-to” guides or other (to be specified by Consultant).

- Performance and status reports (as agreed to per task order): resource performance monitoring and reporting reports (to be proposed by Consultant).

- International resource or teams: GCD retains first right of refusal on international resources, this may include visiting the country, specifically for very high-end resources in order to meet and spend time/decide on placement.

Part 3: Scope of Work

| Document reference | Title | No of pages |
| --- | --- | --- |
|  | This cover page | 1 |
| C3.1 | Employer’s Scope | 32 |
| C3.2 | Consultant’s Scope (insert at award stage or delete if not applicable) |  |
|  | Total number of pages | 33 |

C3.1: Employer’s scope

Contents

Part 3: Scope of Work	31

C3.1: Employer’s scope	32

1	DESCRIPTION OF THE SERVICES	34

1.1	Executive overview	34

1.2	Interpretation and terminology	34

2	BACKGROUND AND CONTEXT	35

2.1 Background	35

2.2 Operational Context	35

2.3 GC&A Key Roles, Functions and Responsibilities	36

3	SPECIFICATION AND DESCRIPTION OF THE SCOPE OF WORK/SERVICES	37

3.1	Background And Motivation for the Scope of Work	37

3.2	General Governance, Compliance and Assurance Services Scope	38

3.3	Objectives and High-Level Deliverables	38

3.4	Detailed Governance, Compliance and Assurance Services and Deliverables	39

3.4.1 Service 1: Enhanced portfolio, programme and project reporting, system and data management	39

3.4.2 Service 2: Reviewed and implemented portfolio, programme, project and related processes governance and compliance	40

3.4.3 Service 3 Performed portfolio, programme, project and related processes oversight, monitoring and assurance reviews and reports	40

3.4.4 Service 4: Enabled project performance	45

3.4.5 Service 5: Capacitated project assessment functionality	46

3.5	Resources and Skills Requirement	46

4	CONSTRAINTS ON HOW THE CONSULTANT PROVIDES THE SERVICES.	47

4.1	Management meetings	47

4.2	Consultant’s key persons	48

4.3	Provision of bonds and guarantees	48

4.4	Documentation control and retention	48

4.4.1	Identification and communication	48

4.4.2	Retention of documents	49

4.5	Invoicing and payment	49

4.6	Records and forecasting of expenses	50

4.7	Records and forecasting of the Time Charge	50

4.8	Contract change management	51

4.9	Inclusions in the programme	51

4.10	Quality management	53

4.10.1	System requirements	53

4.10.2	Information in the quality plan	53

4.11	The Parties use of material provided by the Consultant	53

4.11.1	Employer’s purpose for the material	53

4.11.2	Restrictions on the Consultant’s use of the material for other work	53

4.11.3	Transfer of rights	53

4.12	Management of work done by Task Order	53

4.13	Health and safety	54

4.14	Procurement	54

4.14.1	Supplier Development, Localisation and Industrialisation (SDL&I)	54

4.14.2	Reconstruction and Development Programme (RDP) Goals	55

4.14.3	Skills Development (Professionals Development Programme)	55

4.14.4	B-BBEE Certificate Requirement	55

4.14.5	National Industrial Participation Programme	56

4.14.6	Maintain and/or improve B-BBEE Status	56

4.14.7	Contribution towards Corporate Social Investment (CSI)	56

4.14.8	Monitoring of SDL&I commitments	56

4.14.9	Reporting and Monitoring	56

4.14.10	Limitations on subcontracting	57

4.14.11	Attendance on SubConsultants	57

4.15	Working on the Employer’s property	57

4.15.1	Employer’s entry and security control, permits, and site regulations	57

4.15.2	People restrictions, hours of work, conduct and records	58

4.16	Cooperating with and obtaining acceptance of Others	59

4.17	Things provided by the Employer	59

4.18	Cataloguing requirements by the Consultant	59

5	LIST OF DRAWINGS	60

5.1	Drawings issued by the Employer	60

Appendix A – GC&A: Oversight, Monitoring and Assurance Function	61

# DESCRIPTION OF THE SERVICES

## Executive overview

As part of Eskom’s Group Capital Division (GCD) re-establishment initiative, GCD is contracting a specialist Governance, Compliance and Assurance services provider, to support the functions of governance, compliance and assurance functions across the Eskom business, with a special focus on the portfolios, programmes and project delivery environment.

The services shall be rendered across various business units, technologies and disciplines, on an as and when basis, and as outlined in the relevant Task Order prior to the execution of the works.

## Interpretation and terminology

The following abbreviations are used in this Scope:

| Abbreviation | Meaning given to the abbreviation |
| --- | --- |
| AFI | Approved for final inspection |
| B-BBEE | Broad Based Black Economic Empowerment |
| BRA | Benefits Realisation Approval |
| CRA | Concept Release Approval |
| CTO | Construction turnover per package/milestone |
| DRA | Definition Release Approval |
| DPM | Deliver Projects Methodology |
| EHVC | Eskom Holdings Value Chain |
| EXCO | Eskom Executive Committee |
| EPMO | Eskom Project Management Office |
| ERE | Eskom Real Estate |
| ERA | Execution Release Approval |
| FPMS | Field progress measurement system |
| GE | Group Executive |
| GC&A | Governance, Compliance and Assurance |
| GCD | Group Capital Division |
| IRA | Implementation Readiness |
| HoA | Implement and Handover |
| IT | Information Technology |
| NTCSA | National Transmission Company of South Africa |
| OT | Operational Technology |
| PDRI | Project Definition Rating Index |
| PKHI | Project Key Health Indicator |
| PDF | Portfolio Delivery Framework |
| PCM | Process Control Manuals |
| PLCM | Project Lifecycle Model |
| SDL&I | Supplier Development, Localisation and Industrialisation |
| SHEQ | Safety, Health, Environmental, and Quality |
| SOW | Scope of Work |
| WBS | Work Breakdown Structure |

# BACKGROUND AND CONTEXT

## 2.1 Background

The Group Capital Division (GCD) is accountable for strategically planning, developing, and executing capital projects in Eskom. These capital projects are classified in accordance with its complexity and strategic importance.

GCD should also provide governance, compliance and assurance on all projects within GCD and selected projects across the Eskom divisions and subsidiaries.

GCD has established the GC&A Operating Unit with the mandate to oversee group project governance frameworks, compliance and providing monitoring, oversight and assurance, supported by strategic project reporting and evaluation.

Therefore, the contractor shall provide services to enable GC&A to deliver on its mandate.

## 2.2 Operational Context

An objective of Eskom is to create assets in support of its strategic intent and corporate plan, ensuring economic growth and social prosperity in South Africa.

GC&A is an advisory organisation and mandated to provide Eskom Board, the Eskom Executive Committee (EXCO), the Group Chief Executive Officer and the GCD Group Executive (GE) independent governance, compliance and assurance reports and reviews on validated project data across Eskom’s divisions and subsidiaries’ portfolios, programmes and projects. Timeous visibility on critical and constraining issues, recommendations and solutions are provided in support of successful asset creation and infrastructure project delivery. GC&A is an enabler that strives for continuous improvement through embedment and management of lessons learned.

The GC&A team supports the GE by providing detailed expert analysis of the project reports, which may then be followed by a briefing session to update the GE on the respective projects and the project progress towards achieving forthcoming milestones, including but not limited to discussing key issues/trends and high-risk activities with potential mitigation measures.

The GC&A team will be instrumental in engaging with the project teams, analysing progress and recommending appropriate execution methodology and through the use of skilled personnel to enable key projects specific milestones to be met. The unrelenting focus, coupled with strategic and tactical “deep dives”, collaborative reviews and analysis will result in enhancing the projects likely successful outcome. In addition, collaborative reviews will be scheduled with the intention of undertaking deep interrogation of the project schedules and cost, providing an independent view of project delivery.

GC&A will also provide robust oversight services through issue exploration by following the “Defence in Depth Philosophy”, to make precursors for performance deviations visible, determine root and contributing causes to project performance deviations, provide analysis on organisational weakness classifications and track and monitor delivery with solution driven recommended plans to deal with negative performance deviations.

The purpose is:

- To avoid performance deviations proactively – by anticipating events and managing the way they impact on projects.

- To minimise the error rate by focusing on strengthening GCD’s defences and the rigorous use of prevention and improvement techniques.

- Minimise error consequence – by eliminating latent flaws and focusing on organisational effectiveness and reinforce good practices.

GC&A will implement as part of oversight and integrated business improvement systems, multidisciplinary and holistic frameworks for the project environment (internal, external and international) to ensure organisational and project operational error prevention and performance improvement. More specifically, it will assist in identifying and analysing important human and organisational performance gaps; a defence-in-depth philosophy to mitigate against human and organisational failures or risks; a framework for prevention and improvement principles which could be integrated into core business processes and practices; prevention and improvement techniques on individual, leader and organisational level; and an assurance framework that evaluates effectiveness of the cross-functional integration and interaction between the organisation, leader and individual.

## 2.3 GC&A Key Roles, Functions and Responsibilities

GC&A functions as a professional advisory body, independent of the projects within GCD, should be seen as an enabler that strives for continuous improvement through lessons learned by performing the following key functions:

- Strategic Reporting, Data Management, Systems & Evaluation function: Responsible to consolidate project reports into project, programme, portfolio, executive and strategic levels and distribute to various stakeholders and governance forums as per stakeholder requirements. In addition, provides relevant reports on ad hoc basis and ensure data management for data mining and analysis and record keeping of all the outputs of the group.

- Governance Compliance & Advisory function (Are we doing the right things?): Responsible for monitoring and evaluating regulatory compliance - adherence to policies, procedures, and controls.

- Oversight, Monitoring and Assurance function (Are we doing the things right?): Responsible for continuous strategic and tactical assurance, including collaborative reviews and application of the deep dive methodology to provide independent reviews and an independent opinion about project status and health, and forecasting project performance while embedding lessons learned in collaboration with project teams.

- Project Performance Enablement function: Responsible for providing robust holistic oversight service and integrated performance analysis through issue exploration by applying the “Defence in Depth Philosophy” making precursors for performance deviations proactively visible, determining root and contributing causes to project performance deviations, detecting latent deficiencies and compromised defences/controls that create an environment for performance deviations, and to reinforce good practices.

Furthermore, the GG&A functions ensure the implementation of integrated business improvement to ensure organisational, portfolio, programme and project performance improvement, and is also responsible for verification of project reports and system data.

# SPECIFICATION AND DESCRIPTION OF THE SCOPE OF WORK/SERVICES

## Background And Motivation for the Scope of Work

GCD’s performance has a crucial impact on Eskom and ultimately the economy of South Africa. The stakeholders of GCD involve the organisation’s Shareholder and the wider stakeholder community including regulatory authorities. GCD’s client offices are within the Eskom Real Estate (ERE), Group Technology, Generation, Distribution and Renewables Divisions and the NTCSA subsidiary (but not limited to).

The profile of the capital projects delivered within GCD is summarised (not exclusive) below:

- Coal Fired Technologies

- Hydro and Pumped Storage Technology

- Open or Combined Cycle Gas Turbines Technology

- Heat Recovery Steam Generator Power Technology

- Nuclear Technologies

- Renewables Technologies

- Energy Storage Technologies

- Emissions Abatement Technologies

- Information Technology (IT) /Operational Technology (OT) Projects

- Distribution Infrastructure Technology

- Transmission Infrastructure Technology

The disciplines integrated and involved in delivering a project, apart from the Portfolio, Programme and Project Management capabilities (subject to the Deliver Projects Policy), are various and embrace the application and adherence of the discipline applicable Eskom policies and processes. These are (not exclusive) Procurement and Supply Chain Management, Contracts Management, Project Engineering, Construction Management, Commissioning, Project Controls (addressing project risk, schedule and cost), Quantity Surveying, Finance, Project Accounting, the applicable Business Sustainability capabilities of Safety, Health, Environmental, and Quality (SHEQ), Strategy, Planning and Legal and Regulations.

The projects are assessed in terms of its strategic importance, integration of numerous/various distinct disciplines, the level of impact of legal, social and/or environmental implications while preforming the project, stability of the overall project context and its financial impact on Eskom and ultimately on South Africa.

The spectrum of stakeholders, their strategic importance and the (high) number of reports require an optimal data management process, based on central repositories, data analysis, tracking of treatment actions and reliable, repeatable and “true” information. The quality of reporting to the GE and the GCD stakeholders is critical, and the reporting processes and system(s) in use should be effective and the reports reflecting to balance the quantity and quality of the information.

The GCD project milestones contribute significantly to the Shareholder and annual GCD compact. The GC&A function shall greatly enhance the quality of reporting by robustly interrogating project reports. This will further be supported by continued site presence whereby they will undertake detailed analysis of project activities and progress towards agreed milestones. The outcomes of these analysis and progress updates will be available on a timeous basis, which then allows proactive executive management of GCD projects from an informed independent information base.

Eskom’s current financial health status has also triggered the need for oversight and analysis pertaining to aspects such as cost to completion performance, cost benefit analysis, compensation events/claims, and project delays. Therefore, the focus of the GC&A function is broadened to span across portfolio, programme and project management and the respective project life cycle models (PLCMs) with a strong focus on integrated project controls, addressing, project risk / treatment management, cost/schedule performance, cost and schedule interrelationships, earned value, cost benefit analysis, benefits realisation and contract claims management and other contractual related matters. GC&A will also monitor and provide oversight and assurance on quality, safety, engineering, governance amongst others.

It is also important to note that the number of projects to which oversight, monitoring and assurance is required has significantly increased to the entire Eskom Group (i.e. projects in Eskom divisions and subsidiaries, e.g. Generation, Distribution, Corporate Divisions, Renewables, NTCSA, etc). In addition, collaborative reviews will be scheduled with the intention of undertaking a deep interrogation of the project schedules and cost, providing an independent view of project performance, milestone delivery and probability of meeting approved scope, cost and time approvals, business requirements and benefits.

## General Governance, Compliance and Assurance Services Scope

The Governance, Compliance and Assurance Services will be provided on an “as and when required” basis; in line with a Task Order to be issued by Eskom to the service provider. The service provider must have a proven track record in the provision of Governance, Compliance and Assurance services and carry the appropriate technical qualifications and approved accreditations in line with South African legislative requirements. This shall also apply to personnel which will be assigned by the service provider to perform work under this agreement.

The scope of work entails the provision of Governance, Compliance and Assurance Services to the Group Capital Division, and by extension to the various departments within the portfolio, programme and project delivery value chain within Eskom.

## Objectives and High-Level Deliverables

Objectives

This Scope of Work (SOW) aims to achieve the following strategic objectives:

- Enhanced effectiveness of risk management, governance and controls

- Leveraged digitalisation to improve quality of information

- Improved reputation to be beyond reproach

- Attract, develop and retain skills

Services and High-level Deliverables

The high-level deliverables which form part of the scope of services, and the strategic objectives which are supported by these deliverables are:

| Service # | High level deliverables | Strategic (and GC&A) Objectives |
| --- | --- | --- |
| Service 1: | Enhanced portfolio, programme and project reporting, system and data management. | - Leveraged digitalisation to improve quality of information. - Attract, develop and retain skills. |
| Service 2: | Reviewed and implemented portfolio, programme, project and related processes governance and compliance. | - Ensure portfolio, programmes and portfolios meet their approved objectives and benefits. - Enhanced effectiveness of risk management, governance and controls. - Attract, develop and retain skills. |
| Service 3: | Performed portfolio, programme, project and related processes oversight, monitoring and assurance reviews/reports. | - Ensure portfolio, programmes and portfolios meet their approved objectives and benefits. - Improved reputation to be beyond reproach. - Attract, develop and retain skills. |
| Service 4: | Enabled Project Performance: a) providing robust holistic oversight service and integrated performance analysis through issue exploration by applying the “Defence in Depth Philosophy”. b) Implements integrated business improvement to ensure organisational and portfolio, programme, project and related processes performance improvement. | - Ensure portfolio, programmes and portfolios meet their approved objectives and benefits. - Improved reputation to be beyond reproach. - Attract, develop and retain skills. |
| Service 5: | Capacitated project assessment functionality. | - Enhanced effectiveness of risk management, governance and controls. |

## Detailed Governance, Compliance and Assurance Services and Deliverables

The five services which have been introduced above, together with their related deliverables are expounded in detail as follows:

- 3.4.1 Service 1: Enhanced portfolio, programme and project reporting, system and data management

3.4.1.1 The activities involved are:

- Review, develop/improve and implement current reporting, data management and systems processes, procedures, standards and reporting templates, and close the gaps.

- Develop and implement verification processes and procedures ensuring verified project reports and system data.

- Review current reporting, data management and systems processes and advise on gaps thereby assisting GCD to implement and ensure compliance with all applicable laws, regulations, and standards.

- Consolidate project reports into project, programme, portfolio, executive and strategic levels and distribute to stakeholders and governance forums in accordance with stakeholder requirements.

- Provide relevant reports on ad hoc request basis.

- Ensure data management for data mining, analysis and record keeping of all the outputs of the group.

- Manage business documentation and records.

- Ensure database and analysis systems is compatible with Eskom systems.

- Verify project reports and system data for accuracy, transparency and completeness.

- Verify (oversight) of consolidated reports.

3.4.1.2 Service 1 Deliverables:

- Data mining and analyses applications and tools.

- Design of various reports for applicable stakeholder needs (outline and framework).

- Reporting, process flows and alignment of data systems.

- Reporting tools and templates.

- Optimised reporting.

- Identified shortcomings on data systems and improvement recommendations.

- Verified project reports, verified (oversight) consolidated project reports and system data for accuracy, transparency and completeness.

- Reviewed and updated reporting, data management and systems guidelines, processes, procedures, standards and templates.

- Consolidated and ad hoc reports and presentations.

- 3.4.2 Service 2: Reviewed and implemented portfolio, programme, project and related processes governance and compliance

3.4.2.1 The activities involved are:

- Monitor and evaluate regulatory compliance in terms of adherence to policies, processes, procedures, and controls.

- Develop, improve and implement the monitoring and evaluating regulatory compliance systems, processes and templates while adhering to Eskom policies, processes, procedures, and controls.

- Review and optimise the method(s) and output of the methodology and governance models and frameworks applied within the GC&A operating model.

- Conduct pro-active project reviews/assessments, internal audits, third-party reviews, governance reviews and compliance checks to assess adherence to regulations and policies.

- Develop response plans for governance failures or compliance breaches and facilitate lessons-learned exercises.

- Review, identify gaps, develop/improve current governance and compliance planning processes.

- Review, implement and improve governance frameworks through policies, processes, procedures, and reporting structures.

- Review project governance and structure, as well as implementing agreed recommendations.

- Provide oversight on compliance policies alignment with evolving legal and industry standards.

- Undertake compliance reviews to existing processes across projects in Eskom in accordance with existing policies and the Eskom Holdings Value Chain (EHVC) processes (as captured in Process Control Manuals (PCMs)).

3.4.2.2 Service 2 Deliverables

- Reviewed and updated governance frameworks within the Eskom policies, processes, procedures, and reporting structures.

- Reviewed and updated governance artefacts (such as policies, standards and control points in the EHVC PCMs).

- Reviewed and updated compliance review templates.

- Reviewed and improved GC&A functionality; and specific GC&A methodology and operating model.

- 3.4.3 Service 3 Performed portfolio, programme, project and related processes oversight, monitoring and assurance reviews and reports

3.4.3.1 The activities involved are:

- Review existing assessment/assurance frameworks and templates and develop/implement the necessary improvement.

- Review, refine/develop/implement proactive assurance measures.

- Review, identify gaps, develop/implement improved oversight, monitoring and assurance processes and procedures, emphasizing the necessary planning processes.

- Provide assurance at project, programme and portfolio levels to assess health and viability and whether strategic objectives will be met including risks.

- Establish the systems and processes to ensure continuous strategic and tactical assurance, including collaborative reviews.

- Provide independent reviews and unvarnished opinions about project status and health.

- Analyse project performance and trends and, based on the analysis, forecast future project performance and trends.

- Provide recommendations for potential solutions to project challenges as required.

- Ensure embedment of lessons learned in collaboration with project teams in terms of the tracking, managing and the application thereof in similar projects.

- Conduct strategic and tactical assurance, including collaborative reviews and application of the deep dive methodology to provide independent reviews and an independent opinion about project status and health.

- Review project statuses for consistency.

- Provide cost analysis.

- Undertake Schedule Risk Analysis, analyse variances against the baseline and analyse schedule uncertainties.

- Perform Risk Analysis – analyse the impact of uncertainty and risk events.

- Verify variance to key milestones by cause, effect and mitigation.

- Ensure identification, assessing, and monitoring of business, portfolio, programme and projects risks during project delivery.

- Review resource plans identifying whether the resources are adequate.

- Apply the divisional Benefits Registers and create a project key milestone database.

- Analyse project float.

- Assess methods and benchmarks between sites.

- Review, identify gaps, develop/implement improved schedule methodology for optimisation.

- Perform/assess/conduct/review:

  - schedule cost interrelationship analysis.

  - schedule acceleration investment as cost benefit analysis.

  - resources scheduling and productivity.

  - Earned Value Analysis; produce S-Curves.

  - analysis and recommendations for cost optimisation.

  - cost benefit analysis on operational, tactical and strategic levels.

  - projects integrated schedules for best practice compliance.

- Correlate schedule forecasting with cost forecasting.

- Create analysis presentation material for GE’s based on portfolio, programme and project performance.

- Provide oversight and assurance across the PLCM on all project management matters i.e. quality, safety, cost, claim management, construction laws, permits and licences, compensation events.

- Evaluate and analyse GCD contracts in term of scope definition, contracting strategies and contracting structure; provide reports on findings and recommendations.

- Review Employer Contract Packages/Contractor’s Claims/Employer’s Counter Claims.

- Monitor the resolution of the Employer’s Commercial and Contractual challenges on a task-by-task basis.

- Evaluate/review valuation variations and change orders and impact.

- Determine the probability of achieving a project’s cost and schedule objectives.

- Provide regular feedback with presentations to the relevant Stakeholders e.g. GE, Executives, Project Teams, etc.

- Transfer knowledge and skills to the Eskom GC&A staff & Eskom role players.

- Provide unbiased, independent evaluation of prospects for success.

Oversight, monitoring and assurance key activities grouped and described that may include for example:

- Oversight:

  - Continuously validate reported project progress, physically observed and checked.

  - Strategically analyse the reported progress shortfalls and accept the mitigation plans and revised schedules.

  - Review Integrated Risk Management (Identification, Assessment and Treatment of Risks).

  - Report SHEQ trends and potential outcomes

- Monitoring:

  - Systematically, purposeful and continuously observe the progress to achieve portfolio, programme or project objectives, or the lack thereof.

  - Thus, it forms the basis for corrective actions, both substantive and operational, and enables the reinforcement of initial positive results.

  - Identify the lessons learned when executing similar projects.

  - Track and analyse the progress activities in terms of on-course and on-schedule to meet objectives and performance targets.

- Assurance:

  - Consolidate, implement and track the lessons learned.

  - Validate the data repository to forecast dates.

  - Confirm the robustness of the project schedule (in terms of integrity and timeframes).

  - Verify compliance to the schedule format.

  - Confirm the robustness of the project organisation and resourcing (interface management).

  - Review the completeness of Integrated Risk Management (Identification, Assessment and Treatment of Risks).

  - Strategic Assurance:

    - Part of corporate governance, provide an independent and objective oversight of the likely future performance of projects and their alignment to the strategic direction of the organisation.

    - Provide assurance (conformance and concordance) that what was strategically planned (benefits to achieve), had ultimately been delivered (in terms of projects (benefit enablers) through an Eskom approved PLCM Subset).

Oversight, monitoring and assurance key activities grouped, described and added within the PLCM phases that may include for example:

- Pre-Project phase: Confirm the strategic fit and classification of the project by confirming and validating the following:

  - The provision of the long-term funnel view as input into planning for strategic resource capacity.

  - Registered divisional benefits: Mapped and profiled benefits to enable effective measurement and tracking and adjudicated benefits realisation governance.

  - Planned benefits in approved the Benefits Realisation Plan(s): Linked (long-term funnel) projects to a specific benefit and delivery portfolio (portfolio demand) with determined benefits targets and milestone dates.

  - Generated planning alternatives to satisfy the required business change (pre-feasibility).

  - Validated funding options and selection process.

  - Reviewed appropriateness of the portfolio component structure (governance structure in which projects are delivered).

  - Validate the:

    - Justified project’s thorough appraisal of the short-listed planning alternatives whether to proceed or not.

    - Prepared Concept Release Approval (CRA) to obtain mandate to arrive at a single solution (concept design) in the next phase (feasibility study).

- Concept phase: Provide assurance on the business planning phase and the feasible single solution (concept design) by:

  - Evaluate macro-economic risks associated with portfolio demand.

  - Review the respective project definitions and provide assurance that it meets strategic objectives and will deliver the benefits.

  - Ensure that the projects within the portfolio are delivered within its respective CRA mandate for scope, cost and time.

  - Ensure Engineering governance is followed for the project concept design.

  - Forecast and predict associated risks for the project design and the execution of the project asset.

  - Validate funding options and selection process.

  - Validate the:

    - Demonstrated commercial viability (the financial evaluation to be a bankable project and ascertain affordability).

    - Prepared Definition Release Approval (DRA) to obtain mandate to proceed with formal procurement of a stable converged solution (basic design) in the next phase.

- Definition phase: Provide assurance that the basic designs are conducted as per project specification by:

  - Validate project assumptions and design principles.

  - Validate and assure the optimised Portfolio Investment Plan against the Benefits Realisation Plan.

  - Ensure Engineering governance is followed for the project basic design.

  - Monitor regulatory compliance.

  - Validate funding options and selection process.

  - Review appropriateness of portfolio component structure.

  - Validate the:

    - Demonstrated investment viability.

    - Demonstrated stable, converged solution (basic design) with detailed final project scope, schedule and cost estimate.

    - Prepared Execution Release Approval (ERA) to obtain the decision to contract in the next stage.

- Execution phase: Monitor and assure the project schedule, cost, quality, safety, stakeholder engagement risks and impacts, and confirm the project is handed over for commercial operation by:

  - Collate and validate project information.

  - Ensure Engineering governance is followed for the project final design.

  - Conduct interpretive analysis on project performance.

  - Establish trends and forecasts based on interpretive analysis and monitor these.

  - Identify and track risks and impacts.

  - Identify and highlight lessons learned.

  - Report on portfolio performance, future outlook, risks and recommended actions.

  - Validate the:

    - Implementation Readiness (IRA gate): e.g. finalised project location to establish the site, confirmation of legal approvals, and the final design to be ready for implementation.

    - Implement and Handover (HoA gate), with the objective of:

      - The final design implemented safely, on time, and within budget.

      - The stable project asset is handed over to operations after confirmed operational readiness for operational and commercial use.

- Finalisation phase: Monitor the evaluation of the project and confirm the administrative close-out of the project by:

  - Evaluate the confirmation that all obligations (including warrantees/guarantees, contracts, other legal documents etc.) have been transferred to operations to maintain until maturity e.g. valid appointed DCF Holder(s) per outstanding contract.

  - Monitor that all aspects of the project are closed out, including the relevant systems.

  - Assure the evaluation of the project execution performance in terms of the approved Investment Committee project mandate (scope, time, cost), as well as the performance/effectiveness of each area of the project, in accordance with the measurement metrics as defined for each of the subsidiary plans in the Project Management Plan.

- Post Project phase: Monitor the confirmed realisation of benefits results post the HoA gate by:

  - Evaluate the measured realisation of benefits for the Post Project phase duration up to the predetermined date of the Benefits Realisation Approval (BRA) gate.

  - Validate the evaluated chosen solution (business case) for suitability.

  - Evaluate the approved final Benefits Realisation Report.

  - Conduct interpretive analysis on the required treatment actions identified to achieve desired benefits, including identification of future projects.

  - On a specific benefit, conduct interpretive analysis on the consolidated benefits realisation results of the various delivery portfolios to obtain the summated and final results of the specific benefit. Evaluate these results against the desired future state change the benefit had to achieve, as specified in the Benefits Register, and against the values and its contribution to the divisional objectives.

3.4.3.2 Service 3 Deliverables:

- Output of the activities described in Appendix A.

- Established oversight, monitoring and assurance processes.

- Developed and optimised maturity model.

- Schedule(s) to conduct project reviews.

- Oversight, monitoring and assurance reports and presentations to various stakeholders.

- Captured and embedded lessons learned with implemented and tracked recommended actions.

- Conducted project evaluations (desk top reviews).

- Mini and deep dive reviews on project performance across the Deliver Projects Methodology and EHVC processes applicable to deliver projects.

- Independent reviews and an independent opinion(s) about project status and health.

- Forecasted project performance.

- Embedded lessons learned in collaboration with project teams.

- 3.4.4 Service 4: Enabled project performance

3.4.4.1 The activities involved are:

- Develop and implement, as part of oversight, an integrated business improvement systematic, multidisciplinary and holistic framework for the project environment to ensure organisational and project performance improvement.

- Develop and implement an assurance framework that evaluates effectiveness of the cross-functional integration.

- Provide robust holistic oversight service and integrated performance analysis through issue exploration by applying the “Defence in Depth Philosophy”.

- Make precursors for performance deviations visible.

- Determine root and contributing causes to project performance deviations.

- Provide analysis on organisational weakness classifications.

- Detect latent deficiencies and compromised defences/controls that create an environment for performance deviations.

- Identify latent organisational flaws to be eliminated to reinforce good practices.

- Implement, track and monitor delivery of solution driven recommended plans to deal with negative performance deviations.

- Assist in the development and implementation of project performance and enablement procedures.

- Review, identify gaps, develop/improve current project performance and enablement planning processes.

- Strengthen GCD’s defences and the rigorous use of prevention and improvement techniques.

- Establish and maintain knowledge management.

- Capture lessons learned and ensured successful implementation in the organisation.

- Review effect of lessons learned implementation and reinforcement of good practices.

3.4.4.2 Service 4 Deliverables:

- Integrated business improvement’s systematic, multidisciplinary and holistic framework for the project environment to ensure organisational and project performance improvement.

- Assurance framework that evaluates effectiveness of the cross-functional integration and interaction between the organisation, leader and individual.

- Framework for prevention and improvement principles which could be integrated into core business processes and practices.

- Deviations reports on root and contributing causes to project performance, including recommendations.

- Deviation report tracking of the progress on the implementation of the recommendations.

- Solution driven recommended plans dealing with negative performance deviations.

- Established knowledge management.

- Identified, tracked and eliminated latent organisational flaws.

- Reinforced and implemented good practices.

- 3.4.5 Service 5: Capacitated project assessment functionality

3.4.5.1 The activities involved are:

- Analyse and advise on continuous business improvement of current Deliver Projects Methodology (DPM) project assessment methodology (e.g. gate readiness reviews) and tools (e.g. Project Definition Rating Index (PDRI), Project Key Health Indicator (PKHI), Project Maturity Model (PMM), Construction readiness assessment (accessible/available in the Eskom environment)).

- Analyse and advise on continuous business improvement of the approved divisional gate readiness assessment templates.

- Prepare, update and obtain approval for the plans in accordance with business requirements (across Eskom) for example:

  - Gate readiness reviews.

  - Project assessments.

  - Other project review structures.

- Conduct the reviews and assessments in accordance with the approved plans and schedules.

- Capacitate Eskom teams through formal training, on-job training and appropriate skills transfer interventions.

- Provide the authorised reports for the respective gate readiness reviews and the project assessments.

3.4.5.2 Service 5 Deliverables:

- Change requests on DPM projects assessment methodology.

- Updated and published divisional gate readiness assessment templates.

- Gate readiness assessment plan(s)

- Project assessment plan(s).

- Conducted and authorised gate readiness reviews.

- Conducted project assessments and reports.

# CONSTRAINTS ON HOW THE CONSULTANT PROVIDES THE SERVICES.

## Management meetings

The Employer’s Agent will schedule and communicate the meetings as required for work to be caried out under each Task Order. Regular meetings of a general nature will be convened and chaired by the Employer’s Agent as follows, at a minimum:

| Title and purpose | Approximate time & interval | Location | Attendance by: |
| --- | --- | --- | --- |
| Risk register and compensation events | Weekly on ________ at ___ | TBA | Employer’s Agent, Consultant and other relevant invitees |
| Overall contract progress and feedback | Monthly on _____ at ___ | TBA | Employer’s Agent, Consultant and other relevant invitees |
| Technical Meetings | Fortnightly on ______at ____ | TBA | Employer’s Agent, Consultant and other relevant invitees |

Meetings of a specialist nature may be convened as specified elsewhere in this Scope or if not so specified by persons and at times and locations to suit the Parties, the nature and the progress of the services.  Records of these meetings shall be submitted to the Employer’s Agent by the person convening the meeting within five days of the meeting.

All meetings shall be recorded using minutes or a register prepared and circulated by the person who convened the meeting.   Such minutes or register shall not be used for the purpose of confirming actions or instructions under the contract as these shall be done separately by the person identified in the conditions of contract to carry out such actions or instructions.

- The Consultant and Eskom will review the deliverables in meetings organized and scheduled by the     Consultant.

- The Consultant ensures that all follow-up actions are carried out within the time stipulated.

- Eskom may, in addition to the scheduled review meetings indicated, request additional reviews.

- Eskom may involve independent third parties in any of the review meetings.

## Consultant’s key persons

The Consultant shall appoint a Project Manager / Team Leader as a key person for the contract who:

a)	Functions as single point of contact between Eskom and the Consultant.

b)	Plans and manages the delivery of the services in accordance with the contract requirements.

c)	Acting with care and diligence: ensuring that all duties are carried out with due care, skill and diligence

d)	Compliance with regulations: adhering to the standards and rules set by legislation

e)	Fulfilling contractual obligations: meeting the terms of contracts and agreements

f)	Management and oversight

The Consultant shall submit to the Employer an organogram for the provision of these services, with contact details and line of communication.

## Provision of bonds and guarantees

The form in which a bond or guarantee required by the conditions of contract (if any) is to be provided by the Consultant is given in Part 1 Agreements and Contract Data, document C1.3, Sureties.

The Employer may withhold payment of amounts due to the Consultant until the bond or guarantee required in terms of this contract has been received and accepted by the person notified to the Consultant by the Employer’s Agent to receive and accept such bond or guarantee.  Such withholding of payment due to the Consultant does not affect the Employer’s right to termination stated in this contract.

## Documentation control and retention

### Identification and communication

All documents, except data sheets, conform to the formatting standards as listed in paragraph Document and data numbering. Any deviation from this format is to be agreed to in writing by the Employer.

Where no standard is prescribed, the Consultant proposes the format and contents to the Employer for review and acceptance.

All deliverable data are expressed in SI (metric) units of measurement.

Document Format

Document and data numbering

A unique Identification Code Number is assigned to each document or data so that it can be:

- correctly associated with its related data and items;

- referred to precisely; and

- retrieved when necessary.

Revision identifiers

Documents and data have revision identifiers to indicate the current revision status.

Document identification

Each document provides the data, as listed below, to properly identify the document. The following are indicated on each page of a document:

- Company Name

- Proprietary Classification

- Document Title

- Document Number

- ‘Revision’ – document revision identifier

- Date

- ‘Page number’ of ‘number of pages’

- Each page of a document, including all attachments, is numbered consecutively from the first to the last page.

Amendment history

Each document includes an amendment history that indicates the following for each revision:

- Revision identifier.

- Date (either release date or effective date).

- Preparer.

Approval signatures

Each document includes the names and signatures of the preparer, reviewer and approver.

Document Copies and Software Formats

Documents for interim reviews are submitted in Adobe PDF format and in Microsoft format. All final versions of documents are submitted as one hard (paper) copy and on a USB drive (in Adobe PDF format and in Microsoft format) which is uniquely identified on it as to its contents.

### Retention of documents

Copies of documents, records, calculations and associated raw data are stored in a format that can be read by the user, or converted to human readable form, regardless of the media used. Copies are stored in such a way that they remain legible, readily identifiable and retrievable for the entire lifetime of the services and for at least five years after.

## Invoicing and payment

The following details shall be shown on or attached to each Invoice to show how the amount due has been assessed:

Bill of Items, with unit of measure, quantity, rate and total per item

Task Order Number and Description

Dates/period when services were delivered

Location or place where the services were rendered

The Consultant shall address the tax invoice to _________________________ and include on it the following information:

- Name and address of the Consultant and the Employer’s Agent;

- The contract number and title;

- Consultant’s VAT registration number;

- The Employer’s VAT registration number 4740101508;

- Total amount invoiced excluding VAT, the VAT and the invoiced amount including VAT;

- (add other as required)

The invoice submission must be in compliance with Clause Z20 under Contract Data.

- Invoice to be submitted with supporting evidence such as:

- Travel claims: GPS/ Map image of the distance claimed.

- Flights: a boarding pass, a flight confirmation or itinerary, or a receipt from the airline

- Accommodation: accommodation invoice and proof of payment.

- Car hire invoice.

- Billable hours: shall be claimed as per time tracking system evidence supplied. As the Employer is only liable for hours of work related to the scope of this contract.

- Travel disbursements will be assessed and paid as per Eskom Business Travel Management Procedure 32-1042

- Invoices that are submitted without the correct supporting evidence will be rejected and returned for clarification. Payment periods will recommence upon receipt of a valid and complete invoice with al required supporting documents.

- The Employer reserves the right to request additional supporting documentation for any invoiced amount and to withhold payment for any item not adequately evidenced, pending resolution.

Procedures for invoice submission and payment will be confirmed by the Employer’s Agent.

## Records and forecasting of expenses

- The Consultant shall maintain accurate, complete and up to date records of all expenses incurred in connection with the provision of services under this contract.

- Only time charge, travel costs will be reimbursed as per Eskom’s Eskom Business Travel Management Procedure 32-1042

- All expense records shall be supported by appropriate documentation such as time sheets, invoices and payroll summaries shall be made available to the Employer upon request.

- The Consultant shall prepare and submit to the Employer a monthly forecast of the expected expenses for the duration of the services including staffing levels, rates or other costs elements in line with the reimbursable costs on the pricelist.

- Forecasts shall include:

- Actual expenses incurred to date

- Projected expenses for the remaining period of the service

- Explanations for any material variances from previous forecasts or budgeted costs

- Retention of all expense related records shall be as per clause 13.6.

- The invoices/receipts for all claimed expenses to be reimbursed at cost. In addition, the following must be:

- When claiming km travelled the requirements of the Eskom Travel Procedure 32-1042 is adhered to (providing of google maps for the route travelled, deducted the home-work home km from the total km’s travelled etc.).

- All travel and accommodation need to be pre-approved by the Employer. For approval, the planned travel and booking information requirements (as per 32-1042) are to be submitted timeously to the Employer for approval.

## Records and forecasting of the Time Charge

- The Consultant shall maintain accurate and verifiable records of time worked by all personnel engaged in the delivery of services under this contract.

- These records shall include as a minimum, the name and surname of the individual, their role, dates and hours worked, location and the scope to which the time was charged.

- Time records shall be supported by appropriately authorised timesheets or electronic time-logging systems, and shall be submitted to the Employer as supporting evidence for payment.

- The Consultant shall submit to the Employer on a monthly basis, a forecast of the time charges for the remainder of the contract period. The forecast shall include:

- Cumulative actual time charges to date.

- Forecasted time charges to Completion

- Any known or anticipate changes in staffing, hours or rates that may impact total time-based costs.

- The Consultant shall immediately notify the Employer in writing of any significant variance (+- 10%) between the forecasted time charge and the previously agreed budget.

- The Employer shall have the right to inspect and audit the Consultant’s time records and forecasting methodology upon reasonable notice during normal working hours.

- The Consultant shall retain all time charge records and supporting documentation as per clause 13.6.

- Working hours are as per the site agreements

- Overtime is billable for hours more than hours 8 worked a day at the normal rate, provided it has been pre-approved by the assigned manager

- The Employer will remunerate 50% of the time the Consultant spends travelling, whereas the project site will be the base for the Consultant. Travelling within a 50km radius from base will not be reimbursable.

## Contract change management

Either of the contracted parties can initiate the process for changes to be enacted on the contract. The initiating party shall officially notify the other party, about the intention to initiate change(s) in the contract. Such notification shall be in writing and issued by the authorised or duly delegated official of either of the parties.

The Contract change process shall be managed as follows:

- Submission of the notification to request a change in the contract

- Review of the request to change the contract

- Meeting to discuss the proposed change(s) to the contract, and the implications thereof

- Recording and circulating the meeting minutes for adoption

- Submission of the contract change request to the relevant authorities for consideration

- Presentation of the change request at the relevant committees for approval, as applicable

- Communicating the outcomes of the contract change request submission/presentation

- Preparing and issuing the amended contract or addendum to the contract, based on the approved changes, as applicable

- Signing of the amended contract by the Consultant and the Employer

- Record the contract change and close

## Inclusions in the programme

In addition to the requirements defined within Clause 31.2, the Consultant will need to adhere to the following:

- The Work Breakdown Structure (WBS) shall be deliverable orientated and aligned to the activity schedule.

- The Consultant shall provide the detailed WBS to reflect the entire scope of the project that will be used to develop the Integrated Work Breakdown Structure (IWBS).

- The IWBS for the project shall be based on the final contracted scope of work and will be jointly developed by the Employer’s Agent and the Consultant and will be agreed and finalised with the Consultant within 30 calendar days after contract award.

- The Consultant shall adhere to the IWBS.  Any required changes will be submitted as a project change request and will be managed via the Contract Change Management approval process.

- The programme will be managed in Primavera P6 15.2 or latest version.

- The programme must be based on the agreed WBS and the activities must be coded according to the agreed IWBS.

- The activities shall be deliverable based.

- The method of programming to be used is the CPM (Critical Path Method) and shall be maintained throughout the monitoring and controlling and close out of the contract.

- The Consultant programme shall be a resource loaded programme (to be submitted at tender phase for acceptance).

- The progress measurements method will be agreed with the Consultant.

- The payments shall be linked to all preceding activities that demonstrate full completion of the activities and shall be aligned with the Forecast Rate of Invoicing (FRI) and shall be linked into the succeeding activities.

- Once the programme has been accepted by the Employer’s Agent (i.e. cost loaded according to the pricing structure), the programme shall be baselined.

- The accepted programme sequence will be closely monitored and out of sequence works shall be kept to the minimum and shall timeously submitted for acceptance by the Employer’s Agent.

- The Consultant shall submit the programme technical checklist for ensuring that the programme meets best practice programming (14-point health check) criteria and supports the Critical Path Method (CPM).

- The programme must contain sufficient detail to be able to apply the Earned Value Methodology and to supply the Employer with the relevant data as required by this specification.

- Activities shall not exceed more than thirty (30) days in duration shall be broken down into detailed sub-tasks.

- The Project Calendar shall be based on 5 day working week or as agreed between the Employer’s Agent and Consultant.

- Sigmoid Curve (S-Curve) on baseline, progress and forecast to be submitted with each schedule submission.

- The Consultant will provide a copy of the programme (in Primavera P6 electronic format), with sufficient detail to the working level activities, for inclusion in the project master programme.

- The Consultant programme will be coded with integration codes (IWBS), supplied by the Employer that will enable the integration with the master programme. The Consultant will maintain the integration codes in the Consultant programme throughout the contract.

- The Consultant must submit the list of Project and Payment Milestones to the Employer’s Agent for acceptance 30 calendar days after contact award with the detailed Services Scope Programme.

- Interim milestones or interface dates between milestones will be clearly identified and documented.

- The Consultants progress programme shall coincide with the cost assessment cycle and will be submitted as a minimum on a monthly basis or In accordance with contractual conditions.  The Planning & Programming monthly progress report will contain the following:

- Planned Dates vs Current Dates for main, agreed activities, percentage complete, physical percentage complete and remaining duration.

- Variances, explanations for variances and proposed corrective actions, time impact analysis of each variance (change or delay)

- 30 day and 90-day Look Ahead programme report for main, agreed activities, longest path activities, full programme of outstanding work, milestone status report, resource histogram, report on calendars used.

- Earned Value Management report

- The reports will be in PDF and native format.

- The updated XER program file of the programme shall be submitted via a clearly identified medium e.g. permanent format that cannot be over written or modified or changed.

- The baseline schedule shall be submitted in PDF format.

- Narrative report of all changes and movement within the programme.

- All changes (variations) shall have separate activities and shall be monitored and progressed accordingly.

- Printout presenting calendar information in PDF format.

- On a weekly basis, the Consultant shall provide a 2 week look-ahead report indicating the current week progress and the next 2 week planned work.

- The Consultant will be required to attend regular meetings with the Employer’s Agent where the progress of work will be reviewed.  These meetings are normally held monthly.

- Presumptions to be taken into consideration in planning activities:

- The Employer’s internal approval process at each phase can take up to 2 months of preparation

- The readiness for committee meeting must be at least 1 month prior to the set meeting date, this date will be communicated by the Employers Agent

- It can take up to 2 attempts to obtain approval for each gate

## Quality management

### System requirements

The Consultant is required to produce high-quality work products in accordance with best practice.  This means, among other things, the following:

- All reports and documents will be clear in their identification of issues, be logically structured and drafted or prepared to ultimately meet financier requirements.

- All key outputs will be proof-read, cross-referenced, consistent etc. and have been reviewed in their entirety and approved by the Team Leader before being issued to Eskom and other stakeholders.

- All project documents would be subject to Eskom’s approval before being shared with any external parties.

- The Consultant would be required to enter into a non-disclosure agreement with Eskom.

- All reports and other outputs must be in English.

### Information in the quality plan

Clause 40.1 requires that the Consultant operate a quality management system as stated in 240-105658000 Supplier Quality Management Specification (also referred to in Eskom as QM-58)

## The Parties use of material provided by the Consultant

### Employer’s purpose for the material

Clause 70.1 states that the Employer has the right to use the material provided by the Consultant for the purpose stated in the Scope. Such material will amongst other things be used by the Employer for strategic planning, internal governance approvals, external legislative and regulatory approvals and consultation. The Employer may use the material for any purpose deemed fit in relation with the Project.

### Restrictions on the Consultant’s use of the material for other work

The Consultant’s use of material provided for this contract an only be used for any purpose deemed fit in relation with this project scope of work.

### Transfer of rights

- No Exceptions to core clause X9.1

- The Consultant is required to provide documents that transfer these rights to the Employer for use as the Employer sees fit.

- The Consultant must ensure that any subconsultancy contract includes a provision that transfers IP to the employer in the main contract.

- the Consultant shall not challenge or assist any other party challenging at any time the validity or ownership of any of the intellectual property rights relating to the material created and developed for this contract.

- If the contractor's design team is unwilling to transfer rights, the employer can terminate in accordance with clause 90.4

## Management of work done by Task Order

- Task Orders will be prepared in the format stated in an Annexure C attached to the Scope.

- Consultant to only commence work once the task order has been issued and accepted.

- The Consultant to provide resource schedule and timeline for the completion of the task order as well as financial projection in line with the pricelist.

- The Employer reserves the right to influence the Consultant’s timeline.

- The task order must contain an exit strategy. The exit strategy will clearly define how the scope will conclude, ensuring a smooth transition and continued benefit realisation.

- The task order returnables must include a structured checklist that will be used to ensure all necessary steps for the task to be completed.

- Proposed timelines:

- The Consultant will have 7 days from receipt of the task order to submit a proposal inclusive of the required returnables.

- The Employer shall evaluate the proposal and returnables and respond within 7days.

- Once the proposal has been accepted, the Consultant will have 30days to mobilise and commence work.

## Health and safety

The Consultant shall at all times comply to health and safety requirements prescribed by law and the Employer as they may apply to the services.

The Consultant is expected to establish a SHE Plan which meets the employer’s SHE requirements included in the procurement documents as well as all the relevant applicable legislation.  Eskom in no way assumes the Consultant’s legal responsibilities.  The Consultant as a legal entity, therefore an employer is and remains accountable for the quality and the execution of the health and safety program for their employees and contractor employees.  The supplemented Employer‘s SHE requirements reflects minimum requirements and should not be construed as all encompassing.

The Consultant shall comply with the health and safety requirements contained in Annexure B of the Employer’s SHE requirements to this Scope. In the event of site visits to Employer’s premises, the Consultant shall comply to the site’s specified requirements.

## Procurement

## Supplier Development, Localisation and Industrialisation (SDL&I)

Eskom, as a State-Owned Entity is aligned with the Government’s Development and Growth initiatives. It has committed itself to local development initiatives with the aim of increasing the competitiveness, capacity, and capability of its local supply base as well as supporting government’s goals of shared growth, employment creation, poverty reduction and skills development.

Within Eskom, Supplier Development, Localisation, and Industrialisation (SDL&I)’s mandate is to achieve maximum and sustainable local development impact through leveraging Eskom’s procurement spend in a manner that allows flexibility within the business to accommodate government local development initiatives and policies.

All this should be achieved within the context of Eskom’s Procurement and Supply Chain Management Procedure which is based on the Preferential Procurement Policy Framework Act (PPPFA), 2000 and Eskom’s Preferential Procurement Policy:240-128811268

Supplier Development, Localisation and Industrialisation (SDL&I)’s objective is to leverage this Procurement to achieve the following Specific Goals in line with Section 2 (1) (d) of Preferential Procurement Policy Framework Act (PPPFA):

    - contracting with persons, or categories of persons, historically disadvantaged by unfair discrimination on the basis of race, gender or disability; and

    - implementing the programmes of the Reconstruction and Development Programme as published in Government Gazette No. 16085 dated 23 November 1994

The Specific Goals determined to be applicable for this Procurement are listed herewith below as follows:

- Development and increasing of RSA Skills’ pool through compliance with the CIDB’s Contractor’s Skills Development Goals (CSDG), which may entail Workplace Integrated Learning (WIL) for TVET College, Universities of Technology and University Graduates,

- Empowerment of communities in the vicinity of the Projects through job creation, local procurement, skills development, enterprise and supplier development, subcontracting and corporate social investment initiatives.

- National Industrial Participation Programme (NIPP) is a Department of Trade, Industry and Competition (dtic) that is applicable if the procurement transaction has import material/ goods/services that is equal to or more than USD5 million. Therefore, in this instance, if the Bidder intends to import Human Resources whose costs to company is equal to or more than USD5 million, therefore the NIPP will be applicable.

## Reconstruction and Development Programme (RDP) Goals

4.14.2.1 Empowerment through Subcontracting a minimum of 30% of the Contract Amount.

The objective of Sub-Consulting is to ensure that there will be sharing or transference of expertise to South Africans, in accordance with the requirements of the Reconstruction and Development Programme (RDP) through sub-consulting, which involves mentorship and coaching.

Therefore, the winning bidder will be expected to mentor/coach a small emerging Governance, Compliance and Assurance Services Consulting firm that is owned by previously disadvantaged persons through sub-consulting up to 30% of the scope of work to a South African firm. These sub-consulting requirements are as follows:

Sub-contracting can only be concluded with one or more of the following entities.

- An EME or QSE which is at least 51% owned by Black people; and

- An EME or QSE which is at least 51% owned by Black people who are women.

## Skills Development (Professionals Development Programme)

The objective of Skills Development Programme is to ensure that Eskom’s personnel and Graduates get access to opportunities for Graduate-in-Training programmes. These may include, but not limited to, Governance, Compliance & Assurance, Data Management, Project Management, Master Planning, Various Engineering Disciplines, Monitoring & Assurance categories.

| The Consultant is expected to assist Eskom with the development of skills and professional registration of Eskom employees and/or unemployed Graduates though the Professional Development Programme (PDP): Eskom’s Targets: |  |  |  |
| --- | --- | --- | --- |
| Qualification | Number | Entry Level | Output |
| Project Management | 20 | National Diploma/Degree in Engineering (any Discipline) and Construction experience | SACPCMP Registration |
| Engineering (Mechanical, Civil, Industrial) | 20 | B-Engineering Degree and Project experience | ECSA Registration |
| Cost Engineers | 10 | Degree/Advanced Diploma Quantity Survey and Construction experience | South African Council for Quantity Surveying Profession (SACQSP) |
| Total | 50 |  |  |

### B-BBEE Certificate Requirement

Tenders are required to submit the B-BBEE Certificate as required by South African Law. If the Tenderer is a foreign company, it may submit a letter from the South African National Accreditation Systems (SANAS)’ accredited B-BBEE Verification Agent, confirming that it could not be assessed for B-BBEE compliance as it is foreign company with no presence in South Africa.

### National Industrial Participation Programme

Eskom is required to inform the tenderers of this requirement. NIPP will only be applicable for contracts with a foreign component or content of USD 5 million or more.

“NIPP is a programme that seeks to leverage economic benefits and support the development of South African industry by effectively using the instrument of government procurement. The NIPP programme is mandatory for all government and parastatal purchases or lease contracts (goods and services) with an imported content equal to or exceeding USD 5 million.

“The programme targets South African and foreign industries, enterprises, and suppliers of goods and services to government/parastatals, where the imported content of such goods and services equals to or exceeds USD 5 million. The first customer of NIPP is the South African industry that benefits through the NIPP business plans, which, when implemented, generate new or additional business activities through one or more of the following: investment, export opportunities, job creation, increased local sales, SMME and BEE promotion, R&D, and technology transfer.

“Companies with an NIPP obligation must sign this obligation agreement with the Department of Trade, Industry and Competition (dtic) before the contract with Eskom Holdings SOC Ltd, as a purchasing entity, is signed. The obligation agreement governs the relationship between the dtic and the supplier. It defines the NIPP obligation value(s), requirements to fulfil the NIPP obligation, performance milestones, performance monitoring processes, and the NIPP credit allocation criteria.

“All tenders with an import content that is equal to or exceeds the threshold of USD 5 million compels the winning bidder to negotiate and enter into a NIPP obligation agreement with the dtic before signing the contract with Eskom.”

### Maintain and/or improve B-BBEE Status

Awarded Contractor is expected to maintain or improve their B-BBEE Recognition Level for the duration of the contract, and the foreign company will be expected to comply with South African Law once it has been awarded the Contract.

### Contribution towards Corporate Social Investment (CSI)

The CSI contribution will be ONE PERCENT (1%) of the Contract Value and the Service Provider will be expected to either match or exceed this amount for its own CSI philanthropic contribution.

### Monitoring of SDL&I commitments

SDL&I or the Eskom agent will monitor the meeting of the SDL&I targets in the contract. SDL&I collates SDL&I commitments by contractors and suppliers as stated in their contracts with Eskom. A minimum of 1.5% penalty shall be invoked should a contractor/supplier fail to meet its contractual obligations in terms of the SDL&I targets.

### Reporting and Monitoring

- The winning Bidder shall complete and submit the SDL&I Implementation schedule 28 days after contract award,

- The winning Bidder shall complete and submit the SDL&I Implementation Schedule 28 days after contract award,

- This SDL&I Implementation Schedule will be used as a reference document for monitoring, measuring, and reporting on the Contractor’s progress in delivering on their stated SDL&I commitments,

- The Contractor shall, on a quarterly basis, submit a report to Eskom in accordance with Quarterly Reporting Template on their compliance with the SDL&I obligations described above,

- Eskom shall review the SDL&I reports submitted by the Contractor within thirty (30) days of receipt of the reports and notify the supplier on its performance progress,

- Upon notification by Eskom that the supplier is not meeting its SDL&I obligations, the Contractor shall be required to implement corrective measures to meet those SDL&I obligations before the commencement of the following report.

### Limitations on subcontracting

The Consultant shall not subcontract more than 30% of the contract value under this agreement.

The Employer may require that the Consultant must subcontract certain specialised work, or that the Consultant shall not subcontract more than a specified proportion of the whole of the contract.

### Attendance on SubConsultants

The Consultant shall ensure:

- Supervision and management

- Guidance and assistance

- Resource management

- Efficiency

- Safety and compliance

- Contract interpretation

## Working on the Employer’s property

### Employer’s entry and security control, permits, and site regulations

The Consultant shall comply with all the Employer’s site entry requirements and obtain at his cost all the necessary permits.

- All employees working on the Eskom Project Sites may require to complete induction before work can start.

- Obtain and provide evidence of police clearance required to enter the Employer’s site.

- Personal Protective Equipment (PPE) must be worn at all-times except in the PPE free zones.

- All employees must comply to Eskom Life Saving Rules:

      - Open, isolate, test, earth, bond and/or insulate before touch.

      - Hook up on heights

      - Buckle Up

      - Permit to work

      - Be sober.

Security Vetting:

Acceptance of this tender is subject to the condition that both the contracting firm and its personnel providing the service must be subjected to vetting and or screening in line with Eskom’s Vetting Policy and Vetting Procedure. If the principal contractor appoints a subcontractor, the same provisions and measures will apply to the subcontractor.

As per section 2A(b) of the National Strategic Intelligence Act 39 of 1994, as amended by the General Intelligence Laws Amendments Act 11 of 2013, to conduct the security screening and vetting investigations to determine the competence of a person if such a person:

- Is rendering a service or has given notice of intention to render a service to an organ of state, which service may:

- give him or her access to classified information and intelligence in the possession of the organ of state; or

- give him or her access to areas designated as National Key Points in terms of the National Key Points Act 102 of 1980.

Security vetting is a requirement for access to the Employer’s sites as well as information, therefore, the Consultant shall ensure that all required information required for the completion of the security vetting process is provided correctly, completely, truthfully and timeously. Note:

Consultant is to allow for the following vetting turnaround timelines when submitting task order planning:

- For local employees – one week from receipt of fully completed vetting pack

- For international employees – three weeks from receipt of fully completed vetting pack

- The Employer will not be liable for costs associated to access delays on account of incomplete submitted required vetting information.

- Should the result of the vetting process declare the applicant unsuitable, their application will be rejected and the Consultant will provide another candidate for vetting.

- The Consultant staff shall consent to all the required tests, failure to do so will result in the applicant being rejected and the Consultant will have to provide a replacement as per requirements.

- Every successfully vetted human resource shall sign a Non-disclosure Agreement.

Access into site is managed through compliance to several of relevant security legislative frameworks not limited to National Key Points Act, Firearms Control Act, Control of Access to Public premises and vehicles Act inclusive of Site-specific Standard Operating Procedures not excluding the Contractor Access Control Standard that outlines the brief responsibilities of gaining access to site, i.e.:

- Only a fingerprint criminal clearance record of less than 30 days from the date of issue will be accepted.

- Only fingerprint criminal clearance record with a clear criminal result issued by the SAPS CRC and/or an accredited supplier linked to the SAPS Automated Fingerprint System (AFIS) will be allowed.

- Access/Exit is subject to security protocols and measures applicable to site which includes but not limited to Declaration and bringing personal equipment to site (OV18 Process), prohibited items (i.e. Drugs, Alcohol, weapons, pets etc), prohibition in removing any asset without authorization, Returning of permits on termination, Principles of access – i.e. Only authorized personnel will be granted access, Immediate reporting of incidents to the Security Control Room before tampering, Visitors Pre-arrangement and escort Security Process, etc

- Passive and active substance abuse screening/testing on entry, while inside and on leaving any of the sites controlled by Eskom.

- Access to sites will be revoked in any of the following circumstances prevails (i.e. End of contract, security violations or breaches, Security threat or compromise, Contractor terminated or resigns).

### People restrictions, hours of work, conduct and records

- The Consultant keeps detailed records of his people working on the Employer’s property, including those of his Sub-Consultants.  The Employer’s Agent shall have access to these records at any time.

- The Employer will reject unsuitable personnel should they not meet the requirements as per the contract.

- Upon termination of the Consultant’s human resource’s engagement for any reason, the resource shall promptly return to the Employer all property belonging to the Employer including (but not limited to) equipment, devices, documents, files, access credentials and any other tangible or intangible assets.

- The resource shall also return or securely delete all copies of (electronic or physical) of any confidential or intellectual property created or obtained during the course of the engagement.

- Furthermore, the resource shall promptly assign and transfer to the Employer any work product, inventions, discoveries, developments, improvements, processes, or other intellectual property created, conceived, or developed whole or in part during the engagement and shall cooperate fully in executing any necessary documents to perfect the Employer’s rights therein.

- Failure to return such assets or to comply with the obligations under this clause may result in legal action and/or withholding of any final compensation to the extent permitted by law.

#### Work hours and overtime

Should there be a need for overtime, the Employer shall be advised and shall provide prior approval. Overtime shall be assessed and paid as follows:

- Weekdays 1.5 times the resource rate after the standard 8hour day has been worked Monday to Friday local time.

- Saturday: 1.5times the resource hourly rate

- Sunday: 2 times the resource hourly rate

- Public holidays: 2 times the resource hourly rate. Only south African public holidays shall be recognised.

#### Billable hours

- Billable hours are those directly attributable to the performance of services under this contract as documented in daily time logs.

- Billable hours excludes non-productive time such as Consultant internal training, general staff meetings and administrative overheads.

#### Timekeeping and records

The Consultant shall maintain daily time records using the agreed upon timekeeping software which is to include:

- Employees details

- Date

- Hours worked

- Labour category

- Brief description of work performed

All time sheets to be approved and confirmed for accuracy by the employee’s supervisor and available for audit by the Employer.

## Cooperating with and obtaining acceptance of Others

- Facilitate regular co-ordination meetings to align expectations and address concerns.

- Submit documents timeously for review and approval

- Incorporate feedback efficiently and maintain schedule and quality.

- Promote transparency and collaboration through documentation, shared platforms and responsive communication.

## Things provided by the Employer

Should the need arise, the following will be provided should the Employer deem necessary:

- Access to site or premises

- Relevant project background documents

- Stakeholder contact information

- Meeting and workspace facilities

- Security access and permits to enter restricted areas.

- Timely review and feedback on submitted deliverables.

## Cataloguing requirements by the Consultant

TBA.

# LIST OF DRAWINGS

## Drawings issued by the Employer

This is the list of drawings issued by the Employer at or before the Contract Date and which apply to this contract.

| Drawing number | Revision | Title |
| --- | --- | --- |

- – GC&A: Oversight, Monitoring and Assurance Function

  - Collaborative Review detail

    - Objective

The objective of the Collaborative Review is to undertake an independent review of the project under consideration and provide a bare bones opinion regarding the status of the project and forecast the project completion date/s.

    - Deep dive methodology

The deep dive methodology is a ‘solution-driven/value add’ exercise and will be performed in close coordination with the project execution team.  Any deficiencies or short comings will be debated and communicated along with workable solutions/alternatives.  These solutions will be based on industry-best practices that have been successfully used across the globe.

The time required to complete a Level 1 deep dive would be significantly shorter than a Level 2 deep dive.

    - Leve1 and Level 2 Collaborative Reviews

      - Level 1:

- Schedule Certainty

- Completion Milestones

  - Resource analysis.

  - Schedule review/trends (construction and commissioning) against benchmarking milestones.

  - Critical path analysis.

  - Schedule risk/mitigation.

  - Field checking versus PMP duration (balance to go).

  - FPMS (Field progress measurement system).

- Metrics per Milestone

  - Commodities – planned vs. actual/trends.

  - CTO (construction turnover per package/milestone)/AFI (Approved for final inspection) – planned vs. actual/trends.

  - Data books (S-curve/resources).

- Technical/Engineering Overview

  - Scope definition and review (change management).

  - Quality management tracking deviations.

    - Concessions in progress/outstanding that impact schedule.

    - Compilation of data books to enable AFI/CTO to proceed timeously.

    - Identifying and application of lessons learnt with benefits realization.

- Site Stakeholder Review

  - Schedule alignment.

  - Common goals.

- Risks

  - Milestone risks, impacts and likelihood.

  - Treatment plans and progress.

      - Level 2:

- Project Review & Analysis

- Project Organisation Structure

  - Comparison to best practice in the industry.

- Schedule Validation

  - Detailed analysis of schedule (per package) construction and commissioning.

  - Earning rules, percentage progress and validation.

  - FPMS (Field progress measurement system) review.

  - Site resourcing overview/analysis.

- Contractors’ Schedules

  - Master Schedule comparison against benchmarking milestones.

  - Overview of contractor’s input/opinions.

  - Review of contractor’s progress reporting and constraints.

  - Coordination and resourcing overview.

  - Technical analysis of main package schedules.

  - Turnaround time for information requests.

- Metrics per Milestone

  - Commodities – planned v actual/trends.

  - CTO (construction turnover per package/milestone).

  - AFI (Approved for final inspection) – plan vs. actual.

  - Data books (S-curve/resources).

  - Commissioning.

- Key Risks - Schedule Validation

  - Integrated schedule (Inclusive of commissioning).

  - Outcome from items above.

  - Detailed and measurable mitigation plans.

  - Identifying and application of lessons learnt with benefits realization.

- Safety Management

  - Analysis of stats to assist with trend forecasting.

  - Benchmark statistics to industry norms.

  - The GC&A Partner/Service Provider oversight, monitoring and assurance activities in the table below:

|  | Activity | Description |
| --- | --- | --- |
| 1. | Execute Assurance Plan | - Perform site visit to the area. - Analyse project schedule, cost and risk review. - Test key controls identified - Transactional testing. - Evidence collection. - Paper and desktop review. - Informal/formal communication. - Identify SHEQ compliance and non-compliance. - Formulate preliminary and details findings. - Discuss improvement areas and make recommendations through collaboration. - Identify best practices that can implemented to other areas, programs, etc. (e.g. milestone comparison). - Compile assurance report. |
| 1.1 | Perform Collaborative Reviews | - Perform collaborative reviews (deep dives) and analytics of the following (technical or strategic reviews): - Level 1: Schedule certainty; metrics per milestone; technical/engineering overview; site stakeholder review; risks. - Level 2: Schedule validation; contractors’ schedules; metrics per milestone, key risks, safety management; site resourcing overview/analysis; data books; productivity; startup & operations readiness. - Then discuss preliminary findings and recommendations with Project Manager/Programme Manager and Portfolio Delivery Manager. - Compile feedback on findings and recommendations after discussion with Project Manager/Programme Manager/Portfolio Delivery Manager. |
| 1.2 | Perform Issue Explorations | - Identify potential issue/receive request for issue exploration. - Explore issue/engagement. - Analyse, determine root causes and contributory causes, latent org. weaknesses and make recommendations. - Discuss preliminary findings and recommendations with Project Manager/Programme Manager/Portfolio Delivery Manager/ applicable GCD Exco member/s and obtain agreement. - Feedback (Deliver findings at appropriate forum/ persons). - Escalate non agreement if appropriate (GC&A team believes it is essential that recommendation in question should be implemented). |
| 1.3 | Compile Report | - Compile Issue exploration feedback. - Compile collaborative reviews feedback. - Report on project performance (e.g. weekly report). - Extract action lists & recommendations register, etc. |
| 2. | Monitor and Track Project Performance | - Monitor, track, trend and analyse project performance. - Review weekly project performance independently. - Review project performance reports as submitted by Portfolio Delivery Managers/Programme Managers/Project Managers. |
| 3. | Monitor and track actions and recommendations | - Monitor and track assurance findings, actions and recommendations are addressed. The action and agreed recommendation lists are owned by the Portfolio Delivery Manager Programme Manager / Project Manager while the GC&A team facilitate. - Escalate non-execution of the findings and recommendations. - Follow-up engagement. - Review effectiveness of implemented action/recommendation. |
| 4. | Document Lessons Learned | - Document lessons learned to improve future engagements. - Share with the other Knowledge Management areas at GCD level - Collaborative review. |
| 5. | Perform Oversight and Establish/Optimise GC&A Governance | Oversight: - Perform continuous Oversight on concordance level: are the right things really, right? - Perform oversight across Portfolios, Programmes, Projects and applicable PLCM e.g. phases/stage and gates. - Perform oversight on projects through its lifecycle in ensuring alignment to the business requirements/needs, strategy and delivery on what was promised. - Oversight on project risk to Operations and Maintenance business and versa visa. - Oversight to ensure benefits realisation. |
| 6. | Explore Assurance Data – For Validation and Forecasts | - Analyse assurance data for validation and forecasts. |

Available from Engineering Contract Strategies Tel 011 803 3008 Fax 011 803 3009 and www.ecs.co.za

Available from Engineering Contract Strategies Tel 011 803 3008 Fax 011 803 3009 or www.ecs.co.za